## TKP
HS-TKP_LDG CHG DATE 29 OCT. 2026
Item | Revision | Functional loc. | Confirmation | Notification | Order | Order Type | Ident.Insp.Task | Reference Date | Oper.WorkCenter | Activity | Description | Syste | User status | WBS ord. header | Priority | Priority | Working Group | Main WorkCtr | MaintActivType | External Ident. | Actual start | Bas. start date | Start time | Basic fin. date | Basic fin. time
1 | 70467233 | HS-TKP | 0016573538 |  | 2105183431 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | LDG CHG - TOWING AIRCRAFT. | Wait LAE Sign | MAVA | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.LDG-CHG-10 | 2026-10-23 | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
2 | 70467233 | HS-TKP | 0016573539 |  | 2105183431 | AC02 |  | 2026-10-22 | 11LHM/A | 0020 | LDG CHG - TOWING AIRCRAFT. | Wait LAE Sign | MAVA | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.LDG-CHG-10 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
3 | 70467233 | HS-TKP-32-11-0102-RH_MLG | 0016573499 |  | 2105183394 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | OLD RH MLG -INVENTORY CHK MLG COMPONENTS | Wait MECH Sign |  | H/26-TKP-XXLDG-GNRL-N |  |  |  | BKK_H | REP | 777.OPR.MLG-CHG-R05 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
4 | 70467233 | HS-TKP-32-11-0101-LH_MLG | 0016573359 |  | 2105183356 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | OLD LH MLG -INVENTORY CHK MLG COMPONENTS | Wait MECH Sign |  | H/26-TKP-XXLDG-GNRL-N |  |  |  | BKK_H | REP | 777.OPR.MLG-CHG-L05 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
5 | 70467233 | HS-TKP-32-21-0101-NLG | 0016573332 |  | 2105183311 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | OLD NLG -INVENTORY CHECK NLG COMPONENTS | Wait MECH Sign | MAVA | H/26-TKP-XXLDG-GNRL-N |  |  |  | BKK_H | REP | 777.OPR.NLG-CHG-05 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
6 | 70467233 | HS-TKP-32-11-0101-LH_MLG | 0016573482 |  | 2105183378 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | LH MLG CHG-CHK FWD,AFT TRUNNION BEARING | Wait MECH Sign |  | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-L25 | 2026-10-27 | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
7 | 70467233 | HS-TKP-32-11-0101-LH_MLG | 0016573374 |  | 2105183370 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | LH MLG CHG-CHK MLG AFT TRUNNION BEARING | Wait MECH Sign |  | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-L31 | 2026-10-27 | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
8 | 70467233 | HS-TKP | 0016573542 |  | 2105183434 | AC02 |  | 2026-10-24 | 11LHM/A | 0010 | LDG CHG-ENG#1,2 PRESERVATION(-300ER) | TECO | DPRC | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.LDG-CHG-12 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
9 | 70467233 | HS-TKP | 0016573543 |  | 2105183434 | AC02 |  | 2026-10-24 | 11LHM/A | 0020 | LDG CHG-ENG#1,2 PRESERVATION(-300ER) | TECO | DPRC | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.LDG-CHG-12 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
10 | 70467233 | HS-TKP | 0016573544 |  | 2105183435 | AC02 |  | 2026-10-24 | 11LHM/C | 0010 | LDG CHG-DRAIN AND FLUSH TOILET TANKS. | TECO | DPRC | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.LDG-PREPARE-21 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
11 | 70467233 | HS-TKP-32-11-0101-LH_MLG | 0016573358 |  | 2105183355 | AC02 |  | 2026-10-16 | 11LHM/A | 0010 | NEW LH MLG -INVENTORY CHK MLG COMPONENTS | TECO | ODAT | H/26-TKP-XXLDG-GNRL-N |  |  |  | BKK_H | REP | 777.OPR.MLG-CHG-L05 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
12 | 70467233 | HS-TKP-32-11-0102-RH_MLG | 0016573498 |  | 2105183393 | AC02 |  | 2026-10-16 | 11LHM/A | 0010 | NEW RH MLG -INVENTORY CHK MLG COMPONENTS | TECO | ODAT | H/26-TKP-XXLDG-GNRL-N |  |  |  | BKK_H | REP | 777.OPR.MLG-CHG-R05 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
13 | 70467233 | HS-TKP-32-11-0102-RH_MLG | 0016573518 |  | 2105183412 | AC02 |  | 2026-10-26 | 11LHM/A | 0010 | RH MLG CHG-REM MLG SIDE BRACE ASSY(021-9 | TECO |  | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-R23 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
14 | 70467233 | HS-TKP | 0016573540 |  | 2105183432 | AC02 |  | 2026-10-24 | 11LHM/A | 0010 | LDG CHG-APU PRESERVATION | TECO | DPRC | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.LDG-PREPARE-14 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
15 | 70467233 | HS-TKP-32-21-0101-NLG | 0016573352 |  | 2105183349 | AC02 |  | 2026-10-25 | 11LHM/A | 0010 | NLG CHG-REM NOSE LANDING GEAR LOCK LINK | TECO | DPRC | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.NLG-CHG-22 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
16 | 70467233 | HS-TKP-32-11-0102-RH_MLG | 0016573521 |  | 2105183415 | AC02 |  | 2026-10-26 | 11LHM/A | 0010 | RH MLG CHG-REM MLG DRAG BRACE ASSEMBLY | TECO |  | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-R24 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
17 | 70467233 | HS-TKP-32-11-0102-RH_MLG | 0016573529 |  | 2105183423 | AC02 |  | 2026-10-26 | 11LHM/A | 0010 | RH MLG CHANGE-REMOVE LDG(200,200ER,300,3 | TECO |  | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.MPD.MLG-CHG-R10 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
18 | 70467233 | HS-TKP-32-11-0102-RH_MLG | 0016573530 |  | 2105183423 | AC02 |  | 2026-10-26 | 11LHM/E | 0020 | RH MLG CHANGE-REMOVE LDG(200,200ER,300,3 | TECO |  | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.MPD.MLG-CHG-R10 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
19 | 70467233 | HS-TKP-32-11-0101-LH_MLG | 0016573371 |  | 2105183367 | AC02 |  | 2026-10-24 | 11LHM/A | 0010 | LH MLG CHG-REM MLG DRAG STRUT DOOR | TECO | DPRC | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-L13 | 2026-10-23 | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
20 | 70467233 | HS-TKP-32-11-0101-LH_MLG | 0016573373 |  | 2105183369 | AC02 |  | 2026-10-24 | 11LHM/A | 0010 | LH MLG CHG-REM MLG SHOCK STRUT DOOR. | TECO | DPRC | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-L12 | 2026-10-23 | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
21 | 70467233 | HS-TKP-32-11-0101-LH_MLG | 0016573375 |  | 2105183371 | AC02 |  | 2026-10-24 | 11LHM/A | 0010 | LH MLG CHG-REM MLG TRUNNION DOOR | TECO | DPRC | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-L11 | 2026-10-23 | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
22 | 70467233 | HS-TKP-32-11-0101-LH_MLG | 0016573477 |  | 2105183373 | AC02 |  | 2026-10-25 | 11LHM/A | 0010 | LH MLG CHG-REM MLG SIDE BRACE ASSY(021-9 | TECO | DPRC | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-L23 | 2026-10-24 | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
23 | 70467233 | HS-TKP-32-11-0102-RH_MLG | 0016573512 |  | 2105183406 | AC02 |  | 2026-10-24 | 11LHM/A | 0010 | RH MLG CHG-REM MLG DRAG STRUT DOOR | TECO | DPRC | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-R13 | 2026-10-23 | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
24 | 70467233 | HS-TKP-32-11-0102-RH_MLG | 0016573514 |  | 2105183408 | AC02 |  | 2026-10-24 | 11LHM/A | 0010 | RH MLG CHG-REM MLG SHOCK STRUT DOOR. | TECO | DPRC | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-R12 | 2026-10-23 | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
25 | 70467233 | HS-TKP-32-11-0102-RH_MLG | 0016573516 |  | 2105183410 | AC02 |  | 2026-10-24 | 11LHM/A | 0010 | RH MLG CHG-REM MLG TRUNNION DOOR | TECO | DPRC | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-R11 | 2026-10-23 | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
26 | 70467233 | HS-TKP | 0016573537 |  | 2105183430 | AC02 |  | 2026-10-24 | 11LHM/C | 0010 | LDG CHG-DRAIN POTABLE WATER(200ER,300ER) | TECO | DPRC | H/26-TKP-XXLDG-GNRL-N |  |  |  | BKK_H | REP | 777.OPR.LDG-PREPARE-20 | 2026-10-23 | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
27 | 70467233 | HS-TKP-32-21-0101-NLG | 0016573331 |  | 2105183310 | AC02 |  | 2026-10-16 | 11LHM/A | 0010 | NEW NLG -INVENTORY CHECK NLG COMPONENTS | TECO | ODAT | H/26-TKP-XXLDG-GNRL-N |  |  |  | BKK_H | REP | 777.OPR.NLG-CHG-05 | 2026-10-21 | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
28 | 70467233 | HS-TKP-32-11-0101-LH_MLG | 0016573476 |  | 2105183372 | AC02 |  | 2026-10-24 | 11LHM/A | 0010 | LH MLG CHG-REM WHEEL AND TIRE ASSEMBLY | TECO | DPRC | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-L73 | 2026-10-23 | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
29 | 70467233 | HS-TKP-32-11-0101-LH_MLG | 0016573493 |  | 2105183388 | AC02 |  | 2026-10-24 | 11LHM/A | 0010 | LH MLG CHG-REMOVE MLG BRAKE | TECO | DPRC | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-L74 | 2026-10-23 | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
30 | 70467233 | HS-TKP-32-11-0102-RH_MLG | 0016573517 |  | 2105183411 | AC02 |  | 2026-10-24 | 11LHM/A | 0010 | RH MLG CHG-REM WHEEL AND TIRE ASSEMBLY | TECO | DPRC | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-R73 | 2026-10-23 | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
31 | 70467233 | HS-TKP-32-11-0102-RH_MLG | 0016573534 |  | 2105183427 | AC02 |  | 2026-10-24 | 11LHM/A | 0010 | RH MLG CHG-REMOVE MLG BRAKE | TECO | DPRC | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-R74 | 2026-10-23 | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
32 | 70467233 | HS-TKP-32-11-0102-RH_MLG | 0016573535 |  | 2105183428 | AC02 |  | 2026-10-24 | 11LHM/A | 0010 | RH MLG CHG-LIFT A/C WITH JACKS(777-300,3 | TECO | DPRC | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR. MLG-CHG-L,R22 | 2026-10-23 | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
33 | 70467233 | HS-TKP-32-21-0101-NLG | 0016573334 |  | 2105183313 | AC02 |  | 2026-10-24 | 11LHM/A | 0010 | NLG CHG-LIFT THE AIRPLANE NOSE ON JACKS. | TECO | DPRC | H/26-TKP-XXLDG-GNRL-N |  |  |  | BKK_H | REP | 777.OPR.NLG-CHG-21 | 2026-10-23 | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
34 | 70467233 | HS-TKP-32-21-0101-NLG | 0016573343 |  | 2105183342 | AC02 |  | 2026-10-25 | 11LHM/A | 0010 | REMOVAL OF NLG(200,200ER,300,3 | TECO | DPRC | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.NLG-CHG-10 | 2026-10-24 | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
35 | 70467233 | HS-TKP-32-21-0101-NLG | 0016573344 |  | 2105183342 | AC02 |  | 2026-10-25 | 11LHM/E | 0020 | REMOVAL OF NLG(200,200ER,300,3 | TECO | DPRC | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.NLG-CHG-10 | 2026-10-24 | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
36 | 70467233 | HS-TKP-32-21-0101-NLG | 0016573346 |  | 2105183344 | AC02 |  | 2026-10-24 | 11LHM/A | 0010 | NLG CHG-REM NLG WHEEL,TIRE ASSY(OLDGEAR) | TECO | DPRC | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.NLG-CHG-70 | 2026-10-23 | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
37 | 70467233 | HS-TKP-32-11-0101-LH_MLG | 0016573480 |  | 2105183376 | AC02 |  | 2026-10-25 | 11LHM/A | 0010 | LH MLG CHG-REM MLG DRAG BRACE ASSEMBLY | TECO | DPRC | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-L24 | 2026-10-23 | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
38 | 70467233 | HS-TKP-32-11-0101-LH_MLG | 0016573488 |  | 2105183384 | AC02 |  | 2026-10-26 | 11LHM/A | 0010 | LH MLG CHANGE-REMOVE LDG(200,200ER,300,3 | TECO |  | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-L10 | 2026-10-26 | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
39 | 70467233 | HS-TKP-32-11-0101-LH_MLG | 0016573489 |  | 2105183384 | AC02 |  | 2026-10-26 | 11LHM/E | 0020 | LH MLG CHANGE-REMOVE LDG(200,200ER,300,3 | TECO |  | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-L10 | 2026-10-24 | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
40 | 70467233 | HS-TKP-32-11-0101-LH_MLG | 0016573494 |  | 2105183389 | AC02 |  | 2026-10-24 | 11LHM/A | 0010 | LH MLG CHG-LIFT A/C WITH JACKS(777-300,3 | TECO | DPRC | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-L,R22 | 2026-10-23 | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
41 | 70467233 | HS-TKP-32-11-0102-RH_MLG | 0016573520 |  | 2105183414 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | RH MLG CHG-INST MLG DRAG BRACE ASSY | REL | MAVA | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-R42 | 2026-10-23 | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
42 | 70467233 | HS-TKP-32-21-0101-NLG | 0016573335 |  | 2105183314 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | NLG CHG-OPC LDG ALTERNATE EXTENSION SYS. | REL |  | H/26-TKP-XXLDG-GNRL-N |  |  |  | BKK_H | FUC | 777.OPR.NLG-CHG-58,32-130-00 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
43 | 70467233 | HS-TKP-32-21-0101-NLG | 0016573336 |  | 2105183315 | AC02 |  | 2026-10-22 | 11LHM/E | 0010 | NLG CHG-OPC LDG,RUNWAY TURNOFF,TAXI LT. | REL |  | H/26-TKP-XXLDG-GNRL-N |  |  |  | BKK_H | REP | 777.OPR.NLG-CHG-59 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
44 | 70467233 | HS-TKP-32-21-0101-NLG | 0016573338 |  | 2105183317 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | NLG CHG-OPC SERVICE INTERPHONE SYS | REL |  | H/26-TKP-XXLDG-GNRL-N |  |  |  | BKK_H | REP | 777.OPR.NLG-CHG-61 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
45 | 70467233 | HS-TKP-32-21-0101-NLG | 0016573339 |  | 2105183318 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | NLG CHG-OPC GROUND CREW CALL SYS. | REL |  | H/26-TKP-XXLDG-GNRL-N |  |  |  | BKK_H | REP | 777.OPR.NLG-CHG-62 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
46 | 70467233 | HS-TKP-32-21-0101-NLG | 0016573340 |  | 2105183319 | AC02 |  | 2026-10-22 | 11LHM/E | 0010 | NLG CHG-OPC APU FIRE DETECTION. | REL |  | H/26-TKP-XXLDG-GNRL-N |  |  |  | BKK_H | REP | 777.OPR.NLG-CHG-63 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
47 | 70467233 | HS-TKP-32-21-0101-NLG | 0016573341 |  | 2105183340 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | NLG CHG-OPC LDG GND DOOR RELEASE SYS | REL |  | H/26-TKP-XXLDG-GNRL-N |  |  |  | BKK_H | REP | 777.OPR.NLG-CHG-65 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
48 | 70467233 | HS-TKP-32-21-0101-NLG | 0016573342 |  | 2105183341 | AC02 |  | 2026-10-22 | 11LQ/IA | 0010 | NLG CHG-SUMMARY (777-200,300,200ER,3 | REL |  | H/26-TKP-XXLDG-GNRL-N |  |  |  | BKK_H | REP | 777.OPR.SUMMARY NLG CHANGE |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
49 | 70467233 | HS-TKP-32-21-0101-NLG | 0016573355 |  | 2105183352 | AC02 | RII/DII | 2026-10-22 | 11LHM/A | 0010 | NLG CHG- FUC NLG,MLG EXTEN & RETRACT SYS | REL |  | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | FUC | 777.OPR.NLG-CHG-54 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
50 | 70467233 | HS-TKP-32-11-0101-LH_MLG | 0016573357 |  | 2105183354 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | LH MLG - RECORD THE TRANSFER COMPONENTS | REL |  | H/26-TKP-XXLDG-GNRL-N |  |  |  | BKK_H | REP | 777.OPR.NLG-CHG-05 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
51 | 70467233 | HS-TKP-32-11-0101-LH_MLG | 0016573360 |  | 2105183357 | AC02 | RII/DII | 2026-10-22 | 11LHM/A | 0010 | LH MLG CHG-FUC MLG EXTENSION & RETRACT | REL |  | H/26-TKP-XXLDG-GNRL-N |  |  |  | BKK_H | REP | 777.OPR.MLG-CHG-L59 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
52 | 70467233 | HS-TKP-32-11-0101-LH_MLG | 0016573361 |  | 2105183358 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | LH MLG CHG-OPC LDG ALT EXTENSION SYS | REL |  | H/26-TKP-XXLDG-GNRL-N |  |  |  | BKK_H | REP | 777.OPR.MLG CHG, 32-130-00 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
53 | 70467233 | HS-TKP-32-11-0101-LH_MLG | 0016573362 |  | 2105183359 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | LH MLG CHG-NORMAL HYD BRAKE SYS-BLEEDING | REL |  | H/26-TKP-XXLDG-GNRL-N |  |  |  | BKK_H | REP | 777.OPR.MLG CHG |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
54 | 70467233 | HS-TKP-32-11-0101-LH_MLG | 0016573363 |  | 2105183360 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | LH MLG CHG- STEERING SYS-FUNCTIONAL TEST | REL |  | H/26-TKP-XXLDG-GNRL-N |  |  |  | BKK_H | REP | 777.OPR.MLG CHG |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
55 | 70467233 | HS-TKP-32-11-0101-LH_MLG | 0016573364 |  | 2105183361 | AC02 |  | 2026-10-22 | 11LHM/E | 0010 | LH MLG CHG:WOW LOAD SENSOR CALIBRATION | REL |  | H/26-TKP-XXLDG-GNRL-N |  |  |  | BKK_H | REP | 777.OPR.LH MLG CHG-L61 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
56 | 70467233 | HS-TKP-32-11-0101-LH_MLG | 0016573370 |  | 2105183366 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | LH MLG CHG-BLEED ALTERNATE HYD BRAKE SYS | REL |  | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-L56 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
57 | 70467233 | HS-TKP-32-11-0102-RH_MLG | 0016573497 |  | 2105183392 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | RH MLG - RECORD THE TRANSFER COMPONENTS | REL |  | H/26-TKP-XXLDG-GNRL-N |  |  |  | BKK_H | REP | 777.OPR.MLG-CHG-05 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
58 | 70467233 | HS-TKP-32-11-0102-RH_MLG | 0016573500 |  | 2105183395 | AC02 | RII/DII | 2026-10-22 | 11LHM/A | 0010 | RH MLG CHG-FUC MLG EXTENSION & RETRACT | REL |  | H/26-TKP-XXLDG-GNRL-N |  |  |  | BKK_H | REP | 777.OPR.MLG-CHG-R59 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
59 | 70467233 | HS-TKP-32-11-0102-RH_MLG | 0016573501 |  | 2105183396 | AC02 |  | 2026-10-22 | 11LQ/IA | 0010 | RH MLG CHG-SUMMARY (021-999) | REL |  | H/26-TKP-XXLDG-GNRL-N |  |  |  | BKK_H | REP | 777.OPR.SUMMARY RH MLG CHG |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
60 | 70467233 | HS-TKP-32-11-0102-RH_MLG | 0016573502 |  | 2105183397 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | RH MLG CHG-OPC LDG ALT EXTENSION SYS | REL |  | H/26-TKP-XXLDG-GNRL-N |  |  |  | BKK_H | REP | 777.OPR.MLG CHG, 32-130-00 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
61 | 70467233 | HS-TKP-32-11-0102-RH_MLG | 0016573503 |  | 2105183398 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | RH MLG CHG-NORMAL HYD BRAKE SYS-BLEEDING | REL |  | H/26-TKP-XXLDG-GNRL-N |  |  |  | BKK_H | REP | 777.OPR.MLG CHG |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
62 | 70467233 | HS-TKP-32-11-0102-RH_MLG | 0016573504 |  | 2105183399 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | RH MLG CHG- STEERING SYS-FUNCTIONAL TEST | REL |  | H/26-TKP-XXLDG-GNRL-N |  |  |  | BKK_H | REP | 777.OPR.MLG CHG |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
63 | 70467233 | HS-TKP-32-11-0102-RH_MLG | 0016573505 |  | 2105183400 | AC02 |  | 2026-10-22 | 11LHM/E | 0010 | RH MLG CHG:WOW LOAD SENSOR CALIBRATION | REL |  | H/26-TKP-XXLDG-GNRL-N |  |  |  | BKK_H | REP | 777.OPR.RH MLG CHG-R61 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
64 | 70467233 | HS-TKP-32-11-0102-RH_MLG | 0016573506 |  | 2105183401 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | Eccentric Adjustment Procedure | REL |  | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-L41 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
65 | 70467233 | HS-TKP-32-11-0102-RH_MLG | 0016573511 |  | 2105183405 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | RH MLG CHG-BLEED ALTERNATE HYD BRAKE SYS | REL |  | H/26-TKP-XXLDG-GNRL-N |  |  |  | BKK_H | REP | 777.OPR.MLG-CHG-R56 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
66 | 70467233 | HS-TKP-32-11-0102-RH_MLG | 0016573515 |  | 2105183409 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | RH MLG CHG-CHK MLG AFT TRUNNION BEARING | REL |  | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-R31 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
67 | 70467233 | HS-TKP-32-11-0102-RH_MLG | 0016573523 |  | 2105183417 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | RH MLG CHG-CHK FWD,AFT TRUNNION BEARING | REL |  | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-R25 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
68 | 70467233 | HS-TKP | 0016573541 |  | 2105183433 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | LDG CHG-APU DEPRESERVATION | REL |  | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.LDG-PREPARE-94 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
69 | 70468547 | HS-TKP | 0016607954 | KP883B231026 | KP883B231026 | AC05 |  | 2026-10-23 | 11SH | 0010 | MAIN LANDING GEAR: DICONNECT & CONNECT M | REL |  | H/26-TKP-XXLDG-GNRL-N |  |  |  | BKK_H | REP |  |  | 2026-10-23 | 15:06:00 | 2026-12-31 | 19:00:00
70 | 70468547 | HS-TKP | 0016607955 | KP883B231026 | KP883B231026 | AC05 |  | 2026-10-23 | 11SH | 0020 | MAIN LANDING GEAR: DICONNECT & CONNECT M | REL |  | H/26-TKP-XXLDG-GNRL-N |  |  |  | BKK_H | REP |  |  | 2026-10-23 | 15:06:00 | 2026-12-31 | 19:00:00
71 | 70467233 | HS-TKP-32-21-0101-NLG | 0016573354 |  | 2105183351 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | NLG CHG-LOWER A/C OFF OF JACKS(021-999) | REL |  | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.NLG-CHG-51(300) |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
72 | 70467233 | HS-TKP-32-11-0101-LH_MLG | 0016573367 |  | 2105183364 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | LH MLG CHG-INSTALL MLG TRUNNION DOOR | REL |  | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-L46 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
73 | 70467233 | HS-TKP-32-11-0101-LH_MLG | 0016573372 |  | 2105183368 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | LH MLG CHG-INSTALL MLG SHOCK STRUT DOOR | REL |  | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-L47 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
74 | 70467233 | HS-TKP-32-11-0101-LH_MLG | 0016573478 |  | 2105183374 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | LH MLG CHG-LOWER A/C (777-300<(>,<)>3 | REL |  | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-L,R43 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
75 | 70467233 | HS-TKP-32-11-0101-LH_MLG | 0016573483 |  | 2105183379 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | LH MLG CHG-LUB MLG DOORS& ACTG (021-999) | REL |  | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-L55 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
76 | 70467233 | HS-TKP-32-11-0101-LH_MLG | 0016573484 |  | 2105183380 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | LH MLG CHG-LUB MLG SUPPORT BEAM (021-999 | REL |  | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-L32 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
77 | 70467233 | HS-TKP-32-11-0101-LH_MLG | 0016573486 |  | 2105183382 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | LH MLG CHG-INSTALL DRAG STRUT DOOR. | REL |  | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-L45 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
78 | 70467233 | HS-TKP-32-11-0101-LH_MLG | 0016573487 |  | 2105183383 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | LH MLG CHG-LUB UPPER MLG& ACTG(021-999) | REL |  | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-L33 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
79 | 70467233 | HS-TKP-32-11-0101-LH_MLG | 0016573491 |  | 2105183386 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | LH MLG CHG-LUB LWR GEAR& ACTG(021-999) | REL |  | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-L54 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
80 | 70467233 | HS-TKP-32-11-0101-LH_MLG | 0016573492 |  | 2105183387 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | LH MLG CHG-INST MLG SIDE BRACE ASSY(021- | REL |  | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-L41 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
81 | 70467233 | HS-TKP-32-11-0102-RH_MLG | 0016573508 |  | 2105183403 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | RH MLG CHG-INSTALL MLG TRUNNION DOOR | REL |  | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-R46 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
82 | 70467233 | HS-TKP-32-11-0102-RH_MLG | 0016573513 |  | 2105183407 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | RH MLG CHG-INSTALL MLG SHOCK STRUT DOOR | REL |  | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-R47 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
83 | 70467233 | HS-TKP-32-11-0102-RH_MLG | 0016573519 |  | 2105183413 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | RH MLG CHG-LOWER A/C (777-300,3 | REL |  | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-L,R43 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
84 | 70467233 | HS-TKP-32-11-0102-RH_MLG | 0016573524 |  | 2105183418 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | RH MLG CHG-LUB MLG DOORS& ACTG (021-999) | REL |  | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-R55 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
85 | 70467233 | HS-TKP-32-11-0102-RH_MLG | 0016573525 |  | 2105183419 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | RH MLG CHG-LUB MLG SUPPORT BEAM (021-999 | REL |  | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-R32 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
86 | 70467233 | HS-TKP-32-11-0102-RH_MLG | 0016573528 |  | 2105183422 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | RH MLG CHG-LUB UPPER MLG& ACTG(021-999) | REL |  | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-R33 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
87 | 70467233 | HS-TKP-32-11-0102-RH_MLG | 0016573532 |  | 2105183425 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | RH MLG CHG-LUB LWR GEAR& ACTG(021-999) | REL |  | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-R54 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
88 | 70467233 | HS-TKP-32-11-0102-RH_MLG | 0016573533 |  | 2105183426 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | RH MLG CHG-INST MLG SIDE BRACE ASSY(021- | REL |  | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-R41 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
89 | 70467233 | HS-TKP | 0016573545 |  | 2105183436 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | LDG CHG-CLN ATT FITTING,WHEEL WELL &DOOR | REL | MAVA | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.LDG-PREPARE-06 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
90 | 70467233 | HS-TKP-32-11-0101-LH_MLG | 0016573365 |  | 2105183362 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | Eccentric Adjustment Procedure | REL |  | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-L41 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
91 | 70467233 | HS-TKP-32-21-0101-NLG | 0016573356 |  | 2105183353 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | NLG CHG-INSTALL NLG LOCK LINK | REL | MNOA | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.NLG-CHG-41 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
92 | 70467233 | HS-TKP | 0016573546 |  | 2105183437 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | LDG CHG-ENG#1,2 DEPRESERVE (-300ER) | REL | MNOA | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.LDG-CHG-92 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
93 | 70467233 | HS-TKP | 0016573547 |  | 2105183437 | AC02 |  | 2026-10-22 | 11LHM/A | 0020 | LDG CHG-ENG#1,2 DEPRESERVE (-300ER) | REL | MNOA | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.LDG-CHG-92 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
94 | 70467233 | HS-TKP-32-21-0101-NLG | 0016573349 |  | 2105183347 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | NLG CHG-LUB NLG & ACT MECH'S LWR COMP. | REL |  | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.NLG-CHG-57 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
95 | 70467233 | HS-TKP-32-11-0102-RH_MLG | 0016573527 |  | 2105183421 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | RH MLG CHG-INSTALL DRAG STRUT DOOR. | REL | MAVA | H/26-TKP-XXLDG-GNRL-N |  |  |  | BKK_H | REP | 777.OPR.MLG-CHG-R45 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
96 | 70467233 | HS-TKP-32-21-0101-NLG | 0016573345 |  | 2105183343 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | NLG CHG-INSTALL WHEEL,TIRE ASSY(NEWGEAR) | REL | MNOA | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.NLG-CHG-80 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
97 | 70467233 | HS-TKP-32-21-0101-NLG | 0016573347 |  | 2105183345 | AC02 | RII/DII | 2026-10-22 | 11LHM/A | 0010 | NLG CHG-ADJUST NLG STEERING SYSTEM | REL | MNOA | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.NLG-CHG-56 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
98 | 70467233 | HS-TKP-32-11-0101-LH_MLG | 0016573490 |  | 2105183385 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | LH MLG CHG-INSTALL MLG WHEEL, TIRE ASSY | REL | MNOA | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-L83 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
99 | 70467233 | HS-TKP-32-11-0101-LH_MLG | 0016573495 |  | 2105183390 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | LH MLG CHG-INSTALL MLG BRAKE | REL | MNOA | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-L84 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
100 | 70467233 | HS-TKP-32-11-0102-RH_MLG | 0016573531 |  | 2105183424 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | RH MLG CHG-INSTALL MLG WHEEL, TIRE ASSY | REL | MNOA | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-R83 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
101 | 70467233 | HS-TKP-32-11-0102-RH_MLG | 0016573536 |  | 2105183429 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | RH MLG CHG-INSTALL MLG BRAKE | REL | MNOA | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-R84 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
102 | 70467233 | HS-TKP-32-21-0101-NLG | 0016573348 |  | 2105183346 | AC02 |  | 2026-10-22 | 11LHM/E | 0010 | NLG CHG-TEST PROXIMITY SENSORS NOSE GEAR | REL | MAVA | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.NLG-CHG-55 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
103 | 70467233 | HS-TKP-32-11-0101-LH_MLG | 0016573479 |  | 2105183375 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | LH MLG CHG-INST MLG DRAG BRACE ASSY | REL | MAVA | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-L42 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
104 | 70467233 | HS-TKP-32-11-0101-LH_MLG | 0016573481 |  | 2105183377 | AC02 |  | 2026-10-22 | 11LHM/E | 0010 | LH MLG CHG- TEST BRAKE TEMP MONITOR SYS. | REL | MAVA | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | OPC | 777.OPR.MLG-CHG-L57 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
105 | 70467233 | HS-TKP-32-11-0101-LH_MLG | 0016573485 |  | 2105183381 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | LH MLG CHG-SERV MLG SHOCK STRUT(021-999) | REL | MAVA | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-L53 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
106 | 70467233 | HS-TKP-32-11-0102-RH_MLG | 0016573507 |  | 2105183402 | AC02 |  | 2026-10-22 | 11LHM/E | 0010 | RH MLG CHG-SYS TEST LDG POS IND&WARN SYS | REL | MAVA | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-R58 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
107 | 70467233 | HS-TKP-32-11-0102-RH_MLG | 0016573522 |  | 2105183416 | AC02 |  | 2026-10-22 | 11LHM/E | 0010 | RH MLG CHG- TEST BRAKE TEMP MONITOR SYS. | REL | MAVA | H/26-TKP-XXLDG-GNRL-N |  |  |  | BKK_H | REP | 777.OPR.MLG-CHG-R57 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
108 | 70467233 | HS-TKP-32-11-0102-RH_MLG | 0016573526 |  | 2105183420 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | RH MLG CHG-SERV MLG SHOCK STRUT(021-99 | REL | MAVA | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-R53 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
109 | 70467233 | HS-TKP-32-21-0101-NLG | 0016573337 |  | 2105183316 | AC02 |  | 2026-10-22 | 11LHM/E | 0010 | NLG CHG-SYS TEST FLT INTERPHONE SYS. | REL | MNOA | H/26-TKP-XXLDG-GNRL-N |  |  |  | BKK_H | REP | 777.OPR.NLG-CHG-60 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
110 | 70467233 | HS-TKP-32-21-0101-NLG | 0016573353 |  | 2105183350 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | NLG CHG-SERVICE NLG SHOCK STRUT(021-999) | REL | MAVA | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.NLG-CHG-52 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
111 | 70467233 | HS-TKP-32-11-0101-LH_MLG | 0016573366 |  | 2105183363 | AC02 |  | 2026-10-22 | 11LHM/E | 0010 | LH MLG CHG-SYS TEST LDG POS IND&WARN SYS | REL | MAVA | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-L58 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
112 | 70467233 | HS-TKP-32-11-0102-RH_MLG | 0016573509 |  | 2105183404 | AC02 | RII/DII | 2026-10-22 | 11LHM/A | 0010 | RH MLG CHANGE-INSTALL LDG(200,200ER,300) | REL | MAVA | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-R30 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
113 | 70467233 | HS-TKP-32-11-0102-RH_MLG | 0016573510 |  | 2105183404 | AC02 | RII/DII | 2026-10-22 | 11LHM/E | 0020 | RH MLG CHANGE-INSTALL LDG(200,200ER,300) | REL | MAVA | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-R30 |  | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
114 | 70468547 | HS-TKP | 0016611811 | KP884B261026 | KP884B261026 | AC05 |  | 2026-08-01 | 11PAINT | 0010 | WING REAR SPAR:AFTER REMOVED | REL |  | H/26-TKP-XXLDG-GNRL-N |  |  |  | BKK_H | REP |  | 2026-10-27 | 2026-08-01 | 15:04:00 | 2026-11-30 | 19:00:00
115 | 70467233 | HS-TKP-32-21-0101-NLG | 0016573333 |  | 2105183312 | AC02 |  | 2026-10-22 | 11LHM/A | 0010 | NLG - RECORD THE TRANSFER COMPONENTS | REL |  | H/26-TKP-XXLDG-GNRL-N |  |  |  | BKK_H | REP | 777.OPR.NLG-CHG-05 | 2026-10-25 | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
116 | 70467233 | HS-TKP-32-21-0101-NLG | 0016573350 |  | 2105183348 | AC02 | RII/DII | 2026-10-22 | 11LHM/A | 0010 | INSTALLATION OF NLG(200,200ER,300,3 | REL | MNOA | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.NLG-CHG-40 | 2026-10-25 | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
117 | 70467233 | HS-TKP-32-21-0101-NLG | 0016573351 |  | 2105183348 | AC02 | RII/DII | 2026-10-22 | 11LHM/E | 0020 | INSTALLATION OF NLG(200,200ER,300,3 | REL | MNOA | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.NLG-CHG-40 | 2026-10-25 | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
118 | 70467233 | HS-TKP-32-11-0101-LH_MLG | 0016573368 |  | 2105183365 | AC02 | RII/DII | 2026-10-22 | 11LHM/A | 0010 | LH MLG CHANGE-INSTALL LDG(200,200ER,300) | REL | MAVA | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-L30 | 2026-10-27 | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00
119 | 70467233 | HS-TKP-32-11-0101-LH_MLG | 0016573369 |  | 2105183365 | AC02 | RII/DII | 2026-10-22 | 11LHM/E | 0020 | LH MLG CHANGE-INSTALL LDG(200,200ER,300) | REL | MAVA | H/26-TKP-XXLDG-GNRL-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 777.OPR.MLG-CHG-L30 | 2026-10-27 | 2026-10-22 | 18:00:00 | 2026-10-31 | 23:59:00

## TEXT TKP
####### HS-TKP: LDG CHG ######
EST. TAT 15 DAYS // PERIOD 23OCT– 31OCT2026 REV.70467233
TOW IN : 23OCT26 TIME XXXX AM ,LAST FLIGHT 22 OCT. 2026 TG633
AIRCRAFT SERIAL NUMBER HS-TKP / 415257 , AIRCRAFT EFFECTIVITY CODE 026 TKP
########WORK HIGHLIGHT 29 Oct. 2026##########
SHOP DMK (KHUN SESTHA MB-B TEL 66-8416) REPLACE BUSHING BY HYDRAULIC PRESSURE (COMPLETE)
2105183426 RH MLG CHG-INST MLG SIDE BRACE ASSY(021)
######### HS-TKP ON TIME LINE AS BELOW ####
23OCT26 : AIRCRAFT ARRIVAL → DEFUEL → PREPARATION
24OCT26 : AIRCRAFT JACKING → OPEN ACCESS → WHEEL/BRAKE REMOVAL
25OCT26 : REMOVE NLG, LH MLG & RH MLG
26OCT26 : CLEAN & INSPECT LANDING GEAR ATTACHMENTS
27OCT26 : INSTALL NEW LANDING GEARS → RII/DII
28OCT26 : INSTALL WHEELS & BRAKES → SERVICING & LUBRICATION
29OCT26 : ADJUSTMENT → HYDRAULIC BLEEDING → FUNCTIONAL TESTS
30OCT26 : COMPLETE TESTS → RECTIFICATION → LOWER AIRCRAFT
31OCT26 : FINAL CLEANING → CLOSE-UP → LAE SIGN → CRS/RTS
(PREPARATION → JACKING → REMOVAL → INSPECTION → INSTALLATION → SERVICING → TESTING → RESTORATION → FINAL RELEASE)
REMARK : COPY LINK FULL DASHBOARD ON DESKTOP TG ONLY : http://acm-hpv-app07.dt.thaiairways.co.th/RevisionPlan/BKKStatus.html

## TWA
HS-TWA_C3(9Y)+MOD DATE 21 OCT. 2026
Item | Revision | Functional loc. | Confirmation | Notification | Order | Order Type | Ident.Insp.Task | Reference Date | Oper.WorkCenter | Activity | Description | Syste | User status | WBS ord. header | Priority | Priority | Working Group | Main WorkCtr | MaintActivType | External Ident. | Actual start | Bas. start date | Start time | Basic fin. date | Basic fin. time
1 | 70462433 | HS-TWA | 0016041008 | 1103108360 | 2105035790 | AC02 |  | 2026-10-18 | 11LHM/E | 0010 | OPC INFLAT OCCU RESTRAINT AIRBAG BATT | TECO |  | H/26-TWA-X0C03-NONR | 3 | TG Appr. Req. 3 | IERA_CABIN | BKK_H | OPC | 787.MPD.25-171-00 | 2026-10-16 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
2 | 70462433 | HS-TWA | 0016041009 | 1103108360 | 2105035790 | AC02 |  | 2026-10-18 | 11LHM/C | 0020 | OPC INFLAT OCCU RESTRAINT AIRBAG BATT | TECO |  | H/26-TWA-X0C03-NONR | 3 | TG Appr. Req. 3 | IERA_CABIN | BKK_H | OPC | 787.MPD.25-171-00 |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
3 | 70462433 | HS-TWA | 0016442701 |  | 2105149237 | AC01 | EWIS | 2026-10-08 | 11LQ/IE | 0010 | GVI WIRING WING REAR SPAR TO TRAILING ED | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-2 | 2 | DCA Appr. Req. 2 | INSP-I_FLOOR | BKK_H | GVI | 787.MPD.20-715-00 | 2026-10-06 | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
4 | 70462433 | HS-TWA | 0016570691 |  | 2105149237 | AC01 | EWIS | 2026-10-08 | 11LQ/IE | 0020 | GVI WIRING WING REAR SPAR TO TRAILING ED | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-2 | 2 | DCA Appr. Req. 2 | INSP-I_FLOOR | BKK_H | GVI | 787.MPD.20-715-00 |  | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
5 | 70462433 | HS-TWA | 0016442749 |  | 2105149282 | AC01 |  | 2026-10-10 | 11LHM/E | 0010 | OPC check the Main and APU Bat | TECO |  | H/26-TWA-X0C03-BLOK-I-N | 2 | DCA Appr. Req. 2 | IERA_CABIN | BKK_H | OPC | 787.MPD.24-013-00 | 2026-10-17 | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
6 | 70462433 | HS-TWA | 0016442750 |  | 2105149282 | AC01 |  | 2026-10-10 | 11LHM/E | 0020 | OPC check the Main and APU Bat | TECO |  | H/26-TWA-X0C03-BLOK-I-N | 2 | DCA Appr. Req. 2 | IERA_CABIN | BKK_H | OPC | 787.MPD.24-013-00 | 2026-10-20 | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
7 | 70462433 | HS-TWA | 0016442802 |  | 2105149330 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | GVI(EXT)LE TO FRONT SPAR UP/LWR OUTB,LHW | TECO |  | H/26-TWA-X0C03-BLOK-0-2 |  |  | INSP-W_LEADING EDGE | BKK_H | GVI | 787.MPD.57-822-01 | 2026-10-13 | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
8 | 70462433 | HS-TWA | 0016442987 |  | 2105149502 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | GVI TRAILING EDGE FLAP SEALS | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-2 | 1 | DCA Appr. Req. 1 | WING_LEADING EDGE | BKK_H | GVI | 787.MPD.27-485-00 | 2026-10-14 | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
9 | 70462433 | HS-TWA | 0016442988 |  | 2105149502 | AC01 |  | 2026-10-18 | 11LHM/A | 0020 | GVI TRAILING EDGE FLAP SEALS | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-2 | 1 | DCA Appr. Req. 1 | WING_LEADING EDGE | BKK_H | GVI | 787.MPD.27-485-00 |  | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
10 | 70462433 | HS-TWA | 0016237638 | WA030C160326 | WA030C160326 | AC05 |  | 2026-10-21 | PER | 0010 | 25 TRIM IN FRONT OF SEAT 44A BETWEEN FLO | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2026-03-16 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
11 | 70462433 | HS-TWA | 0016237639 | WA030C160326 | WA030C160326 | AC05 |  | 2026-10-21 | BKK_H | 0020 | 25 TRIM IN FRONT OF SEAT 44A BETWEEN FLO | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2026-10-21 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
12 | 70462433 | HS-TWA | 0015754809 | WA038C080625 | WA038C080625 | AC05 |  | 2026-10-16 | MXP | 0010 | 25 STN 1L ; FLOOR COVERING POOR CONDITIO | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
13 | 70462433 | HS-TWA | 0015754810 | WA038C080625 | WA038C080625 | AC05 |  | 2026-10-16 | BKK_L | 0020 | 25 STN 1L ; FLOOR COVERING POOR CONDITIO | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2025-08-27 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
14 | 70462433 | HS-TWA | 0016372562 | WA041C050626 | WA041C050626 | AC05 |  | 2026-10-15 | BKK_L | 0010 | 25 LAMINATE AT 2R AREA INFRONT OF GALLEY | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2026-10-16 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
15 | 70462433 | HS-TWA | 0016372563 | WA041C050626 | WA041C050626 | AC05 |  | 2026-10-15 | BKK_H | 0020 | 25 LAMINATE AT 2R AREA INFRONT OF GALLEY | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2026-10-16 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
16 | 70462433 | HS-TWA | 0016349422 | WA049F260526 | WA049F260526 | AC05 |  | 2026-10-20 | BKK_L | 0010 | 50 AFT CARGO RH STA 1600 SIDE WALL PANEL | TECO |  | L/26-TWA-LI-MSC-N | P | Responsible Planner |  | BKK_H | REP |  | 2026-05-26 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
17 | 70462433 | HS-TWA | 0016349423 | WA049F260526 | WA049F260526 | AC05 |  | 2026-10-20 | BKK_L | 0020 | 50 AFT CARGO RH STA 1600 SIDE WALL PANEL | TECO |  | L/26-TWA-LI-MSC-N | P | Responsible Planner |  | BKK_H | REP |  | 2026-10-12 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
18 | 70462433 | HS-TWA | 0016473703 | WA050F070826 | WA050F070826 | AC05 |  | 2026-10-15 | BKK_L | 0010 | 71 WAC FOUND ENG1 INNER BARREL PANEL INL | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2026-10-01 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
19 | 70462433 | HS-TWA | 0016473704 | WA050F070826 | WA050F070826 | AC05 |  | 2026-10-15 | BKK_H | 0020 | 71 WAC FOUND ENG1 INNER BARREL PANEL INL | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2026-10-15 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
20 | 70462433 | HS-TWA | 0016069807 | WA052C041225 | WA052C041225 | AC05 |  | 2026-10-16 | BKK_L | 0010 | 25 LAMINATE FLOOR IN FRONT OF FCRC (1L A | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2025-12-04 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
21 | 70462433 | HS-TWA | 0016069809 | WA052C041225 | WA052C041225 | AC05 |  | 2026-10-16 | 11LHM/C | 0020 | 25 LAMINATE FLOOR IN FRONT OF FCRC (1L A | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
22 | 70462433 | HS-TWA | 0016069808 | WA052C041225 | WA052C041225 | AC05 |  | 2026-10-16 | BKK_L | 0020 | 25 LAMINATE FLOOR IN FRONT OF FCRC (1L A | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2026-10-22 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
23 | 70462433 | HS-TWA | 0016125039 | WA053C120126 | WA053C120126 | AC05 |  | 2026-10-16 | BKK_L | 0010 | 25 FLOOR SURFACE AT 4R POOR CONDITION AN | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
24 | 70462433 | HS-TWA | 0016125040 | WA053C120126 | WA053C120126 | AC05 |  | 2026-10-16 | BKK_H | 0020 | 25 FLOOR SURFACE AT 4R POOR CONDITION AN | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2026-01-12 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
25 | 70462433 | HS-TWA | 0016389817 | WA070C190626 | WA070C190626 | AC05 |  | 2026-10-22 | PER | 0010 | 52 CABIN WAC FOUND DAIMABLE WINDOW ELECT | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2026-10-13 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
26 | 70462433 | HS-TWA | 0016389818 | WA070C190626 | WA070C190626 | AC05 |  | 2026-10-22 | BKK_H | 0020 | 52 CABIN WAC FOUND DAIMABLE WINDOW ELECT | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2026-10-13 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
27 | 70462433 | HS-TWA | 0016092806 | WA072C141225 | WA072C141225 | AC05 |  | 2026-10-18 | CTS | 0010 | 25 SIDE STOWAGE AT ARM REST SEAT 14E LOO | TECO | DPRC | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2026-01-28 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
28 | 70462433 | HS-TWA | 0016092807 | WA072C141225 | WA072C141225 | AC05 |  | 2026-10-18 | BKK_L | 0020 | 25 SIDE STOWAGE AT ARM REST SEAT 14E LOO | TECO | DPRC | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2026-01-28 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
29 | 70462433 | HS-TWA | 0016155615 | WA072C141225 | WA072C141225 | AC05 |  | 2026-10-18 | BKK_H | 0030 | 25 SIDE STOWAGE AT ARM REST SEAT 14E LOO | TECO | DPRC | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
30 | 70462433 | HS-TWA | 0016390556 | WA075C200626 | WA075C200626 | AC05 |  | 2026-10-18 | BKK_L | 0010 | 25 SEAT 12K,61B PED POWER FAILURE SHOWN | TECO | DPRC | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2026-06-20 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
31 | 70462433 | HS-TWA | 0016390557 | WA075C200626 | WA075C200626 | AC05 |  | 2026-10-18 | BKK_H | 0020 | 25 SEAT 12K,61B PED POWER FAILURE SHOWN | TECO | DPRC | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
32 | 70462433 | HS-TWA | 0016139616 | WA080C200126 | WA080C200126 | AC05 |  | 2026-10-18 | BKK_L | 0010 | 25 CARPET BETWEEN 12F/12K UNEVEN. | TECO | DPRC | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
33 | 70462433 | HS-TWA | 0016139617 | WA080C200126 | WA080C200126 | AC05 |  | 2026-10-18 | BKK_H | 0020 | 25 CARPET BETWEEN 12F/12K UNEVEN. | TECO | DPRC | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2026-01-23 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
34 | 70462433 | HS-TWA | 0016563965 | WA109F290926 | WA109F290926 | AC05 |  | 2026-10-21 | BKK_L | 0010 | 32 STATUS MSG ''ANTISKID 8'' DISPLAYED | TECO |  | H/26-TWA-X0C03-NONR | C | Category C |  | BKK_H | REP |  | 2026-10-21 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
35 | 70462433 | HS-TWA | 0016563966 | WA109F290926 | WA109F290926 | AC05 |  | 2026-10-21 | BKK_H | 0020 | 32 STATUS MSG ''ANTISKID 8'' DISPLAYED | TECO |  | H/26-TWA-X0C03-NONR | C | Category C |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
36 | 70462433 | HS-TWA | 0016574032 | WA644A071026 | WA644A071026 | AC05 |  | 2026-10-15 | 11PAINT | 0010 | NOSE GEAR DOOR | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-13 | 2026-10-07 | 15:34:00 | 2026-10-14 | 16:00:00
37 | 70462433 | HS-TWA | 0016574034 | WA645A071026 | WA645A071026 | AC05 |  | 2026-10-18 | 11PAINT | 0010 | PASSENGER/CREW DOORS | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-08 | 2026-10-07 | 15:43:00 | 2026-10-14 | 16:00:00
38 | 70462433 | HS-TWA | 0016575352 | WA657B081026 | WA657B081026 | AC05 |  | 2026-10-20 | 11PAINT | 0010 | ATA57:FOUND RH WING INB. AND OUTB. SLAT | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-16 | 2026-10-08 | 14:47:00 | 2026-10-08 | 19:00:00
39 | 70462433 | HS-TWA | 0016575353 | WA657B081026 | WA657B081026 | AC05 |  | 2026-10-20 | 11PAINT | 0020 | ATA57:FOUND RH WING INB. AND OUTB. SLAT | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-16 | 2026-10-08 | 14:47:00 | 2026-10-08 | 19:00:00
40 | 70462433 | HS-TWA | 0016575375 | WA661B081026 | WA661B081026 | AC05 |  | 2026-10-15 | 11PAINT | 0010 | ALL LAVATORY DR HAND PUSH MARKING PAINT | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-11 | 2026-10-08 | 16:06:00 | 2026-10-08 | 19:00:00
41 | 70462433 | HS-TWA | 0016577180 | WA663A081026 | WA663A081026 | AC05 |  | 2026-10-14 | 11CLEAN | 0010 | 50-CARGO,FWD AFT COMPT CEILING PANEL. | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-15 | 2026-10-08 | 16:27:00 | 2026-10-08 | 19:00:00
42 | 70462433 | HS-TWA | 0016576937 | WA663A081026 | WA663A081026 | AC05 |  | 2026-10-14 | 11CMPST | 0020 | 50-CARGO,FWD AFT COMPT CEILING PANEL. | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-14 | 2026-10-08 | 16:27:00 | 2026-10-08 | 19:00:00
43 | 70462433 | HS-TWA | 0016579832 | WA684B101026 | WA684B101026 | AC05 |  | 2026-10-20 | 11CLEAN | 0010 | ATA:57 FOUND ACCESS PANEL LEADING EDGE S | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-13 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
44 | 70462433 | HS-TWA | 0016579833 | WA684B101026 | WA684B101026 | AC05 |  | 2026-10-20 | 11PAINT | 0020 | ATA:57 FOUND ACCESS PANEL LEADING EDGE S | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
45 | 70462433 | HS-TWA | 0016579834 | WA685B101026 | WA685B101026 | AC05 |  | 2026-10-20 | 11CLEAN | 0010 | ATA:57 FOUND ACCESS PANEL LEADING EDGE S | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-13 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
46 | 70462433 | HS-TWA | 0016579835 | WA685B101026 | WA685B101026 | AC05 |  | 2026-10-20 | 11PAINT | 0020 | ATA:57 FOUND ACCESS PANEL LEADING EDGE S | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
47 | 70462433 | HS-TWA | 0016584028 | WA705A131026 | WA705A131026 | AC05 |  | 2026-10-18 | 11SH | 0010 | 25:EQUIPMENT AND FURNISHINGS | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-15 | 2026-10-13 | 16:55:00 | 2026-10-14 | 19:00:00
48 | 70462433 | HS-TWA | 0016585001 | WA708B141026 | WA708B141026 | AC05 |  | 2026-10-15 | 11CMPST | 0010 | ATA72:INSP. ENG NO.2 FOUND OUTLET GUIDE | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-15 | 2026-10-14 | 10:24:00 | 2026-10-14 | 19:00:00
49 | 70462433 | HS-TWA | 0016588752 | WA717A151026 | WA717A151026 | AC05 |  | 2026-10-15 | 11CMPST | 0010 | INLET COWL | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-17 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
50 | 70462433 | HS-TWA | 0016588753 | WA717A151026 | WA717A151026 | AC05 |  | 2026-10-15 | 11CMPST | 0020 | INLET COWL | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-17 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
51 | 70462433 | HS-TWA | 0016589075 | WA718A151026 | WA718A151026 | AC05 |  | 2026-10-22 | 11CMPST | 0010 | ENGINE COWLING | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-17 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
52 | 70462433 | HS-TWA | 0016589576 | WA718A151026 | WA718A151026 | AC05 |  | 2026-10-22 | 11PAINT | 0020 | ENGINE COWLING | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
53 | 70462433 | HS-TWA | 0016591922 | WA738A181026 | WA738A181026 | AC05 |  | 2026-10-21 | 11LHM/C | 0010 | 25:B/C SEAT ACCESS COVER | TECO |  | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
54 | 70462433 | HS-TWA | 0016591923 | WA738A181026 | WA738A181026 | AC05 |  | 2026-10-21 | 11CMPST | 0020 | 25:B/C SEAT ACCESS COVER | TECO |  | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-21 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
55 | 70462433 | HS-TWA | 0016591924 | WA738A181026 | WA738A181026 | AC05 |  | 2026-10-21 | 11LHM/C | 0030 | 25:B/C SEAT ACCESS COVER | TECO |  | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
56 | 70462433 | HS-TWA | 0016598778 | WA759B211026 | WA759B211026 | AC05 |  | 2026-10-22 | 11PAINT | 0010 | 25:PAINT COVER UNDET FOOTREST ALL SEAT Z | TECO |  | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-21 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
57 | 70462433 | HS-TWA | 0016426415 | 1103176072 | 2105145000 | AC02 |  | 2026-10-16 | 11LHM/C | 0010 | REMOVE AND CLEAN ALL TOILET SHROUD. | TECO | DPRC | H/26-TWA-X0C03-NONR | 4 | TG Appr. Req. 4 | CABIN_LAVATORY | BKK_H | CLN | 787.MPD.3832410001-TG01 | 2026-10-20 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
58 | 70462433 | HS-TWA | 0016426416 | 1103176072 | 2105145000 | AC02 |  | 2026-10-16 | 11LHM/C | 0020 | REMOVE AND CLEAN ALL TOILET SHROUD. | TECO | DPRC | H/26-TWA-X0C03-NONR | 4 | TG Appr. Req. 4 | CABIN_LAVATORY | BKK_H | CLN | 787.MPD.3832410001-TG01 |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
59 | 70462433 | HS-TWA | 0016239707 | WA052C200326 | WA052C200326 | AC05 |  | 2026-10-14 | BKK_L | 0010 | 25 SEAT 14F AND 14A FIX ARMREST POOR CON | TECO | DPRC | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2026-03-20 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
60 | 70462433 | HS-TWA | 0016240780 | WA052C200326 | WA052C200326 | AC05 |  | 2026-10-14 | 11LHM/A | 0020 | 25 SEAT 14F AND 14A FIX ARMREST POOR CON | TECO | DPRC | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
61 | 70462433 | HS-TWA | 0016240779 | WA052C200326 | WA052C200326 | AC05 |  | 2026-10-14 | BKK_L | 0020 | 25 SEAT 14F AND 14A FIX ARMREST POOR CON | TECO | DPRC | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
62 | 70462433 | HS-TWA | 0016535290 | WA095F120926 | WA095F120926 | AC05 |  | 2026-10-14 | BKK_L | 0010 | 50 REF W/O 2105170657 GVI-FWD CARGO COMP | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2026-09-12 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
63 | 70462433 | HS-TWA | 0016536013 | WA095F120926 | WA095F120926 | AC05 |  | 2026-10-14 | BKK_H | 0020 | 50 REF W/O 2105170657 GVI-FWD CARGO COMP | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2026-10-14 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
64 | 70462433 | HS-TWA | 0016591731 | WA724A161026 | WA724A161026 | AC05 |  | 2026-10-21 | 11CMPST | 0010 | AFT CARGO DOOR ASSEMBLY | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | 11CMPST | REP |  | 2026-10-21 | 2026-10-16 | 16:24:00 | 2026-10-17 | 16:00:00
65 | 70462433 | HS-TWA | 0016591741 | WA725A161026 | WA725A161026 | AC05 |  | 2026-10-21 | 11CMPST | 0010 | FWD CARGO DOOR ASSEMBLY | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | 11CMPST | REP |  | 2026-10-21 | 2026-10-16 | 16:30:00 | 2026-10-19 | 16:00:00
66 | 70462433 | HS-TWA | 0016367050 | 1103165811 | 2105127301 | AC02 |  | 2026-10-18 | 11CMPST | 0010 | DVI INNER COWL & T/R T/S ENG2 | TECO |  | H/26-TWA-X0C03-NONR | 4 | TG Appr. Req. 4 | WING_ENGINE | BKK_H | REP | 787.MPD.7111010028-TG02 | 2026-10-14 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
67 | 70462433 | HS-TWA | 0016367051 | 1103165811 | 2105127301 | AC02 |  | 2026-10-18 | 11CMPST | 0020 | DVI INNER COWL & T/R T/S ENG2 | TECO |  | H/26-TWA-X0C03-NONR | 4 | TG Appr. Req. 4 | WING_ENGINE | BKK_H | REP | 787.MPD.7111010028-TG02 |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
68 | 70462433 | HS-TWA | 0016367052 | 1103165811 | 2105127301 | AC02 |  | 2026-10-18 | 11CMPST | 0030 | DVI INNER COWL & T/R T/S ENG2 | TECO |  | H/26-TWA-X0C03-NONR | 4 | TG Appr. Req. 4 | WING_ENGINE | BKK_H | REP | 787.MPD.7111010028-TG02 |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
69 | 70462433 | HS-TWA | 0016367053 | 1103165811 | 2105127301 | AC02 |  | 2026-10-18 | 11CMPST | 0040 | DVI INNER COWL & T/R T/S ENG2 | TECO |  | H/26-TWA-X0C03-NONR | 4 | TG Appr. Req. 4 | WING_ENGINE | BKK_H | REP | 787.MPD.7111010028-TG02 |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
70 | 70462433 | HS-TWA | 0016355664 | WA022C290526 | WA022C290526 | AC05 |  | 2026-10-20 | BKK_L | 0010 | 25 KICK STRIP UNDER STOWAGE S6 DR 1L DAM | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
71 | 70462433 | HS-TWA | 0016355666 | WA022C290526 | WA022C290526 | AC05 |  | 2026-10-20 | 11LHM/C | 0020 | 25 KICK STRIP UNDER STOWAGE S6 DR 1L DAM | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
72 | 70462433 | HS-TWA | 0016355665 | WA022C290526 | WA022C290526 | AC05 |  | 2026-10-20 | BKK_L | 0020 | 25 KICK STRIP UNDER STOWAGE S6 DR 1L DAM | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2026-10-27 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
73 | 70462433 | HS-TWA | 0016580688 | WA690A101026 | WA690A101026 | AC05 |  | 2026-10-14 | 11CMPST | 0010 | 25:STOWAGE COMPARTMENTS. | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-12 | 2026-10-10 | 18:16:00 | 2026-10-11 | 19:00:00
74 | 70462433 | HS-TWA | 0016368948 | WA005F080626 | WA005F080626 | AC05 |  | 2026-10-20 | BKK_L | 0010 | 57 INSP FOUND SLAT 6 (LH) WAS GOUGE DAMA | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2026-06-08 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
75 | 70462433 | HS-TWA | 0016371265 | WA005F080626 | WA005F080626 | AC05 |  | 2026-10-20 | 11SH | 0020 | 57 INSP FOUND SLAT 6 (LH) WAS GOUGE DAMA | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2026-10-20 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
76 | 70462433 | HS-TWA | 0016598434 | WA005F080626 | WA005F080626 | AC05 |  | 2026-10-20 | 12LC/AP | 0030 | 57 INSP FOUND SLAT 6 (LH) WAS GOUGE DAMA | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
77 | 70462433 | HS-TWA | 0015754848 | WA009C250525 | WA009C250525 | AC05 |  | 2026-10-20 | BKK_L | 0010 | 25 HJK 35 OVERHEAD BIN BROKEN. | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
78 | 70462433 | HS-TWA | 0015754849 | WA009C250525 | WA009C250525 | AC05 |  | 2026-10-20 | 11CMPST | 0020 | 25 HJK 35 OVERHEAD BIN BROKEN. | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2026-10-16 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
79 | 70462433 | HS-TWA | 0016574037 | WA647A071026 | WA647A071026 | AC05 |  | 2026-10-21 | 11PAINT | 0010 | FUSELAGE | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-08 | 2026-10-07 | 15:49:00 | 2026-10-14 | 16:00:00
80 | 70462433 | HS-TWA | 0016575359 | WA658A081026 | WA658A081026 | AC05 |  | 2026-10-18 | 11PAINT | 0010 | FWD.&AFT.CARGO DOOR FRAME PRESSURE SEAL | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-10 | 2026-10-08 | 15:25:00 | 2026-10-09 | 19:00:00
81 | 70462433 | HS-TWA | 0016575370 | WA660B081026 | WA660B081026 | AC05 |  | 2026-10-18 | 11PAINT | 0010 | 25:ALL BUMPER STRIPS SEAT IN B/C PAINT | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-08 | 2026-10-08 | 15:37:00 | 2026-10-09 | 19:00:00
82 | 70462433 | HS-TWA | 0016579857 | WA687A101026 | WA687A101026 | AC05 |  | 2026-10-15 | 11PAINT | 0010 | PASSENGER ENTRY DOOR CUT OUT | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-12 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
83 | 70462433 | HS-TWA | 0016591901 | WA727A171026 | WA727A171026 | AC05 |  | 2026-10-21 | 11LHM/C | 0010 | 38 VACUMM TOILET LID AND SEAT COVER | TECO |  | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-20 | 2026-10-17 | 16:03:00 | 2026-10-17 | 19:00:00
84 | 70462433 | HS-TWA | 0016591902 | WA727A171026 | WA727A171026 | AC05 |  | 2026-10-21 | 11CLEAN | 0020 | 38 VACUMM TOILET LID AND SEAT COVER | TECO |  | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-17 | 2026-10-17 | 16:03:00 | 2026-10-17 | 19:00:00
85 | 70462433 | HS-TWA | 0016591903 | WA727A171026 | WA727A171026 | AC05 |  | 2026-10-21 | 11LHM/C | 0030 | 38 VACUMM TOILET LID AND SEAT COVER | TECO |  | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-20 | 2026-10-17 | 16:03:00 | 2026-10-17 | 19:00:00
86 | 70462433 | HS-TWA | 0016591927 | WA727A171026 | WA727A171026 | AC05 |  | 2026-10-21 | 11LHM/C | 0040 | 38 VACUMM TOILET LID AND SEAT COVER | TECO |  | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-17 | 16:03:00 | 2026-10-17 | 19:00:00
87 | 70462433 | HS-TWA | 0016442679 |  | 2105148835 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | Replace APU Aft seal & Aft fairing seal. | TECO |  | H/26-TWA-X0C03-BLOK-0-1 | 3 | TG Appr. Req. 3 | FLOOR_TAIL | BKK_H | INS | 787.MPD.49-023-00 | 2026-10-10 | 2026-10-06 | 00:00:00 | 2026-10-06 | 00:00:00
88 | 70462433 | HS-TWA | 0015994372 | WA062C191025 | WA062C191025 | AC05 |  | 2026-10-14 | BKK_L | 0010 | 25 18A, 11A, 16E, 11A, 18E ARMREST POOR | TECO | DPRC | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2026-03-20 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
89 | 70462433 | HS-TWA | 0015994373 | WA062C191025 | WA062C191025 | AC05 |  | 2026-10-14 | BKK_H | 0020 | 25 18A, 11A, 16E, 11A, 18E ARMREST POOR | TECO | DPRC | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
90 | 70462433 | HS-TWA-49-11-0001-000 | 0016258420 | 1103146125 | 2105094233 | AC03 |  | 2026-10-18 | 11LHM/A | 0010 | 490412:BSI APU 1ST AND 2ND STAGE TURBINE | TECO | DPRC WARR ODAT | H/26-TWA-X0C03-MOD | 3 | TG Appr. Req. 3 |  | BKK_H | MOD | 787.TO.490412-02 | 2026-10-12 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
91 | 70462433 | HS-TWA | 0016280645 | 1103150139 | 2105100879 | AC02 |  | 2026-10-18 | 11LHM/C | 0010 | G/26-009:LIFE VEST RFID REGISTRATION | TECO | DPRC ODAT | H/26-TWA-X0C03-MOD | 4 | TG Appr. Req. 4 | CABIN_ALL CABIN | BKK_H | RAR | 787.ED.BKKJA-G/26-009 | 2026-09-15 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
92 | 70462433 | HS-TWA | 0016442726 |  | 2105149262 | AC01 |  | 2026-10-09 | 11LQ/IE | 0010 | GVI STATIC DISCHARG | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-2 | 1 | DCA Appr. Req. 1 | INSP-I_FLOOR | BKK_H | GVI | 787.MPD.23-020-00 | 2026-10-08 | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
93 | 70462433 | HS-TWA | 0015838933 | WA003C290725 | WA003C290725 | AC05 |  | 2026-10-21 | BKK_L | 0010 | 25 MOP 51L CRACKED AT SEAT 34K AND 39K S | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
94 | 70462433 | HS-TWA | 0015838935 | WA003C290725 | WA003C290725 | AC05 |  | 2026-10-21 | 11LHM/A | 0020 | 25 MOP 51L CRACKED AT SEAT 34K AND 39K S | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
95 | 70462433 | HS-TWA | 0015838934 | WA003C290725 | WA003C290725 | AC05 |  | 2026-10-21 | BKK_L | 0020 | 25 MOP 51L CRACKED AT SEAT 34K AND 39K S | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2026-10-21 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
96 | 70462433 | HS-TWA | 0016575994 | WA007F051026 | WA007F051026 | AC05 |  | 2026-10-21 | BKK_H | 0010 | 73 EICAS STATUS MSG "ENG EEC C1 L" DISPL | TECO |  | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-17 | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
97 | 70462433 | HS-TWA | 0015338188 | WA027C290924 | WA027C290924 | AC05 |  | 2026-10-18 | BKK_L | 0010 | 56 SEAT NO.55K-61K DIMMABLE CONTROL FUNC | TECO | DPRC | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
98 | 70462433 | HS-TWA | 0015338190 | WA027C290924 | WA027C290924 | AC05 |  | 2026-10-18 | 11LHM/C | 0020 | 56 SEAT NO.55K-61K DIMMABLE CONTROL FUNC | TECO | DPRC | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
99 | 70462433 | HS-TWA | 0015338189 | WA027C290924 | WA027C290924 | AC05 |  | 2026-10-18 | BKK_L | 0020 | 56 SEAT NO.55K-61K DIMMABLE CONTROL FUNC | TECO | DPRC | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2025-11-10 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
100 | 70462433 | HS-TWA | 0016348874 | WA048F260526 | WA048F260526 | AC05 |  | 2026-10-20 | BKK_L | 0010 | 50 FWD CARGO LH BETWEEN STA 400 TO STA 5 | TECO |  | L/26-TWA-LI-MSC-N | P | Responsible Planner |  | BKK_H | REP |  | 2026-05-26 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
101 | 70462433 | HS-TWA | 0016349426 | WA048F260526 | WA048F260526 | AC05 |  | 2026-10-20 | BKK_L | 0020 | 50 FWD CARGO LH BETWEEN STA 400 TO STA 5 | TECO |  | L/26-TWA-LI-MSC-N | P | Responsible Planner |  | BKK_H | REP |  | 2026-10-15 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
102 | 70462433 | HS-TWA | 0015692968 | WA149F010525 | WA149F010525 | AC05 |  | 2026-10-18 | BKK_L | 0010 | 52 DOOR 2R, MOVEABLE HINGE COVER, UPPER | TECO | DPRC | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
103 | 70462433 | HS-TWA | 0015692969 | WA149F010525 | WA149F010525 | AC05 |  | 2026-10-18 | 11CMPST | 0020 | 52 DOOR 2R, MOVEABLE HINGE COVER, UPPER | TECO | DPRC | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2025-05-02 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
104 | 70462433 | HS-TWA | 0016574035 | WA646B071026 | WA646B071026 | AC05 |  | 2026-10-20 | 11PAINT | 0010 | ATA:57 FOUND LH AND RH WING UPPER AND LO | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-09 | 2026-10-07 | 15:31:00 | 2026-10-07 | 19:00:00
105 | 70462433 | HS-TWA | 0016574036 | WA646B071026 | WA646B071026 | AC05 |  | 2026-10-20 | 11PAINT | 0020 | ATA:57 FOUND LH AND RH WING UPPER AND LO | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-09 | 2026-10-07 | 15:31:00 | 2026-10-07 | 19:00:00
106 | 70462433 | HS-TWA | 0016574038 | WA648A071026 | WA648A071026 | AC05 |  | 2026-10-15 | 11CMPST | 0010 | CARGO COMPARTMENT | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-08 | 2026-10-07 | 16:15:00 | 2026-10-14 | 16:00:00
107 | 70462433 | HS-TWA | 0016574039 | WA648A071026 | WA648A071026 | AC05 |  | 2026-10-15 | 11CMPST | 0020 | CARGO COMPARTMENT | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-07 | 16:15:00 | 2026-10-14 | 16:00:00
108 | 70462433 | HS-TWA | 0016575350 | WA656B081026 | WA656B081026 | AC05 |  | 2026-10-21 | 11PAINT | 0010 | ATA57:FOUND LH WING INB. AND OUTB. SLAT | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-15 | 2026-10-08 | 14:28:00 | 2026-10-08 | 19:00:00
109 | 70462433 | HS-TWA | 0016575351 | WA656B081026 | WA656B081026 | AC05 |  | 2026-10-21 | 11PAINT | 0020 | ATA57:FOUND LH WING INB. AND OUTB. SLAT | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-15 | 2026-10-08 | 14:28:00 | 2026-10-08 | 19:00:00
110 | 70462433 | HS-TWA | 0016577206 | WA669A081026 | WA669A081026 | AC05 |  | 2026-10-18 | 11LHM/A | 0010 | 53-FUSELAGE, NOSE RADOME SEAL. | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-12 | 2026-10-08 | 17:01:00 | 2026-10-08 | 19:00:00
111 | 70462433 | HS-TWA | 0016584031 | WA707A131026 | WA707A131026 | AC05 |  | 2026-10-21 | 11LHM/C | 0010 | 25:EQUIPMENT AND FURNISHINGS | TECO |  | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-16 | 2026-10-13 | 18:13:00 | 2026-10-14 | 19:00:00
112 | 70462433 | HS-TWA | 0016584032 | WA707A131026 | WA707A131026 | AC05 |  | 2026-10-21 | 11CMPST | 0020 | 25:EQUIPMENT AND FURNISHINGS | TECO |  | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-15 | 2026-10-13 | 18:13:00 | 2026-10-14 | 19:00:00
113 | 70462433 | HS-TWA | 0016584033 | WA707A131026 | WA707A131026 | AC05 |  | 2026-10-21 | 11PAINT | 0030 | 25:EQUIPMENT AND FURNISHINGS | TECO |  | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-13 | 18:13:00 | 2026-10-14 | 19:00:00
114 | 70462433 | HS-TWA | 0016584034 | WA707A131026 | WA707A131026 | AC05 |  | 2026-10-21 | 11LHM/C | 0040 | 25:EQUIPMENT AND FURNISHINGS | TECO |  | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-13 | 18:13:00 | 2026-10-14 | 19:00:00
115 | 70462433 | HS-TWA | 0016588751 | WA716A151026 | WA716A151026 | AC05 |  | 2026-10-18 | 11SH | 0010 | INLET COWL ENG LH | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
116 | 70462433 | HS-TWA | 0016589170 | WA716A151026 | WA716A151026 | AC05 |  | 2026-10-18 | 11NDT | 0020 | INLET COWL ENG LH | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-16 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
117 | 70462433 | HS-TWA | 0016589171 | WA716A151026 | WA716A151026 | AC05 |  | 2026-10-18 | 11SH | 0030 | INLET COWL ENG LH | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-16 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
118 | 70462433 | HS-TWA | 0016591918 | WA737A181026 | WA737A181026 | AC05 |  | 2026-10-21 | 11LHM/C | 0010 | 25:EQUIPMENT AND FURNISHINGS | TECO |  | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-18 | 15:20:00 | 2026-10-19 | 19:00:00
119 | 70462433 | HS-TWA | 0016591919 | WA737A181026 | WA737A181026 | AC05 |  | 2026-10-21 | 11CMPST | 0020 | 25:EQUIPMENT AND FURNISHINGS | TECO |  | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-19 | 2026-10-18 | 15:20:00 | 2026-10-19 | 19:00:00
120 | 70462433 | HS-TWA | 0016591920 | WA737A181026 | WA737A181026 | AC05 |  | 2026-10-21 | 11PAINT | 0030 | 25:EQUIPMENT AND FURNISHINGS | TECO |  | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-18 | 15:20:00 | 2026-10-19 | 19:00:00
121 | 70462433 | HS-TWA | 0016591921 | WA737A181026 | WA737A181026 | AC05 |  | 2026-10-21 | 11LHM/C | 0040 | 25:EQUIPMENT AND FURNISHINGS | TECO |  | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-18 | 15:20:00 | 2026-10-19 | 19:00:00
122 | 70462433 | HS-TWA | 0016596159 | WA751A191026 | WA751A191026 | AC05 |  | 2026-10-20 | 11SH | 0010 | FUSELAGE SECTION 49 WING-TO-BODY FAIRING | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | 11SH | REP |  | 2026-10-20 | 2026-10-19 | 16:30:00 | 2026-10-20 | 16:00:00
123 | 70462433 | HS-TWA | 0016600928 | WA761B211026 | WA761B211026 | AC05 |  | 2026-10-21 | 11SH | 0010 | 25: INSPECTION FOUND THE MONITORS LOOSEO | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-21 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
124 | 70462433 | HS-TWA | 0016600929 | WA761B211026 | WA761B211026 | AC05 |  | 2026-10-21 | 11LHM/E | 0020 | 25: INSPECTION FOUND THE MONITORS LOOSEO | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
125 | 70462433 | HS-TWA | 0015884433 | 1103081925 | 2104993943 | AC03 |  | 2026-10-18 | 11LHM/A | 0010 | 531624:HPEC INSP/REPL CGO BARRIER FITTIN | TECO | DPRC ODAT | H/26-TWA-X0C03-MOD -G-F | 0 | AD | INSP-F_ALL FLOOR | BKK_H | NDT | 787.TO.531624 |  | 2026-10-04 | 00:00:00 | 2026-10-16 | 24:00:00
126 | 70462433 | HS-TWA | 0015884434 | 1103081925 | 2104993943 | AC03 |  | 2026-10-18 | 11NDT | 0020 | 531624:HPEC INSP/REPL CGO BARRIER FITTIN | TECO | DPRC ODAT | H/26-TWA-X0C03-MOD -G-F | 0 | AD | INSP-F_ALL FLOOR | BKK_H | NDT | 787.TO.531624 | 2026-10-09 | 2026-10-04 | 00:00:00 | 2026-10-16 | 24:00:00
127 | 70462433 | HS-TWA | 0015884435 | 1103081925 | 2104993943 | AC03 |  | 2026-10-18 | 11SH | 0030 | 531624:HPEC INSP/REPL CGO BARRIER FITTIN | TECO | DPRC ODAT | H/26-TWA-X0C03-MOD -G-F | 0 | AD | INSP-F_ALL FLOOR | BKK_H | NDT | 787.TO.531624 |  | 2026-10-04 | 00:00:00 | 2026-10-16 | 24:00:00
128 | 70462433 | HS-TWA | 0015946435 | WA088C260925 | WA088C260925 | AC05 |  | 2026-10-21 | BKK_L | 0010 | 25 61J USB PORT INOP | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2025-09-26 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
129 | 70462433 | HS-TWA | 0015960946 | WA088C260925 | WA088C260925 | AC05 |  | 2026-10-21 | BKK_H | 0020 | 25 61J USB PORT INOP | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
130 | 70462433 | HS-TWA | 0016562192 | WA104F290926 | WA104F290926 | AC05 |  | 2026-10-21 | PER | 0010 | 25 OFAR CREW BUNK NO.4 SEAT BELT FRAYED | TECO |  | H/26-TWA-X0C03-NONR | C | Category C |  | BKK_H | REP |  | 2026-10-19 | 2026-10-05 | 00:00:00 | 2026-10-29 | 24:00:00
131 | 70462433 | HS-TWA | 0016564966 | WA104F290926 | WA104F290926 | AC05 |  | 2026-10-21 | BKK_H | 0020 | 25 OFAR CREW BUNK NO.4 SEAT BELT FRAYED | TECO |  | H/26-TWA-X0C03-NONR | C | Category C |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-29 | 24:00:00
132 | 70462433 | HS-TWA | 0015826425 | 1103072242 | 2104976806 | AC03 |  | 2026-10-18 | 11LHM/A | 0010 | 531617:INSP SEAT TRACK FITTINGS SEC46 | TECO | DPRC ODAT | H/26-TWA-X0C03-MOD -G-F | 0 | AD | INSP-F_ALL FLOOR | BKK_H | NDT | 787.TO.531617-01 |  | 2026-10-04 | 00:00:00 | 2026-10-16 | 24:00:00
133 | 70462433 | HS-TWA | 0015826426 | 1103072242 | 2104976806 | AC03 |  | 2026-10-18 | 11NDT | 0020 | 531617:INSP SEAT TRACK FITTINGS SEC46 | TECO | DPRC ODAT | H/26-TWA-X0C03-MOD -G-F | 0 | AD | INSP-F_ALL FLOOR | BKK_H | NDT | 787.TO.531617-01 | 2026-10-09 | 2026-10-04 | 00:00:00 | 2026-10-16 | 24:00:00
134 | 70462433 | HS-TWA | 0015826427 | 1103072242 | 2104976806 | AC03 |  | 2026-10-18 | 11SH | 0030 | 531617:INSP SEAT TRACK FITTINGS SEC46 | TECO | DPRC ODAT | H/26-TWA-X0C03-MOD -G-F | 0 | AD | INSP-F_ALL FLOOR | BKK_H | NDT | 787.TO.531617-01 |  | 2026-10-04 | 00:00:00 | 2026-10-16 | 24:00:00
135 | 70462433 | HS-TWA | 0015319714 | 1102987767 | 2104848994 | AC03 |  | 2026-10-18 | 11LHM/A | 0010 | 550248: INSP VERT FIN MAIN BOX REAR SPAR | TECO | DPRC ODAT | H/26-TWA-X0C03-MOD -G-F | 0 | AD | INSP-F_TAIL | BKK_H | SDI | 787.TO.550248-02 |  | 2026-10-04 | 00:00:00 | 2026-10-16 | 24:00:00
136 | 70462433 | HS-TWA | 0015319715 | 1102987767 | 2104848994 | AC03 |  | 2026-10-18 | 11SH | 0020 | 550248: INSP VERT FIN MAIN BOX REAR SPAR | TECO | DPRC ODAT | H/26-TWA-X0C03-MOD -G-F | 0 | AD | INSP-F_TAIL | BKK_H | SDI | 787.TO.550248-02 | 2026-10-08 | 2026-10-04 | 00:00:00 | 2026-10-16 | 24:00:00
137 | 70462433 | HS-TWA | 0015319716 | 1102987767 | 2104848994 | AC03 |  | 2026-10-18 | 11NDT | 0030 | 550248: INSP VERT FIN MAIN BOX REAR SPAR | TECO | DPRC ODAT | H/26-TWA-X0C03-MOD -G-F | 0 | AD | INSP-F_TAIL | BKK_H | SDI | 787.TO.550248-02 |  | 2026-10-04 | 00:00:00 | 2026-10-16 | 24:00:00
138 | 70462433 | HS-TWA | 0015737604 | 1103056706 | 2104954109 | AC03 |  | 2026-10-18 | 11LHM/A | 0010 | 570981:CHG AUX-D BACKUP RIB &MID SPOILER | TECO | DPRC ODAT | H/26-TWA-X0C03-MOD -G-W | 3 | TG Appr. Req. 3 |  | BKK_H | MOD | 787.TO.MTO-570981 | 2026-10-16 | 2026-10-04 | 00:00:00 | 2026-10-16 | 24:00:00
139 | 70462433 | HS-TWA | 0015737605 | 1103056706 | 2104954109 | AC03 |  | 2026-10-18 | BKK_H | 0020 | 570981:CHG AUX-D BACKUP RIB &MID SPOILER | TECO | DPRC ODAT | H/26-TWA-X0C03-MOD -G-W | 3 | TG Appr. Req. 3 |  | BKK_H | MOD | 787.TO.MTO-570981 | 2026-10-14 | 2026-10-04 | 00:00:00 | 2026-10-16 | 24:00:00
140 | 70462433 | HS-TWA | 0016586417 | 1103056706 | 2104954109 | AC03 |  | 2026-10-18 | BKK_H | 0030 | 570981:CHG AUX-D BACKUP RIB &MID SPOILER | TECO | DPRC ODAT | H/26-TWA-X0C03-MOD -G-W | 3 | TG Appr. Req. 3 |  | BKK_H | MOD | 787.TO.MTO-570981 |  | 2026-10-04 | 00:00:00 | 2026-10-16 | 24:00:00
141 | 70462433 | HS-TWA | 0016554541 | WA005F180926 | WA005F180926 | AC05 |  | 2026-10-18 | CGK | 0010 | 21 STS MSG INTEGRATED CLG RECIRC AIR. | TECO | NOGO DPRC | H/26-TWA-X0C03-NONR | C | Category C |  | BKK_H | REP |  | 2026-10-18 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
142 | 70462433 | HS-TWA | 0016554542 | WA005F180926 | WA005F180926 | AC05 |  | 2026-10-18 | BKK_H | 0020 | 21 STS MSG INTEGRATED CLG RECIRC AIR. | TECO | NOGO DPRC | H/26-TWA-X0C03-NONR | C | Category C |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
143 | 70462433 | HS-TWA | 0016240781 | WA050C200326 | WA050C200326 | AC05 |  | 2026-10-18 | BKK_L | 0010 | 44 CS #2 INOP (CONTENT SERVER #2) | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2026-03-20 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
144 | 70462433 | HS-TWA | 0016240782 | WA050C200326 | WA050C200326 | AC05 |  | 2026-10-18 | BKK_H | 0020 | 44 CS #2 INOP (CONTENT SERVER #2) | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
145 | 70462433 | HS-TWA | 0014288915 | 1102818090 | 2104574202 | AC03 |  | 2026-10-18 | 11LHM/A | 0010 | 490424:APU AIR INLET DR INSULATION CHG | TECO | DPRC | H/26-TWA-X0C03-MOD -G-F | 2 | DCA Appr. Req. 2 |  | BKK_H | MOD | 787.TO.490424 | 2026-10-10 | 2026-10-04 | 00:00:00 | 2026-10-16 | 24:00:00
146 | 70462433 | HS-TWA | 0014288916 | 1102818090 | 2104574202 | AC03 |  | 2026-10-18 | 11U | 0020 | 490424:APU AIR INLET DR INSULATION CHG | TECO | DPRC | H/26-TWA-X0C03-MOD -G-F | 2 | DCA Appr. Req. 2 |  | BKK_H | MOD | 787.TO.490424 |  | 2026-10-04 | 00:00:00 | 2026-10-16 | 24:00:00
147 | 70462433 | HS-TWA | 0015346126 | 1102992156 | 2104855661 | AC03 |  | 2026-10-18 | 11LHM/A | 0010 | 540383:Strut Fire Seal and Firewall | TECO | DPRC ODAT | H/26-TWA-X0C03-MOD -G-W | 2 | DCA Appr. Req. 2 |  | BKK_H | MOD | 787.TO.MTO-540383 | 2026-10-15 | 2026-10-04 | 00:00:00 | 2026-10-16 | 24:00:00
148 | 70462433 | HS-TWA | 0016442472 |  | 2105148833 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | 787 APU REMOVAL | TECO |  | H/26-TWA-X0C03-BLOK-0-1 | 4 | TG Appr. Req. 4 | FLOOR_TAIL | BKK_H | INS | 787.MAM.AMM.49-11-00-04 | 2026-10-10 | 2026-10-06 | 00:00:00 | 2026-10-06 | 00:00:00
149 | 70462433 | HS-TWA | 0016442473 |  | 2105148833 | AC01 |  | 2026-10-18 | 11LHM/E | 0020 | 787 APU REMOVAL | TECO |  | H/26-TWA-X0C03-BLOK-0-1 | 4 | TG Appr. Req. 4 | FLOOR_TAIL | BKK_H | INS | 787.MAM.AMM.49-11-00-04 | 2026-10-10 | 2026-10-06 | 00:00:00 | 2026-10-06 | 00:00:00
150 | 70462433 | HS-TWA | 0016442474 |  | 2105148833 | AC01 |  | 2026-10-18 | 11E | 0030 | 787 APU REMOVAL | TECO |  | H/26-TWA-X0C03-BLOK-0-1 | 4 | TG Appr. Req. 4 | FLOOR_TAIL | BKK_H | INS | 787.MAM.AMM.49-11-00-04 |  | 2026-10-06 | 00:00:00 | 2026-10-06 | 00:00:00
151 | 70462433 | HS-TWA | 0016442953 |  | 2105149474 | AC01 |  | 2026-10-15 | 11LHM/A | 0010 | DIS P.FLT CTL(RHW+CTR)HYD SYS CHK V_AILE | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-6 |  |  | WING_HYDRAULIC | BKK_H | DIS | 787.MPD.27-040-00 | 2026-10-17 | 2026-10-08 | 08:15:00 | 2026-10-13 | 08:15:00
152 | 70462433 | HS-TWA | 0016442954 |  | 2105149474 | AC01 |  | 2026-10-15 | 11LHM/A | 0020 | DIS P.FLT CTL(RHW+CTR)HYD SYS CHK V_AILE | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-6 |  |  | WING_HYDRAULIC | BKK_H | DIS | 787.MPD.27-040-00 |  | 2026-10-08 | 08:15:00 | 2026-10-13 | 08:15:00
153 | 70462433 | HS-TWA | 0016442994 |  | 2105149508 | AC01 |  | 2026-10-09 | 11LHM/E | 0010 | FUC Lightning/HIRF Protection Components | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-6 | 2 | DCA Appr. Req. 2 | IERA_WING | BKK_H | FUC | 787.MPD.20-380-02 | 2026-10-21 | 2026-10-13 | 08:15:00 | 2026-10-13 | 08:15:00
154 | 70462433 | HS-TWA | 0016442995 |  | 2105149508 | AC01 |  | 2026-10-09 | 11LHM/E | 0020 | FUC Lightning/HIRF Protection Components | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-6 | 2 | DCA Appr. Req. 2 | IERA_WING | BKK_H | FUC | 787.MPD.20-380-02 |  | 2026-10-13 | 08:15:00 | 2026-10-13 | 08:15:00
155 | 70462433 | HS-TWA | 0016482509 | 1103186707 | 2105159681 | AC02 |  | 2026-10-09 | 11LHM/A | 0010 | SAMPLING HYDRAULIC FLUID | TECO | DPRC | H/26-TWA-X0C03-NONR | 4 | TG Appr. Req. 4 | WING_HYDRAULIC | BKK_H | REP | 787.MPD.291100101-TG01 | 2026-10-09 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
156 | 70462433 | HS-TWA | 0016258396 | WA080C310326 | WA080C310326 | AC05 |  | 2026-10-21 | CTS | 0010 | 25 SEAT 54B PCU INOP (IFE MONITOR IS AVA | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2026-04-01 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
157 | 70462433 | HS-TWA | 0016259714 | WA080C310326 | WA080C310326 | AC05 |  | 2026-10-21 | BKK_H | 0020 | 25 SEAT 54B PCU INOP (IFE MONITOR IS AVA | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
158 | 70462433 | HS-TWA | 0016562208 | WA098F280926 | WA098F280926 | AC05 |  | 2026-10-21 | NGO | 0010 | 32 EICAS STAT MSG 'BRAKE 8" DISPLAYED . | TECO |  | H/26-TWA-X0C03-NONR | C | Category C |  | BKK_H | REP |  | 2026-10-21 | 2026-10-05 | 00:00:00 | 2026-10-29 | 24:00:00
159 | 70462433 | HS-TWA | 0016563128 | WA098F280926 | WA098F280926 | AC05 |  | 2026-10-21 | BKK_H | 0020 | 32 EICAS STAT MSG 'BRAKE 8" DISPLAYED . | TECO |  | H/26-TWA-X0C03-NONR | C | Category C |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-29 | 24:00:00
160 | 70462433 | HS-TWA | 0016388975 | WA103F220626 | WA103F220626 | AC05 |  | 2026-10-18 | BKK_L | 0010 | 56 SEAT 37A, 39K, 41K ELECTRICALLY DIMMA | TECO | DPRC | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2026-06-22 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
161 | 70462433 | HS-TWA | 0016392839 | WA103F220626 | WA103F220626 | AC05 |  | 2026-10-18 | BKK_H | 0020 | 56 SEAT 37A, 39K, 41K ELECTRICALLY DIMMA | TECO | DPRC | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
162 | 70462433 | HS-TWA | 0016572371 | WA634A061026 | WA634A061026 | AC05 |  | 2026-10-11 | 11LHM/E | 0010 | 33: ANTI-COLLISION LIGHT TAIL CONE RH SI | TECO | DPRC | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2026-10-11 | 2026-10-06 | 12:02:00 | 2026-10-06 | 18:59:00
163 | 70462433 | HS-TWA | 0016442839 |  | 2105149367 | AC01 | SCT | 2026-10-18 | 11LHM/A | 0010 | FUC-CHK TRAILING EDGE FLAP GEARED ROTARY | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-8 | 1 | DCA Appr. Req. 1 | FLOOR_LANDING GEAR | BKK_H | FUC | 787.MPD.27-360-00,27-CMR-07 |  | 2026-10-15 | 08:15:00 | 2026-10-15 | 08:15:00
164 | 70462433 | HS-TWA | 0016442462 |  | 2105148823 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | ARRANGEMENT OF DOCKS -WING GROUP | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-I-N | 4 | TG Appr. Req. 4 | WING_ALL WING | BKK_H | SVC | PP.OPR.FOR ARRANGE DOCK |  | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
165 | 70462433 | HS-TWA | 0016442463 |  | 2105148824 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | DE-DOCK AND CHECKLIST-WING GROUP | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-F-I | 4 | TG Appr. Req. 4 | WING_ALL WING | BKK_H | SVC | PP.OPR.FOR DE-DOCK |  | 2026-10-16 | 08:15:00 | 2026-10-16 | 08:15:00
166 | 70462433 | HS-TWA | 0016442464 |  | 2105148825 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | ARRANGEMENT OF DOCKS -FLOOR GROUP | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-I-N | 4 | TG Appr. Req. 4 | FLOOR_ALL FLOOR | BKK_H | SVC | PP.OPR.FOR ARRANGE DOCK |  | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
167 | 70462433 | HS-TWA | 0016442465 |  | 2105148826 | AC01 |  | 2026-10-05 | 11LHM/C | 0010 | ARRANGEMENT OF DOCKS -CABIN GROUP | TECO | DPRC | H/26-TWA-X0C03-BLOK-I-N | 4 | TG Appr. Req. 4 | CABIN_ALL CABIN | BKK_H | SVC | PP.OPR.FOR ARRANGE DOCK |  | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
168 | 70462433 | HS-TWA | 0016442467 |  | 2105148828 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | ARRANGEMENT OF DOCKS-LA-C GROUP | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-I-N | 4 | TG Appr. Req. 4 | ALL_ALL GRP | BKK_H | SVC | PP.OPR.FOR ARRANGE DOCK |  | 2026-10-04 | 08:15:00 | 2026-10-04 | 08:15:00
169 | 70462433 | HS-TWA | 0016442468 |  | 2105148829 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | DE-DOCK AND CHECKLIST-FLOOR GROUP | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-F-I | 4 | TG Appr. Req. 4 | FLOOR_ALL FLOOR | BKK_H | SVC | PP.OPR.FOR DE-DOCK |  | 2026-10-16 | 08:15:00 | 2026-10-16 | 08:15:00
170 | 70462433 | HS-TWA | 0016442469 |  | 2105148830 | AC01 |  | 2026-10-18 | 11LHM/C | 0010 | DE-DOCK AND CHECKLIST- CABIN GROUP | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-F-I | 4 | TG Appr. Req. 4 | CABIN_ALL CABIN | BKK_H | SVC | PP.OPR.FOR DE-DOCK |  | 2026-10-16 | 08:15:00 | 2026-10-16 | 08:15:00
171 | 70462433 | HS-TWA | 0016442470 |  | 2105148831 | AC01 |  | 2026-10-18 | 11LHM/E | 0010 | DE-DOCK AND CHECKLIST- IERA GROUP | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-F-I | 4 | TG Appr. Req. 4 | IERA_ALL IERA | BKK_H | SVC | PP.OPR.FOR DE-DOCK |  | 2026-10-16 | 08:15:00 | 2026-10-16 | 08:15:00
172 | 70462433 | HS-TWA | 0016442471 |  | 2105148832 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | DE-DOCK AND CHECKLIST LA-C GROUP | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-F-I | 4 | TG Appr. Req. 4 | ALL_ALL GRP | BKK_H | SVC | PP.OPR.FOR DE-DOCK |  | 2026-10-16 | 08:15:00 | 2026-10-16 | 08:15:00
173 | 70462433 | HS-TWA | 0016442681 |  | 2105148837 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | DOWN JACK OF AIRCRAFT B787 | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-F-I |  |  | ALL_ALL GRP | BKK_H | SVC | 787.OPR.DOWN JACK OF AIRCRAFT |  | 2026-10-16 | 08:15:00 | 2026-10-16 | 08:15:00
174 | 70462433 | HS-TWA | 0016442682 |  | 2105148838 | AC01 |  | 2026-10-07 | 11LHM/A | 0010 | TOWING OF AIRCRAFT | TECO |  | H/26-TWA-X0C03-BLOK-I-N |  |  | ALL_ALL GRP | BKK_H | SVC | 787.OPR.TOWING OF AIRCRAFT |  | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
175 | 70462433 | HS-TWA | 0016442708 |  | 2105149244 | AC01 | EWIS | 2026-10-09 | 11LQ/IE | 0010 | GVI WIRING AFT LEFT NACELLE STRUT FAIRIN | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-2 | 2 | DCA Appr. Req. 2 | INSP-I_FLOOR | BKK_H | GVI | 787.MPD.20-740-01 |  | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
176 | 70462433 | HS-TWA | 0016442713 |  | 2105149249 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | EXTERNAL-ZONAL(GV):FORWARD TORQUE BOX LH | TECO |  | H/26-TWA-X0C03-BLOK-0-5 | 2 | DCA Appr. Req. 2 | INSP-W_ENGINE | BKK_H | GVI | 787.MPD.54-895-01 |  | 2026-10-12 | 08:15:00 | 2026-10-12 | 08:15:00
177 | 70462433 | HS-TWA | 0016442714 |  | 2105149250 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | INTERNAL-ZONAL(GV):FORWARD TORQUE BOX LH | TECO |  | H/26-TWA-X0C03-BLOK-0-5 | 2 | DCA Appr. Req. 2 | INSP-W_ENGINE | BKK_H | GVI | 787.MPD.54-900-01 |  | 2026-10-12 | 08:15:00 | 2026-10-12 | 08:15:00
178 | 70462433 | HS-TWA | 0016442715 |  | 2105149251 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | EXTERNAL - ZONAL (GV): AFT TORQUE BOX LH | TECO |  | H/26-TWA-X0C03-BLOK-0-5 | 2 | DCA Appr. Req. 2 | INSP-W_ENGINE | BKK_H | GVI | 787.MPD.54-905-01 |  | 2026-10-12 | 08:15:00 | 2026-10-12 | 08:15:00
179 | 70462433 | HS-TWA | 0016442717 |  | 2105149253 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | INTERNAL - ZONAL (GV): AFT TORQUE BOX LH | TECO |  | H/26-TWA-X0C03-BLOK-0-5 | 2 | DCA Appr. Req. 2 | INSP-W_ENGINE | BKK_H | GVI | 787.MPD.54-910-01 |  | 2026-10-12 | 08:15:00 | 2026-10-12 | 08:15:00
180 | 70462433 | HS-TWA | 0016442718 |  | 2105149254 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | INTERNAL-ZONAL (GV):AFT NACELLE STRUT LH | TECO |  | H/26-TWA-X0C03-BLOK-0-5 | 2 | DCA Appr. Req. 2 | INSP-W_ENGINE | BKK_H | GVI | 787.MPD.54-921-01 |  | 2026-10-12 | 08:15:00 | 2026-10-12 | 08:15:00
181 | 70462433 | HS-TWA | 0016442719 |  | 2105149255 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | INTERNAL-ZONAL(GV):FORWARD NACELLE RH | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-0-5 | 2 | DCA Appr. Req. 2 | INSP-W_ENGINE | BKK_H | GVI | 787.MPD.54-935-02 |  | 2026-10-12 | 08:15:00 | 2026-10-12 | 08:15:00
182 | 70462433 | HS-TWA | 0016442723 |  | 2105149259 | AC01 |  | 2026-10-21 | 11LHM/C | 0010 | OPC-FLIGHT COMP SEAT LOCK | TECO |  | H/26-TWA-X0C03-BLOK-I-N |  |  | CABIN_COCKPIT | BKK_H | OPC | 787.MPD.25-095-00 |  | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
183 | 70462433 | HS-TWA | 0016442727 |  | 2105149263 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | INTERNAL-ZONAL (GV):AFT NACELLE STRUT RH | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-0-5 | 2 | DCA Appr. Req. 2 | INSP-W_ENGINE | BKK_H | GVI | 787.MPD.54-962-02 |  | 2026-10-12 | 08:15:00 | 2026-10-12 | 08:15:00
184 | 70462433 | HS-TWA | 0016442728 |  | 2105149264 | AC01 |  | 2026-10-09 | 11LQ/IE | 0010 | DVI the Main and APU Batt | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-5 | 1 | DCA Appr. Req. 1 | INSP-I_FLOOR | BKK_H | DVI | 787.MPD.24-011-00 |  | 2026-10-12 | 08:15:00 | 2026-10-12 | 08:15:00
185 | 70462433 | HS-TWA | 0016442729 |  | 2105149264 | AC01 |  | 2026-10-09 | 11LQ/IE | 0020 | DVI the Main and APU Batt | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-5 | 1 | DCA Appr. Req. 1 | INSP-I_FLOOR | BKK_H | DVI | 787.MPD.24-011-00 |  | 2026-10-12 | 08:15:00 | 2026-10-12 | 08:15:00
186 | 70462433 | HS-TWA | 0016442747 |  | 2105149280 | AC01 |  | 2026-10-07 | 11LQ/IA | 0010 | RECORD-TIME OF A/C ARRIVAL & TOW TO DOCK | TECO |  | H/26-TWA-X0C03-BLOK-I-N |  |  | ALL_ALL GRP | BKK_H | SVC | 787.OPR.RECORD-TIME |  | 2026-10-04 | 08:15:00 | 2026-10-04 | 08:15:00
187 | 70462433 | HS-TWA | 0016442753 |  | 2105149284 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | DEACTIVATION OF SPOILERS | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-I-N |  |  | WING_LEADING EDGE | BKK_H | SVC | 787.OPR.DEACTIVATION OF SPOILERS |  | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
188 | 70462433 | HS-TWA | 0016442757 |  | 2105149287 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | DEACTIVATION-LEADING EDGE SLATS | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-I-N |  |  | WING_LEADING EDGE | BKK_H | SVC | 787.OPR.DEACTIVATION-LEADING |  | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
189 | 70462433 | HS-TWA | 0016442758 |  | 2105149288 | AC01 |  | 2026-10-07 | 11LHM/A | 0010 | CONNECT-AIRCRAFT STATIC GROUNDING | TECO | DPRC | H/26-TWA-X0C03-BLOK-I-N |  |  | FLOOR_FUSELAGE | BKK_H | SVC | 787.OPR.CONNECT-A/C STATIC |  | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
190 | 70462433 | HS-TWA | 0016442761 |  | 2105149291 | AC01 |  | 2026-10-21 | 11LHM/C | 0010 | CHK-TECHNICAL MANUALS ON AIRCRAFT | TECO |  | H/26-TWA-X0C03-BLOK-I-N |  |  | CABIN_COCKPIT | BKK_H | GVI | 787.OPR.CHK-TECHNICAL MANUALS |  | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
191 | 70462433 | HS-TWA | 0016442771 |  | 2105149300 | AC01 |  | 2026-10-18 | 11LQ/IC | 0010 | DVI-FLIGHT SEAT ATTACHMENTS | TECO |  | H/26-TWA-X0C03-BLOK-0-3 |  |  | INSP-C_COCKPIT | BKK_H | DET | 787.MPD.25-100-00 |  | 2026-10-10 | 08:15:00 | 2026-10-10 | 08:15:00
192 | 70462433 | HS-TWA | 0016442773 |  | 2105149302 | AC01 |  | 2026-10-07 | 11LQ/IC | 0010 | DI-FLIGHT COMP SEAT OCCUPANT RESTRAINT | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-3 |  |  | INSP-C_COCKPIT | BKK_H | DI | 787.MPD.25-110-00 |  | 2026-10-10 | 16:30:00 | 2026-10-10 | 16:30:00
193 | 70462433 | HS-TWA | 0016442774 |  | 2105149303 | AC01 |  | 2026-10-05 | 11LHM/E | 0010 | DEACTIVATE-THE SAFETY SENSITIVE SYSTEMS | TECO | DPRC | H/26-TWA-X0C03-BLOK-I-N |  |  | IERA_CABIN | BKK_H | SVC | 787.OPR.DEACTIVATE SAFETY SEN |  | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
194 | 70462433 | HS-TWA | 0016442778 |  | 2105149307 | AC01 |  | 2026-10-07 | 11LQ/IC | 0010 | GVI-ATTENDANT SEAT ATTACHMENT | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-1 |  |  | INSP-I_CABIN | BKK_H | GVI | 787.MPD.25-146-00 |  | 2026-10-06 | 08:15:00 | 2026-10-06 | 08:15:00
195 | 70462433 | HS-TWA | 0016442780 |  | 2105149309 | AC01 |  | 2026-10-21 | 11LHM/C | 0010 | OPC-ATTENDANT SEAT OCCUPANT RESTRAINT | TECO | DPRC | H/26-TWA-X0C03-BLOK-I-N |  |  | CABIN_ALL CABIN | BKK_H | OPC | 787.MPD.25-150-00 |  | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
196 | 70462433 | HS-TWA | 0016442781 |  | 2105149310 | AC01 |  | 2026-10-21 | 11LHM/C | 0010 | OPC-OXYGEN DOOR LATCH | TECO | DPRC | H/26-TWA-X0C03-BLOK-I-N | 1 | DCA Appr. Req. 1 | CABIN_ALL CABIN | BKK_H | OPC | 787.MPD.35-035-00 |  | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
197 | 70462433 | HS-TWA | 0016442783 |  | 2105149312 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | VCK TE FLAP TORQUE TUBE GUARDS,LHW | TECO |  | H/26-TWA-X0C03-BLOK-0-1 |  |  | WING_TRAILING EDGE | BKK_H | VCK | 787.MPD.27-380-00 |  | 2026-10-06 | 00:00:00 | 2026-10-06 | 00:00:00
198 | 70462433 | HS-TWA | 0016442785 |  | 2105149314 | AC01 |  | 2026-10-10 | 11LHM/A | 0010 | OPC TE FLAP PWR DRIVE UNIT(HYD PRESS OFF | TECO |  | H/26-TWA-X0C03-BLOK-I-N |  |  | WING_TRAILING EDGE | BKK_H | OPC | 787.MPD.27-440-00 |  | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
199 | 70462433 | HS-TWA | 0016442786 |  | 2105149315 | AC01 |  | 2026-10-15 | 11LHM/A | 0010 | OPC LE SLAT PWR DRIVE UNIT(HYD PRESS OFF | TECO |  | H/26-TWA-X0C03-BLOK-I-N |  |  | WING_LEADING EDGE | BKK_H | OPC | 787.MPD.27-450-00 |  | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
200 | 70462433 | HS-TWA | 0016442819 |  | 2105149347 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | GVI(EXT) ZONAL SPOILER#8-14,RHW | TECO |  | H/26-TWA-X0C03-BLOK-0-2 |  |  | INSP-W_TRAILING EDGE | BKK_H | GVI | 787.MPD.57-944-02 |  | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
201 | 70462433 | HS-TWA | 0016442821 |  | 2105149349 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | GVI(EXT) ZONAL INB TE FLAP,RHW | TECO |  | H/26-TWA-X0C03-BLOK-0-2 |  |  | INSP-W_TRAILING EDGE | BKK_H | GVI | 787.MPD.57-948-02 |  | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
202 | 70462433 | HS-TWA | 0016442823 |  | 2105149351 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | GVI(EXT) ZONAL FLAPERON,RHW | TECO |  | H/26-TWA-X0C03-BLOK-0-2 |  |  | INSP-W_TRAILING EDGE | BKK_H | GVI | 787.MPD.57-952-02 |  | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
203 | 70462433 | HS-TWA | 0016442829 |  | 2105149357 | AC01 |  | 2026-10-21 | 11LHM/A | 0010 | LHW-INST WING ACCESS PANEL_INTV 3Y | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-7 |  |  | WING_ALL WING | BKK_H | RES | 787.OPR.ACC Z511,521,540,550,561,572 |  | 2026-10-14 | 08:15:00 | 2026-10-14 | 08:15:00
204 | 70462433 | HS-TWA | 0016442834 |  | 2105149362 | AC01 |  | 2026-10-21 | 11LQ/IA | 0010 | RECORD-TIMES OF TOW A/C AND TEST FLT | TECO |  | H/26-TWA-X0C03-BLOK-F-I |  |  | ALL_ALL GRP | BKK_H | SVC | 787.OPR.RECORD-TIMES TOW TEST FLT |  | 2026-10-16 | 08:15:00 | 2026-10-16 | 08:15:00
205 | 70462433 | HS-TWA | 0016442835 |  | 2105149363 | AC01 |  | 2026-10-21 | 11LQ/IA | 0010 | DELIVERY-A/C AFT MAINTENANCE | TECO |  | H/26-TWA-X0C03-BLOK-F-I |  |  | ALL_ALL GRP | BKK_H | SVC | 787.OPR.DELIVERY-A/C AFT MAINT |  | 2026-10-16 | 08:15:00 | 2026-10-16 | 08:15:00
206 | 70462433 | HS-TWA | 0016442837 |  | 2105149365 | AC01 |  | 2026-10-06 | 11LHM/E | 0010 | OPC-CHK HOR.STAB (L2 AND R2) CUTOUT SWIT | TECO | DPRC | H/26-TWA-X0C03-BLOK-I-N | 2 | DCA Appr. Req. 2 | IERA_CABIN | BKK_H | OPC | 787.MPD.27-280-00 |  | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
207 | 70462433 | HS-TWA | 0016442840 |  | 2105149368 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | GVI-ZONAL APU COMPARTMENT | TECO |  | H/26-TWA-X0C03-BLOK-0-3 |  |  | FLOOR_TAIL | BKK_H | GVI | 787.MPD.53-984-00 |  | 2026-10-10 | 08:15:00 | 2026-10-10 | 08:15:00
208 | 70462433 | HS-TWA | 0016442843 |  | 2105149371 | AC01 |  | 2026-10-21 | 11LHM/C | 0010 | INST-LIFE VESTS AND FLASHLIGHTS | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-5 |  |  | CABIN_INTERIOR | BKK_H | RES | 787.OPR.INST-LIFE VESTS AND FLASHLIGHTS |  | 2026-10-12 | 08:15:00 | 2026-10-12 | 08:15:00
209 | 70462433 | HS-TWA | 0016442844 |  | 2105149372 | AC01 |  | 2026-10-21 | 11LHM/A | 0010 | CHK-OIL AND HYD FLUID AFT ENG RUN-UP | TECO |  | H/26-TWA-X0C03-BLOK-0-8 |  |  | WING_ENGINE | BKK_H | SVC | 787.OPR.CHK-OIL HYD AFT ENG RUN-UP |  | 2026-10-15 | 08:15:00 | 2026-10-15 | 08:15:00
210 | 70462433 | HS-TWA | 0016442847 |  | 2105149375 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | ACTIVATION-LEADING EDGE SLATS | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-0-7 |  |  | WING_LEADING EDGE | BKK_H | SVC | 787.OPR.ACTIVATION-LEADING EDGE |  | 2026-10-14 | 08:15:00 | 2026-10-14 | 08:15:00
211 | 70462433 | HS-TWA | 0016442849 |  | 2105149377 | AC01 |  | 2026-10-22 | 11U | 0010 | MSC PRIOR TO FLIGHT | TECO |  | H/26-TWA-X0C03-BLOK-F-I |  |  | ALL_ALL GRP | BKK_H | SVC | 787.OPR.MSC PRIOR TO FLIGHT |  | 2026-10-16 | 08:15:00 | 2026-10-16 | 08:15:00
212 | 70462433 | HS-TWA | 0016442851 |  | 2105149379 | AC01 |  | 2026-10-18 | 11LHM/C | 0010 | OPC-PASSENGER ENTRY DOOR | TECO |  | H/26-TWA-X0C03-BLOK-0-8 |  |  | CABIN_DOOR | BKK_H | OPC | 787.MPD.52-060-00 |  | 2026-10-15 | 08:15:00 | 2026-10-15 | 08:15:00
213 | 70462433 | HS-TWA | 0016442852 |  | 2105149380 | AC01 |  | 2026-10-07 | 11LQ/IC | 0010 | GVI-PANSENGER ENTRY DOOR No.1 (LH) | TECO |  | H/26-TWA-X0C03-BLOK-0-2 | 3 | TG Appr. Req. 3 | INSP-C_DOOR | BKK_H | GVI | 787.MPD.52-835-01 |  | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
214 | 70462433 | HS-TWA | 0016442853 |  | 2105149381 | AC01 |  | 2026-10-07 | 11LQ/IC | 0010 | GVI-PANSENGER ENTRY DOOR No.2 (LH) | TECO |  | H/26-TWA-X0C03-BLOK-0-2 | 3 | TG Appr. Req. 3 | INSP-C_DOOR | BKK_H | GVI | 787.MPD.52-845-01 |  | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
215 | 70462433 | HS-TWA | 0016442854 |  | 2105149382 | AC01 |  | 2026-10-07 | 11LQ/IC | 0010 | GVI-PANSENGER ENTRY DOOR No.3 (LH) | TECO |  | H/26-TWA-X0C03-BLOK-0-2 | 3 | TG Appr. Req. 3 | INSP-C_DOOR | BKK_H | GVI | 787.MPD.52-855-01 |  | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
216 | 70462433 | HS-TWA | 0016442855 |  | 2105149383 | AC01 |  | 2026-10-07 | 11LQ/IC | 0010 | GVI-PANSENGER ENTRY DOOR No.4 (LH) | TECO |  | H/26-TWA-X0C03-BLOK-0-2 | 3 | TG Appr. Req. 3 | INSP-C_DOOR | BKK_H | GVI | 787.MPD.52-865-01 |  | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
217 | 70462433 | HS-TWA | 0016442856 |  | 2105149384 | AC01 |  | 2026-10-07 | 11LQ/IC | 0010 | GVI-PANSENGER ENTRY DOOR No.1 (RH) | TECO |  | H/26-TWA-X0C03-BLOK-0-2 | 3 | TG Appr. Req. 3 | INSP-C_DOOR | BKK_H | GVI | 787.MPD.52-875-02 |  | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
218 | 70462433 | HS-TWA | 0016442857 |  | 2105149385 | AC01 |  | 2026-10-07 | 11LQ/IC | 0010 | GVI-PANSENGER ENTRY DOOR No.2 (RH) | TECO |  | H/26-TWA-X0C03-BLOK-0-2 | 3 | TG Appr. Req. 3 | INSP-C_DOOR | BKK_H | GVI | 787.MPD.52-885-02 |  | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
219 | 70462433 | HS-TWA | 0016442858 |  | 2105149386 | AC01 |  | 2026-10-07 | 11LQ/IC | 0010 | GVI-PANSENGER ENTRY DOOR No.3 (RH) | TECO |  | H/26-TWA-X0C03-BLOK-0-2 | 3 | TG Appr. Req. 3 | INSP-C_DOOR | BKK_H | GVI | 787.MPD.52-895-02 |  | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
220 | 70462433 | HS-TWA | 0016442859 |  | 2105149387 | AC01 |  | 2026-10-07 | 11LQ/IC | 0010 | GVI-PANSENGER ENTRY DOOR No.4 (RH) | TECO |  | H/26-TWA-X0C03-BLOK-0-2 | 3 | TG Appr. Req. 3 | INSP-C_DOOR | BKK_H | GVI | 787.MPD.52-905-02 |  | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
221 | 70462433 | HS-TWA | 0016442860 |  | 2105149388 | AC01 |  | 2026-10-21 | 11LHM/A | 0010 | DISCONNECT-AIRCRAFT STATIC GROUNDING | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-8 |  |  | FLOOR_FUSELAGE | BKK_H | SVC | 787.OPR.DISCONNECT A/C STATIC |  | 2026-10-15 | 08:15:00 | 2026-10-15 | 08:15:00
222 | 70462433 | HS-TWA | 0016442861 |  | 2105149389 | AC01 |  | 2026-10-21 | 11LHM/C | 0010 | CHK-TECHNICAL MANUALS INSTALLATIONS | TECO |  | H/26-TWA-X0C03-BLOK-0-8 |  |  | CABIN_COCKPIT | BKK_H | GVI | 787.OPR.CHK-TECHNICAL MANUALS |  | 2026-10-15 | 08:15:00 | 2026-10-15 | 08:15:00
223 | 70462433 | HS-TWA | 0016442862 |  | 2105149390 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | DEPRESERVATION OF APU | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-0-7 |  |  | FLOOR_TAIL | BKK_H | SVC | 787.OPR.DEPRESERVATION OF APU |  | 2026-10-14 | 08:15:00 | 2026-10-14 | 08:15:00
224 | 70462433 | HS-TWA | 0016442863 |  | 2105149391 | AC01 |  | 2026-10-21 | 11LHM/E | 0010 | ACTIVATE-THE SAFETY SENSITIVE SYSTEMS | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-8 |  |  | IERA_CABIN | BKK_H | SVC | 787.OPR.ACTIVATE-SAFETY |  | 2026-10-15 | 08:15:00 | 2026-10-15 | 08:15:00
225 | 70462433 | HS-TWA | 0016442864 |  | 2105149392 | AC01 |  | 2026-10-21 | 11U | 0010 | CERTIFICATE OF RELEASE TO SERVICE | TECO |  | H/26-TWA-X0C03-BLOK-F-I |  |  | ALL_ALL GRP | BKK_H | SVC | 787.OPR.CERTIFICATE OF RELEASE |  | 2026-10-16 | 08:15:00 | 2026-10-16 | 08:15:00
226 | 70462433 | HS-TWA | 0016442865 |  | 2105149393 | AC01 |  | 2026-10-21 | 11LHM/A | 0010 | LIST-REMAIN ITEMS/UNFINISHED-FLOOR GROUP | TECO |  | H/26-TWA-X0C03-BLOK-F-I |  |  | FLOOR_ALL FLOOR | BKK_H | SVC | 787.OPR.LIST-REMAIN FLOOR GROUP |  | 2026-10-16 | 08:15:00 | 2026-10-16 | 08:15:00
227 | 70462433 | HS-TWA | 0016442866 |  | 2105149394 | AC01 |  | 2026-10-21 | 11LHM/C | 0010 | LIST-REMAIN ITEMS/UNFINISHED-CABIN GROUP | TECO |  | H/26-TWA-X0C03-BLOK-F-I |  |  | CABIN_ALL CABIN | BKK_H | SVC | 787.OPR.LIST-REMAIN CABIN GROUP |  | 2026-10-16 | 08:15:00 | 2026-10-16 | 08:15:00
228 | 70462433 | HS-TWA | 0016442867 |  | 2105149395 | AC01 |  | 2026-10-21 | 11LHM/E | 0010 | LIST-REMAIN ITEMS/UNFINISHED-IERA GROUP | TECO |  | H/26-TWA-X0C03-BLOK-F-I |  |  | IERA_ALL IERA | BKK_H | SVC | 787.OPR.LIST-REMAIN IERA GROUP |  | 2026-10-16 | 08:15:00 | 2026-10-16 | 08:15:00
229 | 70462433 | HS-TWA | 0016442868 |  | 2105149396 | AC01 |  | 2026-10-21 | 11LHM/A | 0010 | LIST-REMAIN ITEMS/UNFINISHED-LH WING/ENG | TECO |  | H/26-TWA-X0C03-BLOK-F-I |  |  | WING_ALL WING | BKK_H | SVC | 787.OPR.LIST-REMAIN LH W/E GROUP |  | 2026-10-16 | 08:15:00 | 2026-10-16 | 08:15:00
230 | 70462433 | HS-TWA | 0016442869 |  | 2105149397 | AC01 |  | 2026-10-21 | 11LHM/A | 0010 | LIST-REMAIN ITEMS/UNFINISHED-RH WING/ENG | TECO |  | H/26-TWA-X0C03-BLOK-F-I |  |  | WING_ALL WING | BKK_H | SVC | 787.OPR.LIST-REMAIN RH W/E GROUP |  | 2026-10-16 | 08:15:00 | 2026-10-16 | 08:15:00
231 | 70462433 | HS-TWA | 0016442870 |  | 2105149398 | AC01 |  | 2026-10-21 | 11LQ/IA | 0010 | CLEARING-REPORTS BEFORE TRIM OF A/C | TECO |  | H/26-TWA-X0C03-BLOK-F-I |  |  | ALL_ALL GRP | BKK_H | SVC | 787.OPR.CLEAR-REPORTS BEFORE TRIM |  | 2026-10-16 | 08:15:00 | 2026-10-16 | 08:15:00
232 | 70462433 | HS-TWA | 0016442871 |  | 2105149399 | AC01 |  | 2026-10-21 | 11U | 0010 | FINAL OPC-FLT CONTL SYS-WING GROUP | TECO |  | H/26-TWA-X0C03-BLOK-F-I |  |  | WING_ALL WING | BKK_H | OPC | 787.OPR.FINAL OPC SYS-WING GROUP |  | 2026-10-16 | 08:15:00 | 2026-10-16 | 08:15:00
233 | 70462433 | HS-TWA | 0016442872 |  | 2105149400 | AC01 |  | 2026-10-21 | 11U | 0010 | FINAL OPC-FLT CONTL SYS-TAIL GROUP | TECO |  | H/26-TWA-X0C03-BLOK-F-I |  |  | FLOOR_TAIL | BKK_H | OPC | 787.OPR.FINAL OPC SYS-TAIL GROUP |  | 2026-10-16 | 08:15:00 | 2026-10-16 | 08:15:00
234 | 70462433 | HS-TWA | 0016442873 |  | 2105149401 | AC01 |  | 2026-10-21 | 11U | 0010 | CHECKLIST-ENG START/RUN-UP/SHUTDOWN | TECO |  | H/26-TWA-X0C03-BLOK-F-I |  |  | WING_ENGINE | BKK_H | SVC | 787.OPR.CHECKLIST-ENG START/RUN-UP/SHUT |  | 2026-10-16 | 08:15:00 | 2026-10-16 | 08:15:00
235 | 70462433 | HS-TWA | 0016442874 |  | 2105149402 | AC01 |  | 2026-10-21 | 11U | 0010 | ENGINE RUN-UP | TECO |  | H/26-TWA-X0C03-BLOK-0-8 |  |  | WING_ENGINE | BKK_H | OPC | 787.OPR.ENGINE RUN-UP |  | 2026-10-15 | 08:15:00 | 2026-10-15 | 08:15:00
236 | 70462433 | HS-TWA | 0016442882 |  | 2105149410 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | IDG DISCONNECT AND RESET MECHANISM | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-0-8 |  |  | WING_ENGINE | BKK_H | SVC | 787.OPR.IDG DISCONNECT AND RESET MECHAN |  | 2026-10-15 | 08:15:00 | 2026-10-15 | 08:15:00
237 | 70462433 | HS-TWA | 0016442888 |  | 2105149416 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | INSP AFT CARGO CONTAINER LOCKS | TECO |  | H/26-TWA-X0C03-BLOK-0-3 | 1 | DCA Appr. Req. 1 | INSP-F_AFT COMPT | BKK_H | DET | 787.MPD.50-025-00 |  | 2026-10-10 | 08:15:00 | 2026-10-10 | 08:15:00
238 | 70462433 | HS-TWA | 0016442891 |  | 2105149419 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | INSP BULK CARGO DOOR SEALS | TECO |  | H/26-TWA-X0C03-BLOK-0-3 |  |  | INSP-F_AFT COMPT | BKK_H | DET | 787.MPD.52-030-00 |  | 2026-10-10 | 16:30:00 | 2026-10-10 | 16:30:00
239 | 70462433 | HS-TWA | 0016442893 |  | 2105149421 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | INSP AFT CARGO INDICATOR | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-3 |  |  | INSP-F_AFT COMPT | BKK_H | VCK | 787.MPD.52-120-00 |  | 2026-10-10 | 16:30:00 | 2026-10-10 | 16:30:00
240 | 70462433 | HS-TWA | 0016442895 |  | 2105149423 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | INSP AFT CARGO DOOR LOCK MECHANISM | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-3 | 2 | DCA Appr. Req. 2 | INSP-F_AFT COMPT | BKK_H | DET | 787.MPD.52-130-00 |  | 2026-10-10 | 16:30:00 | 2026-10-10 | 16:30:00
241 | 70462433 | HS-TWA | 0016442906 |  | 2105149434 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | INSP BULK CARGO DOOR EXTERNAL | TECO |  | H/26-TWA-X0C03-BLOK-0-3 |  |  | INSP-F_AFT COMPT | BKK_H | DET | 787.MPD.52-500-00 |  | 2026-10-10 | 08:15:00 | 2026-10-10 | 08:15:00
242 | 70462433 | HS-TWA | 0016442908 |  | 2105149436 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | INSP AFT CARGO DOOR EXTERNAL | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-0-3 |  |  | INSP-F_AFT COMPT | BKK_H | DET | 787.MPD.52-508-00 |  | 2026-10-10 | 08:15:00 | 2026-10-10 | 08:15:00
243 | 70462433 | HS-TWA | 0016442909 |  | 2105149437 | AC01 |  | 2026-10-21 | 11LQ/IA | 0010 | INSP PASSENGER ENTRY DOOR L STOP FITTING | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-3 |  |  | INSP-C_DOOR | BKK_H | DET | 787.MPD.52-512-01 |  | 2026-10-10 | 16:30:00 | 2026-10-10 | 16:30:00
244 | 70462433 | HS-TWA | 0016442910 |  | 2105149438 | AC01 |  | 2026-10-21 | 11LQ/IA | 0010 | INSP PASSENGER ENTRY DOOR R STOP FITTING | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-3 |  |  | INSP-C_DOOR | BKK_H | DET | 787.MPD.52-514-01 |  | 2026-10-10 | 08:15:00 | 2026-10-10 | 08:15:00
245 | 70462433 | HS-TWA | 0016442911 |  | 2105149439 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | GVI BULK CARGO DOOR EXTERNAL | TECO |  | H/26-TWA-X0C03-BLOK-0-3 |  |  | INSP-F_AFT COMPT | BKK_H | GVI | 787.MPD.52-805-01 |  | 2026-10-10 | 16:30:00 | 2026-10-10 | 16:30:00
246 | 70462433 | HS-TWA | 0016442913 |  | 2105149441 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | GVI AFT CARGO DOOR EXTERNAL | TECO |  | H/26-TWA-X0C03-BLOK-0-3 |  |  | INSP-F_AFT COMPT | BKK_H | GVI | 787.MPD.52-825-02 |  | 2026-10-10 | 16:30:00 | 2026-10-10 | 16:30:00
247 | 70462433 | HS-TWA | 0016442915 |  | 2105149443 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | INSP AFT CARGO DOOR CUTOUT RIGHT | TECO |  | H/26-TWA-X0C03-BLOK-0-3 |  |  | INSP-F_AFT COMPT | BKK_H | DET | 787.MPD.53-526-00 |  | 2026-10-10 | 16:30:00 | 2026-10-10 | 16:30:00
248 | 70462433 | HS-TWA | 0016442916 |  | 2105149444 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | INSP BULK CARGO DOOR CUTOUT LEFT | TECO |  | H/26-TWA-X0C03-BLOK-0-3 |  |  | INSP-F_AFT COMPT | BKK_H | DET | 787.MPD.53-530-00 |  | 2026-10-10 | 08:15:00 | 2026-10-10 | 08:15:00
249 | 70462433 | HS-TWA | 0016442917 |  | 2105149445 | AC01 |  | 2026-10-07 | 11LQ/IC | 0010 | INSP PASSENGER ENTRY DOOR 1 AND 2 LEFT | TECO |  | H/26-TWA-X0C03-BLOK-0-2 |  |  | INSP-C_DOOR | BKK_H | DET | 787.MPD.53-546-00 |  | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
250 | 70462433 | HS-TWA | 0016442920 |  | 2105149448 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | GVI LOWER HALF OF THE FUSELAGE | TECO |  | H/26-TWA-X0C03-BLOK-0-3 |  |  | INSP-F_FUSELAGE | BKK_H | GVI | 787.MPD.53-803-00 |  | 2026-10-10 | 08:15:00 | 2026-10-10 | 08:15:00
251 | 70462433 | HS-TWA | 0016442922 |  | 2105149450 | AC01 |  | 2026-10-21 | 11LQ/IC | 0010 | DET-LAVA WASTE COMPARTMENT | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-4 |  |  | INSP-C_LAVATORY | BKK_H | DET | 787.MPD.26-035-00 |  | 2026-10-11 | 08:15:00 | 2026-10-11 | 08:15:00
252 | 70462433 | HS-TWA | 0016442926 |  | 2105149454 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | DI CASTER ROLLER BOTH AFT CARGO | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-0-2 | 4 | TG Appr. Req. 4 | FLOOR_AFT COMPT | BKK_H | DI | 787.MPD.5021180001-TG01 |  | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
253 | 70462433 | HS-TWA | 0016442927 |  | 2105149455 | AC01 |  | 2026-10-14 | 11U | 0010 | INSPECTION OF EXPIRATION DATE OF C. OF A | TECO | DPRC | H/26-TWA-X0C03-BLOK-I-N |  |  | ALL_ALL GRP | BKK_H | INS | 787.OPR.INITIAL_FINAL |  | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
254 | 70462433 | HS-TWA | 0016442930 |  | 2105149458 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | CENTER HYDRAULIC SYSTEM RESERVOIR AUTO B | TECO |  | H/26-TWA-X0C03-BLOK-I-N |  |  | WING_HYDRAULIC | BKK_H | OPC | 787.MPD.29-115-00 |  | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
255 | 70462433 | HS-TWA | 0016442931 |  | 2105149459 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | Inspect (Detailed) the BULK CARGO DOOR L | TECO |  | H/26-TWA-X0C03-BLOK-0-2 |  |  | INSP-I_FLOOR | BKK_H | DET | 787.MPD.52-170-00 |  | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
256 | 70462433 | HS-TWA | 0016442932 |  | 2105149460 | AC01 |  | 2026-10-21 | 11LQ/IC | 0010 | INSP PASSENGER ENTRY DOOR 1 AND 2 RIGHT | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-2 |  |  | INSP-I_FLOOR | BKK_H | DVI | 787.MPD.53-550-00 |  | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
257 | 70462433 | HS-TWA | 0016442934 |  | 2105149462 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | INSP-LH CAC INLET DUCT AND CHK VALVES | TECO |  | H/26-TWA-X0C03-BLOK-0-2 | 2 | DCA Appr. Req. 2 | FLOOR_AIR COND | BKK_H | DVI | 787.MPD.21-067-00 |  | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
258 | 70462433 | HS-TWA | 0016442957 |  | 2105149477 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | OPC-CARGO HANDLING SYS OPERATION TEST | TECO |  | H/26-TWA-X0C03-BLOK-0-8 | 4 | TG Appr. Req. 4 | INSP-F_FWD COMPT | BKK_H | OPC | 787.MPD.5021000001-TG01 |  | 2026-10-15 | 08:15:00 | 2026-10-15 | 08:15:00
259 | 70462433 | HS-TWA | 0016442958 |  | 2105149477 | AC01 |  | 2026-10-18 | 11LQ/IA | 0020 | OPC-CARGO HANDLING SYS OPERATION TEST | TECO |  | H/26-TWA-X0C03-BLOK-0-8 | 4 | TG Appr. Req. 4 | INSP-F_FWD COMPT | BKK_H | OPC | 787.MPD.5021000001-TG01 |  | 2026-10-15 | 08:15:00 | 2026-10-15 | 08:15:00
260 | 70462433 | HS-TWA | 0016442959 |  | 2105149478 | AC01 |  | 2026-10-10 | 11LQ/IC | 0010 | INSP-FLIGHT DECK DOOR SEAL | TECO |  | H/26-TWA-X0C03-BLOK-0-2 |  |  | INSP-C_DOOR | BKK_H | GVI | 787.MPD.52-155-00 |  | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
261 | 70462433 | HS-TWA | 0016442965 |  | 2105149483 | AC01 |  | 2026-10-10 | 11LHM/A | 0010 | REM LWR RECIRCULATION FAN CHK VALVAL RH | TECO |  | H/26-TWA-X0C03-BLOK-0-1 | 1 | DCA Appr. Req. 1 | FLOOR_AIR COND | BKK_H | DIS | 787.MPD.21-015-00 |  | 2026-10-06 | 00:00:00 | 2026-10-06 | 00:00:00
262 | 70462433 | HS-TWA | 0016442968 |  | 2105149486 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | PRESERVE ENGINE#1(LH) | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-0-1 |  |  | WING_ENGINE | BKK_H | INS | 787.OPR.ENGINE PRESERVE |  | 2026-10-06 | 00:00:00 | 2026-10-06 | 00:00:00
263 | 70462433 | HS-TWA | 0016442969 |  | 2105149486 | AC01 |  | 2026-10-18 | 11LHM/A | 0020 | PRESERVE ENGINE#1(LH) | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-0-1 |  |  | WING_ENGINE | BKK_H | INS | 787.OPR.ENGINE PRESERVE |  | 2026-10-06 | 00:00:00 | 2026-10-06 | 00:00:00
264 | 70462433 | HS-TWA | 0016442970 |  | 2105149487 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | PRESERVE ENGINE#2(RH) | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-0-1 |  |  | WING_ENGINE | BKK_H | INS | 787.OPR.ENGINE PRESERVE |  | 2026-10-06 | 00:00:00 | 2026-10-06 | 00:00:00
265 | 70462433 | HS-TWA | 0016442971 |  | 2105149487 | AC01 |  | 2026-10-18 | 11LHM/A | 0020 | PRESERVE ENGINE#2(RH) | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-0-1 |  |  | WING_ENGINE | BKK_H | INS | 787.OPR.ENGINE PRESERVE |  | 2026-10-06 | 00:00:00 | 2026-10-06 | 00:00:00
266 | 70462433 | HS-TWA | 0016442972 |  | 2105149488 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | DE-PRESERVE ENGINE 1(LH) | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-0-7 |  |  | WING_ENGINE | BKK_H | INS | 787.OPR.ENGINE DE-PRESERVE |  | 2026-10-14 | 08:15:00 | 2026-10-14 | 08:15:00
267 | 70462433 | HS-TWA | 0016442973 |  | 2105149489 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | DE-PRESERVE ENGINE 2(RH) | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-0-7 |  |  | WING_ENGINE | BKK_H | INS | 787.OPR.ENGINE DE-PRESERVE |  | 2026-10-14 | 08:15:00 | 2026-10-14 | 08:15:00
268 | 70462433 | HS-TWA | 0016442975 |  | 2105149491 | AC01 |  | 2026-10-10 | 11LHM/A | 0010 | DAMPER SHEAR OUT CONTROL WHEEL, RUDDER P | TECO |  | H/26-TWA-X0C03-BLOK-0-4 | 2 | DCA Appr. Req. 2 | FLOOR_FUSELAGE | BKK_H | INS | 787.MPD.27-130-00 |  | 2026-10-11 | 08:15:00 | 2026-10-11 | 08:15:00
269 | 70462433 | HS-TWA | 0016442981 |  | 2105149496 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | OPC CENTER RESERVOIR PISTON | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-4 | 1 | DCA Appr. Req. 1 | FLOOR_FUSELAGE | BKK_H | OPC | 787.MPD.29-150-00 |  | 2026-10-11 | 08:15:00 | 2026-10-11 | 08:15:00
270 | 70462433 | HS-TWA | 0016442982 |  | 2105149497 | AC01 |  | 2026-10-20 | 11LHM/C | 0010 | Restore the LIFE VESTS (off aircraft). | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-3 | 1 | DCA Appr. Req. 1 | CABIN_INTERIOR | BKK_H | RST | 787.MPD.25-020-00 |  | 2026-10-10 | 16:30:00 | 2026-10-10 | 16:30:00
271 | 70462433 | HS-TWA | 0016442986 |  | 2105149501 | AC01 |  | 2026-10-20 | 11LHM/A | 0010 | FUNC NEA distribution LINES | TECO | REMN | H/26-TWA-X0C03-BLOK-0-4 | 2 | DCA Appr. Req. 2 | FLOOR_AIR COND | BKK_H | INS | 787.MPD.47-035-00 |  | 2026-10-11 | 08:15:00 | 2026-10-11 | 08:15:00
272 | 70462433 | HS-TWA | 0016442991 |  | 2105149505 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | DVI APU COMPARTMENT SKIN & STRINGERS | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-1 | 1 | DCA Appr. Req. 1 | FLOOR_TAIL | BKK_H | INS | 787.MPD.49-040-00 |  | 2026-10-06 | 00:00:00 | 2026-10-06 | 00:00:00
273 | 70462433 | HS-TWA | 0016442999 |  | 2105149512 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | DET-FIRE SEAL DEPRESSOR LEFT STRUT | TECO |  | H/26-TWA-X0C03-BLOK-0-4 | 1 | DCA Appr. Req. 1 | INSP-W_ALL WING | BKK_H | DET | 787.MPD.54-210-01 |  | 2026-10-11 | 08:15:00 | 2026-10-11 | 08:15:00
274 | 70462433 | HS-TWA | 0016443001 |  | 2105149514 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | DET-THERMAL BLANKETS LEFT STRUT | TECO |  | H/26-TWA-X0C03-BLOK-0-4 | 1 | DCA Appr. Req. 1 | INSP-W_ALL WING | BKK_H | DET | 787.MPD.54-215-01 |  | 2026-10-11 | 08:15:00 | 2026-10-11 | 08:15:00
275 | 70462433 | HS-TWA | 0016443005 |  | 2105149518 | AC01 |  | 2026-10-21 | 11LHM/C | 0010 | Inspect (Detailed) Lavatory Vertical Sid | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-3 | 1 | DCA Appr. Req. 1 | CABIN_LAVATORY | BKK_H | DI | 787.MPD.25-185-00 |  | 2026-10-10 | 08:15:00 | 2026-10-10 | 08:15:00
276 | 70462433 | HS-TWA | 0016443148 |  | 2105149551 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | INSP APU FIRE EXT TUBE | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-2 | 1 | DCA Appr. Req. 1 | FLOOR_TAIL | BKK_H | GVI | 787.MPD.26-060-00 |  | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
277 | 70462433 | HS-TWA | 0016451109 | 1103181151 | 2105151436 | AC02 |  | 2026-10-20 | 11LHM/E | 0010 | OPC EMERGENCY LIGHTING SYSTEM. | TECO |  | H/26-TWA-X0C03-NONR | 1 | DCA Appr. Req. 1 | IERA_IERA | BKK_H | REP | 787.MPD.33-020-00 |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
278 | 70462433 | HS-TWA | 0016465707 | 1103183981 | 2105154993 | AC02 |  | 2026-10-18 | 11LHM/A | 0010 | GVI Intermediate Pressure 8 Air Tubes-LH | TECO | DPRC | H/26-TWA-X0C03-NONR | 3 | TG Appr. Req. 3 | INSP-W_ENGINE | BKK_H | GVI | 787.MPD.75-205-01 |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
279 | 70462433 | HS-TWA | 0016468729 | 1103184456 | 2105156223 | AC02 |  | 2026-10-21 | 11LHM/C | 0010 | DVI LAVATORY WASTE COMPT DOOR AND FLAP | TECO | DPRC | H/26-TWA-X0C03-NONR | 0 | AD | CABIN_LAVATORY | BKK_H | DET | 787.MPD.25-115-00 |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
280 | 70462433 | HS-TWA | 0016481993 |  | 2105159482 | AC01 |  | 2026-10-21 | 11LHM/A | 0010 | LHW-INST WING ACC PANEL_Z552,561 | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-7 |  |  | WING_ALL WING | BKK_H | RES | 787.OPR.ACC Z552,Z561 |  | 2026-10-14 | 08:15:00 | 2026-10-14 | 08:15:00
281 | 70462433 | HS-TWA | 0016481994 |  | 2105159483 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | RHW-REM WING ACC PANEL_Z652,661 | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-0-1 |  |  | WING_ALL WING | BKK_H | REM | 787.OPR.ACC Z652,Z661 |  | 2026-10-06 | 00:00:00 | 2026-10-06 | 00:00:00
282 | 70462433 | HS-TWA | 0016498372 | 1103189851 | 2105163803 | AC02 |  | 2026-10-21 | 11LHM/C | 0010 | DVI INFLAT OCCUPANT RESTRAINT AIRBAG SYS | TECO | DPRC | H/26-TWA-X0C03-NONR | 1 | DCA Appr. Req. 1 | CABIN_ALL CABIN | BKK_H | DVI | 787.MPD.25-167-00 |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
283 | 70462433 | HS-TWA | 0016507886 | 1103191491 | 2105166151 | AC02 |  | 2026-10-18 | 11LHM/C | 0010 | Clean Pax Entry Door Girt Bar Fitting | TECO |  | H/26-TWA-X0C03-NONR | 1 | DCA Appr. Req. 1 | CABIN_DOOR | BKK_H | RST | 787.MPD.52-070-00 |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
284 | 70462433 | HS-TWA | 0016538964 | 1103197240 | 2105174329 | AC02 |  | 2026-10-21 | 11LHM/E | 0010 | GENERATE &DOWNLOAD ALL SYS CONFIG TO ML | TECO | DPRC | H/26-TWA-X0C03-NONR | 4 | TG Appr. Req. 4 | IERA_IERA | BKK_H | SVC | 787.MPD.45-011-01-TG01 |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
285 | 70462433 | HS-TWA | 0016552314 | 1103199819 | 2105177561 | AC02 |  | 2026-10-09 | 11LHM/E | 0010 | CCS-TIME MANAGER POWER CYCLE RESET | TECO | DPRC | H/26-TWA-X0C03-NONR | 0 | AD |  | BKK_H | SVC | 787.MPD.42-010-00 |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
286 | 70462433 | HS-TWA | 0016556601 | 1103200711 | 2105178702 | AC02 |  | 2026-10-21 | 11LHM/C | 0010 | ALL GALLEYS GWIV SYSTEM RINSE | TECO | DPRC | H/26-TWA-X0C03-NONR | 4 | TG Appr. Req. 4 | CABIN_GALLEY | BKK_H | CLN | 787.MPD.3831210002-TG01 |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
287 | 70462433 | HS-TWA | 0016569901 | 1103203668 | 2105182530 | AC02 |  | 2026-10-18 | 11LHM/A | 0010 | DRAIN WATER FROM ALL FUEL TANK | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR | 4 | TG Appr. Req. 4 | WING_FUEL | BKK_H | REP | 787.MPD.2800000101-TG01 |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
288 | 70462433 | HS-TWA | 0016408354 | WA004C300626 | WA004C300626 | AC05 |  | 2026-10-18 | PER | 0010 | 25 56K OUTBD ARMREST IN POOR CONDITION | TECO | DPRC | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
289 | 70462433 | HS-TWA | 0016408355 | WA004C300626 | WA004C300626 | AC05 |  | 2026-10-18 | BKK_H | 0020 | 25 56K OUTBD ARMREST IN POOR CONDITION | TECO | DPRC | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
290 | 70462433 | HS-TWA | 0016576058 | WA008F051026 | WA008F051026 | AC05 |  | 2026-10-21 | BKK_H | 0010 | 73 EICAS STATUS MSG "ENG CONTROL L" DISP | TECO |  | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
291 | 70462433 | HS-TWA | 0016576421 | WA012F061026 | WA012F061026 | AC05 |  | 2026-10-21 | BKK_H | 0010 | A/C REQUIRED C-03 CHECK | TECO |  | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-06 | 00:00:00 | 2026-10-06 | 00:00:00
292 | 70462433 | HS-TWA | 0016603207 | WA020F141026 | WA020F141026 | AC05 |  | 2026-10-14 | BKK_H | 0010 | GVI FWD CARGO COMP AFT ENDWALL | TECO |  | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-14 | 00:00:00 | 2026-10-14 | 00:00:00
293 | 70462433 | HS-TWA | 0016428233 | WA021C070726 | WA021C070726 | AC05 |  | 2026-10-18 | CTS | 0010 | 38 LAV. 3F-1L INNER DOOR LOCK MISSING. | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
294 | 70462433 | HS-TWA | 0016428234 | WA021C070726 | WA021C070726 | AC05 |  | 2026-10-18 | BKK_H | 0020 | 38 LAV. 3F-1L INNER DOOR LOCK MISSING. | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
295 | 70462433 | HS-TWA | 0016603208 | WA021F141026 | WA021F141026 | AC05 |  | 2026-10-14 | BKK_H | 0010 | ELECTRICAL DIMMABLE WINDOW CRACKED | TECO |  | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-14 | 00:00:00 | 2026-10-14 | 00:00:00
296 | 70462433 | HS-TWA | 0016603209 | WA022F151026 | WA022F151026 | AC05 |  | 2026-10-15 | BKK_H | 0010 | UPK WAS USED FROM E3L AT STATION 4L | TECO |  | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-15 | 00:00:00 | 2026-10-15 | 00:00:00
297 | 70462433 | HS-TWA | 0016603211 | WA024F171026 | WA024F171026 | AC05 |  | 2026-10-21 | BKK_H | 0010 | INSPECTED FOUND INLET COWL LIPSKIN ZONE | TECO |  | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-17 | 00:00:00 | 2026-10-17 | 00:00:00
298 | 70462433 | HS-TWA | 0016594770 | WA027F171026 | WA027F171026 | AC05 |  | 2026-10-22 | BKK_L | 0010 | 32 REF ORDER 2105148838 | TECO |  | L/26-TWA-LI-MSC-N |  |  |  | BKK_H | REP |  |  | 2026-10-17 | 07:00:00 | 2026-10-22 | 22:11:00
299 | 70462433 | HS-TWA | 0016603214 | WA029F181026 | WA029F181026 | AC05 |  | 2026-10-18 | BKK_H | 0010 | "BRAKE OFF" STATUS LT ON NOSE GEAR | TECO |  | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-18 | 00:00:00 | 2026-10-18 | 00:00:00
300 | 70462433 | HS-TWA | 0016603215 | WA030F181026 | WA030F181026 | AC05 |  | 2026-10-18 | BKK_H | 0010 | STS MSC INTERGRATED CLR RECIRC AIR | TECO |  | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-18 | 00:00:00 | 2026-10-18 | 00:00:00
301 | 70462433 | HS-TWA | 0016577122 | WA031C041026 | WA031C041026 | AC05 |  | 2026-10-18 | BKK_H | 0010 | 25 : SEAT COVER 56A, 56B, 56C DEEP CLEN | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-04 | 00:00:00 | 2026-10-04 | 00:00:00
302 | 70462433 | HS-TWA | 0016603216 | WA031F211026 | WA031F211026 | AC05 |  | 2026-10-21 | BKK_H | 0010 | EICAS STAT MSG "BRAKE 8" DISPLAYED | TECO |  | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-21 | 00:00:00 | 2026-10-21 | 00:00:00
303 | 70462433 | HS-TWA | 0016603217 | WA033F211026 | WA033F211026 | AC05 |  | 2026-10-20 | BKK_H | 0010 | EICAS STAT MSG "TIRE PRESS SYS" | TECO |  | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-21 | 00:00:00 | 2026-10-21 | 00:00:00
304 | 70462433 | HS-TWA | 0016603218 | WA035F211026 | WA035F211026 | AC05 |  | 2026-10-21 | BKK_H | 0010 | STS MSG "ANTISKID 8" DISPLAYED | TECO |  | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-21 | 00:00:00 | 2026-10-21 | 00:00:00
305 | 70462433 | HS-TWA | 0016603219 | WA036F211026 | WA036F211026 | AC05 |  | 2026-10-21 | BKK_H | 0010 | OFAR CREW BULK NO.4 SEAT BELT FRAYED | TECO |  | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-21 | 00:00:00 | 2026-10-21 | 00:00:00
306 | 70462433 | HS-TWA | 0016603220 | WA037F211026 | WA037F211026 | AC05 |  | 2026-10-21 | BKK_H | 0010 | CREW OXYGEN LOW LIMIT | TECO |  | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-21 | 00:00:00 | 2026-10-21 | 00:00:00
307 | 70462433 | HS-TWA | 0016535257 | WA072C110926 | WA072C110926 | AC05 |  | 2026-10-18 | PER | 0010 | 25 59H ARM REST LOOSE | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
308 | 70462433 | HS-TWA | 0016535258 | WA072C110926 | WA072C110926 | AC05 |  | 2026-10-18 | BKK_H | 0020 | 25 59H ARM REST LOOSE | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
309 | 70462433 | HS-TWA | 0016390560 | WA074C200626 | WA074C200626 | AC05 |  | 2026-10-14 | PER | 0010 | 25 BETWEEN SEAT 12F & 12K CARPET FLOOR T | TECO | DPRC | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
310 | 70462433 | HS-TWA | 0016390561 | WA074C200626 | WA074C200626 | AC05 |  | 2026-10-14 | BKK_H | 0020 | 25 BETWEEN SEAT 12F & 12K CARPET FLOOR T | TECO | DPRC | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
311 | 70462433 | HS-TWA | 0015776305 | WA074C220625 | WA074C220625 | AC05 |  | 2026-10-21 | BKK_L | 0010 | 25 OVEN 2A1L06 OF MID GALLEY THE ROTATIN | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
312 | 70462433 | HS-TWA | 0015776307 | WA074C220625 | WA074C220625 | AC05 |  | 2026-10-21 | 11LHM/C | 0020 | 25 OVEN 2A1L06 OF MID GALLEY THE ROTATIN | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
313 | 70462433 | HS-TWA | 0015776306 | WA074C220625 | WA074C220625 | AC05 |  | 2026-10-21 | BKK_L | 0020 | 25 OVEN 2A1L06 OF MID GALLEY THE ROTATIN | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
314 | 70462433 | HS-TWA | 0016086910 | WA080C171225 | WA080C171225 | AC05 |  | 2026-10-18 | BKK_L | 0010 | 25 11K SEAT NUMBERING SIGN IS CRACK AND | TECO | DPRC | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
315 | 70462433 | HS-TWA | 0016086911 | WA080C171225 | WA080C171225 | AC05 |  | 2026-10-18 | BKK_H | 0020 | 25 11K SEAT NUMBERING SIGN IS CRACK AND | TECO | DPRC | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
316 | 70462433 | HS-TWA | 0016549084 | WA082C170926 | WA082C170926 | AC05 |  | 2026-10-18 | NGO | 0010 | 25 WATER BOILER 115 TAB NOZZLE MISSING | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
317 | 70462433 | HS-TWA | 0016549086 | WA082C170926 | WA082C170926 | AC05 |  | 2026-10-18 | 11LHM/A | 0020 | 25 WATER BOILER 115 TAB NOZZLE MISSING | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
318 | 70462433 | HS-TWA | 0016549085 | WA082C170926 | WA082C170926 | AC05 |  | 2026-10-18 | BKK_L | 0020 | 25 WATER BOILER 115 TAB NOZZLE MISSING | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
319 | 70462433 | HS-TWA | 0015833076 | WA090C250725 | WA090C250725 | AC05 |  | 2026-10-18 | PER | 0010 | 25 11K : SEAT RECLING IN-OP UNABLE LOCK | TECO | DPRC | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
320 | 70462433 | HS-TWA | 0015833077 | WA090C250725 | WA090C250725 | AC05 |  | 2026-10-18 | BKK_H | 0020 | 25 11K : SEAT RECLING IN-OP UNABLE LOCK | TECO | DPRC | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
321 | 70462433 | HS-TWA | 0016563967 | WA110F290926 | WA110F290926 | AC05 |  | 2026-10-21 | BKK_L | 0010 | 32 STATUS MSG ''BRAKE TEMP SYS'' DISPLAY | TECO |  | H/26-TWA-X0C03-NONR | C | Category C |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
322 | 70462433 | HS-TWA | 0016563968 | WA110F290926 | WA110F290926 | AC05 |  | 2026-10-21 | BKK_H | 0020 | 32 STATUS MSG ''BRAKE TEMP SYS'' DISPLAY | TECO |  | H/26-TWA-X0C03-NONR | C | Category C |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
323 | 70462433 | HS-TWA | 0016098910 | WA602A281225 | WA602A281225 | AC05 |  | 2026-10-21 | 11LQ/IA | 0010 | -ENG#2 FAN BLADES EROSTION INSPECTION FO | TECO | DPRC | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
324 | 70462433 | HS-TWA | 0016574031 | WA643A071026 | WA643A071026 | AC05 |  | 2026-10-18 | 11PAINT | 0010 | PASSENGER ENTRY DOOR SYSTEM | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-07 | 15:15:00 | 2026-10-14 | 16:00:00
325 | 70462433 | HS-TWA | 0016575306 | WA649A071026 | WA649A071026 | AC05 |  | 2026-10-18 | 11PAINT | 0010 | 25:FLIGHT COMPARTMENT EQUIPMENT | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-07 | 17:27:00 | 2026-10-08 | 18:59:00
326 | 70462433 | HS-TWA | 0016575330 | WA655A081026 | WA655A081026 | AC05 |  | 2026-10-21 | 11PAINT | 0010 | FWD.CARGO DOOR EXTERNAL SKIN PAINT ONBOL | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-08 | 12:28:00 | 2026-10-09 | 19:00:00
327 | 70462433 | HS-TWA | 0016577183 | WA664B081026 | WA664B081026 | AC05 |  | 2026-10-15 | 11PAINT | 0010 | CONSOLE AND LINING IN COCKPIT PAINT PEEL | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-08 | 16:27:00 | 2026-10-08 | 19:00:00
328 | 70462433 | HS-TWA | 0016578889 | WA674A091026 | WA674A091026 | AC05 |  | 2026-10-18 | 11LHM/A | 0010 | 12-SERVICING,NLG LUBRICATE. | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-09 | 12:00:00 | 2026-10-09 | 19:00:00
329 | 70462433 | HS-TWA | 0016578971 | WA677A091026 | WA677A091026 | AC05 |  | 2026-10-18 | 11PAINT | 0010 | 25-EQUIPMENT,ATTENDANT SEAT PAINTING. | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-09 | 15:11:00 | 2026-10-09 | 19:00:00
330 | 70462433 | HS-TWA | 0016588636 | WA715A151026 | WA715A151026 | AC05 |  | 2026-10-17 | 11PAINT | 0010 | AIR INTAKE SPINNER | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-15 | 10:30:00 | 2026-10-16 | 16:00:00
331 | 70462433 | HS-TWA | 0016591916 | WA735A181026 | WA735A181026 | AC05 |  | 2026-10-21 | 11PAINT | 0010 | 25:EQUIPMENT AND FURNISHINGS | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-18 | 14:32:00 | 2026-10-19 | 19:00:00
332 | 70462433 | HS-TWA | 0016591928 | WA740A181026 | WA740A181026 | AC05 |  | 2026-10-21 | 11PAINT | 0010 | 25:EQUIPMENT AND FURNISHINGS | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-18 | 19:02:00 | 2026-10-19 | 19:00:00
333 | 70462433 | HS-TWA | 0016591931 | WA741A191026 | WA741A191026 | AC05 |  | 2026-10-21 | 11LHM/A | 0010 | 12-SERVICING,TE FLAP LUB. | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
334 | 70462433 | HS-TWA | 0016591933 | WA742A191026 | WA742A191026 | AC05 |  | 2026-10-19 | 11LHM/A | 0010 | 12-SERVICING,LUB RUDDER HINGE AND ACTUAT | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
335 | 70462433 | HS-TWA | 0016591936 | WA743A191026 | WA743A191026 | AC05 |  | 2026-10-19 | 11LHM/A | 0010 | 12-SERVICING,LUB ELEVATOR. | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
336 | 70462433 | HS-TWA | 0016591962 | WA746A191026 | WA746A191026 | AC05 |  | 2026-10-21 | 11LHM/A | 0010 | 12-SERVICING,LUB AILERON AND FLAPERON. | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
337 | 70462433 | HS-TWA | 0016591963 | WA746A191026 | WA746A191026 | AC05 |  | 2026-10-21 | 11LHM/A | 0020 | 12-SERVICING,LUB AILERON AND FLAPERON. | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
338 | 70462433 | HS-TWA | 0016591965 | WA747A191026 | WA747A191026 | AC05 |  | 2026-10-21 | 11LHM/A | 0010 | 12-SERVICING,LUB SPOILER. | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
339 | 70462433 | HS-TWA | 0015664540 | 1103044139 | 2104935247 | AC03 |  | 2026-10-18 | 11LHM/C | 0010 | 253759: INSP LAV LWR FITTING CORROSION | TECO | DPRC ODAT | H/26-TWA-X0C03-MOD -G-C | 0 | AD |  | BKK_H | DET | 787.TO.253759-01 |  | 2026-10-04 | 00:00:00 | 2026-10-16 | 24:00:00
340 | 70462433 | HS-TWA | 0015664541 | 1103044139 | 2104935247 | AC03 |  | 2026-10-18 | 11LHM/C | 0020 | 253759: INSP LAV LWR FITTING CORROSION | TECO | DPRC ODAT | H/26-TWA-X0C03-MOD -G-C | 0 | AD |  | BKK_H | DET | 787.TO.253759-01 |  | 2026-10-04 | 00:00:00 | 2026-10-16 | 24:00:00
341 | 70462433 | HS-TWA | 0016442734 |  | 2105149269 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | INSP (GENERALVISUAL) T/R COWL HINGES LH | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-2 | 2 | DCA Appr. Req. 2 | INSP-W_ENGINE | BKK_H | GVI | 787.MPD.78-210-01 |  | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
342 | 70462433 | HS-TWA | 0016442735 |  | 2105149270 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | INSP (GENERALVISUAL) T/R COWL HINGES RH | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-2 | 2 | DCA Appr. Req. 2 | INSP-W_ENGINE | BKK_H | GVI | 787.MPD.78-210-02 |  | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
343 | 70462433 | HS-TWA | 0016580686 | WA689B101026 | WA689B101026 | AC05 |  | 2026-10-22 | 11PAINT | 0010 | ATA:11 ENG NO.1 FOUND RH FAN COWL PLACAR | TECO |  | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-10 | 16:41:00 | 2026-10-10 | 19:00:00
344 | 70462433 | HS-TWA | 0016442685 |  | 2105149221 | AC01 |  | 2026-10-07 | 11LHM/C | 0010 | INST-PLASTIC SHEET COVER OVER CARPETS | TECO | DPRC | H/26-TWA-X0C03-BLOK-I-N |  |  | CABIN_INTERIOR | BKK_H | SVC | 787.OPR.INST-PLASTIC COVER OVER CARPETS |  | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
345 | 70462433 | HS-TWA | 0016442763 |  | 2105149293 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | PRESERVATION OF APU | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-0-1 |  |  | FLOOR_TAIL | BKK_H | SVC | 787.OPR.PRESERVATION OF APU |  | 2026-10-06 | 00:00:00 | 2026-10-06 | 00:00:00
346 | 70462433 | HS-TWA | 0016495033 | 1103189246 | 2105163235 | AC02 |  | 2026-10-10 | 11LHM/C | 0010 | COCKROACH DISINFESTATION BY CLEAN | TECO | DPRC | H/26-TWA-X0C03-NONR | 4 | TG Appr. Req. 4 | CABIN_GALLEY | BKK_H | REP | 787.MPD.1221000201-TG01 |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
347 | 70462433 | HS-TWA | 0016038930 | WA599A201125 | WA599A201125 | AC05 |  | 2026-10-20 | 11PAINT | 0010 | LB:25 LAVATORY | TECO | DPRC | H/26-TWA-X0C03-NONR | F | Deferred 7 days |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
348 | 70462433 | HS-TWA | 0016581203 | WA697B111026 | WA697B111026 | AC05 |  | 2026-10-12 | 11LHM/A | 0010 | VOID | TECO |  | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-11 | 15:27:00 | 2026-10-11 | 19:00:00
349 | 70462433 | HS-TWA | 0016581204 | WA697B111026 | WA697B111026 | AC05 |  | 2026-10-12 | 11NDT | 0020 | VOID | TECO |  | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-11 | 15:27:00 | 2026-10-11 | 19:00:00
350 | 70462433 | HS-TWA | 0016581205 | WA697B111026 | WA697B111026 | AC05 |  | 2026-10-12 | 11LHM/A | 0030 | VOID | TECO |  | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-11 | 15:27:00 | 2026-10-11 | 19:00:00
351 | 70462433 | HS-TWA | 0016591926 | WA739A181026 | WA739A181026 | AC05 |  | 2026-10-21 | 11LHM/C | 0010 | 25:EQUIPMENT AND FURNISHINGS | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
352 | 70462433 | HS-TWA | 0016598729 | WA755B201026 | WA755B201026 | AC05 |  | 2026-10-21 | 11LHM/C | 0010 | 25:EQUIPMENT AND FURNISHINGS | TECO |  | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-20 | 18:43:00 | 2026-10-21 | 19:00:00
353 | 70462433 | HS-TWA | 0016442466 |  | 2105148827 | AC01 |  | 2026-10-18 | 11LHM/E | 0010 | ARRANGEMENT OF DOCKS -IERA GROUP | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-I-N | 4 | TG Appr. Req. 4 | IERA_ALL IERA | BKK_H | SVC | PP.OPR.FOR ARRANGE DOCK |  | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
354 | 70462433 | HS-TWA | 0016442772 |  | 2105149301 | AC01 |  | 2026-10-18 | 11LHM/C | 0010 | OPC-FLIGHT COMPARTMENT SEAT | TECO |  | H/26-TWA-X0C03-BLOK-0-1 |  |  | CABIN_COCKPIT | BKK_H | OPC | 787.MPD.25-105-00 |  | 2026-10-06 | 00:00:00 | 2026-10-06 | 00:00:00
355 | 70462433 | HS-TWA | 0016442791 |  | 2105149319 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | OPC NEA SUPPLY DRAIN VALVE FOR FLUID ACC | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-8 |  |  | FLOOR_FUSELAGE | BKK_H | OPC | 787.MPD.47-015-00 |  | 2026-10-15 | 08:15:00 | 2026-10-15 | 08:15:00
356 | 70462433 | HS-TWA | 0016442818 |  | 2105149346 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | GVI(EXT) ZONAL SPOILER#1-7,LHW | TECO |  | H/26-TWA-X0C03-BLOK-0-2 |  |  | INSP-W_TRAILING EDGE | BKK_H | GVI | 787.MPD.57-850-01 |  | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
357 | 70462433 | HS-TWA | 0016442827 |  | 2105149355 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | GVI(INT) REAR SPAR TO TE,RHW | TECO |  | H/26-TWA-X0C03-BLOK-0-1 |  |  | INSP-W_TRAILING EDGE | BKK_H | GVI | 787.MPD.57-958-02 |  | 2026-10-06 | 08:15:00 | 2026-10-06 | 08:15:00
358 | 70462433 | HS-TWA | 0016442831 |  | 2105149359 | AC01 |  | 2026-10-21 | 11LHM/A | 0010 | RHW-INST WING ACCESS PANEL_INTV 3Y | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-7 |  |  | WING_ALL WING | BKK_H | RES | 787.OPR.ACC Z611,621,640,650,661,672 |  | 2026-10-14 | 08:15:00 | 2026-10-14 | 08:15:00
359 | 70462433 | HS-TWA | 0016442850 |  | 2105149378 | AC01 |  | 2026-10-18 | 11LHM/C | 0010 | OPC-FLIGHT DECK OVERHEAD | TECO |  | H/26-TWA-X0C03-BLOK-0-8 |  |  | CABIN_COCKPIT | BKK_H | OPC | 787.MPD.52-005-00 |  | 2026-10-15 | 08:15:00 | 2026-10-15 | 08:15:00
360 | 70462433 | HS-TWA | 0016442918 |  | 2105149446 | AC01 |  | 2026-10-07 | 11LQ/IC | 0010 | INSP PASSENGER ENTRY DOOR 3 AND 4 LEFT | TECO |  | H/26-TWA-X0C03-BLOK-0-2 |  |  | INSP-C_DOOR | BKK_H | DET | 787.MPD.53-562-01 |  | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
361 | 70462433 | HS-TWA | 0016442938 |  | 2105149466 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | FUC GROSS INT LEAKAGE RH/LH HYD SYS | TECO |  | H/26-TWA-X0C03-BLOK-I-N |  |  | WING_HYDRAULIC | BKK_H | FUC | 787.MPD.29-040-00 |  | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
362 | 70462433 | HS-TWA | 0016442989 |  | 2105149503 | AC01 |  | 2026-10-21 | 11LHM/C | 0010 | DISCARD INFLAT OCCU REST AIRBAG INFLATOR | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-4 | 1 | DCA Appr. Req. 1 | CABIN_ALL CABIN | BKK_H | DS | 787.MPD.25-168-00 |  | 2026-10-11 | 08:15:00 | 2026-10-11 | 08:15:00
363 | 70462433 | HS-TWA | 0016442998 |  | 2105149511 | AC01 |  | 2026-10-08 | 11LQ/IA | 0010 | DVI-FWD KEEL BEAM BS 857 TO 882 | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-1 |  |  | INSP-F_ALL FLOOR | BKK_H | DVI | 787.MPD.53-511-00 |  | 2026-10-06 | 08:15:00 | 2026-10-06 | 08:15:00
364 | 70462433 | HS-TWA | 0016443004 |  | 2105149517 | AC01 |  | 2026-10-21 | 11LHM/A | 0010 | REFUELING FOR AIRPLANE FUEL TANKS | TECO |  | H/26-TWA-X0C03-BLOK-F-I |  |  | WING_FUEL | BKK_H | SVC | 787.OPR.REFUELING |  | 2026-10-16 | 08:15:00 | 2026-10-16 | 08:15:00
365 | 70462433 | HS-TWA | 0016443146 |  | 2105149549 | AC01 |  | 2026-10-18 | 11LHM/C | 0010 | ENGINE FIRE EXTINGUISHING SYSTEM | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-3 |  |  | WING_ENGINE | BKK_H | INS | 787.MPD.26-015-00 |  | 2026-10-10 | 16:30:00 | 2026-10-10 | 16:30:00
366 | 70462433 | HS-TWA | 0016443147 |  | 2105149550 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | APU FIRE EXTINGUISHING SYSTEM | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-5 |  |  | FLOOR_TAIL | BKK_H | OPC | 787.MPD.26-055-00 |  | 2026-10-12 | 08:15:00 | 2026-10-12 | 08:15:00
367 | 70462433 | HS-TWA | 0016481992 |  | 2105159481 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | LHW-REM WING ACC PANEL_Z552,561 | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-0-1 |  |  | WING_ALL WING | BKK_H | REM | 787.OPR.ACC Z552,Z561 |  | 2026-10-06 | 00:00:00 | 2026-10-06 | 00:00:00
368 | 70462433 | HS-TWA | 0016481995 |  | 2105159484 | AC01 |  | 2026-10-21 | 11LHM/A | 0010 | RHW-INST WING ACC PANEL_Z652,661 | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-7 |  |  | WING_ALL WING | BKK_H | RES | 787.OPR.ACC Z652,Z661 |  | 2026-10-14 | 08:15:00 | 2026-10-14 | 08:15:00
369 | 70462433 | HS-TWA | 0016591904 | WA728A171026 | WA728A171026 | AC05 |  | 2026-10-21 | 11LHM/A | 0010 | APU AIR INLET DOOR | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | 11LHM/A | REP |  |  | 2026-10-17 | 16:28:00 | 2026-10-19 | 16:00:00
370 | 70462433 | HS-TWA | 0016591905 | WA728A171026 | WA728A171026 | AC05 |  | 2026-10-21 | 11PAINT | 0020 | APU AIR INLET DOOR | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | 11LHM/A | REP |  |  | 2026-10-17 | 16:28:00 | 2026-10-19 | 16:00:00
371 | 70462433 | HS-TWA | 0016442732 |  | 2105149267 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | LUB FWD CARGO DOOR | TECO |  | H/26-TWA-X0C03-BLOK-0-5 |  |  | FLOOR_FWD COMPT | BKK_H | LUB | 787.MPD.12-140-00 |  | 2026-10-12 | 08:15:00 | 2026-10-12 | 08:15:00
372 | 70462433 | HS-TWA | 0016442924 |  | 2105149452 | AC01 |  | 2026-10-20 | 11LHM/C | 0010 | REPLACEMENT OF ALL CARPETS. | TECO |  | H/26-TWA-X0C03-BLOK-0-6 |  |  | CABIN_INTERIOR | BKK_H | REM | 787.MPD.2528000101-TG01 |  | 2026-10-13 | 08:15:00 | 2026-10-13 | 08:15:00
373 | 70462433 | HS-TWA | 0016529666 | 1103195003 | 2105171959 | AC02 |  | 2026-10-18 | 11LHM/A | 0010 | E/26-148:INSP MLG SIDE BRACE HARNESS | TECO | DPRC ODAT | H/26-TWA-X0C03-MOD | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 787.ED.BKKJA-E/26-148 |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
374 | 70462433 | HS-TWA | 0016552310 | 1103199795 | 2105177558 | AC02 |  | 2026-10-09 | 11LHM/A | 0010 | LUB THE MLG TRUCK BEAM PIVOT JOINT | TECO | DPRC | H/26-TWA-X0C03-NONR | 0 | AD | FLOOR_LANDING GEAR | BKK_H | REP | 787.MPD.12-095-00 |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
375 | 70462433 | HS-TWA | 0016552311 | 1103199795 | 2105177558 | AC02 |  | 2026-10-09 | 11LHM/A | 0020 | LUB THE MLG TRUCK BEAM PIVOT JOINT | TECO | DPRC | H/26-TWA-X0C03-NONR | 0 | AD | FLOOR_LANDING GEAR | BKK_H | REP | 787.MPD.12-095-00 |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
376 | 70462433 | HS-TWA | 0016239921 | WA049C200326 | WA049C200326 | AC05 |  | 2026-10-20 | BKK_L | 0010 | 11 DOOR MODE SELECTOR ARMED MODE RED PLA | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
377 | 70462433 | HS-TWA | 0016240773 | WA049C200326 | WA049C200326 | AC05 |  | 2026-10-20 | 11LHM/A | 0020 | 11 DOOR MODE SELECTOR ARMED MODE RED PLA | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
378 | 70462433 | HS-TWA | 0016240772 | WA049C200326 | WA049C200326 | AC05 |  | 2026-10-20 | BKK_L | 0020 | 11 DOOR MODE SELECTOR ARMED MODE RED PLA | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
379 | 70462433 | HS-TWA | 0016581187 | WA693B111026 | WA693B111026 | AC05 |  | 2026-10-14 | 11LHM/C | 0010 | 25: SEAT 56H AND 58D ARM REST LOOSE BECA | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-11 | 12:29:00 | 2026-10-11 | 19:00:00
380 | 70462433 | HS-TWA | 0016584025 | WA703A131026 | WA703A131026 | AC05 |  | 2026-10-22 | 11PAINT | 0010 | 11-PLACARDS AND MARKINGS,STAR ALLIANCE. | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-13 | 14:45:00 | 2026-10-13 | 19:00:00
381 | 70462433 | HS-TWA | 0015939469 | 1103090932 | 2105007928 | AC03 |  | 2026-10-21 | 11LHM/E | 0010 | 420042: CCS OSS SOFTWARE CHG | TECO | DPRC | H/26-TWA-X0C03-MOD | 3 | TG Appr. Req. 3 |  | BKK_H | MOD | 787.TO.420042 |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
382 | 70462433 | HS-TWA | 0016442686 |  | 2105149222 | AC01 |  | 2026-10-10 | 11LHM/C | 0010 | REMV-PLASTIC SHEET COVER OVER CARPETS | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-8 |  |  | CABIN_INTERIOR | BKK_H | SVC | 787.OPR.REMV-PLASTIC COVER OVER CARPETS |  | 2026-10-15 | 08:15:00 | 2026-10-15 | 08:15:00
383 | 70462433 | HS-TWA | 0016442709 |  | 2105149245 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | INTERNAL-ZONAL(GV): FWD NACELLE STRUT LH | TECO |  | H/26-TWA-X0C03-BLOK-0-5 | 2 | DCA Appr. Req. 2 | INSP-W_ENGINE | BKK_H | GVI | 787.MPD.54-890-01 |  | 2026-10-12 | 08:15:00 | 2026-10-12 | 08:15:00
384 | 70462433 | HS-TWA | 0016442740 |  | 2105149275 | AC01 |  | 2026-10-10 | 11LHM/E | 0010 | Discard the Main Battery Enclosu | TECO |  | H/26-TWA-X0C03-BLOK-0-1 | 2 | DCA Appr. Req. 2 | IERA_FLOOR | BKK_H | DIS | 787.MPD.24-012-00 |  | 2026-10-06 | 00:00:00 | 2026-10-06 | 00:00:00
385 | 70462433 | HS-TWA | 0016442741 |  | 2105149275 | AC01 |  | 2026-10-10 | 11LHM/E | 0020 | Discard the Main Battery Enclosu | TECO |  | H/26-TWA-X0C03-BLOK-0-1 | 2 | DCA Appr. Req. 2 | IERA_FLOOR | BKK_H | DIS | 787.MPD.24-012-00 |  | 2026-10-06 | 00:00:00 | 2026-10-06 | 00:00:00
386 | 70462433 | HS-TWA | 0016442744 |  | 2105149278 | AC01 |  | 2026-10-10 | 11LHM/E | 0010 | Discard the APU Battery Enclosu | TECO |  | H/26-TWA-X0C03-BLOK-0-1 | 2 | DCA Appr. Req. 2 | IERA_FLOOR | BKK_H | DIS | 787.MPD.24-012-00 |  | 2026-10-06 | 00:00:00 | 2026-10-06 | 00:00:00
387 | 70462433 | HS-TWA | 0016442745 |  | 2105149278 | AC01 |  | 2026-10-10 | 11LHM/E | 0020 | Discard the APU Battery Enclosu | TECO |  | H/26-TWA-X0C03-BLOK-0-1 | 2 | DCA Appr. Req. 2 | IERA_FLOOR | BKK_H | DIS | 787.MPD.24-012-00 |  | 2026-10-06 | 00:00:00 | 2026-10-06 | 00:00:00
388 | 70462433 | HS-TWA | 0016442833 |  | 2105149361 | AC01 |  | 2026-10-07 | 11LHM/C | 0010 | REMV-PROTECTIVE COVERS FROM ALL SEATS | TECO | DPRC | H/26-TWA-X0C03-BLOK-I-N |  |  | CABIN_INTERIOR | BKK_H | REM | 787.OPR.REMV-PROTECTIVE ALL SEATS |  | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
389 | 70462433 | HS-TWA | 0016442842 |  | 2105149370 | AC01 |  | 2026-10-21 | 11LHM/A | 0010 | CLOSE-LANDING GEAR DOORS | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-8 |  |  | FLOOR_LANDING GEAR | BKK_H | RES | 787.OPR.CLOSE-LANDING GEAR DOORS |  | 2026-10-15 | 08:15:00 | 2026-10-15 | 08:15:00
390 | 70462433 | HS-TWA | 0016442884 |  | 2105149412 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | INSP FWD CARGO TIE-DOWNS FITTING | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-0-3 | 1 | DCA Appr. Req. 1 | INSP-F_FWD COMPT | BKK_H | DET | 787.MPD.50-010-00 |  | 2026-10-10 | 08:15:00 | 2026-10-10 | 08:15:00
391 | 70462433 | HS-TWA | 0016442921 |  | 2105149449 | AC01 |  | 2026-10-18 | 11LHM/C | 0010 | RES-(CLEAN) RETURN AIR GRILL | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-0-3 |  |  | CABIN_ALL CABIN | BKK_H | CLN | 787.MPD.21-090-00 |  | 2026-10-10 | 16:30:00 | 2026-10-10 | 16:30:00
392 | 70462433 | HS-TWA | 0016442925 |  | 2105149453 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | DI CASTER ROLLER BOTH FWD CARGO | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-0-2 | 4 | TG Appr. Req. 4 | FLOOR_FWD COMPT | BKK_H | DI | 787.MPD.5021180001-TG01 |  | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
393 | 70462433 | HS-TWA | 0016442960 |  | 2105149479 | AC01 |  | 2026-10-21 | 11LHM/C | 0010 | FUC-(EC) SEAT SCHEDULED | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-2 |  |  | CABIN_ALL CABIN | BKK_H | FUC | 787.MPD.2525010303-TG01 |  | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
394 | 70462433 | HS-TWA | 0016443150 |  | 2105149553 | AC01 |  | 2026-10-15 | 11LHM/A | 0010 | MLGD ACUATOR RETURN LINE CHECK VALVE | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-5 | 1 | DCA Appr. Req. 1 | FLOOR_LANDING GEAR | BKK_H | DIS | 787.MPD.29-210-00 |  | 2026-10-12 | 08:15:00 | 2026-10-12 | 08:15:00
395 | 70462433 | HS-TWA | 0016443151 |  | 2105149554 | AC01 |  | 2026-10-15 | 11LHM/A | 0010 | MLG RETURN CHECK VALVE | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-5 | 1 | DCA Appr. Req. 1 | FLOOR_LANDING GEAR | BKK_H | DIS | 787.MPD.29-230-00 |  | 2026-10-12 | 08:15:00 | 2026-10-12 | 08:15:00
396 | 70462433 | HS-TWA | 0016538958 | 1103197236 | 2105174325 | AC02 |  | 2026-10-21 | 11LHM/C | 0010 | COCKROACH DISINFESTATION BY BLATTANEXGEL | TECO | DPRC | H/26-TWA-X0C03-NONR | 4 | TG Appr. Req. 4 | CABIN_ALL CABIN | BKK_H | REP | 787.MPD.1221000202-TG01 |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
397 | 70462433 | HS-TWA | 0016497315 | WA032C220826 | WA032C220826 | AC05 |  | 2026-10-22 | BKK_L | 0010 | 25 SEAT 55H, 56H, 59H ARMREST COVER MISS | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
398 | 70462433 | HS-TWA | 0016498261 | WA032C220826 | WA032C220826 | AC05 |  | 2026-10-22 | BKK_H | 0020 | 25 SEAT 55H, 56H, 59H ARMREST COVER MISS | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
399 | 70462433 | HS-TWA | 0016205150 | WA093C010326 | WA093C010326 | AC05 |  | 2026-10-18 | BKK_L | 0010 | 25 STOWAGE BIN 41,42 ABC DAMPER POOR CON | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
400 | 70462433 | HS-TWA | 0016211478 | WA093C010326 | WA093C010326 | AC05 |  | 2026-10-18 | 11LHM/A | 0020 | 25 STOWAGE BIN 41,42 ABC DAMPER POOR CON | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
401 | 70462433 | HS-TWA | 0016211477 | WA093C010326 | WA093C010326 | AC05 |  | 2026-10-18 | BKK_L | 0020 | 25 STOWAGE BIN 41,42 ABC DAMPER POOR CON | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
402 | 70462433 | HS-TWA | 0014748345 | WA348B180923 | WA348B180923 | AC05 |  | 2026-10-21 | 11LHM/A | 0010 | 54-NACELLES/PYLONS, STRUT DRAIN | TECO | DPRC | H/26-TWA-X0C03-NONR | I | Perform in A-Check |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
403 | 70462433 | HS-TWA | 0014752959 | WA416B210923 | WA416B210923 | AC05 |  | 2026-10-21 | 11LHM/A | 0010 | 71-POWER PLANT/ FAN COWL | TECO | DPRC | H/26-TWA-X0C03-NONR | I | Perform in A-Check |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
404 | 70462433 | HS-TWA | 0016572981 | WA635A061026 | WA635A061026 | AC05 |  | 2026-10-20 | 11LHM/C | 0010 | 25 : COVER ASSY SLIDE SEAT TRACK MISSING | TECO | DPRC | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-06 | 13:50:00 | 2026-10-06 | 18:59:00
405 | 70462433 | HS-TWA | 0016577196 | WA668A081026 | WA668A081026 | AC05 |  | 2026-10-18 | 11LHM/A | 0010 | 52-DOORS,FWD AND AFT CARGO DOOR POWER PA | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-08 | 16:41:00 | 2026-10-08 | 19:00:00
406 | 70462433 | HS-TWA | 0016578890 | WA675A091026 | WA675A091026 | AC05 |  | 2026-10-18 | 11LHM/A | 0010 | 12-SERVICING,MLG LUBRICATE. | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-09 | 12:05:00 | 2026-10-09 | 19:00:00
407 | 70462433 | HS-TWA | 0016584029 | WA706A131026 | WA706A131026 | AC05 |  | 2026-10-22 | 11PAINT | 0010 | 53-FUSELAGE,THAI AND LOGO. | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-13 | 18:18:00 | 2026-10-13 | 19:00:00
408 | 70462433 | HS-TWA | 0016586235 | WA710A141026 | WA710A141026 | AC05 |  | 2026-10-18 | 11LHM/A | 0010 | REMOVABLE WING TIP | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-14 | 14:59:00 | 2026-10-15 | 16:00:00
409 | 70462433 | HS-TWA | 0016587106 | WA714A151026 | WA714A151026 | AC05 |  | 2026-10-21 | 11LHM/A | 0010 | EQUIPMENT COOLING SYSTEM | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-15 | 08:51:00 | 2026-10-16 | 16:00:00
410 | 70462433 | HS-TWA | 0016587107 | WA714A151026 | WA714A151026 | AC05 |  | 2026-10-21 | 11LHM/A | 0020 | EQUIPMENT COOLING SYSTEM | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-15 | 08:51:00 | 2026-10-16 | 16:00:00
411 | 70462433 | HS-TWA | 0016589864 | WA720A161026 | WA720A161026 | AC05 |  | 2026-10-18 | 11LHM/E | 0010 | 44: CLEAN AREA SEAT ELEC BOX UNDER ALL B | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
412 | 70462433 | HS-TWA | 0016591383 | WA722A161026 | WA722A161026 | AC05 |  | 2026-10-20 | 11LHM/C | 0010 | 25:EQUIPMENT AND FURNISHINGS | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-16 | 14:14:00 | 2026-10-17 | 19:00:00
413 | 70462433 | HS-TWA | 0016591950 | WA744A191026 | WA744A191026 | AC05 |  | 2026-10-19 | 11LHM/A | 0010 | 12-SERVICING, SERVICE HSTA | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 19:00:00
414 | 70462433 | HS-TWA | 0016591951 | WA744A191026 | WA744A191026 | AC05 |  | 2026-10-19 | 11LHM/A | 0020 | 12-SERVICING, SERVICE HSTA | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 19:00:00
415 | 70462433 | HS-TWA | 0016591952 | WA744A191026 | WA744A191026 | AC05 |  | 2026-10-19 | 11LHM/A | 0030 | 12-SERVICING, SERVICE HSTA | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 19:00:00
416 | 70462433 | HS-TWA | 0016598783 | WA760B211026 | WA760B211026 | AC05 |  | 2026-10-21 | 11LHM/C | 0010 | 25:EQUIPMENT AND FURNISHINGS | TECO |  | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
417 | 70462433 | HS-TWA | 0016600996 | WA762B211026 | WA762B211026 | AC05 |  | 2026-10-21 | 11LHM/C | 0010 | 25:EQUIPMENT AND FURNISHINGS | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
418 | 70462433 | HS-TWA | 0016601945 | WA763B211026 | WA763B211026 | AC05 |  | 2026-10-21 | 11LHM/C | 0010 | 25:EQUIPMENT AND FURNISHINGS | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
419 | 70462433 | HS-TWA | 0016604010 | WA766B221026 | WA766B221026 | AC05 |  | 2026-10-22 | 11LHM/C | 0010 | 25: EQUIPMENT AND FURNISHINGS | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
420 | 70462433 | HS-TWA | 0016442984 |  | 2105149499 | AC01 |  | 2026-10-20 | 11LHM/A | 0010 | Discard the Cargo Comp Flow ctrl vlv squ | TECO | REMN | H/26-TWA-X0C03-BLOK-0-4 | 1 | DCA Appr. Req. 1 | FLOOR_AFT COMPT | BKK_H | INS | 787.MPD.26-080-00 |  | 2026-10-11 | 08:15:00 | 2026-10-11 | 08:15:00
421 | 70462433 | HS-TWA | 0016442997 |  | 2105149510 | AC01 |  | 2026-10-15 | 11SH-LQ | 0010 | DVI TR TRANS SLEEVE-ACOUSTIC PANEL ENG2 | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-2 | 4 | TG Appr. Req. 4 | WING_ENGINE | BKK_H | INS | 787.MPD.7831010001-TG02 |  | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
422 | 70462433 | HS-TWA | 0016577224 | WA672A091026 | WA672A091026 | AC05 |  | 2026-10-18 | 11CARPET | 0010 | 50-CARGO,AFT END WALL. | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
423 | 70462433 | HS-TWA | 0016584024 | WA702A131026 | WA702A131026 | AC05 |  | 2026-10-20 | 11CARPET | 0010 | 25-EQUIPMENT AND FURNISHINGS, FLOORMAT. | TECO |  | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-13 | 14:42:00 | 2026-10-13 | 19:00:00
424 | 70462433 | HS-TWA | 0016442946 |  | 2105149471 | AC01 |  | 2026-10-19 | 11LHM/A | 0010 | FUC-PRIMARY FLT CTRL HYD FUSE(787-9) | TECO | REMN | H/26-TWA-X0C03-BLOK-0-1 | 1 | DCA Appr. Req. 1 | FLOOR_TAIL | BKK_H | FNC | 787.MPD.27-030-00 |  | 2026-10-06 | 00:00:00 | 2026-10-06 | 00:00:00
425 | 70462433 | HS-TWA | 0016442947 |  | 2105149471 | AC01 |  | 2026-10-19 | 11LHM/A | 0020 | FUC-PRIMARY FLT CTRL HYD FUSE(787-9) | TECO | REMN | H/26-TWA-X0C03-BLOK-0-1 | 1 | DCA Appr. Req. 1 | FLOOR_TAIL | BKK_H | FNC | 787.MPD.27-030-00 |  | 2026-10-06 | 00:00:00 | 2026-10-06 | 00:00:00
426 | 70462433 | HS-TWA | 0016442948 |  | 2105149471 | AC01 |  | 2026-10-19 | 11LHM/A | 0030 | FUC-PRIMARY FLT CTRL HYD FUSE(787-9) | TECO | REMN | H/26-TWA-X0C03-BLOK-0-1 | 1 | DCA Appr. Req. 1 | FLOOR_TAIL | BKK_H | FNC | 787.MPD.27-030-00 |  | 2026-10-06 | 00:00:00 | 2026-10-06 | 00:00:00
427 | 70462433 | HS-TWA | 0016442983 |  | 2105149498 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | Discard the SMOKE HOODS or PBE. | TECO |  | H/26-TWA-X0C03-BLOK-0-3 |  |  | INSP-C_ALL CABIN | BKK_H | DIS | 787.MPD.25-060-00 |  | 2026-10-10 | 08:15:00 | 2026-10-10 | 08:15:00
428 | 70462433 | HS-TWA | 0016525795 | 1103194571 | 2105171209 | AC02 |  | 2026-10-18 | 11LHM/A | 0010 | SAMPLE FUEL FOR MICROBIOLOGICAL TEST | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR | 4 | TG Appr. Req. 4 | WING_ALL WING | BKK_H | REP | 787.MPD.2811000001-TG01 |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
429 | 70462433 | HS-TWA | 0016577146 | WA013F081026 | WA013F081026 | AC05 |  | 2026-10-18 | BKK_H | 0010 | REM. LH/RH DEFUEL ISOLATION VALVE ACTU. | TECO | NOGO | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-08 | 00:00:00 | 2026-10-08 | 00:00:00
430 | 70462433 | HS-TWA | 0016581918 | WA018F101026 | WA018F101026 | AC05 |  | 2026-10-10 | BKK_H | 0010 | 78 : RH ENG OTBD T/R: CUP-BUMPER | TECO |  | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-10 | 00:00:00 | 2026-10-10 | 00:00:00
431 | 70462433 | HS-TWA | 0016595336 | WA749A191026 | WA749A191026 | AC05 |  | 2026-10-21 | 11PAINT | 0010 | 11-PLACARDS AND MARKINGS,CREW ESCAPE DOO | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
432 | 70462433 | HS-TWA | 0016414793 | 1103174340 | 2105141045 | AC02 |  | 2026-10-18 | 11LHM/A | 0010 | B787-EXTERNAL CLEANING OF THE AIRCRAFT | TECO | DPRC | H/26-TWA-X0C03-NONR | 4 | TG Appr. Req. 4 | ALL_ALL GRP | BKK_H | REP | 787.MPD.5100000201-TG01 |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
433 | 70462433 | HS-TWA | 0016414794 | 1103174340 | 2105141045 | AC02 |  | 2026-10-18 | 11LHM/E | 0020 | B787-EXTERNAL CLEANING OF THE AIRCRAFT | TECO | DPRC | H/26-TWA-X0C03-NONR | 4 | TG Appr. Req. 4 | ALL_ALL GRP | BKK_H | REP | 787.MPD.5100000201-TG01 |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
434 | 70462433 | HS-TWA | 0016414795 | 1103174340 | 2105141045 | AC02 |  | 2026-10-18 | 11CLEAN | 0030 | B787-EXTERNAL CLEANING OF THE AIRCRAFT | TECO | DPRC | H/26-TWA-X0C03-NONR | 4 | TG Appr. Req. 4 | ALL_ALL GRP | BKK_H | REP | 787.MPD.5100000201-TG01 |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
435 | 70462433 | HS-TWA | 0016442680 |  | 2105148836 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | JACKING OF AIRCRAFT B787 | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-I-N |  |  | ALL_ALL GRP | BKK_H | SVC | 787.OPR.JACKING OF AIRCRAFT |  | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
436 | 70462433 | HS-TWA | 0016442738 |  | 2105149273 | AC01 |  | 2026-10-17 | 11LHM/A | 0010 | OPC THRUST REVERSER BY TRANSLATION ENG#2 | TECO |  | H/26-TWA-X0C03-BLOK-0-8 | 2 | DCA Appr. Req. 2 | WING_ENGINE | BKK_H | OPC | 787.MPD.78-220-02 |  | 2026-10-15 | 08:15:00 | 2026-10-15 | 08:15:00
437 | 70462433 | HS-TWA | 0016442756 |  | 2105149286 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | DEACTIVATION-TRAILING EDGE FLAPS | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-I-N |  |  | WING_TRAILING EDGE | BKK_H | SVC | 787.OPR.DEACTIVATION-TRAILING |  | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
438 | 70462433 | HS-TWA | 0016442832 |  | 2105149360 | AC01 |  | 2026-10-18 | 11LHM/C | 0010 | FILL-POTABLE WATER TANK B787 | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-0-7 |  |  | CABIN_GALLEY | BKK_H | SVC | 787.OPR.FILL-POTABLE WATER |  | 2026-10-14 | 08:15:00 | 2026-10-14 | 08:15:00
439 | 70462433 | HS-TWA | 0016442846 |  | 2105149374 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | ACTIVATION-TRAILING EDGE FLAPS | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-0-7 |  |  | WING_TRAILING EDGE | BKK_H | SVC | 787.OPR.ACTIVATION-TRAILING |  | 2026-10-14 | 08:15:00 | 2026-10-14 | 08:15:00
440 | 70462433 | HS-TWA | 0016442848 |  | 2105149376 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | ACTIVATION-SPOILERS | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-0-8 |  |  | WING_LEADING EDGE | BKK_H | SVC | 787.OPR.ACTIVATION-SPOILERS |  | 2026-10-15 | 08:15:00 | 2026-10-15 | 08:15:00
441 | 70462433 | HS-TWA | 0016442877 |  | 2105149405 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | INSTALL HIGH FLOW SHUTOFF VALVE | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-0-7 |  |  | FLOOR_AIR COND | BKK_H | RES | 787.MPD.21-075-00 |  | 2026-10-14 | 08:15:00 | 2026-10-14 | 08:15:00
442 | 70462433 | HS-TWA | 0016442885 |  | 2105149413 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | INSP AFT CARGO TIE-DOWNS FITTING | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-0-3 | 1 | DCA Appr. Req. 1 | INSP-F_AFT COMPT | BKK_H | DET | 787.MPD.50-010-00 |  | 2026-10-10 | 16:30:00 | 2026-10-10 | 16:30:00
443 | 70462433 | HS-TWA | 0016442886 |  | 2105149414 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | INSP BULK CARGO TIE-DOWNS FITTING | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-0-3 | 1 | DCA Appr. Req. 1 | INSP-F_AFT COMPT | BKK_H | DET | 787.MPD.50-010-00 |  | 2026-10-10 | 08:15:00 | 2026-10-10 | 08:15:00
444 | 70462433 | HS-TWA | 0016442941 |  | 2105149468 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | OPC STANDPIPE SOV(CTR HYD SYS) | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-8 |  |  | WING_HYDRAULIC | BKK_H | FUC | 787.MPD.29-170-00 |  | 2026-10-15 | 08:15:00 | 2026-10-15 | 08:15:00
445 | 70462433 | HS-TWA | 0016442963 |  | 2105149481 | AC01 |  | 2026-10-10 | 11LHM/A | 0010 | REM LWR RECIRCULATION FAN CHK VALVAL LH | TECO |  | H/26-TWA-X0C03-BLOK-0-1 | 1 | DCA Appr. Req. 1 | FLOOR_AIR COND | BKK_H | DIS | 787.MPD.21-015-00 |  | 2026-10-06 | 00:00:00 | 2026-10-06 | 00:00:00
446 | 70462433 | HS-TWA | 0016469607 | 1103184477 | 2105156417 | AC03 |  | 2026-10-18 | 11LHM/C | 0010 | 253693:LAVATORY UNITS FAUCET CTRL MODULE | TECO | DPRC ODAT | H/26-TWA-X0C03-MOD | 0 | AD |  | BKK_H | DVI | 787.TO.253693-01 |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
447 | 70462433 | HS-TWA | 0016442676 |  | 2105148834 | AC01 |  | 2026-10-18 | 11LHM/A | 0040 | 787 APU INSTALL | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-4 | 4 | TG Appr. Req. 4 | FLOOR_TAIL | BKK_H | INS | 787.MAM.AMM.49-11-00-04 |  | 2026-10-11 | 08:15:00 | 2026-10-11 | 08:15:00
448 | 70462433 | HS-TWA | 0016442677 |  | 2105148834 | AC01 |  | 2026-10-18 | 11LHM/E | 0050 | 787 APU INSTALL | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-4 | 4 | TG Appr. Req. 4 | FLOOR_TAIL | BKK_H | INS | 787.MAM.AMM.49-11-00-04 |  | 2026-10-11 | 08:15:00 | 2026-10-11 | 08:15:00
449 | 70462433 | HS-TWA | 0016442678 |  | 2105148834 | AC01 |  | 2026-10-18 | 11E | 0060 | 787 APU INSTALL | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-4 | 4 | TG Appr. Req. 4 | FLOOR_TAIL | BKK_H | INS | 787.MAM.AMM.49-11-00-04 |  | 2026-10-11 | 08:15:00 | 2026-10-11 | 08:15:00
450 | 70462433 | HS-TWA | 0016591925 | WA028F171026 | WA028F171026 | AC05 |  | 2026-10-21 | BKK_H | 0010 | REF. QE086F071026 EEC WAS REMOVED | TECO | NOGO DPRC | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-17 | 00:00:00 | 2026-10-17 | 00:00:00
451 | 70462433 | HS-TWA | 0016581188 | WA694B111026 | WA694B111026 | AC05 |  | 2026-10-18 | 11LHM/A | 0010 | ATA:27 FOUND RH WING LEADING EDGE SLAT N | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-11 | 13:30:00 | 2026-10-11 | 19:00:00
452 | 70462433 | HS-TWA | 0015224084 | 1102971622 | 2104825422 | AC03 |  | 2026-10-08 | 11LHM/A | 0010 | 210784: REPL AIR DISTRIBUTION NOZZLE | TECO | DPRC | H/26-TWA-X0C03-MOD -G-F | 4 | TG Appr. Req. 4 | FLOOR_AIR COND | BKK_H | MOD | 787.TO.210784 |  | 2026-10-04 | 00:00:00 | 2026-10-16 | 24:00:00
453 | 70462433 | HS-TWA | 0016442683 |  | 2105148839 | AC01 |  | 2026-10-09 | 11LHM/E | 0010 | INST-PROTECTIVE COVER ON COMPONENTS | TECO | DPRC | H/26-TWA-X0C03-BLOK-I-N |  |  | IERA_FLOOR | BKK_H | SVC | 787.OPR.PROTECTIVE COVER COMPONENTS |  | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
454 | 70462433 | HS-TWA | 0016442767 |  | 2105149297 | AC01 |  | 2026-10-09 | 11LHM/E | 0010 | OPC the UNDERWATER LOCAT | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-8 | 2 | DCA Appr. Req. 2 | IERA_CABIN | BKK_H | OPC | 787.MPD.31-030-00 |  | 2026-10-15 | 08:15:00 | 2026-10-15 | 08:15:00
455 | 70462433 | HS-TWA | 0016442768 |  | 2105149297 | AC01 |  | 2026-10-09 | 11LHM/E | 0020 | OPC the UNDERWATER LOCAT | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-8 | 2 | DCA Appr. Req. 2 | IERA_CABIN | BKK_H | OPC | 787.MPD.31-030-00 |  | 2026-10-15 | 08:15:00 | 2026-10-15 | 08:15:00
456 | 70462433 | HS-TWA | 0016442789 |  | 2105149318 | AC01 |  | 2026-10-18 | 11NDT | 0010 | HFEC FUEL Q.DATA CON(FQDC) MOUNTING BRAC | TECO |  | H/26-TWA-X0C03-BLOK-0-1 |  |  | WING_FUEL | BKK_H | SDI | 787.MPD.28-055-00,28-AWL-89 |  | 2026-10-06 | 08:15:00 | 2026-10-06 | 08:15:00
457 | 70462433 | HS-TWA | 0016442790 |  | 2105149318 | AC01 |  | 2026-10-18 | 11LHM/A | 0020 | HFEC FUEL Q.DATA CON(FQDC) MOUNTING BRAC | TECO |  | H/26-TWA-X0C03-BLOK-0-1 |  |  | WING_FUEL | BKK_H | SDI | 787.MPD.28-055-00,28-AWL-89 |  | 2026-10-06 | 08:15:00 | 2026-10-06 | 08:15:00
458 | 70462433 | HS-TWA | 0016442838 |  | 2105149366 | AC01 |  | 2026-10-21 | 11LHM/A | 0010 | FUC-CHK HOR.STAB BALLNUT TO BALLSCREW | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-7 | 2 | DCA Appr. Req. 2 | FLOOR_TAIL | BKK_H | FUC | 787.MPD.27-340-00 |  | 2026-10-14 | 08:15:00 | 2026-10-14 | 08:15:00
459 | 70462433 | HS-TWA | 0016442928 |  | 2105149456 | AC01 |  | 2026-10-09 | 11LHM/E | 0010 | OPC the ENHANCED AIRBORN | TECO | DPRC | H/26-TWA-X0C03-BLOK-I-N | 2 | DCA Appr. Req. 2 | IERA_CABIN | BKK_H | OPC | 787.MPD.31-025-00 |  | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
460 | 70462433 | HS-TWA | 0016442949 |  | 2105149472 | AC01 |  | 2026-10-15 | 11LHM/A | 0010 | DISC P.FLT CTL HYD SYS CHK V_V.STAB-RUD | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-6 |  |  | FLOOR_TAIL | BKK_H | DIS | 787.MPD.27-040-00 |  | 2026-10-08 | 08:15:00 | 2026-10-13 | 08:15:00
461 | 70462433 | HS-TWA | 0016442950 |  | 2105149472 | AC01 |  | 2026-10-15 | 11LHM/A | 0020 | DISC P.FLT CTL HYD SYS CHK V_V.STAB-RUD | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-6 |  |  | FLOOR_TAIL | BKK_H | DIS | 787.MPD.27-040-00 |  | 2026-10-08 | 08:15:00 | 2026-10-13 | 08:15:00
462 | 70462433 | HS-TWA | 0016442951 |  | 2105149473 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | DIS P.FLT CTL(LHW+CTR)HYD SYS CHK V_AILE | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-6 |  |  | WING_HYDRAULIC | BKK_H | DIS | 787.MPD.27-040-00 |  | 2026-10-08 | 08:15:00 | 2026-10-13 | 08:15:00
463 | 70462433 | HS-TWA | 0016442952 |  | 2105149473 | AC01 |  | 2026-10-18 | 11LHM/A | 0020 | DIS P.FLT CTL(LHW+CTR)HYD SYS CHK V_AILE | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-6 |  |  | WING_HYDRAULIC | BKK_H | DIS | 787.MPD.27-040-00 |  | 2026-10-08 | 08:15:00 | 2026-10-13 | 08:15:00
464 | 70462433 | HS-TWA | 0016442956 |  | 2105149476 | AC01 |  | 2026-10-21 | 11LHM/A | 0010 | FUC-HOR STAB PRIMARY NO-BACK BRAKE | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-8 | 2 | DCA Appr. Req. 2 | FLOOR_TAIL | BKK_H | FNC | 787.MPD.27-320-00,27-CMR-05 |  | 2026-10-15 | 08:15:00 | 2026-10-15 | 08:15:00
465 | 70462433 | HS-TWA | 0016592341 | 1103207794 | 2105188127 | AC02 |  | 2026-10-20 | 11LHM/A | 0010 | JA-E/26-143:SWAP OB SPOILER PCU | TECO | DPRC | H/26-TWA-X0C03-NONR | 4 | TG Appr. Req. 4 | WING_ALL WING | BKK_H | REP | 787.ED.BKKJA-E/26-143 |  | 2026-01-01 | 07:03:00 | 2026-12-31 | 07:00:00
466 | 70462433 | HS-TWA | 0016592342 | 1103207794 | 2105188127 | AC02 |  | 2026-10-20 | 11LHM/A | 0020 | JA-E/26-143:SWAP OB SPOILER PCU | TECO | DPRC | H/26-TWA-X0C03-NONR | 4 | TG Appr. Req. 4 | WING_ALL WING | BKK_H | REP | 787.ED.BKKJA-E/26-143 |  | 2026-01-01 | 07:03:00 | 2026-12-31 | 07:00:00
467 | 70462433 | HS-TWA | 0016592348 | 1103207795 | 2105188128 | AC02 |  | 2026-10-20 | 11LHM/A | 0010 | JA-E/26-145: SWAP OB SPOILER PCU | TECO | DPRC | H/26-TWA-X0C03-NONR | 4 | TG Appr. Req. 4 | WING_ALL WING | BKK_H | REP | 787.ED.BKKJA-E/26-145 |  | 2026-01-01 | 07:09:00 | 2026-12-31 | 07:00:00
468 | 70462433 | HS-TWA | 0016592349 | 1103207795 | 2105188128 | AC02 |  | 2026-10-20 | 11LHM/A | 0020 | JA-E/26-145: SWAP OB SPOILER PCU | TECO | DPRC | H/26-TWA-X0C03-NONR | 4 | TG Appr. Req. 4 | WING_ALL WING | BKK_H | REP | 787.ED.BKKJA-E/26-145 |  | 2026-01-01 | 07:09:00 | 2026-12-31 | 07:00:00
469 | 70462433 | HS-TWA | 0016582483 | WA017F091026 | WA017F091026 | AC05 |  | 2026-10-21 | BKK_H | 0010 | 30 : WIPER MOTOR CONVERTE LEFT | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-09 | 00:00:00 | 2026-10-09 | 00:00:00
470 | 70462433 | HS-TWA | 0016446995 | WA054C230726 | WA054C230726 | AC05 |  | 2026-10-18 | BKK_L | 0010 | 25 OVERHEAD COMP 60HJK SOFT OPEN U/S BIN | TECO | DPRC | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
471 | 70462433 | HS-TWA | 0016448910 | WA054C230726 | WA054C230726 | AC05 |  | 2026-10-18 | BKK_H | 0020 | 25 OVERHEAD COMP 60HJK SOFT OPEN U/S BIN | TECO | DPRC | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
472 | 70462433 | HS-TWA | 0016459633 | WA076C300726 | WA076C300726 | AC05 |  | 2026-10-18 | BRU | 0010 | 25 DIMMABLE BUTTON BROKEN 60A . | TECO | DPRC | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
473 | 70462433 | HS-TWA | 0016459634 | WA076C300726 | WA076C300726 | AC05 |  | 2026-10-18 | BKK_H | 0020 | 25 DIMMABLE BUTTON BROKEN 60A . | TECO | DPRC | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
474 | 70462433 | HS-TWA | 0016553414 | WA091C200926 | WA091C200926 | AC05 |  | 2026-10-18 | PER | 0010 | 25 SEAT 34A WINDOW DIMMING BUTTON RECESS | TECO | NOGO | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
475 | 70462433 | HS-TWA | 0016553415 | WA091C200926 | WA091C200926 | AC05 |  | 2026-10-18 | BKK_H | 0020 | 25 SEAT 34A WINDOW DIMMING BUTTON RECESS | TECO | NOGO | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
476 | 70462433 | HS-TWA | 0016560705 | WA101F280926 | WA101F280926 | AC05 |  | 2026-10-21 | BKK_L | 0010 | 32 EICAS STAT MSG "TIRE PRESS SYS" DISPL | TECO |  | H/26-TWA-X0C03-NONR | D | Category D |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
477 | 70462433 | HS-TWA | 0016562615 | WA101F280926 | WA101F280926 | AC05 |  | 2026-10-21 | 11LHM/E | 0020 | 32 EICAS STAT MSG "TIRE PRESS SYS" DISPL | TECO |  | H/26-TWA-X0C03-NONR | D | Category D |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
478 | 70462433 | HS-TWA | 0016562614 | WA101F280926 | WA101F280926 | AC05 |  | 2026-10-21 | BKK_L | 0020 | 32 EICAS STAT MSG "TIRE PRESS SYS" DISPL | TECO |  | H/26-TWA-X0C03-NONR | D | Category D |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
479 | 70462433 | HS-TWA | 0014749730 | WA377B190923 | WA377B190923 | AC05 |  | 2026-10-21 | 11LHM/A | 0010 | 57-WINGS/ INBD FLAP DROOP PANEL | TECO | DPRC | H/26-TWA-X0C03-NONR | I | Perform in A-Check |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
480 | 70462433 | HS-TWA | 0016573560 | WA637A061026 | WA637A061026 | AC05 |  | 2026-10-18 | 11LHM/E | 0010 | 44: SEAT 12K PED NO POWER | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-06 | 18:42:00 | 2026-10-06 | 18:59:00
481 | 70462433 | HS-TWA | 0016095560 | 1103117624 | 2105051086 | AC03 |  | 2026-10-08 | 11LHM/A | 0010 | 531616: INSP FPB DOME WEB & Y-CHORD | TECO | DPRC | H/26-TWA-X0C03-MOD -G-F | 0 | AD | INSP-F_FUSELAGE | BKK_H | DET | 787.TO.ITO-531616 | 2026-10-08 | 2026-10-04 | 00:00:00 | 2026-10-16 | 24:00:00
482 | 70462433 | HS-TWA-78-31-0104-ENG2RH | 0016298363 | 1103153511 | 2105105895 | AC03 |  | 2026-10-16 | 11LHM/A | 0010 | 780545:GVI Fire Seal & Thermal Blanket | TECO | WARR | H/26-TWA-X0C03-MOD | 0 | AD |  | BKK_H | MOD | 787.TO.TO-780545 | 2026-10-15 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
483 | 70462433 | HS-TWA-78-31-0103-ENG2LH | 0016304666 | 1103154525 | 2105107861 | AC03 |  | 2026-10-17 | 11LHM/A | 0010 | 780545:GVI Fire Seal & Thermal Blanket | TECO | WARR | H/26-TWA-X0C03-MOD | 0 | AD |  | BKK_H | MOD | 787.TO.TO-780545 | 2026-10-17 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
484 | 70462433 | HS-TWA | 0016442688 |  | 2105149224 | AC01 | EWIS | 2026-10-08 | 11LQ/IE | 0010 | GVI WIRING and CONNECTED EWIS in the APU | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-2 | 2 | DCA Appr. Req. 2 | INSP-I_FLOOR | BKK_H | GVI | 787.MPD.20-664-00 | 2026-10-08 | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
485 | 70462433 | HS-TWA | 0016442689 |  | 2105149225 | AC01 | EWIS | 2026-10-09 | 11LQ/IE | 0010 | GVI WIRING EWIS under the FORWARD LEFT N | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-2 | 2 | DCA Appr. Req. 2 | INSP-I_FLOOR | BKK_H | GVI | 787.MPD.20-670-01 | 2026-10-08 | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
486 | 70462433 | HS-TWA | 0016442690 |  | 2105149226 | AC01 | EWIS | 2026-10-09 | 11LQ/IE | 0010 | GVI WIRING EWIS FORWARD RIGHT NACELLE | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-2 | 2 | DCA Appr. Req. 2 | INSP-I_FLOOR | BKK_H | GVI | 787.MPD.20-671-02 | 2026-10-06 | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
487 | 70462433 | HS-TWA | 0016442693 |  | 2105149229 | AC01 |  | 2026-10-10 | 11LQ/IA | 0010 | EXTERNAL - ZONAL (GV): NOSE LANDING GEAR | TECO |  | H/26-TWA-X0C03-BLOK-0-1 | 2 | DCA Appr. Req. 2 | INSP-F_LANDING GEAR | BKK_H | GVI | 787.MPD.32-805-00 | 2026-10-07 | 2026-10-06 | 08:15:00 | 2026-10-06 | 08:15:00
488 | 70462433 | HS-TWA | 0016442694 |  | 2105149230 | AC01 |  | 2026-10-10 | 11LQ/IA | 0010 | EXTERNAL-ZONAL LH MLG AND LANDING GEAR | TECO |  | H/26-TWA-X0C03-BLOK-0-1 | 2 | DCA Appr. Req. 2 | INSP-F_LANDING GEAR | BKK_H | GVI | 787.MPD.32-815-01 | 2026-10-07 | 2026-10-06 | 08:15:00 | 2026-10-06 | 08:15:00
489 | 70462433 | HS-TWA | 0016442695 |  | 2105149231 | AC01 |  | 2026-10-10 | 11LQ/IA | 0010 | EXTERNAL - ZONAL (GV):RIGHT MAIN LANDING | TECO |  | H/26-TWA-X0C03-BLOK-0-1 | 2 | DCA Appr. Req. 2 | INSP-F_LANDING GEAR | BKK_H | GVI | 787.MPD.32-825-02 | 2026-10-07 | 2026-10-06 | 08:15:00 | 2026-10-06 | 08:15:00
490 | 70462433 | HS-TWA | 0016442697 |  | 2105149233 | AC01 | EWIS | 2026-10-08 | 11LQ/IE | 0010 | GVI WING LEADING EDGE TO FRONT SPAR | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-2 | 2 | DCA Appr. Req. 2 | INSP-I_WING | BKK_H | GVI | 787.MPD.20-695-00 | 2026-10-08 | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
491 | 70462433 | HS-TWA | 0016442698 |  | 2105149234 | AC01 | EWIS | 2026-10-08 | 11LQ/IE | 0010 | GVI WIRING LEADING EDGE TO FRONT | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-2 | 2 | DCA Appr. Req. 2 | INSP-I_FLOOR | BKK_H | GVI | 787.MPD.20-700-00 | 2026-10-08 | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
492 | 70462433 | HS-TWA | 0016442699 |  | 2105149235 | AC01 | EWIS | 2026-10-08 | 11LQ/IE | 0010 | GVI WIRING WING REAR SPAR TO LANDING GEA | TECO |  | H/26-TWA-X0C03-BLOK-0-2 | 2 | DCA Appr. Req. 2 | INSP-I_FLOOR | BKK_H | GVI | 787.MPD.20-705-00 | 2026-10-08 | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
493 | 70462433 | HS-TWA | 0016442700 |  | 2105149236 | AC01 | EWIS | 2026-10-08 | 11LQ/IE | 0010 | GVI WIRING LANDING GEAR SUPPORT BEAM TO | TECO |  | H/26-TWA-X0C03-BLOK-0-2 | 2 | DCA Appr. Req. 2 | INSP-I_FLOOR | BKK_H | GVI | 787.MPD.20-710-00 | 2026-10-08 | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
494 | 70462433 | HS-TWA | 0016442702 |  | 2105149238 | AC01 |  | 2026-10-10 | 11LQ/IC | 0010 | VIC-SMOKE HOODS | TECO |  | H/26-TWA-X0C03-BLOK-0-1 |  |  | INSP-C_ALL CABIN | BKK_H | VIC | 787.MPD.25-065-00 | 2026-10-06 | 2026-10-06 | 08:15:00 | 2026-10-06 | 08:15:00
495 | 70462433 | HS-TWA | 0016442703 |  | 2105149239 | AC01 |  | 2026-10-10 | 11LQ/IA | 0010 | INTERNAL - ZONAL (GV): NOSE LANDING GEAR | TECO |  | H/26-TWA-X0C03-BLOK-0-1 | 2 | DCA Appr. Req. 2 | INSP-F_LANDING GEAR | BKK_H | GVI | 787.MPD.53-818-00 | 2026-10-07 | 2026-10-06 | 08:15:00 | 2026-10-06 | 08:15:00
496 | 70462433 | HS-TWA | 0016442704 |  | 2105149240 | AC01 |  | 2026-10-10 | 11LQ/IA | 0010 | INTERNAL - ZONAL (GV): LEFT MAIN LANDING | TECO |  | H/26-TWA-X0C03-BLOK-0-1 | 2 | DCA Appr. Req. 2 | INSP-F_LANDING GEAR | BKK_H | GVI | 787.MPD.53-854-01 | 2026-10-07 | 2026-10-06 | 08:15:00 | 2026-10-06 | 08:15:00
497 | 70462433 | HS-TWA | 0016442705 |  | 2105149241 | AC01 |  | 2026-10-10 | 11LQ/IA | 0010 | INTERNAL - ZONAL (GV): RIGHT MAIN LANDIN | TECO |  | H/26-TWA-X0C03-BLOK-0-1 | 2 | DCA Appr. Req. 2 | INSP-F_LANDING GEAR | BKK_H | GVI | 787.MPD.53-860-02 | 2026-10-07 | 2026-10-06 | 08:15:00 | 2026-10-06 | 08:15:00
498 | 70462433 | HS-TWA | 0016442706 |  | 2105149242 | AC01 | EWIS | 2026-10-08 | 11LQ/IE | 0010 | GVI WIRING LEFT MAIN LANDING GEAR | TECO |  | H/26-TWA-X0C03-BLOK-0-2 |  |  | INSP-I_FLOOR | BKK_H | GVI | 787.MPD.20-730-01 | 2026-10-08 | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
499 | 70462433 | HS-TWA | 0016442707 |  | 2105149243 | AC01 | EWIS | 2026-10-08 | 11LQ/IE | 0010 | GVI WIRING RIGHT MAIN LANDING GEAR | TECO |  | H/26-TWA-X0C03-BLOK-0-2 | 2 | DCA Appr. Req. 2 | INSP-I_FLOOR | BKK_H | GVI | 787.MPD.20-735-02 | 2026-10-08 | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
500 | 70462433 | HS-TWA | 0016442710 |  | 2105149246 | AC01 | EWIS | 2026-10-09 | 11LQ/IE | 0010 | GVI WIRING AFT RIGHT NACELLE STRUT FAIRI | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-2 | 2 | DCA Appr. Req. 2 | INSP-I_FLOOR | BKK_H | GVI | 787.MPD.20-745-02 | 2026-10-07 | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
501 | 70462433 | HS-TWA | 0016442711 |  | 2105149247 | AC01 | EWIS | 2026-10-08 | 11LQ/IE | 0010 | GVI WIRING LEFT MAIN LANDING GEAR WHEEL | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-2 | 2 | DCA Appr. Req. 2 | INSP-I_FLOOR | BKK_H | GVI | 787.MPD.20-750-01 | 2026-10-08 | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
502 | 70462433 | HS-TWA | 0016442712 |  | 2105149248 | AC01 | EWIS | 2026-10-08 | 11LQ/IE | 0010 | GVI WIRING RIGHT MAIN LANDING GEAR WHEEL | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-2 | 2 | DCA Appr. Req. 2 | INSP-I_FLOOR | BKK_H | GVI | 787.MPD.20-755-02 | 2026-10-08 | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
503 | 70462433 | HS-TWA | 0016442716 |  | 2105149252 | AC01 |  | 2026-10-06 | 11LHM/E | 0010 | OPC AUDIO OVERRIDE SWITCH | TECO | DPRC | H/26-TWA-X0C03-BLOK-I-N |  |  | IERA_FLOOR | BKK_H | OPC | 787.MPD.23-005-00 | 2026-10-06 | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
504 | 70462433 | HS-TWA | 0016442720 |  | 2105149256 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | EXTERNAL-ZONAL(GV):FORWARD TORQUE BOX RH | TECO |  | H/26-TWA-X0C03-BLOK-0-5 | 2 | DCA Appr. Req. 2 | INSP-W_ENGINE | BKK_H | GVI | 787.MPD.54-940-02 | 2026-10-14 | 2026-10-12 | 08:15:00 | 2026-10-12 | 08:15:00
505 | 70462433 | HS-TWA | 0016442721 |  | 2105149257 | AC01 |  | 2026-10-10 | 11LQ/IC | 0010 | VIC-CRASH AXE | TECO |  | H/26-TWA-X0C03-BLOK-0-1 |  |  | INSP-C_COCKPIT | BKK_H | VIC | 787.MPD.25-090-00 | 2026-10-06 | 2026-10-06 | 08:15:00 | 2026-10-06 | 08:15:00
506 | 70462433 | HS-TWA | 0016442722 |  | 2105149258 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | INTERNAL-ZONAL(GV):FORWARD TORQUE BOX RH | TECO |  | H/26-TWA-X0C03-BLOK-0-5 | 2 | DCA Appr. Req. 2 | INSP-W_ENGINE | BKK_H | GVI | 787.MPD.54-945-02 | 2026-10-14 | 2026-10-12 | 08:15:00 | 2026-10-12 | 08:15:00
507 | 70462433 | HS-TWA | 0016442724 |  | 2105149260 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | EXTERNAL - ZONAL (GV): AFT TORQUE BOX RH | TECO |  | H/26-TWA-X0C03-BLOK-0-5 | 2 | DCA Appr. Req. 2 | INSP-W_ENGINE | BKK_H | GVI | 787.MPD.54-950-02 | 2026-10-14 | 2026-10-12 | 08:15:00 | 2026-10-12 | 08:15:00
508 | 70462433 | HS-TWA | 0016442725 |  | 2105149261 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | INTERNAL - ZONAL (GV): AFT TORQUE BOX RH | TECO |  | H/26-TWA-X0C03-BLOK-0-5 | 2 | DCA Appr. Req. 2 | INSP-W_ENGINE | BKK_H | GVI | 787.MPD.54-955-02 | 2026-10-14 | 2026-10-12 | 08:15:00 | 2026-10-12 | 08:15:00
509 | 70462433 | HS-TWA | 0016442731 |  | 2105149266 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | INSP (DETAILED) THRUST REVERSER BLOCK RH | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-3 | 2 | DCA Appr. Req. 2 | INSP-W_ENGINE | BKK_H | DET | 787.MPD.78-205-02 | 2026-10-16 | 2026-10-10 | 08:15:00 | 2026-10-10 | 08:15:00
510 | 70462433 | HS-TWA | 0016442736 |  | 2105149271 | AC01 |  | 2026-10-06 | 11LHM/A | 0010 | OPC OUTFLOW VALVES | TECO | DPRC | H/26-TWA-X0C03-BLOK-I-N |  |  | FLOOR_AIR COND | BKK_H | OPC | 787.MPD.21-055-00 | 2026-10-06 | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
511 | 70462433 | HS-TWA | 0016442743 |  | 2105149277 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | GVI THRUST REVERSER INNER V-BLADE ENG#2 | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-2 | 2 | DCA Appr. Req. 2 | INSP-W_ENGINE | BKK_H | GVI | 787.MPD.78-235-02 | 2026-10-14 | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
512 | 70462433 | HS-TWA | 0016442754 |  | 2105149285 | AC01 |  | 2026-10-06 | 11LHM/E | 0010 | OPC the Overhead Flight | TECO | DPRC | H/26-TWA-X0C03-BLOK-I-N | 1 | DCA Appr. Req. 1 | IERA_CABIN | BKK_H | OPC | 787.MPD.26-045-00 | 2026-10-06 | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
513 | 70462433 | HS-TWA | 0016442755 |  | 2105149285 | AC01 |  | 2026-10-06 | 11LHM/E | 0020 | OPC the Overhead Flight | TECO | DPRC | H/26-TWA-X0C03-BLOK-I-N | 1 | DCA Appr. Req. 1 | IERA_CABIN | BKK_H | OPC | 787.MPD.26-045-00 | 2026-10-06 | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
514 | 70462433 | HS-TWA | 0016442760 |  | 2105149290 | AC01 |  | 2026-10-06 | 11LHM/E | 0010 | OPC the Cargo Compartmen | TECO | DPRC | H/26-TWA-X0C03-BLOK-I-N | 1 | DCA Appr. Req. 1 | IERA_CABIN | BKK_H | OPC | 787.MPD.26-090-00 | 2026-10-06 | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
515 | 70462433 | HS-TWA | 0016442764 |  | 2105149294 | AC01 |  | 2026-10-06 | 11LHM/E | 0010 | OPC PDF/MFD Select Switch | TECO | DPRC | H/26-TWA-X0C03-BLOK-I-N | 2 | DCA Appr. Req. 2 | IERA_CABIN | BKK_H | OPC | 787.MPD.31-010-00 | 2026-10-06 | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
516 | 70462433 | HS-TWA | 0016442765 |  | 2105149295 | AC01 |  | 2026-10-06 | 11LHM/E | 0010 | OPC AIR DATA / ATTITUDE SELECT SW | TECO | DPRC | H/26-TWA-X0C03-BLOK-I-N | 2 | DCA Appr. Req. 2 | IERA_CABIN | BKK_H | OPC | 787.MPD.31-015-00 | 2026-10-06 | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
517 | 70462433 | HS-TWA | 0016442766 |  | 2105149296 | AC01 |  | 2026-10-06 | 11LHM/E | 0010 | OPC the primary FLIGHT C | TECO | DPRC | H/26-TWA-X0C03-BLOK-I-N | 2 | DCA Appr. Req. 2 | IERA_CABIN | BKK_H | OPC | 787.MPD.31-020-00 | 2026-10-06 | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
518 | 70462433 | HS-TWA | 0016442770 |  | 2105149299 | AC01 |  | 2026-10-06 | 11LHM/E | 0010 | OPC EXTERIOR PASSENGER DOOR VIEWING LIGH | TECO | DPRC | H/26-TWA-X0C03-BLOK-I-N | 2 | DCA Appr. Req. 2 | IERA_CABIN | BKK_H | OPC | 787.MPD.33-035-00 | 2026-10-06 | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
519 | 70462433 | HS-TWA | 0016442775 |  | 2105149304 | AC01 |  | 2026-10-14 | 11LQ/IC | 0010 | DI-OVERHEAD FLIGHT CREW & ATTENDANT | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-3 |  |  | INSP-I_CABIN | BKK_H | DI | 787.MPD.25-130-00 | 2026-10-09 | 2026-10-10 | 08:15:00 | 2026-10-10 | 08:15:00
520 | 70462433 | HS-TWA | 0016442776 |  | 2105149305 | AC01 |  | 2026-10-08 | 11LQ/IC | 0010 | GVI-PASSENGER SEAT ATTACHMENT | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-1 |  |  | INSP-I_CABIN | BKK_H | GVI | 787.MPD.25-140-00 | 2026-10-17 | 2026-10-06 | 08:15:00 | 2026-10-06 | 08:15:00
521 | 70462433 | HS-TWA | 0016442777 |  | 2105149306 | AC01 |  | 2026-10-18 | 11LQ/IC | 0010 | DI-PASSENGER SEAT OCCUPANT RESTRAINT | TECO | ODAT | H/26-TWA-X0C03-BLOK-0-3 |  |  | INSP-I_CABIN | BKK_H | DI | 787.MPD.25-145-00 | 2026-10-09 | 2026-10-10 | 08:15:00 | 2026-10-10 | 08:15:00
522 | 70462433 | HS-TWA | 0016442779 |  | 2105149308 | AC01 |  | 2026-10-14 | 11LQ/IC | 0010 | DI-ATTENDANT SEAT OCCUPANT RESTRAINT | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-3 |  |  | INSP-I_CABIN | BKK_H | DI | 787.MPD.25-147-00 | 2026-10-09 | 2026-10-10 | 08:15:00 | 2026-10-10 | 08:15:00
523 | 70462433 | HS-TWA | 0016442782 |  | 2105149311 | AC01 |  | 2026-10-06 | 11LHM/E | 0010 | FUC CONTROL WHEEL FORCE TRANSDUCER | TECO | DPRC | H/26-TWA-X0C03-BLOK-I-N |  |  | FLOOR_FUSELAGE | BKK_H | FUC | 787.MPD.27-170-00 | 2026-10-06 | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
524 | 70462433 | HS-TWA | 0016442784 |  | 2105149313 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | VCK TE FLAP TORQUE TUBE GUARDS,RHW | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-1 |  |  | WING_TRAILING EDGE | BKK_H | VCK | 787.MPD.27-380-00 | 2026-10-10 | 2026-10-06 | 00:00:00 | 2026-10-06 | 00:00:00
525 | 70462433 | HS-TWA | 0016442787 |  | 2105149316 | AC01 |  | 2026-10-14 | 11LHM/A | 0010 | GVI FUEL SURGE TANK FLAME ARRESTORS,LHW | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-1 |  |  | WING_FUEL | BKK_H | GVI | 787.MPD.28-010-00 | 2026-10-14 | 2026-10-06 | 00:00:00 | 2026-10-06 | 00:00:00
526 | 70462433 | HS-TWA | 0016442788 |  | 2105149317 | AC01 |  | 2026-10-14 | 11LHM/A | 0010 | GVI FUEL SURGE TANK FLAME ARRESTORS,RHW | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-1 |  |  | WING_FUEL | BKK_H | GVI | 787.MPD.28-010-00 | 2026-10-14 | 2026-10-06 | 00:00:00 | 2026-10-06 | 00:00:00
527 | 70462433 | HS-TWA | 0016442793 |  | 2105149321 | AC01 |  | 2026-10-09 | 11LHM/A | 0010 | GVI(INT) LE TO FRONT SPAR-INB NACELL,RHW | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-1 |  |  | WING_LEADING EDGE | BKK_H | GVI | 787.MPD.57-894-02 | 2026-10-09 | 2026-10-06 | 00:00:00 | 2026-10-06 | 00:00:00
528 | 70462433 | HS-TWA | 0016442794 |  | 2105149322 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | GVI(EXT)LE TO FRONT SPAR UPP/LWR INB,LHW | TECO |  | H/26-TWA-X0C03-BLOK-0-2 |  |  | INSP-W_LEADING EDGE | BKK_H | GVI | 787.MPD.57-802-01 | 2026-10-11 | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
529 | 70462433 | HS-TWA | 0016442795 |  | 2105149323 | AC01 |  | 2026-10-09 | 11LQ/IA | 0010 | GVI(EXT)LE TO FRONT SPAR UPP/LWR INB,RHW | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-2 |  |  | INSP-W_LEADING EDGE | BKK_H | GVI | 787.MPD.57-896-02 | 2026-10-07 | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
530 | 70462433 | HS-TWA | 0016442796 |  | 2105149324 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | GVI(EXT) ZONAL SLAT#1-6,LHW | TECO |  | H/26-TWA-X0C03-BLOK-0-2 |  |  | INSP-W_LEADING EDGE | BKK_H | GVI | 787.MPD.57-804-01 | 2026-10-13 | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
531 | 70462433 | HS-TWA | 0016442797 |  | 2105149325 | AC01 |  | 2026-10-14 | 11LQ/IA | 0010 | GVI(EXT) ZONAL SLAT#7-12,RHW | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-2 |  |  | INSP-W_LEADING EDGE | BKK_H | GVI | 787.MPD.57-898-02 | 2026-10-07 | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
532 | 70462433 | HS-TWA | 0016442798 |  | 2105149326 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | GVI(INT)KRUEGER SEAL FLAP/NACELL GAP,LHW | TECO |  | H/26-TWA-X0C03-BLOK-0-2 |  |  | INSP-W_LEADING EDGE | BKK_H | GVI | 787.MPD.57-818-01 | 2026-10-13 | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
533 | 70462433 | HS-TWA | 0016442799 |  | 2105149327 | AC01 |  | 2026-10-14 | 11LQ/IA | 0010 | GVI(INT)KRUEGER SEAL FLAP/NACELL GAP,RHW | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-2 |  |  | INSP-W_LEADING EDGE | BKK_H | GVI | 787.MPD.57-912-02 | 2026-10-07 | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
534 | 70462433 | HS-TWA | 0016442800 |  | 2105149328 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | GVI(EXT) UPP/LWR KRUEGER SEAL FLAP,LHW | TECO |  | H/26-TWA-X0C03-BLOK-0-2 |  |  | INSP-W_LEADING EDGE | BKK_H | GVI | 787.MPD.57-820-01 | 2026-10-11 | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
535 | 70462433 | HS-TWA | 0016442801 |  | 2105149329 | AC01 |  | 2026-10-14 | 11LQ/IA | 0010 | GVI(EXT) UPP/LWR KRUEGER SEAL FLAP,RHW | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-2 |  |  | INSP-W_LEADING EDGE | BKK_H | GVI | 787.MPD.57-914-02 | 2026-10-07 | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
536 | 70462433 | HS-TWA | 0016442803 |  | 2105149331 | AC01 |  | 2026-10-14 | 11LQ/IA | 0010 | GVI(EXT)LE TO FRONT SPAR UP/LWR OUTB,RHW | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-2 |  |  | INSP-W_LEADING EDGE | BKK_H | GVI | 787.MPD.57-916-02 | 2026-10-07 | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
537 | 70462433 | HS-TWA | 0016442804 |  | 2105149332 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | GVI(INT) LE TO FRONT SPAR-OUTB NACEL,LHW | TECO |  | H/26-TWA-X0C03-BLOK-0-1 |  |  | INSP-W_LEADING EDGE | BKK_H | GVI | 787.MPD.57-824-01 | 2026-10-11 | 2026-10-06 | 08:15:00 | 2026-10-06 | 08:15:00
538 | 70462433 | HS-TWA | 0016442806 |  | 2105149334 | AC01 |  | 2026-10-08 | 11LQ/IA | 0010 | GVI(EXT) WING TIP UPP/LWR SURF OUTB,LHW | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-2 |  |  | INSP-W_TRAILING EDGE | BKK_H | GVI | 787.MPD.57-839-01 | 2026-10-06 | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
539 | 70462433 | HS-TWA | 0016442807 |  | 2105149335 | AC01 |  | 2026-10-08 | 11LQ/IA | 0010 | GVI(EXT) WING TIP UPP/LWR SURF OUTB,RHW | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-2 |  |  | INSP-W_TRAILING EDGE | BKK_H | GVI | 787.MPD.57-933-02 | 2026-10-06 | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
540 | 70462433 | HS-TWA | 0016442808 |  | 2105149336 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | GVI(INT) WING TIP OUTB CLOSURE RIB,LHW | TECO |  | H/26-TWA-X0C03-BLOK-0-1 |  |  | INSP-W_TRAILING EDGE | BKK_H | GVI | 787.MPD.57-840-01 | 2026-10-13 | 2026-10-06 | 08:15:00 | 2026-10-06 | 08:15:00
541 | 70462433 | HS-TWA | 0016442809 |  | 2105149337 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | GVI(INT) WING TIP OUTB CLOSURE RIB,RHW | TECO |  | H/26-TWA-X0C03-BLOK-0-1 |  |  | INSP-W_TRAILING EDGE | BKK_H | GVI | 787.MPD.57-934-02 | 2026-10-10 | 2026-10-06 | 08:15:00 | 2026-10-06 | 08:15:00
542 | 70462433 | HS-TWA | 0016442810 |  | 2105149338 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | GVI(EXT)AFT REAR SPAR-LG BEAM UP/LWR,LHW | TECO |  | H/26-TWA-X0C03-BLOK-0-1 |  |  | INSP-W_TRAILING EDGE | BKK_H | GVI | 787.MPD.57-842-01 | 2026-10-13 | 2026-10-06 | 08:15:00 | 2026-10-06 | 08:15:00
543 | 70462433 | HS-TWA | 0016442811 |  | 2105149339 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | GVI(EXT)AFT REAR SPAR-LG BEAM UP/LWR,RHW | TECO |  | H/26-TWA-X0C03-BLOK-0-1 |  |  | INSP-W_TRAILING EDGE | BKK_H | GVI | 787.MPD.57-936-02 | 2026-10-10 | 2026-10-06 | 08:15:00 | 2026-10-06 | 08:15:00
544 | 70462433 | HS-TWA | 0016442812 |  | 2105149340 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | GVI(INT) AFT REAR SPAR-LG SUPP BEAM,LHW | TECO |  | H/26-TWA-X0C03-BLOK-0-1 |  |  | INSP-W_TRAILING EDGE | BKK_H | GVI | 787.MPD.57-844-01 | 2026-10-14 | 2026-10-06 | 08:15:00 | 2026-10-06 | 08:15:00
545 | 70462433 | HS-TWA | 0016442813 |  | 2105149341 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | GVI(INT) AFT REAR SPAR-LG SUPP BEAM,RHW | TECO |  | H/26-TWA-X0C03-BLOK-0-1 |  |  | INSP-W_TRAILING EDGE | BKK_H | GVI | 787.MPD.57-938-02 | 2026-10-10 | 2026-10-06 | 08:15:00 | 2026-10-06 | 08:15:00
546 | 70462433 | HS-TWA | 0016442814 |  | 2105149342 | AC01 |  | 2026-10-08 | 11LQ/IA | 0010 | GVI(EXT) UPP/LWR WING LG SUP BEAM-TE,LHW | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-2 |  |  | INSP-W_TRAILING EDGE | BKK_H | GVI | 787.MPD.57-846-01 | 2026-10-06 | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
547 | 70462433 | HS-TWA | 0016442815 |  | 2105149343 | AC01 |  | 2026-10-08 | 11LQ/IA | 0010 | GVI(EXT) UPP/LWR WING LG SUP BEAM-TE,RHW | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-2 |  |  | INSP-W_TRAILING EDGE | BKK_H | GVI | 787.MPD.57-940-02 | 2026-10-06 | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
548 | 70462433 | HS-TWA | 0016442816 |  | 2105149344 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | GVI(INT) WING FROM LG SUPP BEAM-TE,LHW | TECO |  | H/26-TWA-X0C03-BLOK-0-1 |  |  | INSP-W_TRAILING EDGE | BKK_H | GVI | 787.MPD.57-848-01 | 2026-10-14 | 2026-10-06 | 08:15:00 | 2026-10-06 | 08:15:00
549 | 70462433 | HS-TWA | 0016442817 |  | 2105149345 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | GVI(INT) WING FROM LG SUPP BEAM-TE,RHW | TECO |  | H/26-TWA-X0C03-BLOK-0-1 |  |  | INSP-W_TRAILING EDGE | BKK_H | GVI | 787.MPD.57-942-02 | 2026-10-10 | 2026-10-06 | 08:15:00 | 2026-10-06 | 08:15:00
550 | 70462433 | HS-TWA | 0016442820 |  | 2105149348 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | GVI(EXT) ZONAL INB TE FLAP,LHW | TECO |  | H/26-TWA-X0C03-BLOK-0-2 |  |  | INSP-W_TRAILING EDGE | BKK_H | GVI | 787.MPD.57-854-01 | 2026-10-14 | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
551 | 70462433 | HS-TWA | 0016442822 |  | 2105149350 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | GVI(EXT) ZONAL FLAPERON,LHW | TECO |  | H/26-TWA-X0C03-BLOK-0-2 |  |  | INSP-W_TRAILING EDGE | BKK_H | GVI | 787.MPD.57-858-01 | 2026-10-13 | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
552 | 70462433 | HS-TWA | 0016442824 |  | 2105149352 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | GVI(EXT) REAR SPAR-OUT INB TE UP/LWR,LHW | TECO |  | H/26-TWA-X0C03-BLOK-0-2 |  |  | INSP-W_TRAILING EDGE | BKK_H | GVI | 787.MPD.57-862-01 | 2026-10-14 | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
553 | 70462433 | HS-TWA | 0016442825 |  | 2105149353 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | GVI(EXT) REAR SPAR-OUT INB TE UP/LWR,RHW | TECO |  | H/26-TWA-X0C03-BLOK-0-2 |  |  | INSP-W_TRAILING EDGE | BKK_H | GVI | 787.MPD.57-956-02 | 2026-10-10 | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
554 | 70462433 | HS-TWA | 0016442826 |  | 2105149354 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | GVI(INT) REAR SPAR TO TE,LHW | TECO |  | H/26-TWA-X0C03-BLOK-0-1 |  |  | INSP-W_TRAILING EDGE | BKK_H | GVI | 787.MPD.57-864-01 | 2026-10-11 | 2026-10-06 | 08:15:00 | 2026-10-06 | 08:15:00
555 | 70462433 | HS-TWA | 0016442836 |  | 2105149364 | AC01 |  | 2026-10-06 | 11LHM/E | 0010 | OPC-CHK RUDDER TRIM SWITCH | TECO | DPRC | H/26-TWA-X0C03-BLOK-I-N | 2 | DCA Appr. Req. 2 | FLOOR_TAIL | BKK_H | OPC | 787.MPD.27-175-00 | 2026-10-06 | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
556 | 70462433 | HS-TWA | 0016442841 |  | 2105149369 | AC01 |  | 2026-10-18 | 11LHM/E | 0010 | OPC the COMMON COMPUTING | TECO | DPRC | H/26-TWA-X0C03-BLOK-I-N | 2 | DCA Appr. Req. 2 | IERA_CABIN | BKK_H | OPC | 787.MPD.42-005-00 | 2026-10-06 | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
557 | 70462433 | HS-TWA | 0016442879 |  | 2105149407 | AC01 |  | 2026-10-08 | 11LQ/IA | 0010 | VISUAL CHK FWD CARGO COMP FIRE EXTING | TECO |  | H/26-TWA-X0C03-BLOK-0-3 | 1 | DCA Appr. Req. 1 | INSP-F_FWD COMPT | BKK_H | VCK | 787.MPD.26-070-00 | 2026-10-08 | 2026-10-10 | 08:15:00 | 2026-10-10 | 08:15:00
558 | 70462433 | HS-TWA | 0016442883 |  | 2105149411 | AC01 |  | 2026-10-08 | 11LQ/IA | 0010 | INSP FWD COMP FIRE EXTING BOTTLE | TECO |  | H/26-TWA-X0C03-BLOK-0-3 |  |  | INSP-F_FWD COMPT | BKK_H | GVI | 787.MPD.26-095-00 | 2026-10-08 | 2026-10-10 | 16:30:00 | 2026-10-10 | 16:30:00
559 | 70462433 | HS-TWA | 0016442887 |  | 2105149415 | AC01 |  | 2026-10-08 | 11LQ/IA | 0010 | INSP FWD CARGO CONTAINER LOCKS | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-3 | 1 | DCA Appr. Req. 1 | INSP-F_FWD COMPT | BKK_H | DET | 787.MPD.50-025-00 | 2026-10-08 | 2026-10-10 | 16:30:00 | 2026-10-10 | 16:30:00
560 | 70462433 | HS-TWA | 0016442889 |  | 2105149417 | AC01 |  | 2026-10-08 | 11LQ/IA | 0010 | INSP FWD CARGO DOOR SEALS | TECO |  | H/26-TWA-X0C03-BLOK-0-3 |  |  | INSP-F_FWD COMPT | BKK_H | DET | 787.MPD.52-025-00 | 2026-10-08 | 2026-10-10 | 16:30:00 | 2026-10-10 | 16:30:00
561 | 70462433 | HS-TWA | 0016442890 |  | 2105149418 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | INSP AFT CARGO DOOR SEALS | TECO |  | H/26-TWA-X0C03-BLOK-0-3 |  |  | INSP-F_AFT COMPT | BKK_H | DET | 787.MPD.52-025-00 | 2026-10-15 | 2026-10-10 | 08:15:00 | 2026-10-10 | 08:15:00
562 | 70462433 | HS-TWA | 0016442892 |  | 2105149420 | AC01 |  | 2026-10-08 | 11LQ/IA | 0010 | INSP FWD CARGO INDICATOR | TECO |  | H/26-TWA-X0C03-BLOK-0-3 |  |  | INSP-F_FWD COMPT | BKK_H | VCK | 787.MPD.52-120-00 | 2026-10-08 | 2026-10-10 | 08:15:00 | 2026-10-10 | 08:15:00
563 | 70462433 | HS-TWA | 0016442894 |  | 2105149422 | AC01 |  | 2026-10-08 | 11LQ/IA | 0010 | INSP FWD CARGO DOOR LOCK MECHANISM | TECO |  | H/26-TWA-X0C03-BLOK-0-3 | 2 | DCA Appr. Req. 2 | INSP-F_FWD COMPT | BKK_H | DET | 787.MPD.52-130-00 | 2026-10-08 | 2026-10-10 | 08:15:00 | 2026-10-10 | 08:15:00
564 | 70462433 | HS-TWA | 0016442912 |  | 2105149440 | AC01 |  | 2026-10-08 | 11LQ/IA | 0010 | GVI FWD CARGO DOOR EXTERNAL | TECO |  | H/26-TWA-X0C03-BLOK-0-3 |  |  | INSP-F_FWD COMPT | BKK_H | GVI | 787.MPD.52-815-02 | 2026-10-08 | 2026-10-10 | 08:15:00 | 2026-10-10 | 08:15:00
565 | 70462433 | HS-TWA | 0016442914 |  | 2105149442 | AC01 |  | 2026-10-08 | 11LQ/IA | 0010 | INSP FWD CARGO DOOR CUTOUT RIGHT | TECO |  | H/26-TWA-X0C03-BLOK-0-3 |  |  | INSP-F_FWD COMPT | BKK_H | DET | 787.MPD.53-507-00 | 2026-10-08 | 2026-10-10 | 08:15:00 | 2026-10-10 | 08:15:00
566 | 70462433 | HS-TWA | 0016442919 |  | 2105149447 | AC01 |  | 2026-10-07 | 11LQ/IC | 0010 | INSP PASSENGER ENTRY DOOR 3 AND 4 RIGHT | TECO |  | H/26-TWA-X0C03-BLOK-0-2 |  |  | INSP-C_DOOR | BKK_H | DET | 787.MPD.53-566-01 | 2026-10-16 | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
567 | 70462433 | HS-TWA | 0016442939 |  | 2105149467 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | FUC GROSS INT LEAKAGE CTR HYD SYS | TECO |  | H/26-TWA-X0C03-BLOK-I-N |  |  | WING_HYDRAULIC | BKK_H | FUC | 787.MPD.29-120-00,29-CMR-02 | 2026-10-20 | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
568 | 70462433 | HS-TWA | 0016442955 |  | 2105149475 | AC01 |  | 2026-10-08 | 11LQ/IA | 0010 | DVI-VISIBLE POSITIONS CTL WHEEL MECHANIS | TECO |  | H/26-TWA-X0C03-BLOK-0-1 |  |  | INSP-F_LANDING GEAR | BKK_H | DET | 787.MPD.27-050-00, 27-CMR-10 | 2026-10-08 | 2026-10-06 | 08:15:00 | 2026-10-06 | 08:15:00
569 | 70462433 | HS-TWA | 0016442974 |  | 2105149490 | AC01 |  | 2026-10-18 | 11LHM/E | 0010 | Restoration (Cleaning) of AREAS UNDER th | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-0-3 |  |  | IERA_ALL IERA | BKK_H | CLN | 787.MPD.20-780-00 | 2026-10-09 | 2026-10-10 | 08:15:00 | 2026-10-10 | 08:15:00
570 | 70462433 | HS-TWA | 0016442977 |  | 2105149493 | AC01 |  | 2026-10-21 | 11LHM/A | 0010 | FUNC RUDDER PEDAL OVERRIDE MECHANISM | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-4 | 2 | DCA Appr. Req. 2 | FLOOR_FUSELAGE | BKK_H | FNC | 787.MPD.27-210-00 | 2026-10-21 | 2026-10-11 | 08:15:00 | 2026-10-11 | 08:15:00
571 | 70462433 | HS-TWA | 0016442985 |  | 2105149500 | AC01 |  | 2026-10-14 | 11LHM/A | 0010 | FUEL VENT CROSSFLOW CHKV IN VENT TUBE -9 | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-1 | 2 | DCA Appr. Req. 2 | FLOOR_AIR COND | BKK_H | INS | 787.MPD.47-025-00 | 2026-10-14 | 2026-10-06 | 00:00:00 | 2026-10-06 | 00:00:00
572 | 70462433 | HS-TWA | 0016442990 |  | 2105149504 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | DVI APU COMPARTMENT THERMAL BARRIER | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-1 | 1 | DCA Appr. Req. 1 | FLOOR_TAIL | BKK_H | INS | 787.MPD.49-035-00 | 2026-10-19 | 2026-10-06 | 00:00:00 | 2026-10-06 | 00:00:00
573 | 70462433 | HS-TWA | 0016443000 |  | 2105149513 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | DET-FIRE SEAL DEPRESSOR RIGHT STRUT | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-0-4 | 1 | DCA Appr. Req. 1 | INSP-W_ALL WING | BKK_H | DET | 787.MPD.54-210-02 | 2026-10-16 | 2026-10-11 | 08:15:00 | 2026-10-11 | 08:15:00
574 | 70462433 | HS-TWA | 0016443002 |  | 2105149515 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | DET-THERMAL BLANKETS RIGHT STRUT | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-0-4 | 1 | DCA Appr. Req. 1 | INSP-W_ALL WING | BKK_H | DET | 787.MPD.54-215-02 | 2026-10-15 | 2026-10-11 | 08:15:00 | 2026-10-11 | 08:15:00
575 | 70462433 | HS-TWA | 0016443003 |  | 2105149516 | AC01 |  | 2026-10-06 | 11LHM/A | 0010 | DEFUELING FOR AIRPLANE FUEL TANKS | TECO | DPRC | H/26-TWA-X0C03-BLOK-I-N |  |  | IERA_WING | BKK_H | SVC | 787.OPR.DEFUELING | 2026-10-06 | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
576 | 70462433 | HS-TWA | 0016456945 | 1103182327 | 2105152584 | AC03 |  | 2026-10-18 | 11LHM/E | 0010 | 440206:CSS OPR S/W &HEALTH MANAGE DB CHG | TECO | DPRC | H/26-TWA-X0C03-MOD | 4 | TG Appr. Req. 4 | IERA_CABIN | BKK_H | MOD | 787.TO.TO.440206 | 2026-10-18 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
577 | 70462433 | HS-TWA | 0016481996 |  | 2105159485 | AC01 |  | 2026-10-14 | 11LQ/IC | 0010 | GVI CREW OXYGEN CYLINDERS MOUNT BRACKETS | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-3 | 2 | DCA Appr. Req. 2 | INSP-I_CABIN | BKK_H | DET | 787.MPD.35-023-00 | 2026-10-09 | 2026-10-10 | 16:30:00 | 2026-10-10 | 16:30:00
578 | 70462433 | HS-TWA | 0016498371 | 1103189850 | 2105163802 | AC02 |  | 2026-10-21 | 11LHM/C | 0010 | Operationally check the Inflatable Occup | TECO | DPRC | H/26-TWA-X0C03-NONR | 1 | DCA Appr. Req. 1 | CABIN_ALL CABIN | BKK_H | OPC | 787.MPD.25-166-00 | 2026-10-21 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
579 | 70462433 | HS-TWA | 0016556605 | 1103200685 | 2105178706 | AC02 |  | 2026-10-18 | 11LHM/A | 0010 | GVI - FWD CARGO COMPARTMENT AFT ENDWAL | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR | 4 | TG Appr. Req. 4 |  | BKK_H | GVI | 787.MPD.5011310001-TG01 | 2026-10-08 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
580 | 70462433 | HS-TWA | 0016566286 | 1103202601 | 2105181543 | AC02 |  | 2026-10-21 | 11LHM/E | 0010 | 4611070301-TG01 : EFB DATA UPDATE. | TECO | DPRC | H/26-TWA-X0C03-NONR | 4 | TG Appr. Req. 4 | IERA | BKK_H | SVC | 787.MPD.4611070301-TG01 | 2026-10-21 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
581 | 70462433 | HS-TWA | 0016569903 | 1103203618 | 2105182532 | AC02 |  | 2026-10-18 | 11LHM/E | 0010 | Download CPL data from A/C MSD to ML | TECO | DPRC | H/26-TWA-X0C03-NONR | 4 | TG Appr. Req. 4 | IERA_IERA | BKK_H | REP | 787.MPD.31-035-01-TG01 | 2026-10-18 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
582 | 70462433 | HS-TWA | 0016575312 | WA650B081026 | WA650B081026 | AC05 |  | 2026-10-14 | 11LHM/E | 0010 | 20: REFER ORDER NO.2105149233 (LEFT INBO | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-11 | 2026-10-08 | 09:23:00 | 2026-10-08 | 19:00:00
583 | 70462433 | HS-TWA | 0016575315 | WA651A081026 | WA651A081026 | AC05 |  | 2026-10-14 | 11LHM/E | 0010 | 20: REFER ORDER NO.2105149234 (LEFT OUTB | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-11 | 2026-10-08 | 10:02:00 | 2026-10-08 | 19:00:00
584 | 70462433 | HS-TWA | 0016575317 | WA652B081026 | WA652B081026 | AC05 |  | 2026-10-14 | 11LHM/E | 0010 | 20: REFER ORDER NO.2105149236 (LEFT WHEE | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-11 | 2026-10-08 | 10:40:00 | 2026-10-08 | 19:00:00
585 | 70462433 | HS-TWA | 0016575323 | WA653A081026 | WA653A081026 | AC05 |  | 2026-10-18 | 11CLEAN | 0010 | 12-SERVICING,LANDING GEAR CLEANING. | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-08 | 2026-10-08 | 10:58:00 | 2026-10-08 | 19:00:00
586 | 70462433 | HS-TWA | 0016575329 | WA654A081026 | WA654A081026 | AC05 |  | 2026-10-18 | 11CLEAN | 0010 | FWD.CARGO FIRE EXTINGUISHING BOTTLES ARO | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-09 | 2026-10-08 | 12:09:00 | 2026-10-09 | 19:00:00
587 | 70462433 | HS-TWA | 0016577186 | WA666B081026 | WA666B081026 | AC05 |  | 2026-10-18 | 11CLEAN | 0010 | 25: BOILER DIRTY ALL ZONE | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-14 | 2026-10-08 | 16:15:00 | 2026-10-09 | 19:00:00
588 | 70462433 | HS-TWA | 0016577191 | WA667B081026 | WA667B081026 | AC05 |  | 2026-10-15 | 11CLEAN | 0010 | 25: OVEN PAINT POOR CONDITION ALL ZONE | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-14 | 2026-10-08 | 16:39:00 | 2026-10-09 | 19:00:00
589 | 70462433 | HS-TWA | 0016577192 | WA667B081026 | WA667B081026 | AC05 |  | 2026-10-15 | 11PAINT | 0020 | 25: OVEN PAINT POOR CONDITION ALL ZONE | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-08 | 2026-10-08 | 16:39:00 | 2026-10-09 | 19:00:00
590 | 70462433 | HS-TWA | 0016578891 | WA676B091026 | WA676B091026 | AC05 |  | 2026-10-25 | 22YYG | 0010 | 25: INSPECTION FOUND CURTAIN OF OFCR AT | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-21 | 2026-10-09 | 12:26:00 | 2026-10-09 | 19:00:00
591 | 70462433 | HS-TWA | 0016579836 | WA686A101026 | WA686A101026 | AC05 |  | 2026-10-14 | 11CMPST | 0010 | 25:STOWAGE COMPARTMENTS | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-12 | 2026-10-05 | 00:00:00 | 2026-10-11 | 19:00:00
592 | 70462433 | HS-TWA | 0016581202 | WA696A111026 | WA696A111026 | AC05 |  | 2026-10-21 | 11CMPST | 0010 | AFT CARGO CELLING | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-14 | 2026-10-11 | 15:33:00 | 2026-10-14 | 16:00:00
593 | 70462433 | HS-TWA | 0016586236 | WA711A141026 | WA711A141026 | AC05 |  | 2026-10-14 | 11CA | 0010 | FLIGHT COMPARTMENT EQUIPMENT | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | 11CA | REP |  | 2026-10-14 | 2026-10-14 | 15:09:00 | 2026-10-18 | 16:00:00
594 | 70462433 | HS-TWA | 0016591391 | WA723A161026 | WA723A161026 | AC05 |  | 2026-10-18 | 11LHM/C | 0010 | 25:EQUIPMENT AND FURNISHINGS | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-16 | 2026-10-16 | 15:01:00 | 2026-10-17 | 19:00:00
595 | 70462433 | HS-TWA | 0016591915 | WA734A181026 | WA734A181026 | AC05 |  | 2026-10-21 | 11CMPST | 0010 | 25:EQUIPMENT AND FURNISHINGS | TECO |  | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-20 | 2026-10-18 | 13:23:00 | 2026-10-19 | 19:00:00
596 | 70462433 | HS-TWA | 0016595323 | WA748A191026 | WA748A191026 | AC05 |  | 2026-10-22 | 11PAINT | 0010 | AIR INLET SECTION | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | 11PAINT | REP |  | 2026-10-19 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
597 | 70462433 | HS-TWA | 0016595337 | WA750A191026 | WA750A191026 | AC05 |  | 2026-10-21 | 11PAINT | 0010 | 40-FLIGHT CONTROLS,HORRIZONTAL STABILIZE | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-21 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
598 | 70462433 | HS-TWA | 0015110196 | 1102953266 | 2104794597 | AC03 |  | 2026-10-18 | 11LHM/A | 0010 | 710342:LH/RH Nacelle Anti-ice Inspection | TECO | DPRC ODAT | H/26-TWA-X0C03-MOD -G-W | 0 | AD |  | BKK_H | SDI | 787.TO.710342 | 2026-10-15 | 2026-10-04 | 00:00:00 | 2026-10-16 | 24:00:00
599 | 70462433 | HS-TWA | 0015110197 | 1102953266 | 2104794597 | AC03 |  | 2026-10-18 | 11LHM/A | 0020 | 710342:LH/RH Nacelle Anti-ice Inspection | TECO | DPRC ODAT | H/26-TWA-X0C03-MOD -G-W | 0 | AD |  | BKK_H | SDI | 787.TO.710342 | 2026-10-15 | 2026-10-04 | 00:00:00 | 2026-10-16 | 24:00:00
600 | 70462433 | HS-TWA | 0016577178 | WA662B081026 | WA662B081026 | AC05 |  | 2026-10-15 | 11CMPST | 0010 | FWD GALLEY LAMINATE SKIN LH SIDE POOR | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-15 | 2026-10-08 | 16:17:00 | 2026-10-08 | 19:00:00
601 | 70462433 | HS-TWA | 0016298455 | 1103153493 | 2105105973 | AC02 |  | 2026-10-20 | 11LHM/E | 0010 | OPC P300 & P400 PANEL | TECO | DPRC | H/26-TWA-X0C03-NONR | 1 | DCA Appr. Req. 1 | INSP-I_CABIN | BKK_H | OPC | 787.MPD.24-065-00 | 2026-10-20 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
602 | 70462433 | HS-TWA | 0016442733 |  | 2105149268 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | LUB AFT CARGO DOOR | TECO |  | H/26-TWA-X0C03-BLOK-0-5 |  |  | FLOOR_AFT COMPT | BKK_H | LUB | 787.MPD.12-140-00 | 2026-10-11 | 2026-10-12 | 08:15:00 | 2026-10-12 | 08:15:00
603 | 70462433 | HS-TWA | 0016449279 | 1103180640 | 2105150876 | AC02 | EWIS | 2026-10-14 | 11LQ/IE | 0010 | Inspect (General Visual) wire bonding | TECO | DPRC | H/26-TWA-X0C03-NONR | 4 | TG Appr. Req. 4 | IERA_FLOOR | BKK_H | GVI | 787.MPD.20-200-29-TG01 | 2026-10-08 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
604 | 70462433 | HS-TWA | 0016442696 |  | 2105149232 | AC01 |  | 2026-10-18 | 11LHM/C | 0010 | OPC-EMERGENCY EVACUATION SIGNAL | TECO |  | H/26-TWA-X0C03-BLOK-0-8 |  |  | CABIN_ALL CABIN | BKK_H | OPC | 787.MPD.25-030-00 | 2026-10-10 | 2026-10-15 | 08:15:00 | 2026-10-15 | 08:15:00
605 | 70462433 | HS-TWA | 0016442730 |  | 2105149265 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | INSP (DETAILED) THRUST REVERSER BLOCK LH | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-3 | 2 | DCA Appr. Req. 2 | INSP-W_ENGINE | BKK_H | DET | 787.MPD.78-205-01 | 2026-10-17 | 2026-10-10 | 16:30:00 | 2026-10-10 | 16:30:00
606 | 70462433 | HS-TWA | 0016442742 |  | 2105149276 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | GVI THRUST REVERSER INNER V-BLADE ENG#1 | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-2 | 2 | DCA Appr. Req. 2 | INSP-W_ENGINE | BKK_H | GVI | 787.MPD.78-235-01 | 2026-10-11 | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
607 | 70462433 | HS-TWA | 0016442792 |  | 2105149320 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | GVI(INT) LE TO FRONT SPAR-INB NACELL,LHW | TECO |  | H/26-TWA-X0C03-BLOK-0-1 |  |  | WING_LEADING EDGE | BKK_H | GVI | 787.MPD.57-801-01 | 2026-10-11 | 2026-10-06 | 00:00:00 | 2026-10-06 | 00:00:00
608 | 70462433 | HS-TWA | 0016442805 |  | 2105149333 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | GVI(INT) LE TO FRONT SPAR-OUTB NACEL,RHW | TECO |  | H/26-TWA-X0C03-BLOK-0-1 |  |  | INSP-W_LEADING EDGE | BKK_H | GVI | 787.MPD.57-918-02 | 2026-10-10 | 2026-10-06 | 08:15:00 | 2026-10-06 | 08:15:00
609 | 70462433 | HS-TWA | 0016442830 |  | 2105149358 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | RHW-REM WING ACCESS PANEL_INTV 3Y | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-0-1 |  |  | WING_ALL WING | BKK_H | REM | 787.OPR.ACC Z611,621,640,650,661,672 | 2026-10-07 | 2026-10-06 | 00:00:00 | 2026-10-06 | 00:00:00
610 | 70462433 | HS-TWA | 0016442875 |  | 2105149403 | AC01 |  | 2026-10-18 | 11LQ/IA | 0010 | INSP HIGH FLOW SHUTOFF CHECK VALVE | TECO |  | H/26-TWA-X0C03-BLOK-0-3 |  |  | FLOOR_AIR COND | BKK_H | DET | 787.MPD.21-075-00 | 2026-10-12 | 2026-10-10 | 08:15:00 | 2026-10-10 | 08:15:00
611 | 70462433 | HS-TWA | 0016442876 |  | 2105149404 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | REM HIGH FLOW SHUTOFF VALVE | TECO | ODAT | H/26-TWA-X0C03-BLOK-I-N |  |  | FLOOR_AIR COND | BKK_H | REM | 787.MPD.21-075-00 | 2026-10-12 | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
612 | 70462433 | HS-TWA | 0016442878 |  | 2105149406 | AC01 |  | 2026-10-21 | 11LHM/A | 0010 | OPC PACK CONTROL UNITS | TECO | DPRC | H/26-TWA-X0C03-BLOK-I-N |  |  | FLOOR_AIR COND | BKK_H | OPC | 787.MPD.21-105-00 | 2026-10-18 | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
613 | 70462433 | HS-TWA | 0016442901 |  | 2105149429 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | CHECK AFT CARGO DOOR HYDRAULIC FLUID LV | TECO |  | H/26-TWA-X0C03-BLOK-0-8 | 2 | DCA Appr. Req. 2 | FLOOR_AFT COMPT | BKK_H | SVC | 787.MPD.52-140-00 | 2026-10-15 | 2026-10-15 | 08:15:00 | 2026-10-15 | 08:15:00
614 | 70462433 | HS-TWA | 0016442907 |  | 2105149435 | AC01 |  | 2026-10-08 | 11LQ/IA | 0010 | EXTERNAL-DET FWD CARGO DOOR | TECO |  | H/26-TWA-X0C03-BLOK-0-3 |  |  | INSP-F_FWD COMPT | BKK_H | DET | 787.MPD.52-504-00 | 2026-10-08 | 2026-10-10 | 16:30:00 | 2026-10-10 | 16:30:00
615 | 70462433 | HS-TWA | 0016442993 |  | 2105149507 | AC01 |  | 2026-10-09 | 11LHM/E | 0010 | Inspect (Detailed) the CURRENT RETURN NE | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-2 | 2 | DCA Appr. Req. 2 | IERA_FLOOR | BKK_H | DI | 787.MPD.20-200-24 | 2026-10-09 | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
616 | 70462433 | HS-TWA | 0016443149 |  | 2105149552 | AC01 |  | 2026-10-21 | 11LHM/A | 0010 | OPC ALTERNATE STABILIZER TRIM CONTROL SY | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-4 | 2 | DCA Appr. Req. 2 | IERA_WING | BKK_H | OPC | 787.MPD.27-270-00 | 2026-10-07 | 2026-10-11 | 08:15:00 | 2026-10-11 | 08:15:00
617 | 70462433 | HS-TWA | 0016558630 | 1103201144 | 2105179451 | AC02 |  | 2026-10-18 | 11LHM/E | 0010 | D/26-111:TERRAIN DATABASE UPDATE TO V654 | TECO | DPRC | H/26-TWA-X0C03-MOD | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 787.ED.JA-D/26-111 | 2026-10-18 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
618 | 70462433 | HS-TWA | 0016577185 | WA665A081026 | WA665A081026 | AC05 |  | 2026-10-12 | 11CMPST | 0010 | 50-CARGO,FWD AND AFT COMPT WALK WAY. | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-09 | 2026-10-08 | 16:32:00 | 2026-10-08 | 19:00:00
619 | 70462433 | HS-TWA | 0016577210 | WA670A081026 | WA670A081026 | AC05 |  | 2026-10-21 | 11PAINT | 0010 | 53-FUSELAGE,TAIL SECTION AND SPEED LINE | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-10 | 2026-10-08 | 17:40:00 | 2026-10-08 | 19:00:00
620 | 70462433 | HS-TWA | 0016577212 | WA671A081026 | WA671A081026 | AC05 |  | 2026-10-21 | 11PAINT | 0010 | FUSELAGE | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-14 | 2026-10-08 | 18:49:00 | 2026-10-14 | 16:00:00
621 | 70462433 | HS-TWA | 0016442687 |  | 2105149223 | AC01 |  | 2026-10-10 | 11LHM/C | 0010 | DRAIN/FLUSH-WASTE TANKS B787 | TECO |  | H/26-TWA-X0C03-BLOK-I-N |  |  | CABIN_LAVATORY | BKK_H | SVC | 787.OPR.DRAIN/FLUSH-WASTE TANKS | 2026-10-06 | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
622 | 70462433 | HS-TWA | 0016442759 |  | 2105149289 | AC01 |  | 2026-10-14 | 11LHM/C | 0010 | INST-PROTECTIVE COVERS ON ALL SEATS | TECO | DPRC | H/26-TWA-X0C03-BLOK-I-N |  |  | CABIN_INTERIOR | BKK_H | SVC | 787.OPR.PROTECTIVE COVERS SEATS | 2026-10-14 | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
623 | 70462433 | HS-TWA | 0016442978 |  | 2105149494 | AC01 |  | 2026-10-14 | 11LHM/A | 0010 | FUC SURGE TANK PRESSURE RELIEFE VALVE | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-4 | 1 | DCA Appr. Req. 1 | WING_FUEL | BKK_H | FUC | 787.MPD.28-005-00 | 2026-10-14 | 2026-10-11 | 08:15:00 | 2026-10-11 | 08:15:00
624 | 70462433 | HS-TWA | 0016442979 |  | 2105149494 | AC01 |  | 2026-10-14 | 11LHM/A | 0020 | FUC SURGE TANK PRESSURE RELIEFE VALVE | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-4 | 1 | DCA Appr. Req. 1 | WING_FUEL | BKK_H | FUC | 787.MPD.28-005-00 | 2026-10-14 | 2026-10-11 | 08:15:00 | 2026-10-11 | 08:15:00
625 | 70462433 | HS-TWA | 0016549088 | WA083C170926 | WA083C170926 | AC05 |  | 2026-10-18 | BKK_L | 0010 | 33 ONE WORK LT AT FWD GALLEY INOP | TECO | DPRC | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2026-10-18 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
626 | 70462433 | HS-TWA | 0016549090 | WA083C170926 | WA083C170926 | AC05 |  | 2026-10-18 | 11LHM/C | 0020 | 33 ONE WORK LT AT FWD GALLEY INOP | TECO | DPRC | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
627 | 70462433 | HS-TWA | 0016549089 | WA083C170926 | WA083C170926 | AC05 |  | 2026-10-18 | BKK_L | 0020 | 33 ONE WORK LT AT FWD GALLEY INOP | TECO | DPRC | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2026-10-18 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
628 | 70462433 | HS-TWA | 0016574026 | WA642A071026 | WA642A071026 | AC05 |  | 2026-10-21 | 11CMPST | 0010 | CARGO DOOR | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-07 | 2026-10-07 | 14:47:00 | 2026-10-14 | 16:00:00
629 | 70462433 | HS-TWA | 0016577914 | WA673B091026 | WA673B091026 | AC05 |  | 2026-10-14 | 11LHM/C | 0010 | 25: REFER ORDER NO.2105149308 INSPECTION | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-11 | 2026-10-05 | 00:00:00 | 2026-10-09 | 19:00:00
630 | 70462433 | HS-TWA | 0015021436 | 1102938874 | 2104773135 | AC03 |  | 2026-10-18 | 11LHM/A | 0010 | 531538:Tail Strike Protection System | TECO | DPRC ODAT | H/26-TWA-X0C03-MOD -G-F | 2 | DCA Appr. Req. 2 |  | BKK_H | MOD | 787.TO.MTO-531538-01 | 2026-10-11 | 2026-10-04 | 00:00:00 | 2026-10-16 | 24:00:00
631 | 70462433 | HS-TWA | 0016281787 | 1103150115 | 2105101909 | AC02 |  | 2026-10-14 | 11LHM/C | 0010 | G/26-009:EMERG EQUIPMENT RFID REGISTRATI | TECO | DPRC | H/26-TWA-X0C03-MOD | 4 | TG Appr. Req. 4 | CABIN_ALL CABIN | BKK_H | RAR | 787.ED.BKKJA-G/26-009 | 2026-09-15 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
632 | 70462433 | HS-TWA | 0016442684 |  | 2105149220 | AC01 |  | 2026-10-21 | 11LHM/E | 0010 | REMV-PROTECTIVE COVER FROM COMPONENTS | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-7 |  |  | IERA_FLOOR | BKK_H | SVC | 787.OPR.REMV-PROTECTIVE COVER | 2026-10-21 | 2026-10-14 | 08:15:00 | 2026-10-14 | 08:15:00
633 | 70462433 | HS-TWA | 0016442746 |  | 2105149279 | AC01 |  | 2026-10-06 | 11LHM/C | 0010 | REMV-LIFE VESTS AND FLASHLIGHTS | TECO | DPRC | H/26-TWA-X0C03-BLOK-I-N |  |  | CABIN_INTERIOR | BKK_H | REM | 787.OPR.REMV-LIFE,VESTS,FLASHLIGHTS | 2026-10-06 | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
634 | 70462433 | HS-TWA | 0016442769 |  | 2105149298 | AC01 |  | 2026-10-10 | 11LHM/E | 0010 | OPC EMERGENCY LIGHTING SYSTEM | TECO |  | H/26-TWA-X0C03-BLOK-I-N | 1 | DCA Appr. Req. 1 | IERA_CABIN | BKK_H | OPC | 787.MPD.33-025-00 | 2026-10-06 | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
635 | 70462433 | HS-TWA | 0016442828 |  | 2105149356 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | LHW-REM WING ACCESS PANEL_INTV 3Y | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-0-1 |  |  | WING_ALL WING | BKK_H | REM | 787.OPR.ACC Z511,521,540,550,561,572 | 2026-10-07 | 2026-10-06 | 00:00:00 | 2026-10-06 | 00:00:00
636 | 70462433 | HS-TWA | 0016442900 |  | 2105149428 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | CHECK FWD CARGO DOOR HYDRAULIC FLUID LV | TECO |  | H/26-TWA-X0C03-BLOK-0-8 | 2 | DCA Appr. Req. 2 | FLOOR_FWD COMPT | BKK_H | SVC | 787.MPD.52-140-00 | 2026-10-15 | 2026-10-15 | 08:15:00 | 2026-10-15 | 08:15:00
637 | 70462433 | HS-TWA | 0016442935 |  | 2105149463 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | INSP-RH CAC INLET DUCT AND CHK VALVES | TECO |  | H/26-TWA-X0C03-BLOK-0-2 | 2 | DCA Appr. Req. 2 | FLOOR_AIR COND | BKK_H | DVI | 787.MPD.21-067-00 | 2026-10-13 | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
638 | 70462433 | HS-TWA | 0016442936 |  | 2105149464 | AC01 |  | 2026-10-18 | 11LHM/A | 0010 | LUB-BULK CARGO DOOR LATCH MECH | TECO |  | H/26-TWA-X0C03-BLOK-0-5 | 2 | DCA Appr. Req. 2 | FLOOR_AFT COMPT | BKK_H | LUB | 787.MPD.12-180-00 | 2026-10-11 | 2026-10-12 | 08:15:00 | 2026-10-12 | 08:15:00
639 | 70462433 | HS-TWA | 0016442976 |  | 2105149492 | AC01 |  | 2026-10-20 | 11LHM/A | 0010 | VIC(CONTROL COLUMN, PEDAL, WHEEL) DAMPER | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-4 |  |  | FLOOR_FUSELAGE | BKK_H | VIC | 787.MPD.27-120-00 | 2026-10-21 | 2026-10-11 | 08:15:00 | 2026-10-11 | 08:15:00
640 | 70462433 | HS-TWA | 0016442980 |  | 2105149495 | AC01 |  | 2026-10-14 | 11LHM/A | 0010 | OPC-L CTR R TANK FUEL VENT FLOAT VALVE | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-4 | 2 | DCA Appr. Req. 2 | WING_FUEL | BKK_H | OPC | 787.MPD.28-015-00 | 2026-10-14 | 2026-10-11 | 08:15:00 | 2026-10-11 | 08:15:00
641 | 70462433 | HS-TWA | 0016450067 | 1103180893 | 2105151176 | AC02 |  | 2026-10-06 | 11LHM/C | 0010 | INSPECTION THE EXPIRED DATE OF UPK | TECO | DPRC | H/26-TWA-X0C03-NONR | 4 | TG Appr. Req. 4 | CABIN_INTERIOR | BKK_H | REP | 787.MPD.2565000001-TG01 | 2026-10-06 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
642 | 70462433 | HS-TWA | 0016386628 | WA068C170626 | WA068C170626 | AC05 |  | 2026-10-21 | BKK_L | 0010 | 25 LAMINATE ON TOP OF COUNTER IN FRONT O | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2026-06-17 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
643 | 70462433 | HS-TWA | 0016386630 | WA068C170626 | WA068C170626 | AC05 |  | 2026-10-21 | 11CMPST | 0020 | 25 LAMINATE ON TOP OF COUNTER IN FRONT O | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
644 | 70462433 | HS-TWA | 0016386629 | WA068C170626 | WA068C170626 | AC05 |  | 2026-10-21 | BKK_L | 0020 | 25 LAMINATE ON TOP OF COUNTER IN FRONT O | TECO |  | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2026-10-16 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
645 | 70462433 | HS-TWA | 0016573559 | WA636A061026 | WA636A061026 | AC05 |  | 2026-10-18 | 11LHM/E | 0010 | 44 INFLIGHT ENTERTAINMENT : FOUND MONITO | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-13 | 2026-10-06 | 17:52:00 | 2026-10-07 | 18:59:00
646 | 70462433 | HS-TWA | 0016573573 | WA640A071026 | WA640A071026 | AC05 |  | 2026-10-07 | 11LHM/E | 0010 | 25: INSPECTION OF THE EMERGENCY LIGHT FO | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-07 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
647 | 70462433 | HS-TWA | 0016575367 | WA659A081026 | WA659A081026 | AC05 |  | 2026-10-14 | 11CLEAN | 0010 | FWD.CARGO COMPARTMENT INNER LH/RH SIDE W | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-15 | 2026-10-08 | 15:36:00 | 2026-10-09 | 19:00:00
648 | 70462433 | HS-TWA | 0016579797 | WA679B091026 | WA679B091026 | AC05 |  | 2026-10-14 | 11LHM/C | 0010 | 25: INSPECTION FOUND PASSENGER SEAT ARMR | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-11 | 2026-10-09 | 15:21:00 | 2026-10-09 | 19:00:00
649 | 70462433 | HS-TWA | 0016579802 | WA680B091026 | WA680B091026 | AC05 |  | 2026-10-14 | 11LHM/C | 0010 | 25: INSPECTION FOUND PASSENGER SEAT OCCU | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-11 | 2026-10-09 | 16:04:00 | 2026-10-09 | 19:00:00
650 | 70462433 | HS-TWA | 0016581062 | WA692B111026 | WA692B111026 | AC05 |  | 2026-10-14 | 11LHM/C | 0010 | 25: INSPECTION FOUND ESCUTCHEON SOME SEA | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-11 | 2026-10-11 | 09:48:00 | 2026-10-11 | 19:00:00
651 | 70462433 | HS-TWA | 0016583991 | WA698B131026 | WA698B131026 | AC05 |  | 2026-10-18 | 11LHM/E | 0010 | 25: INSPECTION FOUND THE MONITORS LOOSEO | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-15 | 2026-10-13 | 07:03:00 | 2026-10-13 | 19:00:00
652 | 70462433 | HS-TWA | 0016586119 | WA698B131026 | WA698B131026 | AC05 |  | 2026-10-18 | 11SH | 0020 | 25: INSPECTION FOUND THE MONITORS LOOSEO | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-14 | 2026-10-13 | 07:03:00 | 2026-10-13 | 19:00:00
653 | 70462433 | HS-TWA | 0016583994 | WA699B131026 | WA699B131026 | AC05 |  | 2026-10-18 | 11LHM/E | 0010 | 25: INSPECTION FOUND THE MONITORS LOOSEO | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-15 | 2026-10-13 | 08:51:00 | 2026-10-13 | 19:00:00
654 | 70462433 | HS-TWA | 0016586118 | WA699B131026 | WA699B131026 | AC05 |  | 2026-10-18 | 11SH | 0020 | 25: INSPECTION FOUND THE MONITORS LOOSEO | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-14 | 2026-10-13 | 08:51:00 | 2026-10-13 | 19:00:00
655 | 70462433 | HS-TWA | 0016583995 | WA700B131026 | WA700B131026 | AC05 |  | 2026-10-18 | 11LHM/E | 0010 | 25: INSPECTION FOUND THE MONITORS LOOSEO | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-15 | 2026-10-13 | 09:07:00 | 2026-10-13 | 19:00:00
656 | 70462433 | HS-TWA | 0016586117 | WA700B131026 | WA700B131026 | AC05 |  | 2026-10-18 | 11SH | 0020 | 25: INSPECTION FOUND THE MONITORS LOOSEO | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-14 | 2026-10-13 | 09:07:00 | 2026-10-13 | 19:00:00
657 | 70462433 | HS-TWA | 0016583996 | WA701B131026 | WA701B131026 | AC05 |  | 2026-10-18 | 11LHM/E | 0010 | 24: CIRCUIT BREAKER OF CONTROL ASSY-ELEC | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-12 | 2026-10-13 | 09:11:00 | 2026-10-13 | 19:00:00
658 | 70462433 | HS-TWA | 0016584027 | WA704A131026 | WA704A131026 | AC05 |  | 2026-10-18 | 11SH | 0010 | 25:EQUIPMENT AND FURNISHINGS | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-15 | 2026-10-13 | 16:34:00 | 2026-10-14 | 19:00:00
659 | 70462433 | HS-TWA | 0016585002 | WA709A141026 | WA709A141026 | AC05 |  | 2026-10-18 | 11LHM/A | 0010 | FIXED TRAILING EDGE | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-14 | 2026-10-14 | 10:22:00 | 2026-10-17 | 16:00:00
660 | 70462433 | HS-TWA | 0016591911 | WA731A181026 | WA731A181026 | AC05 |  | 2026-10-18 | 11LHM/E | 0010 | 44: SEAT 62E MOUNT MONITOR RH SIDE MISSI | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-18 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
661 | 70462433 | HS-TWA | 0016591917 | WA736A181026 | WA736A181026 | AC05 |  | 2026-10-21 | 11CMPST | 0010 | 25:EQUIPMENT AND FURNISHINGS | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-19 | 2026-10-18 | 14:46:00 | 2026-10-19 | 19:00:00
662 | 70462433 | HS-TWA | 0016598718 | WA752B201026 | WA752B201026 | AC05 |  | 2026-10-21 | 11LHM/E | 0010 | 25: WAC FOUND THE GROMMETS OF VIDEO ARM | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-21 | 2026-10-20 | 14:44:00 | 2026-10-20 | 19:00:00
663 | 70462433 | HS-TWA | 0016442996 |  | 2105149509 | AC01 |  | 2026-10-15 | 11SH-LQ | 0010 | DVI TR TRANS SLEEVE-ACOUSTIC PANEL ENG1 | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-2 | 4 | TG Appr. Req. 4 | WING_ENGINE | BKK_H | INS | 787.MPD.7831010001-TG01 | 2026-10-18 | 2026-10-08 | 08:15:00 | 2026-10-08 | 08:15:00
664 | 70462433 | HS-TWA | 0016442692 |  | 2105149228 | AC01 |  | 2026-10-10 | 11LHM/A | 0010 | FUC THE NOSE LANDING GEAR | TECO |  | H/26-TWA-X0C03-BLOK-I-N | 2 | DCA Appr. Req. 2 | FLOOR_LANDING GEAR | BKK_H | FNC | 787.MPD.32-070-00 | 2026-10-07 | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
665 | 70462433 | HS-TWA | 0016570865 | WA009F051026 | WA009F051026 | AC05 |  | 2026-10-21 | BKK_L | 0010 | WHEEL 4 BRAKE - WIRE HARNESS ASSY | TECO | NOGO | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-19 | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
666 | 70462433 | HS-TWA | 0016570866 | WA010F051026 | WA010F051026 | AC05 |  | 2026-10-21 | BKK_L | 0010 | EICAS STATUS MSG "BRAKE CABLE 1 ACTUATOR | TECO | NOGO | H/26-TWA-X0C03-NONR |  |  |  | BKK_L | REP |  | 2026-10-19 | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
667 | 70462433 | HS-TWA | 0016582480 | WA014F091026 | WA014F091026 | AC05 |  | 2026-10-21 | BKK_H | 0010 | 33 : SEAT 39D OVERHEAD EMER LT WELS BATT | TECO |  | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-17 | 2026-10-09 | 00:00:00 | 2026-10-09 | 00:00:00
668 | 70462433 | HS-TWA | 0016579830 | WA683B101026 | WA683B101026 | AC05 |  | 2026-10-18 | 11LHM/C | 0010 | 11: SEAT ROLL MARKER ON 15A DAMAGED. | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2026-10-17 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
669 | 70462433 | HS-TWA | 0016442739 |  | 2105149274 | AC01 |  | 2026-10-10 | 11LHM/C | 0010 | DRAIN-POTABLE WATER SYSTEM | TECO |  | H/26-TWA-X0C03-BLOK-I-N |  |  | CABIN_GALLEY | BKK_H | SVC | 787.OPR.DRAIN-POTABLE WATER | 2026-10-07 | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
670 | 70462433 | HS-TWA | 0016442929 |  | 2105149457 | AC01 |  | 2026-10-20 | 11LHM/E | 0010 | FUC LH Main LDG Lightning/HIRF Protectio | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-8 | 2 | DCA Appr. Req. 2 | IERA_FLOOR | BKK_H | FUC | 787.MPD.20-380-19 | 2026-10-20 | 2026-10-15 | 08:15:00 | 2026-10-15 | 08:15:00
671 | 70462433 | HS-TWA | 0016442937 |  | 2105149465 | AC01 |  | 2026-10-25 | 11LHM/A | 0010 | OPC FUEL JETTISON SYSTEM | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-8 |  |  | WING_FUEL | BKK_H | FUC | 787.MPD.28-050-00 | 2026-10-21 | 2026-10-15 | 08:15:00 | 2026-10-15 | 08:15:00
672 | 70462433 | HS-TWA | 0016499113 | 1103189995 | 2105163923 | AC02 |  | 2026-10-20 | 11LHM/A | 0010 | REM A10:FUCAIRCONDPACKHEATEXCHANGERASSY | TECO | DPRC | H/26-TWA-X0C03-NONR | 3 | TG Appr. Req. 3 | FLOOR_AIR COND | BKK_H | REP | 787.MPD.21-069-00 | 2026-10-21 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
673 | 70462433 | HS-TWA | 0016532480 | 1103195767 | 2105172450 | AC02 |  | 2026-10-18 | 11LHM/E | 0010 | D/26-104:HYBRID AIRLINE CERT OAS AMI | TECO | DPRC ODAT | H/26-TWA-X0C03-MOD | 4 | TG Appr. Req. 4 | TG_E | BKK_H | REP | 787.ED.JA-D/26-104 | 2026-10-14 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
674 | 70462433 | HS-TWA | 0016148179 | 1103126787 | 2105063786 | AC02 |  | 2026-10-18 | 11LHM/A | 0010 | E/26-015:REPL SLAT GRA & PGA | TECO | DPRC ODAT | H/26-TWA-X0C03-MOD -G-W | 1 | DCA Appr. Req. 1 | WING_LEADING EDGE | BKK_H | REP | 787.ED.JA-E/26-015 | 2026-10-10 | 2026-10-04 | 00:00:00 | 2026-10-16 | 24:00:00
675 | 70462433 | HS-TWA | 0016442691 |  | 2105149227 | AC01 |  | 2026-10-09 | 11LHM/A | 0010 | FUC THE MAIN LANDING GEAR | TECO | DPRC | H/26-TWA-X0C03-BLOK-I-N | 2 | DCA Appr. Req. 2 | FLOOR_LANDING GEAR | BKK_H | FNC | 787.MPD.32-020-00 | 2026-10-07 | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
676 | 70462433 | HS-TWA | 0016442923 |  | 2105149451 | AC01 |  | 2026-10-21 | 11LHM/C | 0010 | REPLACED ALL PASSENGER SEAT COVERS | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-0-1 |  |  | CABIN_INTERIOR | BKK_H | INS | 787.MPD.2525000002-TG01 | 2026-10-06 | 2026-10-06 | 00:00:00 | 2026-10-06 | 00:00:00
677 | 70462433 | HS-TWA | 0016582481 | WA015F091026 | WA015F091026 | AC05 |  | 2026-10-21 | BKK_H | 0010 | 33 : SEAT 51D WELS BATT REMOVED TO HS-TQ | TECO |  | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-17 | 2026-10-09 | 00:00:00 | 2026-10-09 | 00:00:00
678 | 70462433 | HS-TWA | 0016582482 | WA016F091026 | WA016F091026 | AC05 |  | 2026-10-18 | BKK_H | 0010 | 23 : EICAS STATUS MSG "TCP LH" DISPLAYED | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-17 | 2026-10-09 | 00:00:00 | 2026-10-09 | 00:00:00
679 | 70462433 | HS-TWA | 0016568824 | WA136F021026 | WA136F021026 | AC05 |  | 2026-10-18 | PER | 0010 | 32 BRAKE ''OFF'' STATUS LIGHT ON NOSE GE | TECO | DPRC | H/26-TWA-X0C03-NONR | C | Category C |  | BKK_H | REP |  | 2026-10-17 | 2026-10-05 | 00:00:00 | 2026-10-23 | 24:00:00
680 | 70462433 | HS-TWA | 0016568825 | WA136F021026 | WA136F021026 | AC05 |  | 2026-10-18 | BKK_H | 0020 | 32 BRAKE ''OFF'' STATUS LIGHT ON NOSE GE | TECO | DPRC | H/26-TWA-X0C03-NONR | C | Category C |  | BKK_H | REP |  | 2026-10-17 | 2026-10-05 | 00:00:00 | 2026-10-23 | 24:00:00
681 | 70462433 | HS-TWA | 0016579829 | WA682B101026 | WA682B101026 | AC05 |  | 2026-10-14 | 11LHM/C | 0010 | 11: SEAT ROLL MARKER ON 43ABC DAMAGED. | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-11 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
682 | 70462433 | HS-TWA | 0016591910 | WA730A181026 | WA730A181026 | AC05 |  | 2026-10-21 | 11LHM/A | 0010 | 50-CARGO,PDU INOP. | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-21 | 2026-10-18 | 06:51:00 | 2026-10-18 | 19:00:00
683 | 70462433 | HS-TWA | 0016442737 |  | 2105149272 | AC01 |  | 2026-10-17 | 11LHM/A | 0010 | OPC THRUST REVERSER BY TRANSLATION ENG#1 | TECO |  | H/26-TWA-X0C03-BLOK-0-8 | 2 | DCA Appr. Req. 2 | WING_ENGINE | BKK_H | OPC | 787.MPD.78-220-01 | 2026-10-17 | 2026-10-15 | 08:15:00 | 2026-10-15 | 08:15:00
684 | 70462433 | HS-TWA | 0016442748 |  | 2105149281 | AC01 |  | 2026-10-10 | 11LHM/A | 0010 | OPEN-LDG DOORS AND INSTALL LOCKS | TECO |  | H/26-TWA-X0C03-BLOK-I-N |  |  | FLOOR_LANDING GEAR | BKK_H | SVC | 787.OPR.OPEN-LDG DRS INSTALL LOCK | 2026-10-07 | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
685 | 70462433 | HS-TWA | 0016442751 |  | 2105149283 | AC01 |  | 2026-10-20 | 11LHM/E | 0010 | Functionally check the Main and APU Batt | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-7 | 2 | DCA Appr. Req. 2 | IERA_CABIN | BKK_H | FUC | 787.MPD.24-014-00 | 2026-10-07 | 2026-10-14 | 08:15:00 | 2026-10-14 | 08:15:00
686 | 70462433 | HS-TWA | 0016442752 |  | 2105149283 | AC01 |  | 2026-10-20 | 11LHM/E | 0020 | Functionally check the Main and APU Batt | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-7 | 2 | DCA Appr. Req. 2 | IERA_CABIN | BKK_H | FUC | 787.MPD.24-014-00 | 2026-10-21 | 2026-10-14 | 08:15:00 | 2026-10-14 | 08:15:00
687 | 70462433 | HS-TWA | 0016442762 |  | 2105149292 | AC01 |  | 2026-10-20 | 11LHM/E | 0010 | OPC of the ENGINE FIRE SWI | TECO | REMN | H/26-TWA-X0C03-BLOK-I-N | 1 | DCA Appr. Req. 1 | IERA_CABIN | BKK_H | OPC | 787.MPD.26-100-00 | 2026-10-06 | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
688 | 70462433 | HS-TWA | 0016442845 |  | 2105149373 | AC01 |  | 2026-10-18 | 11LHM/E | 0010 | FUC CABIN SPEAKERS for volume and ensure | TECO |  | H/26-TWA-X0C03-BLOK-0-8 | 2 | DCA Appr. Req. 2 | IERA_CABIN | BKK_H | FUC | 787.MPD.44-005-00 | 2026-10-10 | 2026-10-15 | 08:15:00 | 2026-10-15 | 08:15:00
689 | 70462433 | HS-TWA | 0016442933 |  | 2105149461 | AC01 |  | 2026-10-20 | 11LHM/E | 0010 | FUC RH Main LDG Lightning/HIRF Protectio | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-8 | 2 | DCA Appr. Req. 2 | IERA_FLOOR | BKK_H | FUC | 787.MPD.20-380-19 | 2026-10-20 | 2026-10-15 | 08:15:00 | 2026-10-15 | 08:15:00
690 | 70462433 | HS-TWA | 0016442961 |  | 2105149480 | AC01 |  | 2026-10-20 | 11LHM/A | 0010 | FUC-COLUMN TORQUE TUBE/CTL WHEEL ROTARY | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-8 |  |  | FLOOR_FWD COMPT | BKK_H | FNC | 787.MPD.27-070-00, 27-CMR-11 | 2026-10-21 | 2026-10-15 | 08:15:00 | 2026-10-15 | 08:15:00
691 | 70462433 | HS-TWA | 0016442962 |  | 2105149480 | AC01 |  | 2026-10-20 | 11LHM/A | 0020 | FUC-COLUMN TORQUE TUBE/CTL WHEEL ROTARY | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-8 |  |  | FLOOR_FWD COMPT | BKK_H | FNC | 787.MPD.27-070-00, 27-CMR-11 | 2026-10-21 | 2026-10-15 | 08:15:00 | 2026-10-15 | 08:15:00
692 | 70462433 | HS-TWA | 0016442964 |  | 2105149482 | AC01 |  | 2026-10-10 | 11LHM/A | 0010 | INST LWR RECIRCULAT FAN CHK VALVAL LH | TECO |  | H/26-TWA-X0C03-BLOK-0-5 | 1 | DCA Appr. Req. 1 | FLOOR_AIR COND | BKK_H | RES | 787.MPD.21-015-00 | 2026-10-21 | 2026-10-12 | 08:15:00 | 2026-10-12 | 08:15:00
693 | 70462433 | HS-TWA | 0016442966 |  | 2105149484 | AC01 |  | 2026-10-10 | 11LHM/A | 0010 | INST LWR RECIRCULAT FAN CHK VALVAL RH | TECO |  | H/26-TWA-X0C03-BLOK-0-5 | 1 | DCA Appr. Req. 1 | FLOOR_AIR COND | BKK_H | RES | 787.MPD.21-015-00 | 2026-10-21 | 2026-10-12 | 08:15:00 | 2026-10-12 | 08:15:00
694 | 70462433 | HS-TWA | 0016442967 |  | 2105149485 | AC01 |  | 2026-10-20 | 11LHM/A | 0010 | FUC - POSITIVE PRESSURE RELIEF VALVES | TECO | DPRC | H/26-TWA-X0C03-BLOK-0-8 | 2 | DCA Appr. Req. 2 | FLOOR_FWD COMPT | BKK_H | FNC | 787.MPD.21-060-00 | 2026-10-21 | 2026-10-15 | 08:15:00 | 2026-10-15 | 08:15:00
695 | 70462433 | HS-TWA | 0016442992 |  | 2105149506 | AC01 |  | 2026-10-18 | 11LHM/E | 0010 | FUC CURRENT RETURN NETWORK (CRN) BONDING | TECO | DPRC ODAT | H/26-TWA-X0C03-BLOK-0-6 | 2 | DCA Appr. Req. 2 | IERA_FLOOR | BKK_H | FUC | 787.MPD.20-200-23 | 2026-10-10 | 2026-10-13 | 08:15:00 | 2026-10-13 | 08:15:00
696 | 70462433 | HS-TWA | 0016524800 | 1103194218 | 2105170907 | AC02 |  | 2026-10-14 | 11LHM/C | 0010 | CHECK EXPIRATION DATE OF EQUIPMENT B787 | TECO | DPRC | H/26-TWA-X0C03-NONR | 1 | DCA Appr. Req. 1 | CABIN_INTERIOR | BKK_H | REP | 787.MPD.25-047-00-001-TG01 | 2026-10-09 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
697 | 70462433 | HS-TWA | 0016524801 | 1103194218 | 2105170907 | AC02 |  | 2026-10-14 | 11LHM/C | 0020 | CHECK EXPIRATION DATE OF EQUIPMENT B787 | TECO | DPRC | H/26-TWA-X0C03-NONR | 1 | DCA Appr. Req. 1 | CABIN_INTERIOR | BKK_H | REP | 787.MPD.25-047-00-001-TG01 | 2026-10-14 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
698 | 70462433 | HS-TWA-72-00-0001-ENG2 | 0016539024 | 1103197110 | 2105174382 | AC02 | SCT | 2026-10-18 | 11LHM/A | 0010 | TRENT1000 ENG PACK-C FUEL PUMP REPL | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR | 0 | AD |  | BKK_H |  | 787.MPD.73-230-01,73-230-02 | 2026-10-01 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
699 | 70462433 | HS-TWA-72-00-0001-ENG2 | 0016539025 | 1103197110 | 2105174382 | AC02 | SCT | 2026-10-18 | 11LHM/A | 0020 | TRENT1000 ENG PACK-C FUEL PUMP REPL | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR | 0 | AD |  | BKK_H |  | 787.MPD.73-230-01,73-230-02 | 2026-10-01 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
700 | 70462433 | HS-TWA | 0016044109 | WA001C201125 | WA001C201125 | AC05 |  | 2026-10-18 | PER | 0010 | 25 WINDOW SHADE FROM 54K-61K NOT DIMMABL | TECO | DPRC | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2026-10-13 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
701 | 70462433 | HS-TWA | 0016044110 | WA001C201125 | WA001C201125 | AC05 |  | 2026-10-18 | BKK_H | 0020 | 25 WINDOW SHADE FROM 54K-61K NOT DIMMABL | TECO | DPRC | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2026-10-13 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
702 | 70462433 | HS-TWA | 0016573989 | WA011F061026 | WA011F061026 | AC05 |  | 2026-10-21 | BKK_L | 0010 | 32 WIRE HARNESS BRAKE NO.6 REMVED FOR HS | TECO |  | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-19 | 2026-10-06 | 00:00:00 | 2026-10-06 | 00:00:00
703 | 70462433 | HS-TWA | 0016341997 | WA618B220526 | WA618B220526 | AC05 |  | 2026-10-25 | 11LHM/E | 0010 | 27:FLIGHT CONTROLS / TWB | TECO | DPRC | H/26-TWA-X0C03-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2026-10-21 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
704 | 70462433 | HS-TWA | 0016578972 | WA678A091026 | WA678A091026 | AC05 |  | 2026-10-18 | 11LHM/A | 0010 | 32-LANDING GEAR,TIRE NO.3,4,5,6,7,8. | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-10 | 2026-10-09 | 15:20:00 | 2026-10-09 | 19:00:00
705 | 70462433 | HS-TWA | 0016579789 | WA678A091026 | WA678A091026 | AC05 |  | 2026-10-18 | 11LHM/A | 0020 | 32-LANDING GEAR,TIRE NO.3,4,5,6,7,8. | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-10 | 2026-10-09 | 15:20:00 | 2026-10-09 | 19:00:00
706 | 70462433 | HS-TWA | 0016579790 | WA678A091026 | WA678A091026 | AC05 |  | 2026-10-18 | 11LHM/A | 0030 | 32-LANDING GEAR,TIRE NO.3,4,5,6,7,8. | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-10 | 2026-10-09 | 15:20:00 | 2026-10-09 | 19:00:00
707 | 70462433 | HS-TWA | 0016579791 | WA678A091026 | WA678A091026 | AC05 |  | 2026-10-18 | 11LHM/A | 0040 | 32-LANDING GEAR,TIRE NO.3,4,5,6,7,8. | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-10 | 2026-10-09 | 15:20:00 | 2026-10-09 | 19:00:00
708 | 70462433 | HS-TWA | 0016579792 | WA678A091026 | WA678A091026 | AC05 |  | 2026-10-18 | 11LHM/A | 0050 | 32-LANDING GEAR,TIRE NO.3,4,5,6,7,8. | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-10 | 2026-10-09 | 15:20:00 | 2026-10-09 | 19:00:00
709 | 70462433 | HS-TWA | 0016579793 | WA678A091026 | WA678A091026 | AC05 |  | 2026-10-18 | 11LHM/A | 0060 | 32-LANDING GEAR,TIRE NO.3,4,5,6,7,8. | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-10 | 2026-10-09 | 15:20:00 | 2026-10-09 | 19:00:00
710 | 70462433 | HS-TWA | 0016579806 | WA681B091026 | WA681B091026 | AC05 |  | 2026-10-14 | 11LHM/C | 0010 | 11:SEAT ROLL MARKER ON 31HJK MISSING. | TECO | DPRC | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-11 | 2026-10-09 | 16:14:00 | 2026-10-09 | 19:00:00
711 | 70462433 | HS-TWA | 0016586241 | WA712A141026 | WA712A141026 | AC05 |  | 2026-10-18 | 11LHM/E | 0010 | 56 : SEAT 40A DIMMABLE WINDOW CONTROLLER | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-14 | 2026-10-14 | 15:58:00 | 2026-10-15 | 18:59:00
712 | 70462433 | HS-TWA | 0016591914 | WA733A181026 | WA733A181026 | AC05 |  | 2026-10-18 | 11LHM/E | 0010 | 44: SEAT 42HJK PED INOP REPLACE SEAT POW | TECO | DPRC ODAT | H/26-TWA-X0C03-NONR |  |  |  | BKK_H | REP |  | 2026-10-18 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00
713 | 70462433 | HS-TWA | 0016591960 | WA745A191026 | WA745A191026 | AC05 |  | 2026-10-20 | 11CARPET | 0010 | FLOOR COVERING | TECO |  | H/26-TWA-X0C03-NONR |  |  |  | 11CARPET | REP |  | 2026-10-19 | 2026-10-05 | 00:00:00 | 2026-10-19 | 24:00:00

## TEXT TWA
####### HS-TWA: C3(9Y)+MOD ######
EST. TAT 15 DAYS // PERIOD 06OCT– 20OCT2026 REV.70462433
TOW IN : 06OCT26 TIME XXXX AM ,LAST FLIGHT 06 OCT. 2026 TGXXX
AIRCRAFT SERIAL NUMBER HS-TWA / 38777 , AIRCRAFT EFFECTIVITY CODE 124 TWA
########## WORK HIGHLIGHT 21 Oct. 2026 ##########
COMPLETE RTS
TG0662_20261022_173000_BKK>PVG
TG0663_20261022_233000_PVG>BKK
######### HS-TWA PLAN TIME LINE ACTIVITY AS BELOW ##########
06OCT26 : PARK 122
06OCT26 : TOW IN HANGAR 3 AFTER TIME 1800 PM
06OCT26 : AIRCRAFT IN → TOW/DOCK → GROUNDING/SAFETY → DEACTIVATE → OPEN ACCESS / REMOVE / PRESERVE
07-09OCT26 : GVI / DVI / DI / DET → NDT / SDI ตามพื้นที่ที่เปิดและพร้อม
10-14OCT26 : INSPECTION ต่อเนื่อง → RECTIFICATION / REPAIR / REPLACE / MOD → RE-INSPECTION
15-16OCT26 : INSTALL / RESTORE → SVC / LUB → CABIN / EQUIPMENT CONFIGURATION → CLOSE-UP ตามพื้นที่ที่ CLEAR
17OCT26 : FUEL / FLUID CONDITION → INVENTORY → REMOVE TOOLS/TRASH → DRY AIRCRAFT → CONFIGURE CONTROLS/TIRES → AIRCRAFT WEIGHING → W&B / CG CALCULATION → REPORT
18-20OCT26 : DE-PRESERVE → ACTIVATE → OPC / FUC / FNC → ENGINE RUN-UP → FLUID / LEAK CHECK → CLEAR TEST FINDINGS
21OCT26 : FINAL OPC / FLIGHT CONTROL→ CLEAR REMAIN / REPORTS → MSC → CRS → DELIVERY / TEST FLIGHT / RTS (Process by JB-B)
REMARK : COPY LINK FULL DASHBOARD ON DESKTOP TG ONLY : http://acm-hpv-app07.dt.thaiairways.co.th/RevisionPlan/BKKStatus.html

## TEV
HS-TEV C10(24M)+MOD DATE 06 OCT. 2026
Item | Revision | Functional loc. | Confirmation | Notification | Order | Order Type | Ident.Insp.Task | Reference Date | Oper.WorkCenter | Activity | Description | Syste | WBS ord. header | Priority | Priority | Working Group | Main WorkCtr | MaintActivType | External Ident. | Actual start | Bas. start date | Start time | Basic fin. date | Basic fin. time
1 | 70461604 | HS-TEV | 0015813506 | 1103070119 | 2104973224 | AC02 |  | 2026-09-07 | 11SH | 0010 | E/25-127:INSP AFT CGO DR FR58-FR66 | TECO | H/26-TEV-X0C10-MOD -G-F | 1 | DCA Appr. Req. 1 |  | BKK_H | DVI | A330.ED.BKKJA-E/25-127 | 2026-09-07 | 2026-08-22 | 00:00:00 | 2026-09-02 | 00:00:00
2 | 70461604 | HS-TEV | 0016099731 | 1103118776 | 2105051417 | AC02 |  | 2026-09-09 | 11LQ/IA | 0010 | E/24-051: Insp Vertical Stabilizer L/E | TECO | H/26-TEV-X0C10-MOD -G-F | 4 | TG Appr. Req. 4 |  | BKK_H | GVI | A330.ED.BKKJA-E/24-051 | 2026-09-09 | 2026-08-22 | 00:00:00 | 2026-09-02 | 00:00:00
3 | 70461604 | HS-TEV | 0016402767 |  | 2105137748 | AC01 | EWIS | 2026-09-07 | 11LQ/IA | 0010 | INSP-TAIL CONE APU AND ACCESS.COMP(EWIS) | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | FLOOR_TAIL | BKK_H | GVI | A330.MPD.ZL-315-01-1 | 2026-09-10 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
4 | 70461604 | HS-TEV | 0016402768 |  | 2105137749 | AC01 | EWIS | 2026-09-07 | 11LQ/IA | 0010 | INSP OF TAIL CONE APU XHAUST AREA (EWIS) | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | FLOOR_TAIL | BKK_H | GVI | A330.MPD.ZL-317-01-1 | 2026-09-10 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
5 | 70461604 | HS-TEV | 0016403788 |  | 2105137789 | AC01 | EWIS | 2026-09-24 | 11LQ/IA | 0010 | GVI RH OUTER T/E FIXED STRUCTURE | TECO | H/26-TEV-X0C10-BLOK-0-2 |  |  | WING_TRAILING EDGE | BKK_H | GVI | A330.MPD.ZL-575-01-1 | 2026-09-25 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
6 | 70461604 | HS-TEV | 0016403789 |  | 2105137790 | AC01 |  | 2026-09-23 | 11LHM/A | 0010 | CLOSE-UP FOR GVI LH OUTER T/E FIXED | TECO | H/26-TEV-X0C10-BLOK-0-5 |  |  | WING_TRAILING EDGE | BKK_H | RES | A330.MPD.ZL-575-01-1 | 2026-09-25 | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
7 | 70461604 | HS-TEV | 0016403794 |  | 2105137795 | AC01 | EWIS | 2026-09-10 | 11LQ/IA | 0010 | GVI RH INBOARD AILERON | TECO | H/26-TEV-X0C10-BLOK-0-2 |  |  | WING_TRAILING EDGE | BKK_H | GVI | A330.MPD.ZL-591-01-1 | 2026-09-13 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
8 | 70461604 | HS-TEV | 0016403798 |  | 2105137799 | AC01 |  | 2026-09-10 | 11LHM/A | 0010 | JOB SET-UP GVI RH OUTBOARD AILERON | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | WING_TRAILING EDGE | BKK_H | REM | A330.MPD.ZL-592-01-1 | 2026-09-10 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
9 | 70461604 | HS-TEV | 0016403803 |  | 2105137804 | AC01 |  | 2026-08-26 | 11LHM/C | 0010 | OPC LAVATORY WASTE COMPARTMENT FLAP | TECO | H/26-TEV-X0C10-BLOK-0-3 | 2 | DCA Appr. Req. 2 | CABIN_LAVATORY | BKK_H | OPC | A330.MPD.254000-01-1 | 2026-09-08 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
10 | 70461604 | HS-TEV | 0016403804 |  | 2105137805 | AC01 |  | 2026-08-26 | 11LHM/C | 0010 | DVI WASTE COMPT FOR FIRE CONT CAP | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | CABIN_LAVATORY | BKK_H | DET | A330.MPD.254000-02-1 | 2026-09-08 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
11 | 70461604 | HS-TEV | 0016403847 |  | 2105137848 | AC01 |  | 2026-09-10 | 11LQ/IA | 0010 | INSPECTION OF T/E SKIN RIB8-12 ,LH | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | WING_TRAILING EDGE | BKK_H | DET | A330.MPD.575025-01-5;575025-01-7 | 2026-09-13 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
12 | 70461604 | HS-TEV | 0016403856 |  | 2105137857 | AC01 |  | 2026-09-20 | 11NDT | 0010 | NDT - DOOR No.4 CUTOUT UPPER CORNERS | TECO | H/26-TEV-X0C10-BLOK-0-3 | 0 | AD | CABIN_DOOR | BKK_H | SDI | A330.MPD.534131-01-2 | 2026-09-10 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
13 | 70461604 | HS-TEV | 0016403862 |  | 2105137863 | AC01 |  | 2026-09-07 | 11LHM/E | 0010 | FUC OVERSTEER INDICATING SYSTEM | TECO | H/26-TEV-X0C10-BLOK-0-6 |  |  | IERA_FLOOR | BKK_H | OP | A330.MPD.325300-01-1 | 2026-09-07 | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
14 | 70461604 | HS-TEV | 0016403903 |  | 2105137899 | AC01 |  | 2026-09-15 | 11LHM/A | 0010 | PREPARE FOR NDT WING RIB 1-7 , RH | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | WING_FUEL | BKK_H | INS | A330.MPD.572052-03-4,-5,-7 | 2026-09-14 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
15 | 70461604 | HS-TEV | 0016403905 |  | 2105137901 | AC01 |  | 2026-09-15 | 11LHM/A | 0010 | CLOSE SET-UP FOR NDT WING RIB 1-7 , RH | TECO | H/26-TEV-X0C10-BLOK-0-5 |  |  | WING_FUEL | BKK_H | RES | A330.MPD.572052-03-4,-5,-7 | 2026-09-14 | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
16 | 70461604 | HS-TEV | 0016403918 |  | 2105137912 | AC01 |  | 2026-09-10 | 11LQ/IC | 0010 | INSP. - STRUCTURE TORSION BOX AT DOOR 3. | TECO | H/26-TEV-X0C10-BLOK-0-3 |  |  | CABIN_DOOR | BKK_H | DVI | A330.MPD.533198-01-1 | 2026-09-10 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
17 | 70461604 | HS-TEV | 0016403972 |  | 2105137964 | AC01 |  | 2026-09-07 | 11LHM/A | 0010 | REMOVE LOWER FAIRING (RR)#RH | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | WING_ENGINE | BKK_H | REM | A330.OPR.545100-07-1,545100-10-1 | 2026-09-07 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
18 | 70461604 | HS-TEV | 0016404003 |  | 2105137993 | AC01 |  | 2026-08-26 | 11LQ/IC | 0010 | INSP OF LAVATORY FIRE EXTINGUISHER | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | CABIN_LAVATORY | BKK_H | GVI | A330.MPD.262500-03-1 | 2026-09-08 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
19 | 70461604 | HS-TEV | 0016404005 |  | 2105137995 | AC01 |  | 2026-09-04 | 11LHM/A | 0010 | REM BELLY FAIRING 195 196 | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | FLOOR_FUSELAGE | BKK_H | REM | A330.MPD.ZL-195-03-1 | 2026-09-04 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
20 | 70461604 | HS-TEV | 0016404011 |  | 2105138001 | AC01 |  | 2026-09-07 | 11LQ/IA | 0010 | GENERAL VISUAL INSPECTION OF DIVERTER. | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | FLOOR_TAIL | BKK_H | GVI | A330.MPD.491600-03-1 | 2026-09-10 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
21 | 70461604 | HS-TEV | 0016404038 |  | 2105138028 | AC01 |  | 2026-08-26 | 11LHM/C | 0010 | OPERATIONAL CHECK OF DOOR DAMPING | TECO | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | CABIN_DOOR | BKK_H | OPC | A330.MPD.521000-14-1 | 2026-09-08 | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
22 | 70461604 | HS-TEV | 0016404039 |  | 2105138029 | AC01 |  | 2026-09-09 | 11LHM/A | 0010 | GVI HORIZONTAL STABILIZER | TECO | H/26-TEV-X0C10-BLOK-0-3 | 2 | DCA Appr. Req. 2 | FLOOR_TAIL | BKK_H | GVI | A330.MPD.551021-01-2 | 2026-09-21 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
23 | 70461604 | HS-TEV | 0016404050 |  | 2105138038 | AC01 |  | 2026-09-24 | 11LQ/IA | 0010 | DET of FUSELAGE SKIN EXTERNAL SURFACE | TECO | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | FLOOR_FUSELAGE | BKK_H | DET | A330.MPD.534026-02-1 | 2026-09-21 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
24 | 70461604 | HS-TEV | 0016404059 |  | 2105138044 | AC01 |  | 2026-09-10 | 11LHM/A | 0010 | DET OUTER WING TOP SKIN UPPER SURFA, LHW | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | WING_ALL WING | BKK_H | DET | A330.MPD.572033-01-8 | 2026-09-12 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
25 | 70461604 | HS-TEV | 0016404060 |  | 2105138045 | AC01 |  | 2026-09-10 | 11LHM/A | 0010 | DET OUTER WING TOP SKIN UPPER SURFA, RHW | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | WING_ALL WING | BKK_H | DET | A330.MPD.572033-01-8 | 2026-09-12 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
26 | 70461604 | HS-TEV | 0016404061 |  | 2105138046 | AC01 |  | 2026-09-15 | 11LHM/A | 0010 | DET OUTER WING CENTER SPAR ASSEMBLY FORW | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | WING_FUEL | BKK_H | DET | A330.MPD.572081-01-13 | 2026-09-14 | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
27 | 70461604 | HS-TEV | 0016404062 |  | 2105138046 | AC01 |  | 2026-09-15 | 11LHM/A | 0020 | DET OUTER WING CENTER SPAR ASSEMBLY FORW | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | WING_FUEL | BKK_H | DET | A330.MPD.572081-01-13 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
28 | 70461604 | HS-TEV | 0016404069 |  | 2105138053 | AC01 |  | 2026-09-10 | 11LHM/A | 0010 | DET OUT WING BOT SKIN LOW SURFACE - RH | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | WING_ALL WING | BKK_H | DET | A330.MPD.572111-01-12,572111-01-13 | 2026-09-13 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
29 | 70461604 | HS-TEV | 0016404072 |  | 2105138056 | AC01 |  | 2026-09-15 | 11LHM/A | 0010 | DET OUT WING BOT SKIN STR15 18 RIBS26 28 | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | WING_ALL WING | BKK_H | DET | A330.MPD.572183-01-10 | 2026-09-14 | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
30 | 70461604 | HS-TEV | 0016404073 |  | 2105138056 | AC01 |  | 2026-09-15 | 11LHM/A | 0020 | DET OUT WING BOT SKIN STR15 18 RIBS26 28 | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | WING_ALL WING | BKK_H | DET | A330.MPD.572183-01-10 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
31 | 70461604 | HS-TEV | 0016404150 |  | 2105138109 | AC01 |  | 2026-09-25 | 11LHM/E | 0010 | Radio Electrical Test Radome | TECO | H/26-TEV-X0C10-BLOK-0-5 |  |  | IERA_FLOOR | BKK_H | INS | A330.MPD.344100-01-1 | 2026-09-25 | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
32 | 70461604 | HS-TEV | 0016404159 |  | 2105138117 | AC01 |  | 2026-08-26 | 11LHM/C | 0010 | DRAIN,FLUSH TOILET TANK | TECO | H/26-TEV-X0C10-BLOK-I-N |  |  | CABIN_LAVATORY | BKK_H | INS | A330.OPR.001ACA05 | 2026-09-08 | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
33 | 70461604 | HS-TEV | 0016404161 |  | 2105138119 | AC01 |  | 2026-09-23 | 11LQ/IC | 0010 | CHK-ALL LOOSE & EMERG EQUIPMENTS | TECO | H/26-TEV-X0C10-BLOK-I-N |  |  | CABIN_INTERIOR | BKK_H | INS | A330.OPR.001ACA08,901ACW03 | 2026-09-25 | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
34 | 70461604 | HS-TEV | 0016404219 |  | 2105138170 | AC01 |  | 2026-09-07 | 11NDT | 0010 | NDT ACTUATOR ATTACH FITTING FWD CGO DOOR | TECO | H/26-TEV-X0C10-BLOK-0-3 | 2 | DCA Appr. Req. 2 | FLOOR_FWD COMPT | BKK_H | SDI | A330.MPD.523105-01-1,523105-01-2 | 2026-09-04 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
35 | 70461604 | HS-TEV | 0016404221 |  | 2105138172 | AC01 |  | 2026-09-20 | 11NDT | 0010 | NDT-INSP FUSELAGE OUTFLOW VLV | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | FLOOR_FWD COMPT | BKK_H | SDI | A330.MPD.532153-01-2 | 2026-09-11 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
36 | 70461604 | HS-TEV | 0016404235 |  | 2105138184 | AC01 |  | 2026-09-07 | 11LHM/A | 0010 | REMOVAL OF WATER EXTRACTOR | TECO | H/26-TEV-X0C10-BLOK-0-1 | 2 | DCA Appr. Req. 2 | FLOOR_AIR COND | BKK_H | REM | A330.MPD.215000-12-1;215200-01-1 | 2026-09-07 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
37 | 70461604 | HS-TEV | 0016404237 |  | 2105138186 | AC01 |  | 2026-09-07 | 11LHM/A | 0010 | REM -THE REHEATER PIPE ASSY | TECO | H/26-TEV-X0C10-BLOK-0-1 | 2 | DCA Appr. Req. 2 | FLOOR_AIR COND | BKK_H | DIS | A330.MPD.215000-12-1;215200-01-1 | 2026-09-07 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
38 | 70461604 | HS-TEV | 0016404239 |  | 2105138188 | AC01 |  | 2026-09-07 | 11LHM/A | 0010 | REM -THE REHEATER | TECO | H/26-TEV-X0C10-BLOK-0-1 | 2 | DCA Appr. Req. 2 | FLOOR_AIR COND | BKK_H | DIS | A330.MPD.215000-12-1;215200-01-1 | 2026-09-07 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
39 | 70461604 | HS-TEV | 0016404241 |  | 2105138190 | AC01 |  | 2026-09-07 | 11LHM/A | 0010 | REM -CONDENSER | TECO | H/26-TEV-X0C10-BLOK-0-1 | 2 | DCA Appr. Req. 2 | FLOOR_AIR COND | BKK_H | REM | A330.MPD.215200-01-1 | 2026-09-07 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
40 | 70461604 | HS-TEV | 0016404242 |  | 2105138191 | AC01 |  | 2026-09-07 | 11LHM/A | 0010 | REM -CONDENSER PIPE ASSIES | TECO | H/26-TEV-X0C10-BLOK-0-1 | 2 | DCA Appr. Req. 2 | FLOOR_AIR COND | BKK_H | RES | A330.MPD.215200-01-1-TG02,215200-01-1 | 2026-09-07 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
41 | 70461604 | HS-TEV | 0016404252 |  | 2105138201 | AC01 |  | 2026-09-07 | 11LHM/A | 0010 | RMV -EMERGENCY RAM AIR CHECK VALVE | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | FLOOR_AIR COND | BKK_H | DVI | A330.MPD.215500-04-1 | 2026-09-07 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
42 | 70461604 | HS-TEV | 0016404255 |  | 2105138204 | AC01 |  | 2026-09-07 | 11LHM/A | 0010 | RMV -THE SKIN CHECK VALVE | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | FLOOR_AIR COND | BKK_H | DVI | A330.MPD.215500-02-1 | 2026-09-07 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
43 | 70461604 | HS-TEV | 0016404258 |  | 2105138207 | AC01 |  | 2026-09-07 | 11LHM/A | 0010 | REM -GROUND CONNECT CHECK VALVE | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | FLOOR_AIR COND | BKK_H | REM | A330.MPD.215500-03-1 | 2026-09-07 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
44 | 70461604 | HS-TEV | 0016404273 |  | 2105138222 | AC01 |  | 2026-09-09 | 11LHM/A | 0010 | REMOVE/OPEN ACCESS PNL AFT CGO DOOR | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | FLOOR_AFT COMPT | BKK_H | REM | A330.MPD.523200-01-1;ZL-822-02-1 | 2026-09-04 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
45 | 70461604 | HS-TEV | 0016404282 |  | 2105138231 | AC01 |  | 2026-09-07 | 11LHM/A | 0010 | REM -BULK CARGO DOOR LINING | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | FLOOR_AFT COMPT | BKK_H | DVI | A330.MPD.523300-03-1;523302-01-1 | 2026-09-07 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
46 | 70461604 | HS-TEV | 0016404295 |  | 2105138244 | AC01 |  | 2026-09-07 | 11NDT | 0010 | NDT-ACTUATOR ATTACH FITTINGS-AFT CGO | TECO | H/26-TEV-X0C10-BLOK-0-3 | 2 | DCA Appr. Req. 2 | FLOOR_AFT COMPT | BKK_H | SDI | A330.MPD.523205-01-1,523205-01-2 | 2026-09-07 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
47 | 70461604 | HS-TEV | 0016404298 |  | 2105138247 | AC01 |  | 2026-09-08 | 11SH | 0010 | REM -AFT PAX/CREW DOOR SCUFF PLATES | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | CABIN_DOOR | BKK_H | DVI | A330.MPD.534132-01-1;534132-02-1 | 2026-09-07 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
48 | 70461604 | HS-TEV | 0016404304 |  | 2105138253 | AC01 |  | 2026-09-24 | 11LQ/IA | 0010 | INSP-UPPER HALF OF FUSELAGE | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | FLOOR_FUSELAGE | BKK_H | GVI | A330.MPD.ZL-200-01-1 | 2026-09-23 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
49 | 70461604 | HS-TEV | 0016404314 |  | 2105138263 | AC01 |  | 2026-08-26 | 11LHM/C | 0010 | RMV-COFFEE CONTAINERS | TECO | H/26-TEV-X0C10-BLOK-I-N | 4 | TG Appr. Req. 4 | CABIN_GALLEY | BKK_H | RES | A330.MPD.2536010201-TG01 | 2026-09-08 | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
50 | 70461604 | HS-TEV | 0016404318 |  | 2105138267 | AC01 |  | 2026-09-07 | 11LHM/C | 0010 | RMV - PASSENGER SEAT CUSHIONS | TECO | H/26-TEV-X0C10-BLOK-I-N | 4 | TG Appr. Req. 4 | CABIN_INTERIOR | BKK_H | RES | A330.MPD.2521000004-TG01 | 2026-09-09 | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
51 | 70461604 | HS-TEV | 0016404325 |  | 2105138274 | AC01 |  | 2026-08-26 | 11LQ/IC | 0010 | INSP OF LAVATORY FIRE EXTINGUISHER | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | CABIN_LAVATORY | BKK_H | GVI | A330.MPD.262500-01-1 | 2026-09-08 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
52 | 70461604 | HS-TEV | 0016404335 |  | 2105138284 | AC01 |  | 2026-09-07 | 11LQ/IC | 0010 | DVI - C/A SEAT ATTACHMENT POINTS. | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | CABIN_INTERIOR | BKK_H | DET | A330.MPD.252200-02-1 | 2026-09-09 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
53 | 70461604 | HS-TEV | 0016404339 |  | 2105138288 | AC01 |  | 2026-08-26 | 11LHM/C | 0010 | OPC - EMERGENCY EXIT DOORS. | TECO | H/26-TEV-X0C10-BLOK-0-6 | 0 | AD | CABIN_DOOR | BKK_H | OPC | A330.MPD.522200-04-1 | 2026-08-26 | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
54 | 70461604 | HS-TEV | 0016404340 |  | 2105138289 | AC01 |  | 2026-08-26 | 11LHM/C | 0010 | OPC-UNLOCKING/LOCKING OF EMERG EXIT DOOR | TECO | H/26-TEV-X0C10-BLOK-0-6 | 1 | DCA Appr. Req. 1 | CABIN_DOOR | BKK_H | OPC | A330.MPD.522200-01-1 | 2026-08-26 | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
55 | 70461604 | HS-TEV | 0016404349 |  | 2105138298 | AC01 |  | 2026-08-26 | 11LQ/IC | 0010 | INSP - MECH PART OF DOOR LOCKING SYSTEM | TECO | H/26-TEV-X0C10-BLOK-0-3 | 2 | DCA Appr. Req. 2 | CABIN_COCKPIT | BKK_H | DVI | A330.MPD.525111-02-1 | 2026-08-26 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
56 | 70461604 | HS-TEV | 0016404352 |  | 2105138301 | AC01 |  | 2026-09-01 | 11LQ/IC | 0010 | INSP-FULL-FACE/QUICK DONNING OXYGEN MASK | TECO | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | CABIN_COCKPIT | BKK_H | VIC | A330.MPD.351200-04-1 | 2026-09-01 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
57 | 70461604 | HS-TEV | 0016404354 |  | 2105138303 | AC01 |  | 2026-09-07 | 11LHM/C | 0010 | OPC-ESCAPE SLIDE RELEASE WARNING SYSTEM | TECO | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | CABIN_DOOR | BKK_H | OPC | A330.MPD.527100-02-1 | 2026-08-26 | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
58 | 70461604 | HS-TEV | 0016404358 |  | 2105138307 | AC01 |  | 2026-09-07 | 11LHM/E | 0010 | REMOVAL OF TEMPERATURE SENSOR | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | IERA_CABIN | BKK_H | RS | A330.MPD.216000-03-1 | 2026-09-07 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
59 | 70461604 | HS-TEV | 0016404360 |  | 2105138309 | AC01 |  | 2026-08-24 | 11LHM/E | 0010 | CLEAN COCKPIT & CABIN TEMP SENSORS | TECO | H/26-TEV-X0C10-BLOK-0-7 | 2 | DCA Appr. Req. 2 | IERA_CABIN | BKK_H | OPC | A330.MPD.216000-03-1 | 2026-08-23 | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
60 | 70461604 | HS-TEV | 0016404361 |  | 2105138309 | AC01 |  | 2026-08-24 | 11LHM/E | 0020 | CLEAN COCKPIT & CABIN TEMP SENSORS | TECO | H/26-TEV-X0C10-BLOK-0-7 | 2 | DCA Appr. Req. 2 | IERA_CABIN | BKK_H | OPC | A330.MPD.216000-03-1 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
61 | 70461604 | HS-TEV | 0016404362 |  | 2105138309 | AC01 |  | 2026-08-24 | 11LHM/E | 0030 | CLEAN COCKPIT & CABIN TEMP SENSORS | TECO | H/26-TEV-X0C10-BLOK-0-7 | 2 | DCA Appr. Req. 2 | IERA_CABIN | BKK_H | OPC | A330.MPD.216000-03-1 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
62 | 70461604 | HS-TEV | 0016404401 |  | 2105138348 | AC01 |  | 2026-09-07 | 11LHM/C | 0010 | FUC-PAX/CREW DOORS LOCKING MECHANISM | TECO | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | CABIN_DOOR | BKK_H | FUC | A330.MPD.521000-01-1 | 2026-08-26 | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
63 | 70461604 | HS-TEV | 0016404414 |  | 2105138361 | AC01 |  | 2026-09-07 | 11LQ/IA | 0010 | INSPECTION OF APU SUSPENSION SYSTEM. | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | FLOOR_TAIL | BKK_H | GVI | A330.MPD.491200-02-1 | 2026-09-10 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
64 | 70461604 | HS-TEV | 0016404416 |  | 2105138363 | AC01 |  | 2026-09-07 | 11LHM/A | 0010 | INSP OF THE V-CLAMP AND EXHAUST MUFFFLER | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | FLOOR_TAIL | BKK_H | GVI | A330.MPD.498100-02-1 | 2026-09-09 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
65 | 70461604 | HS-TEV | 0016404418 |  | 2105138365 | AC01 | EWIS | 2026-09-07 | 11LQ/IA | 0010 | INSP OF TAIL CONE APU AIR INTAKE AREA | TECO | H/26-TEV-X0C10-BLOK-0-1 | 2 | DCA Appr. Req. 2 | FLOOR_TAIL | BKK_H | GVI | A330.MPD.ZL-313-01-1 | 2026-09-10 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
66 | 70461604 | HS-TEV | 0016404420 |  | 2105138367 | AC01 | EWIS | 2026-09-09 | 11LQ/IA | 0010 | INSP OF HOR STAB TRAILING EDGE (EWIS). | TECO | H/26-TEV-X0C10-BLOK-0-1 | 2 | DCA Appr. Req. 2 | FLOOR_TAIL | BKK_H | GVI | A330.MPD.ZL-334-01-1 | 2026-09-07 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
67 | 70461604 | HS-TEV | 0016404421 |  | 2105138368 | AC01 | EWIS | 2026-09-09 | 11LQ/IA | 0010 | INSP ELEVATOR BTW RIB 8-9 (EWIS). | TECO | H/26-TEV-X0C10-BLOK-0-1 | 2 | DCA Appr. Req. 2 | FLOOR_TAIL | BKK_H | GVI | A330.MPD.ZL-335-01-1 | 2026-09-08 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
68 | 70461604 | HS-TEV | 0016404442 |  | 2105138389 | AC01 | EWIS | 2026-09-09 | 11LQ/IA | 0010 | INSP LOWER/REAR PYLON FAIRINGS-RR PYLON2 | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | WING_ENGINE | BKK_H | GVI | A330.MPD.ZL-454-05-2 | 2026-09-06 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
69 | 70461604 | HS-TEV | 0016404447 |  | 2105138394 | AC01 |  | 2026-09-07 | 11LHM/A | 0010 | REM UPPER FWD PYLON PANEL-RR PYL#2 | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | WING_ENGINE | BKK_H | REM | A330.MPD.ZL-452-01-1 | 2026-09-05 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
70 | 70461604 | HS-TEV | 0016404487 |  | 2105138434 | AC01 | EWIS | 2026-09-09 | 11LQ/IA | 0010 | RH,INSP-EXTERNAL WING AREA | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | WING_LEADING EDGE | BKK_H | GVI | A330.MPD.ZL-521-01-1 | 2026-09-13 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
71 | 70461604 | HS-TEV | 0016404489 |  | 2105138436 | AC01 | EWIS | 2026-09-10 | 11LQ/IA | 0010 | RH,INSP-EXTERNAL WING AREA | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | WING_LEADING EDGE | BKK_H | GVI | A330.MPD.ZL-522-01-1 | 2026-09-13 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
72 | 70461604 | HS-TEV | 0016404503 |  | 2105138450 | AC01 |  | 2026-09-24 | 11LQ/IA | 0010 | RHW INSP FIXED L/E PLATE&STRAPS | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | WING_LEADING EDGE | BKK_H | DVI | A330.MPD.574109-02-3 | 2026-09-24 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
73 | 70461604 | HS-TEV | 0016404505 |  | 2105138452 | AC01 |  | 2026-09-23 | 11LHM/A | 0010 | CLOSE-UP:INSP FIXED L/E PLATE AND STRAP | TECO | H/26-TEV-X0C10-BLOK-0-5 |  |  | WING_LEADING EDGE | BKK_H | RES | A330.MPD.574109-02-3 | 2026-09-25 | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
74 | 70461604 | HS-TEV | 0016404588 |  | 2105138532 | AC01 |  | 2026-09-10 | 11NDT | 0010 | NDT MID PAX/CREW DR UNDER SCUFF PLATES | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | CABIN_DOOR | BKK_H | SDI | A330.MPD.532124-02-5,532124-02-9 | 2026-09-10 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
75 | 70461604 | HS-TEV | 0016404589 |  | 2105138533 | AC01 |  | 2026-09-10 | 11NDT | 0010 | NDT MID PAX/CREW DR CUTOUT UPPER CORNER | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | CABIN_DOOR | BKK_H | SDI | A330.MPD.532125-01-9 | 2026-09-10 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
76 | 70461604 | HS-TEV | 0016404591 |  | 2105138535 | AC01 |  | 2026-09-13 | 11NDT | 0010 | NDT-AREA BEHIND AFT PAX DR SCUFF-PLATE | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | CABIN_DOOR | BKK_H | SDI | A330.MPD.534132-02-1;534132-02-2 | 2026-09-10 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
77 | 70461604 | HS-TEV | 0016503086 | EV082B250826 | EV082B250826 | AC05 |  | 2026-09-07 | 11CMPST | 0010 | CABIN MID GALLEY | TECO | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  | 2026-08-26 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
78 | 70461604 | HS-TEV | 0016526074 | EV104A070926 | EV104A070926 | AC05 |  | 2026-09-10 | 11CMPST | 0010 | ELEVATOR | TECO | H/26-TEV-X0C10-NONR |  |  |  | 11CMPST | REP |  | 2026-09-07 | 2026-09-07 | 12:13:00 | 2026-09-14 | 09:00:00
79 | 70461604 | HS-TEV | 0016526689 | EV104A070926 | EV104A070926 | AC05 |  | 2026-09-10 | 11CMPST | 0020 | ELEVATOR | TECO | H/26-TEV-X0C10-NONR |  |  |  | 11CMPST | REP |  |  | 2026-09-07 | 12:13:00 | 2026-09-14 | 09:00:00
80 | 70461604 | HS-TEV | 0016528020 | EV104A070926 | EV104A070926 | AC05 |  | 2026-09-10 | 11PAINT | 0030 | ELEVATOR | TECO | H/26-TEV-X0C10-NONR |  |  |  | 11CMPST | REP |  |  | 2026-09-07 | 12:13:00 | 2026-09-14 | 09:00:00
81 | 70461604 | HS-TEV | 0016531086 | EV118B090926 | EV118B090926 | AC05 |  | 2026-09-15 | 11PAINT | 0010 | LEADING EDGE VERTICAL STABILIZER HOIST P | TECO | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  | 2026-09-14 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
82 | 70461604 | HS-TEV | 0016404010 |  | 2105138000 | AC01 |  | 2026-09-24 | 11NDT | 0010 | SDI-BULK CARGO COMP DR CUT-OUT CORNERS | TECO | H/26-TEV-X0C10-BLOK-0-3 |  |  | FLOOR_AFT COMPT | BKK_H | SDI | A330.MPD.534143-02-1 | 2026-09-20 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
83 | 70461604 | HS-TEV | 0016404024 |  | 2105138014 | AC01 |  | 2026-09-24 | 11LQ/IA | 0010 | DVI-FUSELAGE SKIN BETWEEN FR 54 AND 80 | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | FLOOR_FUSELAGE | BKK_H | GVI | A330.MPD.534124-02-3 | 2026-09-23 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
84 | 70461604 | HS-TEV | 0016404025 |  | 2105138015 | AC01 |  | 2026-09-24 | 11NDT | 0010 | SDI-BULK CARGO COMPARTMENT DOOR CUT-OUT | TECO | H/26-TEV-X0C10-BLOK-0-3 |  |  | FLOOR_AFT COMPT | BKK_H | SDI | A330.MPD.534144-03-1 | 2026-09-20 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
85 | 70461604 | HS-TEV | 0016404123 |  | 2105138094 | AC01 |  | 2026-09-12 | 11LHM/C | 0010 | GVI OF PAX DOOR 2 EXTERNAL SURFACE | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | CABIN_DOOR | BKK_H | GVI | A330.MPD.521204-01-1 | 2026-09-10 | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
86 | 70461604 | HS-TEV | 0016404124 |  | 2105138094 | AC01 |  | 2026-09-12 | 11LHM/C | 0020 | GVI OF PAX DOOR 2 EXTERNAL SURFACE | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | CABIN_DOOR | BKK_H | GVI | A330.MPD.521204-01-1 | 2026-09-10 | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
87 | 70461604 | HS-TEV | 0016404228 |  | 2105138179 | AC01 | EWIS | 2026-09-10 | 11LHM/A | 0010 | INSP FWD AVIONICS COMPT DOOR | TECO | H/26-TEV-X0C10-BLOK-0-4 | 2 | DCA Appr. Req. 2 | FLOOR_FWD COMPT | BKK_H | GVI | A330.MPD.ZL-811-01-1 | 2026-09-10 | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
88 | 70461604 | HS-TEV | 0016404229 |  | 2105138179 | AC01 | EWIS | 2026-09-10 | 11LQ/IA | 0020 | INSP FWD AVIONICS COMPT DOOR | TECO | H/26-TEV-X0C10-BLOK-0-4 | 2 | DCA Appr. Req. 2 | FLOOR_FWD COMPT | BKK_H | GVI | A330.MPD.ZL-811-01-1 | 2026-09-05 | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
89 | 70461604 | HS-TEV | 0016404230 |  | 2105138179 | AC01 | EWIS | 2026-09-10 | 11LHM/A | 0030 | INSP FWD AVIONICS COMPT DOOR | TECO | H/26-TEV-X0C10-BLOK-0-4 | 2 | DCA Appr. Req. 2 | FLOOR_FWD COMPT | BKK_H | GVI | A330.MPD.ZL-811-01-1 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
90 | 70461604 | HS-TEV | 0016404422 |  | 2105138369 | AC01 | EWIS | 2026-09-09 | 11LQ/IA | 0010 | INSP OF VERT STAB TRAILING EDGE (EWIS). | TECO | H/26-TEV-X0C10-BLOK-0-1 | 2 | DCA Appr. Req. 2 | FLOOR_TAIL | BKK_H | GVI | A330.MPD.ZL-325-01-1 | 2026-09-09 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
91 | 70461604 | HS-TEV | 0016403787 |  | 2105137788 | AC01 | EWIS | 2026-09-12 | 11LQ/IA | 0010 | GVI LH OUTER T/E FIXED STRUCTURE | TECO | H/26-TEV-X0C10-BLOK-0-2 |  |  | WING_TRAILING EDGE | BKK_H | GVI | A330.MPD.ZL-575-01-1 | 2026-09-12 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
92 | 70461604 | HS-TEV | 0016403793 |  | 2105137794 | AC01 | EWIS | 2026-09-12 | 11LQ/IA | 0010 | GVI LH INBOARD AILERON | TECO | H/26-TEV-X0C10-BLOK-0-2 |  |  | WING_TRAILING EDGE | BKK_H | GVI | A330.MPD.ZL-591-01-1 | 2026-09-14 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
93 | 70461604 | HS-TEV | 0016403802 |  | 2105137803 | AC01 |  | 2026-09-15 | 11LHM/A | 0010 | CLOSE-UP GVI RH OUTBOARD AILERON | TECO | H/26-TEV-X0C10-BLOK-0-5 |  |  | WING_TRAILING EDGE | BKK_H | RES | A330.MPD.ZL-592-01-1 | 2026-09-14 | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
94 | 70461604 | HS-TEV | 0016403829 |  | 2105137830 | AC01 |  | 2026-09-12 | 11NDT | 0010 | NDT-INTERNAL STRUCTURE FR47 STGR20-23. | TECO | H/26-TEV-X0C10-BLOK-0-3 | 0 | AD | CABIN_INTERIOR | BKK_H | SDI | A330.MPD.533114-01-10 | 2026-09-11 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
95 | 70461604 | HS-TEV | 0016403895 |  | 2105137893 | AC01 |  | 2026-09-16 | 11LHM/A | 0010 | PREPARE FOR NDT WING RIB 1-7 , LH | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | WING_FUEL | BKK_H | INS | A330.MPD.572052-03-4,-5,-7 | 2026-09-14 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
96 | 70461604 | HS-TEV | 0016403897 |  | 2105137895 | AC01 |  | 2026-09-15 | 11LHM/A | 0010 | CLOSE SET-UP FOR NDT WING RIB 1-7 , LH | TECO | H/26-TEV-X0C10-BLOK-0-5 |  |  | WING_FUEL | BKK_H | RES | A330.MPD.572052-03-4,-5,-7 | 2026-09-14 | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
97 | 70461604 | HS-TEV | 0016403978 |  | 2105137970 | AC01 |  | 2026-09-24 | 11LQ/IA | 0010 | GVI EXTERNAL SURFACE FR53.3 AND FR54 | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | FLOOR_FUSELAGE | BKK_H | GVI | A330.MPD.533197-01-1 | 2026-09-22 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
98 | 70461604 | HS-TEV | 0016404040 |  | 2105138030 | AC01 |  | 2026-09-08 | 11LHM/A | 0010 | GVI ELEVATOR TOP AND BOTTOM | TECO | H/26-TEV-X0C10-BLOK-0-3 | 2 | DCA Appr. Req. 2 | FLOOR_TAIL | BKK_H | GVI | A330.MPD.552001-01-3 | 2026-09-08 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
99 | 70461604 | HS-TEV | 0016404064 |  | 2105138048 | AC01 |  | 2026-09-09 | 11LHM/A | 0010 | GVI HORIZONTAL STABILIZER CENTER BOX TOP | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | FLOOR_TAIL | BKK_H | GVI | A330.MPD.551023-01-1 | 2026-09-07 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
100 | 70461604 | HS-TEV | 0016404070 |  | 2105138054 | AC01 |  | 2026-09-15 | 11LHM/A | 0010 | DET OUT WING BOT SKIN STR15 18 LHW | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | WING_ALL WING | BKK_H | DET | A330.MPD.572180-01-7 | 2026-09-14 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
101 | 70461604 | HS-TEV | 0016404071 |  | 2105138055 | AC01 |  | 2026-09-15 | 11LHM/A | 0010 | DET OUT WING BOT SKIN STR15 18 RHW | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | WING_ALL WING | BKK_H | DET | A330.MPD.572180-01-7 | 2026-09-14 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
102 | 70461604 | HS-TEV | 0016404085 |  | 2105138066 | AC01 |  | 2026-09-06 | 11LHM/A | 0010 | GVI OUTER FUEL TANK (EWIS) LHW | TECO | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | WING_FUEL | BKK_H | GVI | A330.MPD.ZL-542-03-1 | 2026-09-07 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
103 | 70461604 | HS-TEV | 0016404296 |  | 2105138245 | AC01 |  | 2026-09-08 | 11SH | 0010 | REM -MID PAX/CREW DOOR SCUFF PLATE | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | CABIN_DOOR | BKK_H | DVI | A330.MPD.532124-01-1 | 2026-09-08 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
104 | 70461604 | HS-TEV | 0016404303 |  | 2105138252 | AC01 |  | 2026-09-24 | 11LQ/IA | 0010 | INSP OF LOWER HALF FUSELAGE | TECO | H/26-TEV-X0C10-BLOK-0-1 | 2 | DCA Appr. Req. 2 | FLOOR_FUSELAGE | BKK_H | GVI | A330.MPD.ZL-100-01-2 | 2026-09-10 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
105 | 70461604 | HS-TEV | 0016404334 |  | 2105138283 | AC01 |  | 2026-09-07 | 11LHM/C | 0010 | OPC-C/A SEAT BELTS AND BELT ATTACHMENT | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | CABIN_INTERIOR | BKK_H | OPC | A330.MPD.252200-03-1 | 2026-09-09 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
106 | 70461604 | HS-TEV | 0016404355 |  | 2105138304 | AC01 |  | 2026-09-07 | 11LHM/E | 0010 | REMOVAL OF TEMPERATURE SENSOR 001-049 | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | IERA_CABIN | BKK_H | RS | A330.MPD.216000-03-1 | 2026-09-07 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
107 | 70461604 | HS-TEV | 0016404419 |  | 2105138366 | AC01 |  | 2026-09-07 | 11LQ/IA | 0010 | INSP SEALING RING COUPLING AND BELLOW | TECO | H/26-TEV-X0C10-BLOK-0-1 | 2 | DCA Appr. Req. 2 | FLOOR_TAIL | BKK_H | DVI | A330.MPD.498100-01-1 | 2026-09-10 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
108 | 70461604 | HS-TEV | 0016404482 |  | 2105138429 | AC01 |  | 2026-09-30 | 11LHM/A | 0010 | [OPENING-TRACK FAIRING ACCESS] | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | WING_TRAILING EDGE | BKK_H | GVI | A330.MPD.ZL-531-01-1 | 2026-09-30 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
109 | 70461604 | HS-TEV | 0016404493 |  | 2105138440 | AC01 | EWIS | 2026-09-30 | 11LQ/IA | 0010 | INSP EXTERNAL WING -RH WING | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | WING_TRAILING EDGE | BKK_H | GVI | A330.MPD.ZL-500-02-1;ZL-531-01-1 | 2026-09-30 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
110 | 70461604 | HS-TEV | 0016403909 |  | 2105137905 | AC01 |  | 2026-09-15 | 11NDT | 0010 | NDT STRUC SPLICING AREA FR48-53 LH/RH. | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | FLOOR_FUSELAGE | BKK_H | SDI | A330.MPD.533161-01-9 | 2026-09-10 | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
111 | 70461604 | HS-TEV | 0016403910 |  | 2105137905 | AC01 |  | 2026-09-15 | 11SH | 0020 | NDT STRUC SPLICING AREA FR48-53 LH/RH. | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | FLOOR_FUSELAGE | BKK_H | SDI | A330.MPD.533161-01-9 | 2026-09-10 | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
112 | 70461604 | HS-TEV | 0016403911 |  | 2105137905 | AC01 |  | 2026-09-15 | 11SH | 0030 | NDT STRUC SPLICING AREA FR48-53 LH/RH. | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | FLOOR_FUSELAGE | BKK_H | SDI | A330.MPD.533161-01-9 | 2026-09-11 | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
113 | 70461604 | HS-TEV | 0016404250 |  | 2105138199 | AC01 |  | 2026-09-15 | 11LHM/A | 0010 | INSTALL-DOWN STREAM CHECK VALVE | TECO | H/26-TEV-X0C10-BLOK-0-5 |  |  | FLOOR_AIR COND | BKK_H | DVI | A330.MPD.215000-06-1 | 2026-09-13 | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
114 | 70461604 | HS-TEV | 0016404057 |  | 2105138043 | AC01 |  | 2026-09-07 | 11LQ/IA | 0010 | DET FUSELAGE EXTERNAL STRUCTURE, KEEL BE | TECO | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | FLOOR_FUSELAGE | BKK_H | DET | A330.MPD.571164-01-2 | 2026-09-05 | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
115 | 70461604 | HS-TEV | 0016404058 |  | 2105138043 | AC01 |  | 2026-09-07 | 11LHM/A | 0020 | DET FUSELAGE EXTERNAL STRUCTURE, KEEL BE | TECO | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | FLOOR_FUSELAGE | BKK_H | DET | A330.MPD.571164-01-2 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
116 | 70461604 | HS-TEV | 0016404139 |  | 2105138105 | AC01 |  | 2026-09-08 | 11LHM/A | 0010 | GVI FUSELAGE SKIN BELOW SATCOM ANTENNA | TECO | H/26-TEV-X0C10-BLOK-0-6 | 1 | DCA Appr. Req. 1 | IERA_FLOOR | BKK_H | GVI | A330.MPD.532025-02-1 | 2026-09-08 | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
117 | 70461604 | HS-TEV | 0016404140 |  | 2105138105 | AC01 |  | 2026-09-08 | 11LHM/A | 0020 | GVI FUSELAGE SKIN BELOW SATCOM ANTENNA | TECO | H/26-TEV-X0C10-BLOK-0-6 | 1 | DCA Appr. Req. 1 | IERA_FLOOR | BKK_H | GVI | A330.MPD.532025-02-1 | 2026-09-08 | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
118 | 70461604 | HS-TEV | 0016404141 |  | 2105138105 | AC01 |  | 2026-09-08 | 11LHM/A | 0030 | GVI FUSELAGE SKIN BELOW SATCOM ANTENNA | TECO | H/26-TEV-X0C10-BLOK-0-6 | 1 | DCA Appr. Req. 1 | IERA_FLOOR | BKK_H | GVI | A330.MPD.532025-02-1 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
119 | 70461604 | HS-TEV | 0016404142 |  | 2105138106 | AC01 |  | 2026-09-12 | 11LHM/A | 0010 | GVI OF INTERNAL STRUCTURE AROUND DOOR3 | TECO | H/26-TEV-X0C10-BLOK-0-5 | 1 | DCA Appr. Req. 1 | CABIN_DOOR | BKK_H | GVI | A330.MPD.533190-02-1 | 2026-09-10 | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
120 | 70461604 | HS-TEV | 0016404143 |  | 2105138106 | AC01 |  | 2026-09-12 | 11LHM/A | 0020 | GVI OF INTERNAL STRUCTURE AROUND DOOR3 | TECO | H/26-TEV-X0C10-BLOK-0-5 | 1 | DCA Appr. Req. 1 | CABIN_DOOR | BKK_H | GVI | A330.MPD.533190-02-1 | 2026-09-10 | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
121 | 70461604 | HS-TEV | 0016404144 |  | 2105138106 | AC01 |  | 2026-09-12 | 11LHM/A | 0030 | GVI OF INTERNAL STRUCTURE AROUND DOOR3 | TECO | H/26-TEV-X0C10-BLOK-0-5 | 1 | DCA Appr. Req. 1 | CABIN_DOOR | BKK_H | GVI | A330.MPD.533190-02-1 | 2026-09-12 | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
122 | 70461604 | HS-TEV | 0016404485 |  | 2105138432 | AC01 | EWIS | 2026-09-10 | 11LQ/IA | 0010 | RH,INSP-EXTERNAL WING AREA | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | WING_LEADING EDGE | BKK_H | GVI | A330.MPD.ZL-500-01-1 | 2026-09-13 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
123 | 70461604 | HS-TEV | 0016404520 |  | 2105138467 | AC01 |  | 2026-09-30 | 11CLEAN | 0010 | RHW-CLEAN OF FLAP HYD ACTUATION&POWER TR | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | WING_TRAILING EDGE | BKK_H | INS | A330.MPD.275400-03-1 | 2026-09-30 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
124 | 70461604 | HS-TEV | 0016522944 | EV098B040926 | EV098B040926 | AC05 |  | 2026-09-05 | 11LHM/A | 0010 | APU SURGE BLEED AIR DUCT TORN OFF. | TECO | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  | 2026-09-10 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
125 | 70461604 | HS-TEV | 0016522975 | EV100A040926 | EV100A040926 | AC05 |  | 2026-09-10 | 11SH | 0010 | REAR FUSELAGE | TECO | H/26-TEV-X0C10-NONR |  |  |  | 11SH | REP |  | 2026-09-07 | 2026-09-04 | 16:46:00 | 2026-09-11 | 16:00:00
126 | 70461604 | HS-TEV | 0016523576 | EV100A040926 | EV100A040926 | AC05 |  | 2026-09-10 | 11SH | 0020 | REAR FUSELAGE | TECO | H/26-TEV-X0C10-NONR |  |  |  | 11SH | REP |  | 2026-09-08 | 2026-09-04 | 16:46:00 | 2026-09-11 | 16:00:00
127 | 70461604 | HS-TEV | 0016523577 | EV100A040926 | EV100A040926 | AC05 |  | 2026-09-10 | 11SH | 0030 | REAR FUSELAGE | TECO | H/26-TEV-X0C10-NONR |  |  |  | 11SH | REP |  | 2026-09-07 | 2026-09-04 | 16:46:00 | 2026-09-11 | 16:00:00
128 | 70461604 | HS-TEV | 0016526861 | EV100A040926 | EV100A040926 | AC05 |  | 2026-09-10 | 11SH | 0040 | REAR FUSELAGE | TECO | H/26-TEV-X0C10-NONR |  |  |  | 11SH | REP |  |  | 2026-09-04 | 16:46:00 | 2026-09-11 | 16:00:00
129 | 70461604 | HS-TEV | 0016526862 | EV100A040926 | EV100A040926 | AC05 |  | 2026-09-10 | 11NDT | 0050 | REAR FUSELAGE | TECO | H/26-TEV-X0C10-NONR |  |  |  | 11SH | REP |  | 2026-09-07 | 2026-09-04 | 16:46:00 | 2026-09-11 | 16:00:00
130 | 70461604 | HS-TEV | 0016526863 | EV100A040926 | EV100A040926 | AC05 |  | 2026-09-10 | 11NDT | 0060 | REAR FUSELAGE | TECO | H/26-TEV-X0C10-NONR |  |  |  | 11SH | REP |  | 2026-09-07 | 2026-09-04 | 16:46:00 | 2026-09-11 | 16:00:00
131 | 70461604 | HS-TEV | 0016526864 | EV100A040926 | EV100A040926 | AC05 |  | 2026-09-10 | 11NDT | 0070 | REAR FUSELAGE | TECO | H/26-TEV-X0C10-NONR |  |  |  | 11SH | REP |  | 2026-09-07 | 2026-09-04 | 16:46:00 | 2026-09-11 | 16:00:00
132 | 70461604 | HS-TEV | 0016526865 | EV100A040926 | EV100A040926 | AC05 |  | 2026-09-10 | 11NDT | 0080 | REAR FUSELAGE | TECO | H/26-TEV-X0C10-NONR |  |  |  | 11SH | REP |  |  | 2026-09-04 | 16:46:00 | 2026-09-11 | 16:00:00
133 | 70461604 | HS-TEV | 0016526866 | EV100A040926 | EV100A040926 | AC05 |  | 2026-09-10 | 11SH | 0090 | REAR FUSELAGE | TECO | H/26-TEV-X0C10-NONR |  |  |  | 11SH | REP |  |  | 2026-09-04 | 16:46:00 | 2026-09-11 | 16:00:00
134 | 70461604 | HS-TEV | 0016527276 | EV100A040926 | EV100A040926 | AC05 |  | 2026-09-10 | 11SH | 0100 | REAR FUSELAGE | TECO | H/26-TEV-X0C10-NONR |  |  |  | 11SH | REP |  | 2026-09-08 | 2026-09-04 | 16:46:00 | 2026-09-11 | 16:00:00
135 | 70461604 | HS-TEV | 0016527277 | EV100A040926 | EV100A040926 | AC05 |  | 2026-09-10 | 11PAINT | 0110 | REAR FUSELAGE | TECO | H/26-TEV-X0C10-NONR |  |  |  | 11SH | REP |  | 2026-09-09 | 2026-09-04 | 16:46:00 | 2026-09-11 | 16:00:00
136 | 70461604 | HS-TEV | 0016526691 | EV105B070926 | EV105B070926 | AC05 |  | 2026-09-15 | 11LHM/A | 0010 | FUEL:BONDING GND DAMAGED. | TECO | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  | 2026-09-14 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
137 | 70461604 | HS-TEV | 0016533889 | EV130B110926 | EV130B110926 | AC05 |  | 2026-09-11 | 11SH | 0010 | FWD.CARGO COMPARTMENT FR55-FR57 RH SIDE | TECO | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  | 2026-09-11 | 2026-09-11 | 10:37:00 | 2026-09-11 | 19:00:00
138 | 70461604 | HS-TEV | 0016555295 | EV151B240926 | EV151B240926 | AC05 |  | 2026-09-24 | 11LHM/A | 0010 | RH WING I/B SLAT NUMBER 1 SEAL TORN OFF. | TECO | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  | 2026-09-24 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
139 | 70461604 | HS-TEV | 0016555296 | EV152B240926 | EV152B240926 | AC05 |  | 2026-09-24 | 11LHM/A | 0010 | SLAT 2 I/B LOWER SEAL TORN OFF. | TECO | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  | 2026-09-24 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
140 | 70461604 | HS-TEV | 0016555297 | EV153B240926 | EV153B240926 | AC05 |  | 2026-09-24 | 11LHM/A | 0010 | RH WING SLAT NUMBER 7 O/BSEAL TORN OFF. | TECO | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  | 2026-09-25 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
141 | 70461604 | HS-TEV | 0016403818 |  | 2105137819 | AC01 |  | 2026-09-07 | 11LQ/IA | 0010 | INSPECTION OF ALL APU COMPARTMENT. | TECO | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | FLOOR_TAIL | BKK_H | DVI | A330.MPD.491300-01-1 | 2026-09-09 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
142 | 70461604 | HS-TEV | 0016404076 |  | 2105138058 | AC01 |  | 2026-09-10 | 11LQ/IA | 0010 | DET OUT WING LEAD EDGE BOT RIB 1-9 (LH) | TECO | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | WING_LEADING EDGE | BKK_H | DET | A330.MPD.574110-02-10 | 2026-09-12 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
143 | 70461604 | HS-TEV | 0016404413 |  | 2105138360 | AC01 |  | 2026-09-07 | 11LQ/IA | 0010 | INSPECTION OF APU SUSPENSION SYSTEM. | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | FLOOR_TAIL | BKK_H | GVI | A330.MPD.491200-01-1 | 2026-09-09 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
144 | 70461604 | HS-TEV | 0016403974 |  | 2105137966 | AC01 |  | 2026-08-25 | 11LQ/IA | 0010 | INSP OF MLG AXLE SLEEVES # LH | TECO | H/26-TEV-X0C10-BLOK-I-N | 2 | DCA Appr. Req. 2 | FLOOR_LANDING GEAR | BKK_H | DET | A330.MPD.324000-19-1 | 2026-08-25 | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
145 | 70461604 | HS-TEV | 0016403975 |  | 2105137967 | AC01 |  | 2026-08-25 | 11LQ/IA | 0010 | INSP OF MLG AXLE SLEEVES # RH | TECO | H/26-TEV-X0C10-BLOK-I-N | 2 | DCA Appr. Req. 2 | FLOOR_LANDING GEAR | BKK_H | DET | A330.MPD.324000-19-1 | 2026-08-25 | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
146 | 70461604 | HS-TEV | 0016404166 |  | 2105138123 | AC01 |  | 2026-09-07 | 11LHM/A | 0010 | OPEN LDG DOORS | TECO | H/26-TEV-X0C10-BLOK-I-N |  |  | FLOOR_LANDING GEAR | BKK_H | INS | A330.OPR.001ACA16 | 2026-09-09 | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
147 | 70461604 | HS-TEV | 0016404167 |  | 2105138124 | AC01 |  | 2026-09-07 | 11LHM/A | 0010 | OPEN NLG DOORS | TECO | H/26-TEV-X0C10-BLOK-I-N |  |  | FLOOR_LANDING GEAR | BKK_H | INS | A330.OPR.001ACA16 | 2026-09-09 | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
148 | 70461604 | HS-TEV | 0016404168 |  | 2105138125 | AC01 |  | 2026-09-24 | 11LHM/A | 0010 | EXTENSION OF FLAPS AND SAFETY | TECO | H/26-TEV-X0C10-BLOK-I-N |  |  | WING_TRAILING EDGE | BKK_H | INS | A330.OPR.001ACA17 | 2026-09-25 | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
149 | 70461604 | HS-TEV | 0016404169 |  | 2105138126 | AC01 |  | 2026-09-24 | 11LHM/A | 0010 | EXTENSION SPOILER AND SAFETY | TECO | H/26-TEV-X0C10-BLOK-I-N |  |  | WING_TRAILING EDGE | BKK_H | INS | A330.OPR.001ACA17 | 2026-09-15 | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
150 | 70461604 | HS-TEV | 0016404331 |  | 2105138280 | AC01 |  | 2026-08-26 | 11LHM/C | 0010 | RMV - DECORATIVE COVER TO GET THE ACCESS | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | CABIN_DOOR | BKK_H | REM | A330.MPD.521000-07-1 | 2026-08-26 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
151 | 70461604 | HS-TEV | 0016404400 |  | 2105138347 | AC01 |  | 2026-09-07 | 11LHM/C | 0010 | OPC-DOOR LATCHING IN FULLY OPEN POSITION | TECO | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | CABIN_DOOR | BKK_H | OPC | A330.MPD.521000-03-1 | 2026-08-26 | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
152 | 70461604 | HS-TEV | 0016404402 |  | 2105138349 | AC01 |  | 2026-08-26 | 11LHM/C | 0010 | FUC-EMERG EXIT DOORS LOCKING MECHANISM | TECO | H/26-TEV-X0C10-BLOK-0-6 | 1 | DCA Appr. Req. 1 | CABIN_DOOR | BKK_H | FUC | A330.MPD.522200-02-1 | 2026-09-08 | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
153 | 70461604 | HS-TEV | 0016404403 |  | 2105138350 | AC01 |  | 2026-08-26 | 11LHM/C | 0010 | OPC - ALL PAX/CREW DOORS | TECO | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | CABIN_DOOR | BKK_H | OPC | A330.MPD.521000-02-1 | 2026-09-09 | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
154 | 70461604 | HS-TEV | 0016404517 |  | 2105138464 | AC01 |  | 2026-09-30 | 11LHM/A | 0010 | [RHW-INSP CRUISE ROLLER,FLAP TRACK,ETC] | TECO | H/26-TEV-X0C10-BLOK-0-3 | 2 | DCA Appr. Req. 2 | WING_TRAILING EDGE | BKK_H | DVI | A330.MPD.275400-03-1 | 2026-09-30 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
155 | 70461604 | HS-TEV | 0016281810 | 1103150248 | 2105101982 | AC02 |  | 2026-09-24 | 11LHM/C | 0020 | G/26-012:EMERG EQUIPMENT RFID REGISTRATI | TECO | H/26-TEV-X0C10-MOD -G-C | 4 | TG Appr. Req. 4 | CABIN_ALL CABIN | BKK_H | REP | A330.ED.BKKJA-G/26-012 | 2026-09-25 | 2026-08-22 | 00:00:00 | 2026-09-02 | 00:00:00
156 | 70461604 | HS-TEV | 0016403890 |  | 2105137890 | AC01 |  | 2026-09-24 | 11NDT | 0010 | SDI LHW OUTERWING REAR SPAR FWD FACE | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | WING_FUEL | BKK_H | SDI | A330.MPD.572052-03-7 | 2026-09-24 | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
157 | 70461604 | HS-TEV | 0016403891 |  | 2105137890 | AC01 |  | 2026-09-24 | 11NDT | 0020 | SDI LHW OUTERWING REAR SPAR FWD FACE | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | WING_FUEL | BKK_H | SDI | A330.MPD.572052-03-7 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
158 | 70461604 | HS-TEV | 0016403892 |  | 2105137890 | AC01 |  | 2026-09-24 | 11NDT | 0030 | SDI LHW OUTERWING REAR SPAR FWD FACE | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | WING_FUEL | BKK_H | SDI | A330.MPD.572052-03-7 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
159 | 70461604 | HS-TEV | 0016403898 |  | 2105137896 | AC01 |  | 2026-09-24 | 11NDT | 0010 | SDI RHW OUTERWING REAR SPAR FWD FACE | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | WING_FUEL | BKK_H | SDI | A330.MPD.572052-03-4,-5,-7 | 2026-09-24 | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
160 | 70461604 | HS-TEV | 0016403899 |  | 2105137896 | AC01 |  | 2026-09-24 | 11NDT | 0020 | SDI RHW OUTERWING REAR SPAR FWD FACE | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | WING_FUEL | BKK_H | SDI | A330.MPD.572052-03-4,-5,-7 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
161 | 70461604 | HS-TEV | 0016403900 |  | 2105137896 | AC01 |  | 2026-09-24 | 11NDT | 0030 | SDI RHW OUTERWING REAR SPAR FWD FACE | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | WING_FUEL | BKK_H | SDI | A330.MPD.572052-03-4,-5,-7 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
162 | 70461604 | HS-TEV | 0016403969 |  | 2105137961 | AC01 |  | 2026-09-09 | 11LQ/IA | 0010 | INSP NACELLE/PYLON DRAIN (RR)#RH | TECO | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | WING_ENGINE | BKK_H | DET | A330.MPD.545100-07-1,545100-10-1 | 2026-09-08 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
163 | 70461604 | HS-TEV | 0016403968 |  | 2105137960 | AC01 |  | 2026-09-09 | 11LQ/IA | 0010 | INSP NACELLE/PYLON DRAIN (RR)#LH | TECO | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | WING_ENGINE | BKK_H | DET | A330.MPD.545100-07-1,545100-10-1 | 2026-09-09 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
164 | 70461604 | HS-TEV | 0016404450 |  | 2105138397 | AC01 |  | 2026-09-09 | 11LQ/IE | 0010 | [GVI-HARNESS END FITTING(RIB10-TEE):PYL# | TECO | H/26-TEV-X0C10-BLOK-0-3 | 2 | DCA Appr. Req. 2 | WING_ENGINE | BKK_H | GVI | A330.MPD.200004-01-1 | 2026-09-08 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
165 | 70461604 | HS-TEV | 0016404501 |  | 2105138448 | AC01 |  | 2026-09-24 | 11LHM/A | 0010 | JOB SETUP:INSP FIXED L/E PLATE AND STRAP | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | WING_LEADING EDGE | BKK_H | REM | A330.MPD.574109-02-3 | 2026-09-24 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
166 | 70461604 | HS-TEV | 0016404572 |  | 2105138518 | AC01 |  | 2026-09-10 | 11LHM/A | 0010 | APU PRESERVATION. | TECO | H/26-TEV-X0C10-BLOK-I-N |  |  | FLOOR_TAIL | BKK_H | INS | A330.OPR.4900000101-TG01 | 2026-09-10 | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
167 | 70461604 | HS-TEV | 0016404573 |  | 2105138518 | AC01 |  | 2026-09-10 | 11LHM/A | 0020 | APU PRESERVATION. | TECO | H/26-TEV-X0C10-BLOK-I-N |  |  | FLOOR_TAIL | BKK_H | INS | A330.OPR.4900000101-TG01 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
168 | 70461604 | HS-TEV | 0016555598 | 1103188320 | 2105163309 | AC02 |  | 2026-09-25 | 11LHM/E | 0010 | OPC-LOW FREQUENCY UNDERWATER LOCATOR | TECO | H/26-TEV-X0C10-NONR | 2 | DCA Appr. Req. 2 | IERA_FLOOR | BKK_H | OPC | A330.MPD.256536-01-1 | 2026-09-25 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
169 | 70461604 | HS-TEV | 0016495229 | 1103188320 | 2105163309 | AC02 |  | 2026-09-25 | 11LHM/E | 0030 | OPC-LOW FREQUENCY UNDERWATER LOCATOR | TECO | H/26-TEV-X0C10-NONR | 2 | DCA Appr. Req. 2 | IERA_FLOOR | BKK_H | OPC | A330.MPD.256536-01-1 |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
170 | 70461604 | HS-TEV | 0016513146 | EV018F280826 | EV018F280826 | AC05 |  | 2026-09-09 | BKK_L | 0010 | REMOVE RH PITCH PRIMMER | TECO | H/26-TEV-X0C10-NONR |  |  |  | BKK_L | REP |  | 2026-09-23 | 2026-08-28 | 00:00:00 | 2026-08-28 | 00:00:00
171 | 70461604 | HS-TEV | 0016549075 | EV143B210926 | EV143B210926 | AC05 |  | 2026-09-23 | 11LHM/A | 0010 | INSPECTION FOUND BRAKE NO.3 HEAT SHEILD | TECO | H/26-TEV-X0C10-NONR |  |  |  | 11LHM/A | REP |  | 2026-09-21 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
172 | 70461604 | HS-TEV | 0016550613 | EV144B220926 | EV144B220926 | AC05 |  | 2026-09-24 | 11LHM/A | 0010 | MAIN WHEEL NO.1 BRAKE PISTON HYDRAULIC L | TECO | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  | 2026-09-22 | 2026-08-24 | 00:00:00 | 2026-09-22 | 19:00:00
173 | 70461604 | HS-TEV | 0016550634 | EV145B220926 | EV145B220926 | AC05 |  | 2026-09-24 | 11LQ/IA | 0010 | MAIN WHEEL NO.2 BRAKE ASSY HEAT SHIELD B | TECO | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  | 2026-09-22 | 2026-08-24 | 00:00:00 | 2026-09-22 | 19:00:00
174 | 70461604 | HS-TEV | 0016404189 |  | 2105138146 | AC01 | EWIS | 2026-09-09 | 11LQ/IA | 0010 | INSPECTION OF NOSE GEAR WELL | TECO | H/26-TEV-X0C10-BLOK-I-N | 2 | DCA Appr. Req. 2 | FLOOR_LANDING GEAR | BKK_H | GVI | A330.MPD.ZL-123-01-1 |  | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
175 | 70461604 | HS-TEV | 0016402772 |  | 2105137753 | AC01 | EWIS | 2026-09-09 | 11LQ/IA | 0010 | GVI RH MAIN LANDING GEAR WELL | TECO | H/26-TEV-X0C10-BLOK-0-2 |  |  | FLOOR_LANDING GEAR | BKK_H | INS | A330.MPD.ZL-571-01-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
176 | 70461604 | HS-TEV | 0016403783 |  | 2105137784 | AC01 |  | 2026-09-23 | 11LHM/A | 0010 | CLOSE-UP FOR GVI LH CENTER T/E FIXED | TECO | H/26-TEV-X0C10-BLOK-0-5 |  |  | WING_TRAILING EDGE | BKK_H | RES | A330.MPD.ZL-574-01-1 |  | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
177 | 70461604 | HS-TEV | 0016403784 |  | 2105137785 | AC01 | EWIS | 2026-09-23 | 11LHM/A | 0030 | CLOSE-UP FOR GVI RH CENTER T/E FIXED | TECO | H/26-TEV-X0C10-BLOK-0-5 |  |  | WING_TRAILING EDGE | BKK_H | RES | A330.MPD.ZL-574-01-1 |  | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
178 | 70461604 | HS-TEV | 0016403790 |  | 2105137791 | AC01 |  | 2026-09-23 | 11LHM/A | 0010 | CLOSE-UP FOR GVI RH OUTER T/E FIXED | TECO | H/26-TEV-X0C10-BLOK-0-5 |  |  | WING_TRAILING EDGE | BKK_H | RES | A330.MPD.ZL-575-01-1 |  | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
179 | 70461604 | HS-TEV | 0016403791 |  | 2105137792 | AC01 |  | 2026-09-11 | 11LHM/A | 0010 | JOB SET-UP GVI LH INBOARD AILERON | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | WING_TRAILING EDGE | BKK_H | REM | A330.MPD.ZL-591-01-1 |  | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
180 | 70461604 | HS-TEV | 0016403792 |  | 2105137793 | AC01 |  | 2026-09-15 | 11LHM/A | 0010 | JOB SET-UP GVI RH INBOARD AILERON | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | WING_TRAILING EDGE | BKK_H | REM | A330.MPD.ZL-591-01-1 |  | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
181 | 70461604 | HS-TEV | 0016403795 |  | 2105137796 | AC01 |  | 2026-09-15 | 11LHM/A | 0010 | CLOSE-UP GVI LH INBOARD AILERON | TECO | H/26-TEV-X0C10-BLOK-0-5 |  |  | WING_TRAILING EDGE | BKK_H | RES | A330.MPD.ZL-591-01-1 |  | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
182 | 70461604 | HS-TEV | 0016403796 |  | 2105137797 | AC01 |  | 2026-09-15 | 11LHM/A | 0030 | CLOSE-UP GVI RH INBOARD AILERON | TECO | H/26-TEV-X0C10-BLOK-0-5 |  |  | WING_TRAILING EDGE | BKK_H | RES | A330.MPD.ZL-591-01-1 |  | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
183 | 70461604 | HS-TEV | 0016403797 |  | 2105137798 | AC01 |  | 2026-09-11 | 11LHM/A | 0010 | JOB SET-UP GVI LH OUTBOARD AILERON | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | WING_TRAILING EDGE | BKK_H | REM | A330.MPD.ZL-592-01-1 |  | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
184 | 70461604 | HS-TEV | 0016403799 |  | 2105137800 | AC01 | EWIS | 2026-09-15 | 11LQ/IA | 0010 | GVI LH OUTBOARD AILERON | TECO | H/26-TEV-X0C10-BLOK-0-2 |  |  | WING_TRAILING EDGE | BKK_H | GVI | A330.MPD.ZL-592-01-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
185 | 70461604 | HS-TEV | 0016403800 |  | 2105137801 | AC01 | EWIS | 2026-09-15 | 11LQ/IA | 0010 | GVI RH OUTBOARD AILERON | TECO | H/26-TEV-X0C10-BLOK-0-2 |  |  | WING_TRAILING EDGE | BKK_H | GVI | A330.MPD.ZL-592-01-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
186 | 70461604 | HS-TEV | 0016403806 |  | 2105137807 | AC01 |  | 2026-08-24 | 11LHM/E | 0010 | CHECK OF DMC OUTPUT CIRCUITS TO FWC'S | TECO | H/26-TEV-X0C10-BLOK-0-6 |  |  | IERA_ALL IERA | BKK_H | INS | A330.MPD.315000-02-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
187 | 70461604 | HS-TEV | 0016403810 |  | 2105137811 | AC01 |  | 2026-08-24 | 11LHM/E | 0010 | OPC IFEC SMOKE DET BY MCDU | TECO | H/26-TEV-X0C10-BLOK-0-6 | 1 | DCA Appr. Req. 1 | IERA_CABIN | BKK_H | OPC | A330.MPD.261800-12-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
188 | 70461604 | HS-TEV | 0016403812 |  | 2105137813 | AC01 |  | 2026-08-24 | 11LHM/E | 0010 | OPC ELECTRONIC INSTRUMENT SYSTEM 2 | TECO | H/26-TEV-X0C10-BLOK-0-6 | 1 | DCA Appr. Req. 1 | IERA_CABIN | BKK_H | OPC | A330.MPD.316001-04-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
189 | 70461604 | HS-TEV | 0016403817 |  | 2105137818 | AC01 |  | 2026-08-25 | 11LHM/E | 0010 | OPC-APU FUEL PUMP SYSTEM | TECO | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | IERA_FLOOR | BKK_H | OPC | A330.MPD.282200-12-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
190 | 70461604 | HS-TEV | 0016403848 |  | 2105137849 | AC01 |  | 2026-09-23 | 11LHM/A | 0010 | CLOSE-UP FOR DVI T/E SKIN RIB8-12 ,LH | TECO | H/26-TEV-X0C10-BLOK-0-5 |  |  | WING_TRAILING EDGE | BKK_H | RES | A330.MPD.575025-01-5;575025-01-7 |  | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
191 | 70461604 | HS-TEV | 0016403860 |  | 2105137861 | AC01 |  | 2026-08-24 | 11LHM/E | 0010 | OPC PFTU-TRIM 2 NORMAL/BACK-UPP | TECO | H/26-TEV-X0C10-BLOK-0-6 |  |  | IERA_FLOOR | BKK_H | OP | A330.MPD.279000-20-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
192 | 70461604 | HS-TEV | 0016403863 |  | 2105137864 | AC01 |  | 2026-08-24 | 11LHM/E | 0010 | OPC the back up speed scale display | TECO | H/26-TEV-X0C10-BLOK-0-7 |  |  | IERA_CABIN | BKK_H | OP | A330.MPD.341300-05-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
193 | 70461604 | HS-TEV | 0016403867 |  | 2105137867 | AC01 |  | 2026-09-03 | 11LHM/E | 0010 | CONNECT-AIRCRAFT STATIC GROUNDING | TECO | H/26-TEV-X0C10-BLOK-I-N |  |  | IERA_FLOOR | BKK_H | SVC | A330.OPR.CONNECT-AIRCRAF |  | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
194 | 70461604 | HS-TEV | 0016403906 |  | 2105137902 | AC01 |  | 2026-08-24 | 11LHM/E | 0010 | OPC OF BATTERY POWERED CIDS | TECO | H/26-TEV-X0C10-BLOK-0-6 | 1 | DCA Appr. Req. 1 | IERA_ALL IERA | BKK_H | OPC | A330.MPD.237300-10-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
195 | 70461604 | HS-TEV | 0016403940 |  | 2105137934 | AC01 |  | 2026-09-04 | 11LHM/E | 0010 | OPC-AUTO FIXED ELT (HS-TEN-U, TBA-G) | TECO | H/26-TEV-X0C10-BLOK-0-6 | 1 | DCA Appr. Req. 1 | IERA_ALL IERA | BKK_H | OPC | A330.MPD.256535-01-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
196 | 70461604 | HS-TEV | 0016403951 |  | 2105137945 | AC01 |  | 2026-09-24 | 11CLEAN | 0010 | CLEAN-(IFES) PICCOLO TUBES | TECO | H/26-TEV-X0C10-BLOK-0-4 |  |  | CABIN_INTERIOR | BKK_H | CLN | A330.MPD.261800-13-1 |  | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
197 | 70461604 | HS-TEV | 0016403952 |  | 2105137946 | AC01 |  | 2026-09-24 | 11LHM/A | 0010 | RMV-SMOKE DETECT OF AIR-EX DUCT OF IFEC | TECO | H/26-TEV-X0C10-BLOK-0-3 |  |  | CABIN_INTERIOR | BKK_H | REM | A330.MPD.261800-13-1 |  | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
198 | 70461604 | HS-TEV | 0016403955 |  | 2105137949 | AC01 |  | 2026-08-24 | 11LHM/E | 0010 | FUC IFES SMOKE DETEC AND DIS MCDU | TECO | H/26-TEV-X0C10-BLOK-0-6 |  |  | IERA_CABIN | BKK_H | OPC | A330.MPD.261800-13-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
199 | 70461604 | HS-TEV | 0016403979 |  | 2105137971 | AC01 |  | 2026-09-24 | 11LHM/E | 0010 | FUC HEATER INSUL RESISTANCE PITOT PROBES | TECO | H/26-TEV-X0C10-BLOK-0-4 |  |  | IERA_FLOOR | BKK_H | INS | A330.MPD.303100-01-1 |  | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
200 | 70461604 | HS-TEV | 0016404007 |  | 2105137997 | AC01 |  | 2026-09-04 | 11E | 0010 | INSPECTION OF EXPIRATION DATE OF C. OF A | TECO | H/26-TEV-X0C10-BLOK-I-N |  |  | ALL_ALL GRP | BKK_H | INS | PP.OPR.INITIAL_FINAL |  | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
201 | 70461604 | HS-TEV | 0016404043 |  | 2105138032 | AC01 |  | 2026-09-09 | 11LQ/IE | 0010 | GVI OF TR1 AND TR2 | TECO | H/26-TEV-X0C10-BLOK-0-3 | 2 | DCA Appr. Req. 2 | IERA_IERA_FLOOR | BKK_H | GVI | A330.MPD.243000-08-1 |  | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
202 | 70461604 | HS-TEV | 0016404044 |  | 2105138033 | AC01 |  | 2026-09-09 | 11LQ/IE | 0010 | GVI OF APU TR | TECO | H/26-TEV-X0C10-BLOK-0-3 | 2 | DCA Appr. Req. 2 | IERA_IERA_FLOOR | BKK_H | GVI | A330.MPD.243000-09-1 |  | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
203 | 70461604 | HS-TEV | 0016404067 |  | 2105138051 | AC01 |  | 2026-09-12 | 11LHM/A | 0010 | DET OUTER WING BOTTOM SKIN RHW | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | WING_ALL WING | BKK_H | DET | A330.MPD.572023-02-15 |  | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
204 | 70461604 | HS-TEV | 0016404084 |  | 2105138065 | AC01 |  | 2026-09-24 | 11LHM/A | 0010 | GVI AREA BELOW THE SATCOM ANTENNA RADOME | TECO | H/26-TEV-X0C10-BLOK-0-3 | 2 | DCA Appr. Req. 2 | FLOOR_FUSELAGE | BKK_H | GVI | A330.MPD.ZL-200-04-1 |  | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
205 | 70461604 | HS-TEV | 0016404111 |  | 2105138086 | AC01 |  | 2026-09-09 | 11LHM/E | 0010 | DETAILED INSPECTION OF PANASONIC EXPHONE | TECO | H/26-TEV-X0C10-BLOK-0-3 | 4 | TG Appr. Req. 4 | IERA_CABIN | BKK_H | INS | A330.MPD.233600-91-1-TG01 |  | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
206 | 70461604 | HS-TEV | 0016404162 |  | 2105138120 | AC01 |  | 2026-09-01 | 11LHM/C | 0010 | REMOVE FLASH LIGHTS AND LIFE VESTS | TECO | H/26-TEV-X0C10-BLOK-I-N |  |  | CABIN_INTERIOR | BKK_H | INS | A330.OPR.001ACA09 |  | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
207 | 70461604 | HS-TEV | 0016404179 |  | 2105138136 | AC01 |  | 2026-09-08 | 11LQ/IA | 0010 | CHK APU HOURMETER | TECO | H/26-TEV-X0C10-BLOK-I-N |  |  | FLOOR_TAIL | BKK_H | INS | A330.OPR.4973000101-TG01 |  | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
208 | 70461604 | HS-TEV | 0016404180 |  | 2105138137 | AC01 |  | 2026-09-03 | 11LHM/E | 0010 | DEACT ELEC SOCKETS | TECO | H/26-TEV-X0C10-BLOK-I-N |  |  | IERA_CABIN | BKK_H | INS | A330.OPR.001ACA71 |  | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
209 | 70461604 | HS-TEV | 0016404183 |  | 2105138140 | AC01 |  | 2026-09-10 | 11LHM/A | 0010 | OPEN-RADOME ZONE 110 | TECO | H/26-TEV-X0C10-BLOK-I-N |  |  | FLOOR_FUSELAGE | BKK_H | GVI | A330.MPD.ZL-110-01-1 |  | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
210 | 70461604 | HS-TEV | 0016404184 |  | 2105138141 | AC01 |  | 2026-09-15 | 11LHM/A | 0010 | CLOSE-RADOME ZONE 110 | TECO | H/26-TEV-X0C10-BLOK-0-5 |  |  | FLOOR_FUSELAGE | BKK_H | GVI | A330.MPD.ZL-110-01-1 |  | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
211 | 70461604 | HS-TEV | 0016404198 |  | 2105138154 | AC01 |  | 2026-09-09 | 11LHM/A | 0010 | REM ACCESS PANEL ABOUT 131 132 | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | FLOOR_FWD COMPT | BKK_H | REM | A330.MPD.262300-01-1 |  | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
212 | 70461604 | HS-TEV | 0016404206 |  | 2105138162 | AC01 |  | 2026-09-24 | 11LHM/E | 0010 | OPC-AVIONICS COMPT SMOKE DETECTORS | TECO | H/26-TEV-X0C10-BLOK-0-4 |  |  | IERA_FLOOR | BKK_H | OPC | A330.MPD.261500-02-1 |  | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
213 | 70461604 | HS-TEV | 0016404217 |  | 2105138168 | AC01 |  | 2026-09-09 | 11LHM/A | 0010 | PREPARE-FOR NDT FWD CARGO ATTACH FITTING | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | FLOOR_FWD COMPT | BKK_H | SDI | A330.MPD.523105-01-1,523105-01-2 |  | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
214 | 70461604 | HS-TEV | 0016404278 |  | 2105138227 | AC01 |  | 2026-09-13 | 11LQ/IA | 0010 | INSP-AFT CARGO DOOR HINGE ARM | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | FLOOR_AFT COMPT | BKK_H | DVI | A330.MPD.523204-01-1 |  | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
215 | 70461604 | HS-TEV | 0016404283 |  | 2105138232 | AC01 |  | 2026-09-09 | 11LHM/A | 0010 | INST-BULK CARGO DOOR LINING | TECO | H/26-TEV-X0C10-BLOK-0-5 |  |  | FLOOR_AFT COMPT | BKK_H | DVI | A330.MPD.523300-03-1;523302-01-1 |  | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
216 | 70461604 | HS-TEV | 0016404289 |  | 2105138238 | AC01 |  | 2026-09-09 | 11CLEAN | 0010 | CLEAN-BULK CARGO DOOR CUTOUT | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | FLOOR_AFT COMPT | BKK_H | CLN | A330.MPD.534149-01-1 |  | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
217 | 70461604 | HS-TEV | 0016404293 |  | 2105138242 | AC01 |  | 2026-09-09 | 11LHM/A | 0010 | PREPARE FOR NDT AFT CARGO ATTACH FITTING | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | FLOOR_AFT COMPT | BKK_H | SDI | A330.MPD.523205-01-1,523205-01-2 |  | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
218 | 70461604 | HS-TEV | 0016404308 |  | 2105138257 | AC01 |  | 2026-09-12 | 11CLEAN | 0010 | CLEANING - LAVATORY AREAS. | TECO | H/26-TEV-X0C10-BLOK-0-2 | 4 | TG Appr. Req. 4 | CABIN_LAVATORY | BKK_H | RES | A330.MPD.2500000101-TG01 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
219 | 70461604 | HS-TEV | 0016404316 |  | 2105138265 | AC01 |  | 2026-09-23 | 11LHM/C | 0010 | RMV - EMERG EXIT DOOR FRAME LININGS | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | CABIN_DOOR | BKK_H | INS | A330.OPR.200ACD47 |  | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
220 | 70461604 | HS-TEV | 0016404322 |  | 2105138271 | AC01 |  | 2026-09-30 | 11LQ/IC | 0010 | INSP - DADO PANELS | TECO | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | CABIN_INTERIOR | BKK_H | VCK | A330.MPD.252344-02-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
221 | 70461604 | HS-TEV | 0016404326 |  | 2105138275 | AC01 | EWIS | 2026-09-30 | 11LQ/IC | 0010 | ZONAL INSP-FWD PAX/CREW DOOR. | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | CABIN_DOOR | BKK_H | GVI | A330.MPD.ZL-831-01-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
222 | 70461604 | HS-TEV | 0016404327 |  | 2105138276 | AC01 | EWIS | 2026-09-30 | 11LQ/IC | 0010 | ZONAL INSP-MID PAX/CREW DOOR | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | CABIN_DOOR | BKK_H | GVI | A330.MPD.ZL-832-01-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
223 | 70461604 | HS-TEV | 0016404328 |  | 2105138277 | AC01 | EWIS | 2026-09-30 | 11LQ/IC | 0010 | ZONAL INSP-AFT PAX/CREW DOOR | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | CABIN_DOOR | BKK_H | GVI | A330.MPD.ZL-833-01-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
224 | 70461604 | HS-TEV | 0016404329 |  | 2105138278 | AC01 | EWIS | 2026-09-30 | 11LQ/IC | 0010 | ZONAL INSP-EMERG EXIT DOOR | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | CABIN_DOOR | BKK_H | GVI | A330.MPD.ZL-834-01-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
225 | 70461604 | HS-TEV | 0016404341 |  | 2105138290 | AC01 |  | 2026-08-24 | 11LHM/E | 0010 | OPC OF CABIN SIGN VIA MCDU | TECO | H/26-TEV-X0C10-BLOK-0-6 |  |  | IERA_CABIN | BKK_H | INS | A330.OPR.209ACT09 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
226 | 70461604 | HS-TEV | 0016404345 |  | 2105138294 | AC01 |  | 2026-09-01 | 11LHM/C | 0010 | INST - COCKPIT SIDEWALL PANELS | TECO | H/26-TEV-X0C10-BLOK-0-5 |  |  | CABIN_COCKPIT | BKK_H | GVI | A330.MPD.ZL-211-01-1 |  | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
227 | 70461604 | HS-TEV | 0016404347 |  | 2105138296 | AC01 |  | 2026-09-01 | 11LHM/C | 0010 | RMV - PANELS AT COCKPIT DOOR | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | CABIN_COCKPIT | BKK_H | DVI | A330.MPD.525111-02-1 |  | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
228 | 70461604 | HS-TEV | 0016404348 |  | 2105138297 | AC01 |  | 2026-09-01 | 11LHM/C | 0010 | INST - PANELS AT COCKPIT DOOR | TECO | H/26-TEV-X0C10-BLOK-0-5 |  |  | CABIN_COCKPIT | BKK_H | DVI | A330.MPD.525111-02-1 |  | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
229 | 70461604 | HS-TEV | 0016404351 |  | 2105138300 | AC01 |  | 2026-09-01 | 11LQ/IC | 0010 | OPC-COCKPIT DOOR | TECO | H/26-TEV-X0C10-BLOK-0-7 | 2 | DCA Appr. Req. 2 | CABIN_COCKPIT | BKK_H | OPC | A330.MPD.525111-03-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
230 | 70461604 | HS-TEV | 0016404356 |  | 2105138305 | AC01 |  | 2026-09-24 | 11LHM/E | 0010 | INSTALL OF TEMPERATURE SENSOR 001-049 | TECO | H/26-TEV-X0C10-BLOK-0-4 |  |  | IERA_CABIN | BKK_H | RES | A330.MPD.216000-03-1 |  | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
231 | 70461604 | HS-TEV | 0016404357 |  | 2105138306 | AC01 |  | 2026-08-24 | 11LHM/E | 0010 | TEST OF COCKPIT & CABIN TEMP CONTROL | TECO | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | IERA_CABIN | BKK_H | OPC | A330.MPD.216000-03-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
232 | 70461604 | HS-TEV | 0016404359 |  | 2105138308 | AC01 |  | 2026-09-24 | 11LHM/E | 0010 | INSTALL OF TEMPERATURE SENSOR | TECO | H/26-TEV-X0C10-BLOK-0-4 |  |  | IERA_CABIN | BKK_H | RES | A330.MPD.216000-03-1 |  | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
233 | 70461604 | HS-TEV | 0016404364 |  | 2105138311 | AC01 |  | 2026-09-07 | 11LHM/E | 0010 | OPC-CVR INCLUDE RECORDING ON 4 CHANNELS | TECO | H/26-TEV-X0C10-BLOK-0-7 | 2 | DCA Appr. Req. 2 | IERA_CABIN | BKK_H | OPC | A330.MPD.237100-01-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
234 | 70461604 | HS-TEV | 0016404365 |  | 2105138312 | AC01 |  | 2026-08-24 | 11LHM/E | 0010 | OPC-LOUDSPEAKERS VIA MCDU | TECO | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | IERA_CABIN | BKK_H | OPC | A330.MPD.237300-03-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
235 | 70461604 | HS-TEV | 0016404367 |  | 2105138314 | AC01 |  | 2026-08-24 | 11LHM/E | 0010 | OPC-EMERGENCY GCU FROM CMS | TECO | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | IERA_CABIN | BKK_H | OPC | A330.MPD.242400-03-2 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
236 | 70461604 | HS-TEV | 0016404368 |  | 2105138315 | AC01 |  | 2026-08-24 | 11LHM/E | 0010 | OPC-AC ESSENTIAL GENERATION SWITCHING | TECO | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | IERA_CABIN | BKK_H | OPC | A330.MPD.242500-01-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
237 | 70461604 | HS-TEV | 0016404369 |  | 2105138316 | AC01 |  | 2026-08-24 | 11LHM/E | 0010 | OPC-DC MAIN GENERATION SWITCHING | TECO | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | IERA_CABIN | BKK_H | OPC | A330.MPD.243500-01-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
238 | 70461604 | HS-TEV | 0016404370 |  | 2105138317 | AC01 |  | 2026-08-25 | 11LHM/E | 0010 | OPC-DC ESSENTIAL GENERATION SWITCHING | TECO | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | IERA_CABIN | BKK_H | OPC | A330.MPD.243500-02-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
239 | 70461604 | HS-TEV | 0016404371 |  | 2105138318 | AC01 |  | 2026-08-24 | 11LHM/E | 0010 | OPC-AC MAIN DISTR COMMERCIAL LOAD SHED | TECO | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | IERA_CABIN | BKK_H | OPC | A330.MPD.245000-01-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
240 | 70461604 | HS-TEV | 0016404372 |  | 2105138319 | AC01 |  | 2026-08-25 | 11LHM/E | 0010 | OPC-COOLING EFF DET OF AVIONIC EQPT VENT | TECO | H/26-TEV-X0C10-BLOK-0-6 | 1 | DCA Appr. Req. 1 | IERA_CABIN | BKK_H | OPC | A330.MPD.212600-04-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
241 | 70461604 | HS-TEV | 0016404373 |  | 2105138320 | AC01 |  | 2026-08-24 | 11LHM/E | 0010 | OPC-LAND RECOVERY CONFIGURATION | TECO | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | IERA_CABIN | BKK_H | OPC | A330.MPD.245000-02-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
242 | 70461604 | HS-TEV | 0016404378 |  | 2105138325 | AC01 |  | 2026-08-24 | 11LHM/E | 0010 | OPC-FCPC 1 & FCSC 1 POWER SUPPLY | TECO | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | IERA_CABIN | BKK_H | OPC | A330.MPD.279000-06-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
243 | 70461604 | HS-TEV | 0016404380 |  | 2105138327 | AC01 |  | 2026-08-24 | 11LHM/E | 0010 | OPC-ATTITUDE/HEADING SWITCHING | TECO | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | IERA_CABIN | BKK_H | OPC | A330.MPD.341400-01-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
244 | 70461604 | HS-TEV | 0016404381 |  | 2105138328 | AC01 |  | 2026-08-24 | 11LHM/E | 0010 | OPC-SIDE STICK TAKEOVER & PRIORITY FUNCT | TECO | H/26-TEV-X0C10-BLOK-0-6 | 1 | DCA Appr. Req. 1 | IERA_CABIN | BKK_H | OPC | A330.MPD.279000-04-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
245 | 70461604 | HS-TEV | 0016404385 |  | 2105138332 | AC01 |  | 2026-08-24 | 11LHM/E | 0010 | OPC-905XP BUSBAR SHEDDING IN EMERG CONFI | TECO | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | IERA_CABIN | BKK_H | OPC | A330.MPD.245000-03-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
246 | 70461604 | HS-TEV | 0016404391 |  | 2105138338 | AC01 |  | 2026-08-24 | 11LHM/E | 0010 | OPC-AIR DATA/INU1,2&3 PWR SUPPLY I EMERG | TECO | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | IERA_CABIN | BKK_H | OPC | A330.MPD.341400-02-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
247 | 70461604 | HS-TEV | 0016404397 |  | 2105138344 | AC01 |  | 2026-08-24 | 11LHM/E | 0010 | OPC-DFDR PLAYBACK DATA VIA MCDU | TECO | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | IERA_CABIN | BKK_H | OPC | A330.MPD.313300-02-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
248 | 70461604 | HS-TEV | 0016404408 |  | 2105138355 | AC01 |  | 2026-09-10 | 11LQ/IA | 0010 | INSP OF APU FIRE XTING PIPING. | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | FLOOR_TAIL | BKK_H | DVI | A330.MPD.262200-04-1 |  | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
249 | 70461604 | HS-TEV | 0016404409 |  | 2105138356 | AC01 |  | 2026-09-09 | 11LQ/IA | 0010 | INSP H.STAB LATERAL BOX BTTM. SKIN LH/RH | TECO | H/26-TEV-X0C10-BLOK-0-3 | 2 | DCA Appr. Req. 2 | FLOOR_TAIL | BKK_H | GVI | A330.MPD.551027-01-2 |  | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
250 | 70461604 | HS-TEV | 0016404423 |  | 2105138370 | AC01 | EWIS | 2026-09-09 | 11LQ/IA | 0010 | INSPECTION OF RUDDER (EWIS). | TECO | H/26-TEV-X0C10-BLOK-0-1 | 2 | DCA Appr. Req. 2 | FLOOR_TAIL | BKK_H | GVI | A330.MPD.ZL-326-01-1 |  | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
251 | 70461604 | HS-TEV | 0016404430 |  | 2105138377 | AC01 |  | 2026-09-09 | 11LHM/A | 0010 | INSP OF THS HYD ACTUATION | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | FLOOR_TAIL | BKK_H | DVI | A330.MPD.274400-06-1 |  | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
252 | 70461604 | HS-TEV | 0016404433 |  | 2105138380 | AC01 | EWIS | 2026-09-24 | 11LQ/IA | 0010 | INSP OF REAR FUSELGE SECTION (EWIS). | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | FLOOR_TAIL | BKK_H | GVI | A330.MPD.ZL-311-01-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
253 | 70461604 | HS-TEV | 0016404443 |  | 2105138390 | AC01 |  | 2026-09-09 | 11LHM/A | 0010 | INSP UPPER FWD PYLON -RR PYLON#1 | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | WING_ENGINE | BKK_H | GVI | A330.MPD.ZL-452-01-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
254 | 70461604 | HS-TEV | 0016404444 |  | 2105138391 | AC01 |  | 2026-09-09 | 11LHM/A | 0010 | INSP UPPER FWD PYLON -RR PYLON#2 | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | WING_ENGINE | BKK_H | GVI | A330.MPD.ZL-452-01-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
255 | 70461604 | HS-TEV | 0016404483 |  | 2105138430 | AC01 |  | 2026-09-30 | 11LHM/A | 0010 | [CLOSING-TRACK FAIRING ACCESS] | TECO | H/26-TEV-X0C10-BLOK-0-7 |  |  | WING_TRAILING EDGE | BKK_H | GVI | A330.MPD.ZL-531-01-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
256 | 70461604 | HS-TEV | 0016404498 |  | 2105138445 | AC01 |  | 2026-09-23 | 11LHM/A | 0010 | CLOSE-UP INSP-WING ICE PROT. COMPONENTS | TECO | H/26-TEV-X0C10-BLOK-0-5 |  |  | WING_LEADING EDGE | BKK_H | RES | A330.MPD.301100-01-1 |  | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
257 | 70461604 | HS-TEV | 0016404504 |  | 2105138451 | AC01 |  | 2026-09-23 | 11LHM/A | 0010 | CLOSE-UP:INSP FIXED L/E PLATE AND STRAP | TECO | H/26-TEV-X0C10-BLOK-0-5 |  |  | WING_LEADING EDGE | BKK_H | RES | A330.MPD.574109-02-3 |  | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
258 | 70461604 | HS-TEV | 0016404509 |  | 2105138456 | AC01 |  | 2026-09-23 | 11LHM/A | 0010 | [LHW-INST OF ACCESS PANELS LOWER T/E] | TECO | H/26-TEV-X0C10-BLOK-0-5 |  |  | WING_TRAILING EDGE | BKK_H | DVI | A330.MPD.275400-02-1 |  | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
259 | 70461604 | HS-TEV | 0016404512 |  | 2105138459 | AC01 |  | 2026-09-23 | 11LHM/A | 0010 | [RHW-INST OF ACCESS PANELS LOWER T/E] | TECO | H/26-TEV-X0C10-BLOK-0-5 |  |  | WING_TRAILING EDGE | BKK_H | DVI | A330.MPD.275400-02-1 |  | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
260 | 70461604 | HS-TEV | 0016404548 |  | 2105138494 | AC01 |  | 2026-09-09 | 11LQ/IE | 0010 | DVI-1LBD1B END FITTING-LH MLG BRAID COND | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | FLOOR_LANDING GEAR | BKK_H | DVI | A330.MPD.200005-01-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
261 | 70461604 | HS-TEV | 0016488362 |  | 2105161340 | AC01 |  | 2026-09-23 | 11LQ/IA | 0010 | DET INTERNAL STRUCTURE TORSION BOX, INCL | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | FLOOR_FWD COMPT | BKK_H | DET | A330.MPD.534154-01-3 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
262 | 70461604 | HS-TEV | 0016488363 |  | 2105161340 | AC01 |  | 2026-09-23 | 11LHM/A | 0020 | DET INTERNAL STRUCTURE TORSION BOX, INCL | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | FLOOR_FWD COMPT | BKK_H | DET | A330.MPD.534154-01-3 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
263 | 70461604 | HS-TEV | 0016537839 | EV140B140926 | EV140B140926 | AC05 |  | 2026-09-16 | 11PAINT | 0010 | INSP FOUND VERTICAL STABILIZER TIP PAINT | TECO | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
264 | 70461604 | HS-TEV | 0016541950 | EV141B160926 | EV141B160926 | AC05 |  | 2026-09-16 | 11LHM/A | 0010 | VOID | TECO | L/26-TEV-LI-MPC-N |  |  |  | BKK_H | REP |  |  | 2026-01-01 | 10:39:00 | 2026-12-31 | 10:39:00
265 | 70461604 | HS-TEV | 0016541951 | EV141B160926 | EV141B160926 | AC05 |  | 2026-09-16 | 11SH | 0020 | VOID | TECO | L/26-TEV-LI-MPC-N |  |  |  | BKK_H | REP |  |  | 2026-01-01 | 10:39:00 | 2026-12-31 | 10:39:00
266 | 70461604 | HS-TEV | 0016541952 | EV141B160926 | EV141B160926 | AC05 |  | 2026-09-16 | 11PAINT | 0030 | VOID | TECO | L/26-TEV-LI-MPC-N |  |  |  | BKK_H | REP |  |  | 2026-01-01 | 10:39:00 | 2026-12-31 | 10:39:00
267 | 70461604 | HS-TEV | 0016541953 | EV141B160926 | EV141B160926 | AC05 |  | 2026-09-16 | 11LHM/A | 0040 | VOID | TECO | L/26-TEV-LI-MPC-N |  |  |  | BKK_H | REP |  |  | 2026-01-01 | 10:39:00 | 2026-12-31 | 10:39:00
268 | 70461604 | HS-TEV | 0016541956 | EV142B160926 | EV142B160926 | AC05 |  | 2026-09-16 | 11PAINT | 0010 | VOID | TECO | L/26-TEV-LI-MPC-N |  |  |  | BKK_H | REP |  |  | 2026-01-01 | 10:51:00 | 2026-12-31 | 10:51:00
269 | 70461604 | HS-TEV | 0016404245 |  | 2105138194 | AC01 |  | 2026-09-24 | 11LHM/A | 0010 | REM -THE PACK TEMPERATURE SENSOR | TECO | H/26-TEV-X0C10-BLOK-0-1 | 2 | DCA Appr. Req. 2 | FLOOR_AIR COND | BKK_H | RES | A330.MPD.215200-01-1 |  | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
270 | 70461604 | HS-TEV | 0016403917 |  | 2105137911 | AC01 |  | 2026-09-23 | 11LHM/C | 0010 | PREPARE FOR INSP TORSION BOX DOOR3. | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | CABIN_INTERIOR | BKK_H | REM | A330.MPD.533198-01-1 |  | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
271 | 70461604 | HS-TEV | 0016403953 |  | 2105137947 | AC01 |  | 2026-09-24 | 11LHM/A | 0010 | INST-SMOKE DETECT OF AIR-EX DUCT OF IFEC | TECO | H/26-TEV-X0C10-BLOK-0-3 |  |  | CABIN_INTERIOR | BKK_H | RES | A330.MPD.261800-13-1 |  | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
272 | 70461604 | HS-TEV | 0016404001 |  | 2105137991 | AC01 |  | 2026-09-10 | 11LHM/A | 0010 | LUB OF ALL SLAT STEADY BEARINGS - RHW | TECO | H/26-TEV-X0C10-BLOK-0-4 | 2 | DCA Appr. Req. 2 | WING_TRAILING EDGE | BKK_H | LUB | A330.MPD.278000-06-1 |  | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
273 | 70461604 | HS-TEV | 0016404117 |  | 2105138091 | AC01 |  | 2026-09-23 | 11LHM/C | 0010 | GVI OF PAX DOOR 1 INTERNAL STRUCTURE | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | CABIN_DOOR | BKK_H | GVI | A330.MPD.521104-02-1 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
274 | 70461604 | HS-TEV | 0016404118 |  | 2105138091 | AC01 |  | 2026-09-23 | 11LHM/C | 0020 | GVI OF PAX DOOR 1 INTERNAL STRUCTURE | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | CABIN_DOOR | BKK_H | GVI | A330.MPD.521104-02-1 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
275 | 70461604 | HS-TEV | 0016404121 |  | 2105138093 | AC01 |  | 2026-09-23 | 11LHM/C | 0010 | GVI OF PAX DOOR 2 INTERNAL STRUCTURE | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | CABIN_DOOR | BKK_H | GVI | A330.MPD.521202-02-1 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
276 | 70461604 | HS-TEV | 0016404122 |  | 2105138093 | AC01 |  | 2026-09-23 | 11LHM/C | 0020 | GVI OF PAX DOOR 2 INTERNAL STRUCTURE | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | CABIN_DOOR | BKK_H | GVI | A330.MPD.521202-02-1 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
277 | 70461604 | HS-TEV | 0016404125 |  | 2105138095 | AC01 |  | 2026-09-23 | 11LHM/C | 0010 | GVI OF PAX DOOR 4 INTERNAL STRUCTURE | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | CABIN_DOOR | BKK_H | GVI | A330.MPD.521302-02-1 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
278 | 70461604 | HS-TEV | 0016404126 |  | 2105138095 | AC01 |  | 2026-09-23 | 11LHM/C | 0020 | GVI OF PAX DOOR 4 INTERNAL STRUCTURE | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | CABIN_DOOR | BKK_H | GVI | A330.MPD.521302-02-1 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
279 | 70461604 | HS-TEV | 0016404145 |  | 2105138107 | AC01 |  | 2026-09-23 | 11LHM/A | 0010 | GVI OF INTERNAL STRUCTURE AROUND DOOR4 | TECO | H/26-TEV-X0C10-BLOK-0-5 | 1 | DCA Appr. Req. 1 | CABIN_DOOR | BKK_H | GVI | A330.MPD.534133-02-1 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
280 | 70461604 | HS-TEV | 0016404146 |  | 2105138107 | AC01 |  | 2026-09-23 | 11LHM/A | 0020 | GVI OF INTERNAL STRUCTURE AROUND DOOR4 | TECO | H/26-TEV-X0C10-BLOK-0-5 | 1 | DCA Appr. Req. 1 | CABIN_DOOR | BKK_H | GVI | A330.MPD.534133-02-1 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
281 | 70461604 | HS-TEV | 0016404147 |  | 2105138107 | AC01 |  | 2026-09-23 | 11LHM/A | 0030 | GVI OF INTERNAL STRUCTURE AROUND DOOR4 | TECO | H/26-TEV-X0C10-BLOK-0-5 | 1 | DCA Appr. Req. 1 | CABIN_DOOR | BKK_H | GVI | A330.MPD.534133-02-1 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
282 | 70461604 | HS-TEV | 0016404182 |  | 2105138139 | AC01 |  | 2026-09-09 | 11LQ/IE | 0010 | GVI HARNESS END FITTING-FR 39 TO 40 2 | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | IERA_FLOOR | BKK_H | GVI | A330.MPD.200003-01-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
283 | 70461604 | HS-TEV | 0016404204 |  | 2105138160 | AC01 |  | 2026-09-09 | 11LHM/E | 0010 | INSTAL-AVIONICS COMPT SMOKE DETECTORS | TECO | H/26-TEV-X0C10-BLOK-0-6 |  |  | IERA_FLOOR | BKK_H | RES | A330.MPD.261500-02-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
284 | 70461604 | HS-TEV | 0016404222 |  | 2105138173 | AC01 |  | 2026-09-09 | 11CLEAN | 0010 | CLEN-FWD CARGO DOOR HINGE ARMS | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | FLOOR_FWD COMPT | BKK_H | CLN | A330.MPD.523104-01-1 |  | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
285 | 70461604 | HS-TEV | 0016404259 |  | 2105138208 | AC01 |  | 2026-09-24 | 11LHM/A | 0010 | INSTL-GROUND CONNECT CHECK VALVE | TECO | H/26-TEV-X0C10-BLOK-0-4 |  |  | FLOOR_AIR COND | BKK_H | RES | A330.MPD.215500-03-1 |  | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
286 | 70461604 | HS-TEV | 0016404281 |  | 2105138230 | AC01 |  | 2026-09-15 | 11LHM/A | 0010 | LUBRICATION OF BULK CGO DOOR | TECO | H/26-TEV-X0C10-BLOK-0-5 | 2 | DCA Appr. Req. 2 | FLOOR_AFT COMPT | BKK_H | LUB | A330.MPD.523300-03-1 |  | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
287 | 70461604 | HS-TEV | 0016402771 |  | 2105137752 | AC01 | EWIS | 2026-09-09 | 11LQ/IA | 0010 | GVI LH MAIN LANDING GEAR WELL | TECO | H/26-TEV-X0C10-BLOK-0-2 |  |  | FLOOR_LANDING GEAR | BKK_H | INS | A330.MPD.ZL-571-01-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
288 | 70461604 | HS-TEV | 0016404031 |  | 2105138021 | AC01 |  | 2026-09-24 | 11LQ/IA | 0010 | GVI of External ELT Antenna | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | FLOOR_FUSELAGE | BKK_H | GVI | A330.MPD.256535-05-1 |  | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
289 | 70461604 | HS-TEV | 0016404086 |  | 2105138067 | AC01 |  | 2026-09-06 | 11LHM/A | 0010 | GVI OUTER FUEL TANK (EWIS) RHW | TECO | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | WING_FUEL | BKK_H | GVI | A330.MPD.ZL-542-03-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
290 | 70461604 | HS-TEV | 0016404203 |  | 2105138159 | AC01 |  | 2026-09-09 | 11LHM/E | 0010 | REMOVE-AVIONICS COMPT SMOKE DETECTORS | TECO | H/26-TEV-X0C10-BLOK-0-3 |  |  | IERA_FLOOR | BKK_H | REM | A330.MPD.261500-02-1 |  | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
291 | 70461604 | HS-TEV | 0016404305 |  | 2105138254 | AC01 |  | 2026-09-24 | 11LQ/IA | 0010 | INSP-ALL DOORS EXTERNAL ZONE-100 | TECO | H/26-TEV-X0C10-BLOK-0-1 | 2 | DCA Appr. Req. 2 | FLOOR_FWD COMPT | BKK_H | GVI | A330.MPD.ZL-800-01-1 |  | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
292 | 70461604 | HS-TEV | 0016404344 |  | 2105138293 | AC01 |  | 2026-09-01 | 11LHM/C | 0010 | RMV - COCKPIT SIDEWALL PANELS | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | CABIN_COCKPIT | BKK_H | GVI | A330.MPD.ZL-211-01-1 |  | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
293 | 70461604 | HS-TEV | 0016404441 |  | 2105138388 | AC01 | EWIS | 2026-09-09 | 11LQ/IA | 0010 | INSP LOWER/REAR PYLON FAIRINGS-RR PYLON1 | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | WING_ENGINE | BKK_H | GVI | A330.MPD.ZL-454-05-2 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
294 | 70461604 | HS-TEV | 0016528690 | EV115B080926 | EV115B080926 | AC05 |  | 2026-09-13 | 11LQ/IA | 0010 | AFT.CARGO DOOR PANEL RECEPTACLE NUT DAMA | TECO | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  |  | 2026-09-08 | 13:47:00 | 2026-09-08 | 19:00:00
295 | 70461604 | HS-TEV | 0016404033 |  | 2105138023 | AC01 |  | 2026-09-09 | 11LHM/A | 0010 | DVI FWD CARGO COMP DOOR | TECO | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | FLOOR_FWD COMPT | BKK_H | DET | A330.MPD.523105-02-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
296 | 70461604 | HS-TEV | 0016403801 |  | 2105137802 | AC01 |  | 2026-09-15 | 11LHM/A | 0010 | CLOSE-UP GVI LH OUTBOARD AILERON | TECO | H/26-TEV-X0C10-BLOK-0-5 |  |  | WING_TRAILING EDGE | BKK_H | RES | A330.MPD.ZL-592-01-1 |  | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
297 | 70461604 | HS-TEV | 0016403808 |  | 2105137809 | AC01 |  | 2026-09-24 | 11LHM/E | 0010 | CLEAN-WIRING AFT CARGO COMPARTMENT | TECO | H/26-TEV-X0C10-BLOK-0-4 |  |  | IERA_FLOOR | BKK_H | INS | A330.MPD.200151-01-1 |  | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
298 | 70461604 | HS-TEV | 0016403819 |  | 2105137820 | AC01 |  | 2026-09-25 | 11LHM/C | 0010 | CLEAN-VENTILATION GRIDS AND HOUSING. | TECO | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | CABIN_INTERIOR | BKK_H | DVI | A330.MPD.233300-03-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
299 | 70461604 | HS-TEV | 0016403851 |  | 2105137852 | AC01 |  | 2026-09-23 | 11LHM/A | 0010 | CLOSE-UP FOR DVI T/E SKIN RIB8-12 ,RH | TECO | H/26-TEV-X0C10-BLOK-0-5 |  |  | WING_TRAILING EDGE | BKK_H | RES | A330.MPD.575025-01-5;575025-01-7 |  | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
300 | 70461604 | HS-TEV | 0016404181 |  | 2105138138 | AC01 |  | 2026-09-09 | 11LQ/IE | 0010 | GVI OF STATIC DISCHARGER | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | IERA_FLOOR | BKK_H | GVI | A330.MPD.236100-02-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
301 | 70461604 | HS-TEV | 0016404196 |  | 2105138152 | AC01 |  | 2026-09-09 | 11LHM/A | 0010 | REMOVE/OPEN ACCESS PNL FWD CGO DOOR | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | FLOOR_FWD COMPT | BKK_H | GVI | A330.MPD.523100-01-1,ZL-821-03-1 |  | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
302 | 70461604 | HS-TEV | 0016404306 |  | 2105138255 | AC01 |  | 2026-09-30 | 11LQ/IC | 0010 | ZONAL INSP - ALL PAX/CREW&EMERG EXIT | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | CABIN_DOOR | BKK_H | GVI | A330.MPD.ZL-800-01-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
303 | 70461604 | HS-TEV | 0016404346 |  | 2105138295 | AC01 | EWIS | 2026-09-24 | 11LQ/IC | 0010 | ZONAL INSP OF THE COCKPIT | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | CABIN_COCKPIT | BKK_H | GVI | A330.MPD.ZL-211-01-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
304 | 70461604 | HS-TEV | 0016404428 |  | 2105138375 | AC01 |  | 2026-09-07 | 11LHM/E | 0010 | OPC-ULB OF CVR | TECO | H/26-TEV-X0C10-BLOK-0-7 | 2 | DCA Appr. Req. 2 | IERA_FLOOR | BKK_H | OPC | A330.MPD.237135-02-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
305 | 70461604 | HS-TEV | 0016526008 | EV102B070926 | EV102B070926 | AC05 |  | 2026-09-10 | 11LHM/A | 0010 | INSP FOUND BRAKE NO.5 ,3 QAD FITTING HYD | TECO | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  |  | 2026-09-07 | 09:51:00 | 2026-09-07 | 19:00:00
306 | 70461604 | HS-TEV | 0016535601 | EV137A140926 | EV137A140926 | AC05 |  | 2026-09-24 | BKK_H | 0010 | FOUND CABIN CEILING LIGHT NOT ILLUMINATE | TECO | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  |  | 2026-01-01 | 09:23:00 | 2026-12-31 | 19:00:00
307 | 70461604 | HS-TEV | 0016404077 |  | 2105138059 | AC01 |  | 2026-09-10 | 11LQ/IA | 0010 | DET OUT WING LEAD EDGE BOT RIB 1-9 (RH) | TECO | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | WING_LEADING EDGE | BKK_H | DET | A330.MPD.574110-02-10 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
308 | 70461604 | HS-TEV | 0016404029 |  | 2105138019 | AC01 |  | 2026-09-29 | 11NDT | 0010 | SDI-FUSELAGE EXT. BETWEEN STR18 AND 22 | TECO | H/26-TEV-X0C10-BLOK-0-3 |  |  | FLOOR_FUSELAGE | BKK_H | SDI | A330.MPD.533106-02-3 |  | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
309 | 70461604 | HS-TEV | 0016404078 |  | 2105138060 | AC01 |  | 2026-09-09 | 11LQ/IA | 0010 | DET OUT WING LEAD EDGE BOT RIB 9-11 (LH) | TECO | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | WING_LEADING EDGE | BKK_H | DET | A330.MPD.574115-02-10 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
310 | 70461604 | HS-TEV | 0016404079 |  | 2105138061 | AC01 |  | 2026-09-15 | 11LQ/IA | 0010 | DET OUT WING LEAD EDGE BOT RIB 9-11 (RH) | TECO | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | WING_LEADING EDGE | BKK_H | DET | A330.MPD.574115-02-10 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
311 | 70461604 | HS-TEV | 0016404148 |  | 2105138108 | AC01 |  | 2026-09-29 | 11NDT | 0010 | SDI (PAUT) HOR STAB HINGE FITTING RIB3 | TECO | H/26-TEV-X0C10-BLOK-0-3 | 2 | DCA Appr. Req. 2 | FLOOR_TAIL | BKK_H | SDI | A330.MPD.551004-04-1 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
312 | 70461604 | HS-TEV | 0016404149 |  | 2105138108 | AC01 |  | 2026-09-29 | 11NDT | 0020 | SDI (PAUT) HOR STAB HINGE FITTING RIB3 | TECO | H/26-TEV-X0C10-BLOK-0-3 | 2 | DCA Appr. Req. 2 | FLOOR_TAIL | BKK_H | SDI | A330.MPD.551004-04-1 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
313 | 70461604 | HS-TEV | 0016404175 |  | 2105138132 | AC01 |  | 2026-09-03 | 11LHM/E | 0010 | INSTALL CVR PITOT,STATIC INTAKE | TECO | H/26-TEV-X0C10-BLOK-I-N |  |  | IERA_FLOOR | BKK_H | INS | A330.OPR.001ACA23 |  | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
314 | 70461604 | HS-TEV | 0016404427 |  | 2105138374 | AC01 |  | 2026-09-09 | 11LQ/IE | 0010 | DVI-HARNESS END FITTING AT FR 87 | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | IERA_FLOOR | BKK_H | DVI | A330.MPD.200002-01-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
315 | 70461604 | HS-TEV | 0016404469 |  | 2105138416 | AC01 |  | 2026-09-15 | 11LHM/A | 0010 | TOP-UP FLAP SYS TORQUE LIMITER-LH | TECO | H/26-TEV-X0C10-BLOK-0-4 | 2 | DCA Appr. Req. 2 | WING_TRAILING EDGE | BKK_H | SVC | A330.MPD.275400-06-1 |  | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
316 | 70461604 | HS-TEV | 0016404475 |  | 2105138422 | AC01 |  | 2026-09-09 | 11LQ/IE | 0010 | GVI HARNESS END FITTING-RIB19 TO 14-RHW | TECO | H/26-TEV-X0C10-BLOK-0-3 | 2 | DCA Appr. Req. 2 | IERA_WING | BKK_H | GVI | A330.MPD.200001-05-1 |  | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
317 | 70461604 | HS-TEV | 0016404479 |  | 2105138426 | AC01 |  | 2026-09-09 | 11LQ/IE | 0010 | GVI-HARNES END FITG-RH WING TIP TO RIB39 | TECO | H/26-TEV-X0C10-BLOK-0-3 | 2 | DCA Appr. Req. 2 | IERA_WING | BKK_H | GVI | A330.MPD.200001-04-1 |  | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
318 | 70461604 | HS-TEV | 0016404215 |  | 2105138166 | AC01 |  | 2026-09-12 | 11LQ/IA | 0010 | INSP OF LWR DECK CGO FIREX (TEN AND ON) | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | FLOOR_FWD COMPT | BKK_H | DVI | A330.MPD.262300-04-2 |  | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
319 | 70461604 | HS-TEV | 0016404036 |  | 2105138026 | AC01 |  | 2026-09-07 | 11LHM/E | 0010 | FUC-STANDBY AOA PROBE | TECO | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | IERA_ALL IERA | BKK_H | OPC | A330.MPD.341300-08-2 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
320 | 70461604 | HS-TEV | 0016404163 |  | 2105138121 | AC01 |  | 2026-08-25 | 11LHM/A | 0010 | JACKING AIRCRAFT IN HANGAR | TECO | H/26-TEV-X0C10-BLOK-I-N |  |  | ALL_ALL GRP | BKK_H | INS | A330.OPR.001ACA10 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
321 | 70461604 | HS-TEV | 0016404164 |  | 2105138121 | AC01 |  | 2026-08-25 | 11LHM/E | 0020 | JACKING AIRCRAFT IN HANGAR | TECO | H/26-TEV-X0C10-BLOK-I-N |  |  | ALL_ALL GRP | BKK_H | INS | A330.OPR.001ACA10 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
322 | 70461604 | HS-TEV | 0016404404 |  | 2105138351 | AC01 |  | 2026-08-26 | 11LHM/C | 0010 | OPC-EMERGENCY EXIT DOORS | TECO | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | CABIN_DOOR | BKK_H | OPC | A330.MPD.522200-05-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
323 | 70461604 | HS-TEV | 0016404449 |  | 2105138396 | AC01 |  | 2026-09-09 | 11LQ/IE | 0010 | GVI-HARNESS END FITTING(RIB10-TEE):PYL#1 | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | WING_ENGINE | BKK_H | GVI | A330.MPD.200004-01-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
324 | 70461604 | HS-TEV | 0016404470 |  | 2105138417 | AC01 |  | 2026-09-15 | 11LHM/A | 0010 | [TOP-UP FLAP SYS TORQUE LIMITER]-RH | TECO | H/26-TEV-X0C10-BLOK-0-4 | 2 | DCA Appr. Req. 2 | WING_TRAILING EDGE | BKK_H | SVC | A330.MPD.275400-06-1 |  | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
325 | 70461604 | HS-TEV | 0016503076 | EV075A250826 | EV075A250826 | AC05 |  | 2026-09-07 | 11LHM/A | 0010 | NORMAL BRAKING | TECO | H/26-TEV-X0C10-NONR |  |  |  | 11LHM/A | REP |  |  | 2026-08-24 | 00:00:00 | 2026-08-26 | 16:00:00
326 | 70461604 | HS-TEV | 0016503077 | EV076A250826 | EV076A250826 | AC05 |  | 2026-08-25 | 11LHM/A | 0010 | WHEEL | TECO | H/26-TEV-X0C10-NONR |  |  |  | 11LHM/A | REP |  |  | 2026-08-24 | 00:00:00 | 2026-08-26 | 16:00:00
327 | 70461604 | HS-TEV | 0016404034 |  | 2105138024 | AC01 |  | 2026-09-07 | 11LHM/A | 0010 | DVI AFT CARGO COMP DOOR | TECO | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | FLOOR_AFT COMPT | BKK_H | DET | A330.MPD.523205-02-1 | 2026-09-07 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
328 | 70461604 | HS-TEV | 0016404136 |  | 2105138102 | AC01 |  | 2026-09-12 | 11LHM/A | 0010 | GVI OF AFT CARGO DOOR EXTERNAL SURFACE | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | FLOOR_AFT COMPT | BKK_H | GVI | A330.MPD.523213-01-1 | 2026-08-24 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
329 | 70461604 | HS-TEV | 0015362442 | 1102995057 | 2104859418 | AC03 |  | 2026-09-09 | 11LHM/A | 0010 | 280678: INSP RIB3 AFT FUEL TK LEAK TEST | TECO | H/26-TEV-X0C10-MOD -G-W | 0 | AD | WING_ALL WING | BKK_H | DET | A330.TO.280678 | 2026-09-23 | 2026-08-22 | 00:00:00 | 2026-09-02 | 00:00:00
330 | 70461604 | HS-TEV | 0016403809 |  | 2105137810 | AC01 |  | 2026-09-09 | 11LQ/IE | 0010 | GVI WIRING IN TAIL CONE APU AND ACCESSOR | TECO | H/26-TEV-X0C10-BLOK-0-2 |  |  | IERA_FLOOR | BKK_H | INS | A330.MPD.200315-01-1 | 2026-09-12 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
331 | 70461604 | HS-TEV | 0016403811 |  | 2105137812 | AC01 |  | 2026-08-24 | 11LHM/E | 0010 | OPC ELECTRONIC INSTRUMENT SYSTEM 2 | TECO | H/26-TEV-X0C10-BLOK-0-6 | 1 | DCA Appr. Req. 1 | IERA_CABIN | BKK_H | OPC | A330.MPD.316001-01-1 | 2026-08-19 | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
332 | 70461604 | HS-TEV | 0016403813 |  | 2105137814 | AC01 |  | 2026-09-08 | 11LHM/E | 0010 | FLUSHING OF PRINCIPAL TOTAL PRESSURE LIN | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | IERA_FLOOR | BKK_H | OPC | A330.MPD.341300-03-1 | 2026-09-08 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
333 | 70461604 | HS-TEV | 0016403815 |  | 2105137816 | AC01 | SCT | 2026-09-08 | 11LHM/E | 0010 | DRAIN AND FLUSH STANDBY PNEUMATIC CIRCUI | TECO | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | IERA_FLOOR | BKK_H | OPC | A330.MPD.342200-01-1 | 2026-09-04 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
334 | 70461604 | HS-TEV | 0016403869 |  | 2105137869 | AC01 |  | 2026-09-09 | 11LQ/IE | 0010 | DVI-LIGHTNING HIRF PROTECTION-VERTICAL F | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | IERA_FLOOR | BKK_H | DVI | A330.MPD.200007-02-3 | 2026-09-09 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
335 | 70461604 | HS-TEV | 0016403876 |  | 2105137876 | AC01 |  | 2026-09-08 | 11LHM/A | 0010 | REMOVAL PYLON ACCESS PANELS PYLON1 | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | WING_ENGINE | BKK_H | REM | A330.MPD.ZL-453-01-1,ZL-454-05-2 | 2026-09-08 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
336 | 70461604 | HS-TEV | 0016403939 |  | 2105137933 | AC01 |  | 2026-09-13 | 11LQ/IA | 0010 | GVI AIR CONDITIONING COMPART VENTILATIO | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | FLOOR_AIR COND | BKK_H | GVI | A330.MPD.212500-03-1 | 2026-09-13 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
337 | 70461604 | HS-TEV | 0016403970 |  | 2105137962 | AC01 |  | 2026-09-08 | 11LHM/A | 0010 | REMOVE LOWER FAIRING (RR)#LH | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | WING_ENGINE | BKK_H | REM | A330.OPR.545100-07-1,545100-10-1 | 2026-09-08 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
338 | 70461604 | HS-TEV | 0016403982 |  | 2105137974 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | INSP NLG UPLOCK UNITS | TECO | H/26-TEV-X0C10-BLOK-0-1 | 1 | DCA Appr. Req. 1 | FLOOR_LANDING GEAR | BKK_H | DET | A330.MPD.323000-20-1 | 2026-09-05 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
339 | 70461604 | HS-TEV | 0016403983 |  | 2105137975 | AC01 |  | 2026-09-09 | 11LHM/A | 0010 | INSP LH-MLG UPLOCK UNITS | TECO | H/26-TEV-X0C10-BLOK-0-1 | 1 | DCA Appr. Req. 1 | FLOOR_LANDING GEAR | BKK_H | DET | A330.MPD.323000-20-1 | 2026-09-09 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
340 | 70461604 | HS-TEV | 0016403984 |  | 2105137976 | AC01 |  | 2026-09-09 | 11LHM/A | 0010 | INSP RH-MLG UPLOCK UNITS | TECO | H/26-TEV-X0C10-BLOK-0-1 | 1 | DCA Appr. Req. 1 | FLOOR_LANDING GEAR | BKK_H | DET | A330.MPD.323000-20-1 | 2026-09-09 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
341 | 70461604 | HS-TEV | 0016404004 |  | 2105137994 | AC01 | EWIS | 2026-09-10 | 11LQ/IA | 0010 | GVI HYDRAULIC COMPARTMENT AND FAIRINGS | TECO | H/26-TEV-X0C10-BLOK-0-2 |  |  | WING_HYDRAULIC | BKK_H | GVI | A330.MPD.ZL-195-03-1 | 2026-09-10 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
342 | 70461604 | HS-TEV | 0016404037 |  | 2105138027 | AC01 |  | 2026-09-10 | 11LHM/A | 0010 | DVI PACK OUTLET DUCTS AND BELLOWS | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | FLOOR_AIR COND | BKK_H | DET | A330.MPD.215300-02-1 | 2026-09-10 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
343 | 70461604 | HS-TEV | 0016404045 |  | 2105138034 | AC01 |  | 2026-09-09 | 11LQ/IE | 0010 | GVI OF ESS TR | TECO | H/26-TEV-X0C10-BLOK-0-3 | 2 | DCA Appr. Req. 2 | IERA_IERA_FLOOR | BKK_H | GVI | A330.MPD.243000-10-1 | 2026-09-15 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
344 | 70461604 | HS-TEV | 0016404066 |  | 2105138050 | AC01 |  | 2026-09-12 | 11LHM/A | 0010 | DET OUTER WING BOTTOM SKIN LHW | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | WING_ALL WING | BKK_H | DET | A330.MPD.572023-02-15 | 2026-09-12 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
345 | 70461604 | HS-TEV | 0016404080 |  | 2105138062 | AC01 |  | 2026-09-12 | 11LHM/A | 0010 | DET OUT WING TRAILING EDGE LHW | TECO | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | WING_TRAILING EDGE | BKK_H | DET | A330.MPD.575012-01-16 | 2026-09-12 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
346 | 70461604 | HS-TEV | 0016404081 |  | 2105138063 | AC01 |  | 2026-09-12 | 11LHM/A | 0010 | DET OUT WING TRAILING EDGE RHW | TECO | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | WING_TRAILING EDGE | BKK_H | DET | A330.MPD.575012-01-16 | 2026-09-12 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
347 | 70461604 | HS-TEV | 0016404160 |  | 2105138118 | AC01 |  | 2026-09-12 | 11LHM/C | 0010 | DRAIN FRESH WTR SYSTEM | TECO | H/26-TEV-X0C10-BLOK-I-N |  |  | CABIN_GALLEY | BKK_H | INS | A330.OPR.001ACA07 | 2026-09-12 | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
348 | 70461604 | HS-TEV | 0016404185 |  | 2105138142 | AC01 | EWIS | 2026-09-12 | 11LQ/IA | 0010 | INSP-RADOME ZONE 110 | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | FLOOR_FUSELAGE | BKK_H | GVI | A330.MPD.ZL-110-01-1 | 2026-09-12 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
349 | 70461604 | HS-TEV | 0016404186 |  | 2105138143 | AC01 |  | 2026-09-08 | 11LHM/A | 0010 | CLEAN RELAY BOX VU PANELS GRIDS | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | IERA_FLOOR | BKK_H | RES | A330.MPD.212600-07-1 | 2026-09-05 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
350 | 70461604 | HS-TEV | 0016404190 |  | 2105138147 | AC01 | EWIS | 2026-09-13 | 11LQ/IA | 0010 | INSP OF AVIONICS COMPT | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | FLOOR_FWD COMPT | BKK_H | GVI | A330.MPD.ZL-121-01-1 | 2026-09-13 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
351 | 70461604 | HS-TEV | 0016404224 |  | 2105138175 | AC01 |  | 2026-09-13 | 11LQ/IA | 0010 | INSP-FWD CARGO DOOR HINGE ARMS | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | FLOOR_FWD COMPT | BKK_H | DVI | A330.MPD.523104-01-1 | 2026-09-13 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
352 | 70461604 | HS-TEV | 0016404251 |  | 2105138200 | AC01 |  | 2026-09-13 | 11LQ/IA | 0010 | INSP-DOWN STREAM CHECK VALVE | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | FLOOR_AIR COND | BKK_H | DVI | A330.MPD.215000-06-1 | 2026-09-15 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
353 | 70461604 | HS-TEV | 0016404254 |  | 2105138203 | AC01 |  | 2026-09-07 | 11LQ/IA | 0010 | INSP-EMERGENCY RAM AIR CHECK VALVE | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | FLOOR_AIR COND | BKK_H | DVI | A330.MPD.215500-04-1 | 2026-09-07 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
354 | 70461604 | HS-TEV | 0016404257 |  | 2105138206 | AC01 |  | 2026-09-07 | 11LQ/IA | 0010 | INSP-THE SKIN CHECK VALVE | TECO | H/26-TEV-X0C10-BLOK-0-3 | 2 | DCA Appr. Req. 2 | FLOOR_AIR COND | BKK_H | DVI | A330.MPD.215500-02-1 | 2026-09-07 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
355 | 70461604 | HS-TEV | 0016404260 |  | 2105138209 | AC01 |  | 2026-09-07 | 11LQ/IA | 0010 | INSP-LOW PRESSURE GROUND AIR CHECK VALVE | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | FLOOR_AIR COND | BKK_H | DVI | A330.MPD.215500-03-1 | 2026-09-07 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
356 | 70461604 | HS-TEV | 0016404276 |  | 2105138225 | AC01 |  | 2026-09-09 | 11CLEAN | 0010 | CLEN-AFT CARGO DOOR HINGE ARM | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | FLOOR_FWD COMPT | BKK_H | CLN | A330.MPD.523204-01-1 | 2026-09-07 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
357 | 70461604 | HS-TEV | 0016404279 |  | 2105138228 | AC01 |  | 2026-09-07 | 11LHM/A | 0010 | REMOVE/OPEN ACCESS PNL BULK CGO (FR73) | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | FLOOR_AFT COMPT | BKK_H | INS | A330.OPR.161ACP01 | 2026-09-07 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
358 | 70461604 | HS-TEV | 0016404286 |  | 2105138235 | AC01 |  | 2026-09-09 | 11LQ/IA | 0010 | INSP-BULK CARGO DOOR STOP FITTINGS | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | FLOOR_AFT COMPT | BKK_H | DVI | A330.MPD.523303-01-1 | 2026-09-09 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
359 | 70461604 | HS-TEV | 0016404287 |  | 2105138236 | AC01 | EWIS | 2026-09-13 | 11LQ/IA | 0010 | INSPECTION OF BULK CARGO COMPT | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | FLOOR_AFT COMPT | BKK_H | GVI | A330.MPD.ZL-171-01-1 | 2026-09-13 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
360 | 70461604 | HS-TEV | 0016404288 |  | 2105138237 | AC01 |  | 2026-09-12 | 11LQ/IA | 0010 | INSP-BULK CARGO DOOR CUTOUT | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | FLOOR_AFT COMPT | BKK_H | GVI | A330.MPD.534149-01-1 | 2026-09-12 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
361 | 70461604 | HS-TEV | 0016404337 |  | 2105138286 | AC01 |  | 2026-09-07 | 11LHM/C | 0010 | OPC-MEGAPHONE | TECO | H/26-TEV-X0C10-BLOK-0-7 | 2 | DCA Appr. Req. 2 | CABIN_INTERIOR | BKK_H | OPC | A330.MPD.256551-02-1 | 2026-09-09 | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
362 | 70461604 | HS-TEV | 0016404363 |  | 2105138310 | AC01 |  | 2026-08-25 | 11LHM/E | 0010 | OPC-MASK MICROPHONE | TECO | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | IERA_CABIN | BKK_H | OPC | A330.MPD.235100-01-1 | 2026-08-25 | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
363 | 70461604 | HS-TEV | 0016404366 |  | 2105138313 | AC01 |  | 2026-08-24 | 11LHM/E | 0010 | OPC-SIDE1&SIDE2 ISOLATION OF EL NETWORK | TECO | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | IERA_CABIN | BKK_H | OPC | A330.MPD.242200-01-1 | 2026-08-22 | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
364 | 70461604 | HS-TEV | 0016404375 |  | 2105138322 | AC01 |  | 2026-08-25 | 11LHM/E | 0010 | OPC-APU AUTO FIRE EXTING TRIGGER CIRCUIT | TECO | H/26-TEV-X0C10-BLOK-0-7 | 2 | DCA Appr. Req. 2 | IERA_FLOOR | BKK_H | OPC | A330.MPD.262200-05-1 | 2026-08-25 | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
365 | 70461604 | HS-TEV | 0016404376 |  | 2105138323 | AC01 |  | 2026-08-24 | 11LHM/E | 0010 | OPC-CARGO FIREX BTL LOW PRESS IND CCT | TECO | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | IERA_FLOOR | BKK_H | OPC | A330.MPD.262300-03-1 | 2026-08-19 | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
366 | 70461604 | HS-TEV | 0016404382 |  | 2105138329 | AC01 |  | 2026-08-25 | 11LHM/E | 0010 | OPC-CAPT & F/O ACP SW TO THE THIRD ACP | TECO | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | IERA_CABIN | BKK_H | OPC | A330.MPD.235100-02-1 | 2026-08-25 | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
367 | 70461604 | HS-TEV | 0016404383 |  | 2105138330 | AC01 |  | 2026-08-25 | 11LHM/E | 0010 | OPC-CVR RECORDING LOGIC | TECO | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | IERA_CABIN | BKK_H | OPC | A330.MPD.237100-02-1 | 2026-08-25 | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
368 | 70461604 | HS-TEV | 0016404389 |  | 2105138336 | AC01 |  | 2026-08-25 | 11LHM/E | 0010 | OPC-EMER LT SYS AUTO&MANUAL CTL CCT | TECO | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | IERA_CABIN | BKK_H | OPC | A330.MPD.335100-03-1 | 2026-08-25 | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
369 | 70461604 | HS-TEV | 0016404484 |  | 2105138431 | AC01 | EWIS | 2026-09-12 | 11LQ/IA | 0010 | LH,INSP-EXTERNAL WING AREA | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | WING_LEADING EDGE | BKK_H | GVI | A330.MPD.ZL-500-01-1 | 2026-09-12 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
370 | 70461604 | HS-TEV | 0016404488 |  | 2105138435 | AC01 | EWIS | 2026-09-24 | 11LQ/IA | 0010 | LH,INSP-EXTERNAL WING AREA | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | WING_LEADING EDGE | BKK_H | GVI | A330.MPD.ZL-522-01-1 | 2026-09-24 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
371 | 70461604 | HS-TEV | 0016404491 |  | 2105138438 | AC01 | EWIS | 2026-09-10 | 11LQ/IA | 0010 | RH,INSP-EXTERNAL WING AREA | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | WING_LEADING EDGE | BKK_H | GVI | A330.MPD.ZL-523-01-1 | 2026-09-13 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
372 | 70461604 | HS-TEV | 0016404497 |  | 2105138444 | AC01 |  | 2026-09-24 | 11LQ/IA | 0010 | INSP-WING ICE PROTECTION COMPONENTS,RH | TECO | H/26-TEV-X0C10-BLOK-0-3 | 2 | DCA Appr. Req. 2 | WING_LEADING EDGE | BKK_H | DET | A330.MPD.301100-01-1 | 2026-09-24 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
373 | 70461604 | HS-TEV | 0016404506 |  | 2105138453 | AC01 |  | 2026-09-08 | 11LHM/A | 0010 | [LHW-INSP-REFUEL/DEFUEL SYSTEM AREA] | TECO | H/26-TEV-X0C10-BLOK-0-1 | 2 | DCA Appr. Req. 2 | WING_FUEL | BKK_H | DVI | A330.MPD.282500-01-3 | 2026-09-08 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
374 | 70461604 | HS-TEV | 0016404541 |  | 2105138487 | AC01 |  | 2026-09-08 | 11LQ/IE | 0010 | DVI-HARNESS END FITTING AT NLG BRAID CON | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | IERA_FLOOR | BKK_H | DVI | A330.MPD.200006-01-1 | 2026-09-03 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
375 | 70461604 | HS-TEV | 0016404549 |  | 2105138495 | AC01 |  | 2026-09-09 | 11LQ/IE | 0010 | DVI-1LBD1B END FITTING-RH MLG BRAID CON | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | FLOOR_LANDING GEAR | BKK_H | DVI | A330.MPD.200005-01-1 | 2026-09-09 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
376 | 70461604 | HS-TEV | 0016404593 |  | 2105138537 | AC01 |  | 2026-09-13 | 11LQ/IA | 0010 | INSP-BULK CARGO NET AND ASSEMBLIES | TECO | H/26-TEV-X0C10-BLOK-0-3 | 2 | DCA Appr. Req. 2 | FLOOR_AFT COMPT | BKK_H | DET | A330.MPD.255400-04-1 | 2026-09-13 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
377 | 70461604 | HS-TEV | 0016404594 |  | 2105138538 | AC01 |  | 2026-09-13 | 11LQ/IA | 0010 | INSP-BULK CARGO NET SCREEN | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | FLOOR_AFT COMPT | BKK_H | DET | A330.MPD.255400-05-1 | 2026-09-12 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
378 | 70461604 | HS-TEV | 0016404595 |  | 2105138539 | AC01 |  | 2026-09-13 | 11LQ/IA | 0010 | INSP-BULK CARGO SCREEN DECOMPRESSION TAR | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | FLOOR_AFT COMPT | BKK_H | DET | A330.MPD.255400-06-1 | 2026-09-13 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
379 | 70461604 | HS-TEV | 0016404618 |  | 2105138550 | AC01 |  | 2026-09-13 | 11LQ/IA | 0010 | INSP THE BULK CARGO COMP (ZONE 823) | TECO | H/26-TEV-X0C10-BLOK-0-3 | 2 | DCA Appr. Req. 2 | FLOOR_AFT COMPT | BKK_H | INS | A330.MPD.ZL-823-01-1 | 2026-09-13 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
380 | 70461604 | HS-TEV | 0016452457 |  | 2105151067 | AC01 |  | 2026-09-09 | 11NDT | 0010 | NDT-EMERGENCY EXIT UNDER SCUFF PLATE | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | CABIN_DOOR | BKK_H | SDI | A330.MPD.533195-02-1;533195-02-9 | 2026-09-09 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
381 | 70461604 | HS-TEV | 0016526404 |  | 2105151067 | AC01 |  | 2026-09-09 | 11SH | 0020 | NDT-EMERGENCY EXIT UNDER SCUFF PLATE | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | CABIN_DOOR | BKK_H | SDI | A330.MPD.533195-02-1;533195-02-9 | 2026-09-09 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
382 | 70461604 | HS-TEV | 0016491391 | 1103188489 | 2105162148 | AC02 |  | 2026-09-15 | 11LHM/A | 0010 | GVI OF LININGS,FLOOR PANELS AT FR 73 | TECO | H/26-TEV-X0C10-NONR | 1 | DCA Appr. Req. 1 |  | BKK_H | VCK | A330.MPD.255400-01-1 | 2026-09-13 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
383 | 70461604 | HS-TEV | 0016506097 | EV086B270826 | EV086B270826 | AC05 |  | 2026-09-08 | 11PAINT | 0010 | 57:L/E WING UPPER LANDING LIGHT OUTER SK | TECO | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  | 2026-09-07 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
384 | 70461604 | HS-TEV | 0016506108 | EV091B270826 | EV091B270826 | AC05 |  | 2026-09-15 | 11PAINT | 0010 | 11:LH/RH MANHOLE NUMBERING | TECO | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  | 2026-09-04 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
385 | 70461604 | HS-TEV | 0016506139 | EV095B270826 | EV095B270826 | AC05 |  | 2026-09-15 | 11CMPST | 0010 | CABIN COCKPIT DOOR | TECO | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  | 2026-08-27 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
386 | 70461604 | HS-TEV | 0016522970 | EV099B040926 | EV099B040926 | AC05 |  | 2026-09-04 | 11SH | 0010 | WAC FOUND AFT CARGO LIP POOR CONDITION | TECO | H/26-TEV-X0C10-NONR |  |  |  | 11SH | REP |  | 2026-09-04 | 2026-09-04 | 16:46:00 | 2026-09-08 | 19:00:00
387 | 70461604 | HS-TEV | 0016526726 | EV109B070926 | EV109B070926 | AC05 |  | 2026-09-15 | 11CLEAN | 0010 | CABIN DADO PANEL | TECO | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  | 2026-09-09 | 2026-09-07 | 16:18:00 | 2026-09-08 | 19:00:00
388 | 70461604 | HS-TEV | 0016526730 | EV111B070926 | EV111B070926 | AC05 |  | 2026-09-15 | 11PAINT | 0010 | CABIN GALLEY | TECO | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  | 2026-09-11 | 2026-09-07 | 16:29:00 | 2026-09-07 | 19:00:00
389 | 70461604 | HS-TEV | 0016527784 | EV112B080926 | EV112B080926 | AC05 |  | 2026-09-15 | 11CLEAN | 0010 | CABIN GALLEYS | TECO | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  | 2026-09-09 | 2026-09-08 | 09:26:00 | 2026-09-08 | 19:00:00
390 | 70461604 | HS-TEV | 0016528741 | EV116B080926 | EV116B080926 | AC05 |  | 2026-09-15 | 11PAINT | 0010 | LH/RH ELEVATOR INBORD UPPER SKIN ALONG T | TECO | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  | 2026-09-15 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
391 | 70461604 | HS-TEV | 0016531089 | EV119B090926 | EV119B090926 | AC05 |  | 2026-09-15 | 11PAINT | 0010 | VERTICAL STABILIZER TIP LEADING EDGE OUT | TECO | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  | 2026-09-14 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
392 | 70461604 | HS-TEV | 0016537838 | EV139B140926 | EV139B140926 | AC05 |  | 2026-09-15 | 11CMPST | 0010 | INSP FOUND PACK AIR CONDITION DISTRIBUTI | TECO | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  | 2026-09-14 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
393 | 70461604 | HS-TEV | 0016404119 |  | 2105138092 | AC01 |  | 2026-09-12 | 11LHM/C | 0010 | GVI OF PAX DOOR 1 EXTERNAL SURFACE | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | CABIN_DOOR | BKK_H | GVI | A330.MPD.521106-01-1 | 2026-09-10 | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
394 | 70461604 | HS-TEV | 0016404120 |  | 2105138092 | AC01 |  | 2026-09-12 | 11LHM/C | 0020 | GVI OF PAX DOOR 1 EXTERNAL SURFACE | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | CABIN_DOOR | BKK_H | GVI | A330.MPD.521106-01-1 | 2026-09-10 | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
395 | 70461604 | HS-TEV | 0016404127 |  | 2105138096 | AC01 |  | 2026-09-12 | 11LHM/C | 0010 | GVI OF PAX DOOR 4 EXTERNAL SURFACE | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | CABIN_DOOR | BKK_H | GVI | A330.MPD.521304-01-1 | 2026-09-10 | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
396 | 70461604 | HS-TEV | 0016404128 |  | 2105138096 | AC01 |  | 2026-09-12 | 11LHM/C | 0020 | GVI OF PAX DOOR 4 EXTERNAL SURFACE | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | CABIN_DOOR | BKK_H | GVI | A330.MPD.521304-01-1 | 2026-09-10 | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
397 | 70461604 | HS-TEV | 0016404129 |  | 2105138097 | AC01 |  | 2026-09-12 | 11LHM/C | 0010 | GVI OF DOOR 3 INTERNAL STRUCTURE | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | CABIN_DOOR | BKK_H | GVI | A330.MPD.522202-02-1 | 2026-09-11 | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
398 | 70461604 | HS-TEV | 0016404130 |  | 2105138097 | AC01 |  | 2026-09-12 | 11LHM/C | 0020 | GVI OF DOOR 3 INTERNAL STRUCTURE | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | CABIN_DOOR | BKK_H | GVI | A330.MPD.522202-02-1 | 2026-09-10 | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
399 | 70461604 | HS-TEV | 0016404131 |  | 2105138098 | AC01 |  | 2026-09-12 | 11LHM/C | 0010 | GVI OF DOOR 3 EXTERNAL SURFACE | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | CABIN_DOOR | BKK_H | GVI | A330.MPD.522204-01-1 | 2026-09-12 | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
400 | 70461604 | HS-TEV | 0016404132 |  | 2105138098 | AC01 |  | 2026-09-12 | 11LHM/C | 0020 | GVI OF DOOR 3 EXTERNAL SURFACE | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | CABIN_DOOR | BKK_H | GVI | A330.MPD.522204-01-1 | 2026-09-12 | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
401 | 70461604 | HS-TEV | 0016404133 |  | 2105138099 | AC01 |  | 2026-09-12 | 11LHM/A | 0010 | GVI OF FWD CARGO DOOR INTERNAL STRUCTURE | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | FLOOR_FWD COMPT | BKK_H | GVI | A330.MPD.523102-02-1 | 2026-09-12 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
402 | 70461604 | HS-TEV | 0016404137 |  | 2105138103 | AC01 |  | 2026-09-09 | 11LHM/A | 0010 | GVI OF BULK CARGO DOOR INTERNAL STRUCTUR | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | FLOOR_AFT COMPT | BKK_H | GVI | A330.MPD.523302-02-1 | 2026-09-09 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
403 | 70461604 | HS-TEV | 0016404138 |  | 2105138104 | AC01 |  | 2026-09-09 | 11LHM/A | 0010 | GVI OF BULK CARGO DOOR EXTERNAL SURFACE | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | FLOOR_AFT COMPT | BKK_H | GVI | A330.MPD.523304-01-1 | 2026-09-09 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
404 | 70461604 | HS-TEV | 0016404216 |  | 2105138167 | AC01 |  | 2026-09-09 | 11LHM/A | 0010 | LUBRICATION OF FWD CGO DOOR | TECO | H/26-TEV-X0C10-BLOK-0-5 | 2 | DCA Appr. Req. 2 | FLOOR_FWD COMPT | BKK_H | LUB | A330.MPD.523100-01-1 | 2026-09-07 | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
405 | 70461604 | HS-TEV | 0016404253 |  | 2105138202 | AC01 |  | 2026-09-24 | 11LHM/A | 0010 | INSTL-EMERGENCY RAM AIR CHECK VALVE | TECO | H/26-TEV-X0C10-BLOK-0-4 |  |  | FLOOR_AIR COND | BKK_H | DVI | A330.MPD.215500-04-1 | 2026-09-23 | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
406 | 70461604 | HS-TEV | 0016404256 |  | 2105138205 | AC01 |  | 2026-09-24 | 11LHM/A | 0010 | INSTL-OF SKIN CHECK VALVE | TECO | H/26-TEV-X0C10-BLOK-0-4 |  |  | FLOOR_AIR COND | BKK_H | DVI | A330.MPD.215500-02-1 | 2026-09-23 | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
407 | 70461604 | HS-TEV | 0016404275 |  | 2105138224 | AC01 |  | 2026-09-09 | 11LHM/A | 0010 | LUBRICATION OF AFT CGO DOOR | TECO | H/26-TEV-X0C10-BLOK-0-5 | 2 | DCA Appr. Req. 2 | FLOOR_AFT COMPT | BKK_H | LUB | A330.MPD.523200-01-1 | 2026-09-07 | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
408 | 70461604 | HS-TEV | 0016404415 |  | 2105138362 | AC01 |  | 2026-09-09 | 11LHM/A | 0010 | INSP MGNETIC CHIP DETECTOR THS ACTUATOR | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | FLOOR_TAIL | BKK_H | DVI | A330.MPD.274400-05-1 | 2026-09-08 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
409 | 70461604 | HS-TEV | 0016404527 |  | 2105138474 | AC01 |  | 2026-09-07 | 11LHM/A | 0010 | INSTALLATION OF MLG AXLE SLEEVE-LH MLG | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | FLOOR_LANDING GEAR | BKK_H | RES | A330.MPD.324100-05-1,324000-19-1 | 2026-08-24 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
410 | 70461604 | HS-TEV | 0016404533 |  | 2105138480 | AC01 |  | 2026-09-07 | 11LHM/A | 0010 | INSTALLATION OF MLG AXLE SLEEVE-RH MLG | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | FLOOR_LANDING GEAR | BKK_H | RES | A330.MPD.324100-05-1,324000-19-1 | 2026-08-24 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
411 | 70461604 | HS-TEV | 0016404550 |  | 2105138496 | AC01 |  | 2026-09-09 | 11LQ/IE | 0010 | DVI-COM ON ROUTE 2M AT LH MLG BRAID COND | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | FLOOR_LANDING GEAR | BKK_H | DVI | A330.MPD.200005-02-1 | 2026-09-12 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
412 | 70461604 | HS-TEV | 0016404551 |  | 2105138497 | AC01 |  | 2026-09-09 | 11LQ/IE | 0010 | DVI-COM ON ROUTE 2M AT RH MLG BRAID CON | TECO | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | FLOOR_LANDING GEAR | BKK_H | DVI | A330.MPD.200005-02-1 | 2026-09-08 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
413 | 70461604 | HS-TEV | 0016403807 |  | 2105137808 | AC01 |  | 2026-09-09 | 11LQ/IE | 0010 | DVI LIGHTNING/HIRF PROTECTION-WING(teg-t | TECO | H/26-TEV-X0C10-BLOK-0-2 |  |  | IERA_WING | BKK_H | INS | A330.MPD.200001-09-1 | 2026-09-13 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
414 | 70461604 | HS-TEV | 0016403859 |  | 2105137860 | AC01 |  | 2026-08-25 | 11LHM/E | 0010 | OPC FCSC1 RUDDER SERVO LOOP | TECO | H/26-TEV-X0C10-BLOK-0-6 |  |  | IERA_FLOOR | BKK_H | OP | A330.MPD.279000-15-1 | 2026-08-25 | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
415 | 70461604 | HS-TEV | 0016403877 |  | 2105137877 | AC01 |  | 2026-09-07 | 11LHM/A | 0010 | REMOVAL PYLON ACCESS PANELS PYLON2 | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | WING_ENGINE | BKK_H | REM | A330.MPD.ZL-453-01-1,ZL-454-05-2 | 2026-09-07 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
416 | 70461604 | HS-TEV | 0016404191 |  | 2105138148 | AC01 |  | 2026-09-09 | 11LQ/IA | 0010 | INSP-SKIN & FAIL SAFE RING DR NO 1 | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | FLOOR_FUSELAGE | BKK_H | DVI | A330.MPD.531112-02-1 | 2026-09-09 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
417 | 70461604 | HS-TEV | 0016404207 |  | 2105138163 | AC01 |  | 2026-09-12 | 11LHM/A | 0010 | REM OF LWR DECK CGO FIREX COMPONENTS | TECO | H/26-TEV-X0C10-BLOK-0-2 |  |  | FLOOR_FWD COMPT | BKK_H | DVI | A330.MPD.262300-04-1;262300-04-2 | 2026-09-08 | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
418 | 70461604 | HS-TEV | 0016404208 |  | 2105138163 | AC01 |  | 2026-09-12 | 11LHM/A | 0020 | REM OF LWR DECK CGO FIREX COMPONENTS | TECO | H/26-TEV-X0C10-BLOK-0-2 |  |  | FLOOR_FWD COMPT | BKK_H | DVI | A330.MPD.262300-04-1;262300-04-2 | 2026-09-08 | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
419 | 70461604 | HS-TEV | 0016404209 |  | 2105138163 | AC01 |  | 2026-09-12 | 11LHM/A | 0030 | REM OF LWR DECK CGO FIREX COMPONENTS | TECO | H/26-TEV-X0C10-BLOK-0-2 |  |  | FLOOR_FWD COMPT | BKK_H | DVI | A330.MPD.262300-04-1;262300-04-2 | 2026-09-12 | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
420 | 70461604 | HS-TEV | 0016404249 |  | 2105138198 | AC01 |  | 2026-09-08 | 11LHM/A | 0010 | REM -DOWN STREAM CHECK VALVE | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | FLOOR_AIR COND | BKK_H | DVI | A330.MPD.215000-06-1 | 2026-09-08 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
421 | 70461604 | HS-TEV | 0016404263 |  | 2105138212 | AC01 |  | 2026-09-04 | 11LQ/IA | 0010 | REM-PARTITION PANEL FR39.1 | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | FLOOR_FWD COMPT | BKK_H | REM | A330.MPD.215000-05-1,215000-06-1 | 2026-09-04 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
422 | 70461604 | HS-TEV | 0016404300 |  | 2105138249 | AC01 |  | 2026-09-09 | 11SH | 0010 | REM -BULK CARGO DOOR SCUFF PLATE | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | FLOOR_AFT COMPT | BKK_H | DVI | A330.MPD.534144-01-1;534144-03-1 | 2026-09-09 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
423 | 70461604 | HS-TEV | 0016404396 |  | 2105138343 | AC01 |  | 2026-08-24 | 11LHM/E | 0010 | OPC-POWER SUPPLY OF FCSC 2 | TECO | H/26-TEV-X0C10-BLOK-0-7 | 2 | DCA Appr. Req. 2 | IERA_FLOOR | BKK_H | OPC | A330.MPD.279000-09-2 | 2026-08-23 | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
424 | 70461604 | HS-TEV | 0016404445 |  | 2105138392 | AC01 |  | 2026-09-08 | 11LHM/A | 0010 | REM UPPER FWD PYLON PANEL-RR PYL#1 | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | WING_ENGINE | BKK_H | REM | A330.MPD.ZL-452-01-1 | 2026-09-08 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
425 | 70461604 | HS-TEV | 0016404507 |  | 2105138454 | AC01 |  | 2026-09-08 | 11LHM/A | 0010 | [INSP-REFUEL/DEFUEL SYSTEM AREA] | TECO | H/26-TEV-X0C10-BLOK-0-1 | 2 | DCA Appr. Req. 2 | WING_FUEL | BKK_H | DVI | A330.MPD.282500-01-3 | 2026-09-08 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
426 | 70461604 | HS-TEV | 0016404508 |  | 2105138455 | AC01 |  | 2026-09-09 | 11LHM/A | 0010 | LHW-REM OF ACCESS PANELS LOWER T/E | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | WING_TRAILING EDGE | BKK_H | DVI | A330.MPD.275400-02-1 | 2026-09-08 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
427 | 70461604 | HS-TEV | 0016404511 |  | 2105138458 | AC01 |  | 2026-09-09 | 11LHM/A | 0010 | [RHW-REM OF ACCESS PANELS LOWER T/E] | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | WING_TRAILING EDGE | BKK_H | DVI | A330.MPD.275400-02-1 | 2026-09-09 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
428 | 70461604 | HS-TEV | 0016404617 |  | 2105138549 | AC01 |  | 2026-09-13 | 11LQ/IA | 0010 | INSP THE AFT CARGO COMP (ZONE 822) | TECO | H/26-TEV-X0C10-BLOK-0-3 | 2 | DCA Appr. Req. 2 | FLOOR_AFT COMPT | BKK_H | INS | A330.MPD.ZL-822-01-1 | 2026-09-05 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
429 | 70461604 | HS-TEV-78-32-0007-4130KS_ENG2 | 0016541858 | 1103197533 | 2105174511 | AC02 |  | 2026-09-16 | 11LHM/A | 0010 | F/26-236:HS-TEV Engine2 T/R LH_REMOVAL | TECO | H/26-TEV-X0C10-MOD -G-W | 1 | DCA Appr. Req. 1 |  | BKK_H | REM | A330.ED.BKKJA-F/26-236 | 2026-09-16 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
430 | 70461604 | HS-TEV-78-32-0007-4130KS_ENG2 | 0016541859 | 1103197533 | 2105174511 | AC02 |  | 2026-09-16 | 11U | 0020 | F/26-236:HS-TEV Engine2 T/R LH_REMOVAL | TECO | H/26-TEV-X0C10-MOD -G-W | 1 | DCA Appr. Req. 1 |  | BKK_H | REM | A330.ED.BKKJA-F/26-236 | 2026-09-16 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
431 | 70461604 | HS-TEV | 0016531940 | EV122B100926 | EV122B100926 | AC05 |  | 2026-09-15 | 11PAINT | 0010 | RH WING TIP LEADING EDGE OUTER SKIN PAIN | TECO | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  | 2026-09-11 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
432 | 70461604 | HS-TEV | 0016404017 |  | 2105138007 | AC01 |  | 2026-09-09 | 11LHM/A | 0010 | INSPECTION OF TRIMMABLE HOR STAB. | TECO | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | FLOOR_TAIL | BKK_H | DVI | A330.MPD.274000-01-1 | 2026-09-09 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
433 | 70461604 | HS-TEV | 0016526728 | EV110B070926 | EV110B070926 | AC05 |  | 2026-09-15 | 11PAINT | 0010 | CABIN COCKPIT | TECO | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  | 2026-09-11 | 2026-09-07 | 16:25:00 | 2026-09-07 | 19:00:00
434 | 70461604 | HS-TEV | 0016281804 | 1103150242 | 2105101916 | AC02 |  | 2026-09-24 | 11LHM/C | 0010 | G/26-012:LIFE VEST RFID REGISTRATION | TECO | H/26-TEV-X0C10-MOD -G-C | 4 | TG Appr. Req. 4 | CABIN_ALL CABIN | BKK_H | REP | A330.ED.BKKJA-G/26-012 | 2026-09-24 | 2026-08-22 | 00:00:00 | 2026-09-02 | 00:00:00
435 | 70461604 | HS-TEV | 0016403996 |  | 2105137986 | AC01 |  | 2026-09-10 | 11LHM/A | 0010 | TOP-UP FLAP PCU TO CONFIRM THE FLUID LVL | TECO | H/26-TEV-X0C10-BLOK-0-4 | 2 | DCA Appr. Req. 2 | WING_TRAILING EDGE | BKK_H | SVC | A330.MPD.275100-01-1 | 2026-09-10 | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
436 | 70461604 | HS-TEV | 0016404000 |  | 2105137990 | AC01 |  | 2026-09-12 | 11LHM/A | 0010 | LUB OF ALL SLAT STEADY BEARINGS - LHW | TECO | H/26-TEV-X0C10-BLOK-0-4 | 2 | DCA Appr. Req. 2 | WING_TRAILING EDGE | BKK_H | LUB | A330.MPD.278000-06-1 | 2026-09-12 | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
437 | 70461604 | HS-TEV | 0016404134 |  | 2105138100 | AC01 |  | 2026-09-13 | 11LHM/A | 0010 | GVI OF FWD CARGO DOOR EXTERNAL SURFACE | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | FLOOR_FWD COMPT | BKK_H | GVI | A330.MPD.523111-01-1 | 2026-09-12 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
438 | 70461604 | HS-TEV | 0016404135 |  | 2105138101 | AC01 |  | 2026-09-13 | 11LHM/A | 0010 | GVI OF AFT CARGO DOOR INTERNAL STRUCTURE | TECO | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | FLOOR_AFT COMPT | BKK_H | GVI | A330.MPD.523202-02-1 | 2026-09-12 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
439 | 70461604 | HS-TEV | 0016404187 |  | 2105138144 | AC01 |  | 2026-09-15 | 11CLEAN | 0010 | CLEAN OF NLG WELL COMPARTMENT & DOORS | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | FLOOR_LANDING GEAR | BKK_H | CLN | A330.MPD.ZL-123-01-1 | 2026-09-09 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
440 | 70461604 | HS-TEV | 0016404210 |  | 2105138164 | AC01 |  | 2026-09-12 | 11LHM/A | 0010 | INST OF LWR DECK CGO FIREX COMPONENTS | TECO | H/26-TEV-X0C10-BLOK-0-4 |  |  | FLOOR_FWD COMPT | BKK_H | DVI | A330.MPD.262300-04-1;262300-04-2 | 2026-09-12 | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
441 | 70461604 | HS-TEV | 0016404211 |  | 2105138164 | AC01 |  | 2026-09-12 | 11LHM/A | 0020 | INST OF LWR DECK CGO FIREX COMPONENTS | TECO | H/26-TEV-X0C10-BLOK-0-4 |  |  | FLOOR_FWD COMPT | BKK_H | DVI | A330.MPD.262300-04-1;262300-04-2 | 2026-09-12 | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
442 | 70461604 | HS-TEV | 0016404212 |  | 2105138164 | AC01 |  | 2026-09-12 | 11LHM/A | 0030 | INST OF LWR DECK CGO FIREX COMPONENTS | TECO | H/26-TEV-X0C10-BLOK-0-4 |  |  | FLOOR_FWD COMPT | BKK_H | DVI | A330.MPD.262300-04-1;262300-04-2 | 2026-09-12 | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
443 | 70461604 | HS-TEV | 0016491390 | 1103188487 | 2105162147 | AC02 |  | 2026-09-15 | 11LHM/A | 0010 | GVI LININGS,FLOOR PANELS AT AFT CGO COMP | TECO | H/26-TEV-X0C10-NONR | 1 | DCA Appr. Req. 1 |  | BKK_H | VCK | A330.MPD.255300-01-1 | 2026-09-13 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
444 | 70461604 | HS-TEV | 0016503084 | EV080B250826 | EV080B250826 | AC05 |  | 2026-08-25 | 11CMPST | 0010 | CABIN LAVATORY | TECO | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  | 2026-08-26 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
445 | 70461604 | HS-TEV | 0016503162 | EV084B260826 | EV084B260826 | AC05 |  | 2026-08-26 | 11CMPST | 0010 | 72:LP COMPRESSOR ANNULUS FILLERS | TECO | H/26-TEV-X0C10-INSP-N-W |  |  |  | BKK_H | REP |  | 2026-08-26 | 2026-08-26 | 13:54:00 | 2026-08-26 | 19:00:00
446 | 70461604 | HS-TEV | 0016506086 | EV085B270826 | EV085B270826 | AC05 |  | 2026-09-10 | 11PAINT | 0010 | 57:L/E WING UPPER PYLON | TECO | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  | 2026-09-04 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
447 | 70461604 | HS-TEV | 0016522870 | EV097B040926 | EV097B040926 | AC05 |  | 2026-09-07 | 11SH | 0010 | AFT CRG DOOR FRAME BROKEN | TECO | H/26-TEV-X0C10-NONR |  |  |  | 11SH | REP |  | 2026-09-04 | 2026-01-01 | 11:19:00 | 2026-09-04 | 18:00:00
448 | 70461604 | HS-TEV | 0016523587 | EV101B050926 | EV101B050926 | AC05 |  | 2026-09-10 | 11LHM/A | 0010 | RH PYLON FWD BOTTLE - FIRE EXTINGUISHER | TECO | H/26-TEV-X0C10-NONR |  |  |  | 11LHM/A | REP |  | 2026-09-10 | 2026-09-05 | 08:39:00 | 2026-09-08 | 19:00:00
449 | 70461604 | HS-TEV | 0016526693 | EV107B070926 | EV107B070926 | AC05 |  | 2026-09-08 | 11LHM/A | 0010 | FUEL:VALVE WATER DRAIN VALVE POOR CONDIT | TECO | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  | 2026-09-08 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
450 | 70461604 | HS-TEV | 0016404432 |  | 2105138379 | AC01 |  | 2026-09-08 | 11LHM/A | 0010 | INSP WING AND TRIM TANK NACA VENT INTAKE | TECO | H/26-TEV-X0C10-BLOK-0-3 | 2 | DCA Appr. Req. 2 | WING_FUEL | BKK_H | VIC | A330.MPD.281200-02-1 | 2026-09-08 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
451 | 70461604 | HS-TEV | 0016404474 |  | 2105138421 | AC01 |  | 2026-09-09 | 11LQ/IE | 0010 | GVI HARNESS END FITTING-RIB19 TO 14-LHW | TECO | H/26-TEV-X0C10-BLOK-0-3 | 2 | DCA Appr. Req. 2 | IERA_WING | BKK_H | GVI | A330.MPD.200001-05-1 | 2026-09-09 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
452 | 70461604 | HS-TEV | 0016404476 |  | 2105138423 | AC01 |  | 2026-09-12 | 11LQ/IE | 0010 | GVI BRAID CONDUIT END FITTING-FROM RIB 6 | TECO | H/26-TEV-X0C10-BLOK-0-3 | 2 | DCA Appr. Req. 2 | IERA_WING | BKK_H | GVI | A330.MPD.200001-08-1 | 2026-09-15 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
453 | 70461604 | HS-TEV | 0016404478 |  | 2105138425 | AC01 |  | 2026-09-09 | 11LQ/IE | 0010 | GVI-HARNES END FITG-LH WING TIP TO RIB39 | TECO | H/26-TEV-X0C10-BLOK-0-3 | 2 | DCA Appr. Req. 2 | IERA_WING | BKK_H | GVI | A330.MPD.200001-04-1 | 2026-09-12 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
454 | 70461604 | HS-TEV | 0016404522 |  | 2105138469 | AC01 |  | 2026-09-07 | 11LHM/A | 0010 | REMOVAL OF MLG WHEELS-LH MLG | TECO | H/26-TEV-X0C10-BLOK-I-N |  |  | FLOOR_LANDING GEAR | BKK_H | REM | A330.MPD.324100-05-1,324000-19-1 | 2026-08-24 | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
455 | 70461604 | HS-TEV | 0016404524 |  | 2105138471 | AC01 |  | 2026-08-25 | 11LHM/A | 0010 | REMOVAL OF MLG WHEEL BRAKE -LH MLG | TECO | H/26-TEV-X0C10-BLOK-I-N |  |  | FLOOR_LANDING GEAR | BKK_H | REM | A330.MPD.324100-05-1,324000-19-1 | 2026-08-24 | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
456 | 70461604 | HS-TEV | 0016404526 |  | 2105138473 | AC01 |  | 2026-09-07 | 11LHM/A | 0010 | REMOVAL OF MLG AXLE SLEEVE-LH MLG | TECO | H/26-TEV-X0C10-BLOK-I-N |  |  | FLOOR_LANDING GEAR | BKK_H | REM | A330.MPD.324100-05-1,324000-19-1 | 2026-08-24 | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
457 | 70461604 | HS-TEV | 0016404528 |  | 2105138475 | AC01 |  | 2026-09-07 | 11LHM/A | 0010 | REMOVAL OF MLG WHEELS-RH MLG | TECO | H/26-TEV-X0C10-BLOK-I-N |  |  | FLOOR_LANDING GEAR | BKK_H | REM | A330.MPD.324100-05-1,324000-19-1 | 2026-08-24 | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
458 | 70461604 | HS-TEV | 0016404530 |  | 2105138477 | AC01 |  | 2026-08-25 | 11LHM/A | 0010 | REMOVAL OF MLG WHEEL BRAKE-RH MLG | TECO | H/26-TEV-X0C10-BLOK-I-N |  |  | FLOOR_LANDING GEAR | BKK_H | REM | A330.MPD.324100-05-1,324000-19-1 | 2026-08-24 | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
459 | 70461604 | HS-TEV | 0016404532 |  | 2105138479 | AC01 |  | 2026-08-25 | 11LHM/A | 0010 | REMOVAL OF MLG AXLE SLEEVE-RH MLG | TECO | H/26-TEV-X0C10-BLOK-I-N |  |  | FLOOR_LANDING GEAR | BKK_H | REM | A330.MPD.324100-05-1,324000-19-1 | 2026-08-24 | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
460 | 70461604 | HS-TEV | 0016404560 |  | 2105138506 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | DRAIN TRIM TNK WTR CONTAMINATION | TECO | H/26-TEV-X0C10-BLOK-F-I |  |  | WING_FUEL | BKK_H | INS | A330.OPR.902ACW15 | 2026-09-05 | 2026-09-06 | 08:15:00 | 2026-09-06 | 08:15:00
461 | 70461604 | HS-TEV | 0016403823 |  | 2105137824 | AC01 |  | 2026-09-12 | 11LHM/C | 0010 | LEAK CHECK VACUUM TOILET BEFORE CLEAN | TECO | H/26-TEV-X0C10-BLOK-0-2 |  |  | CABIN_LAVATORY | BKK_H | OPC | A330.MPD.383100-05-1 | 2026-09-12 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
462 | 70461604 | HS-TEV | 0016403999 |  | 2105137989 | AC01 |  | 2026-09-10 | 11LHM/A | 0010 | TOP-UP SLAT PCU GEARBOX TO CONFRM FLUID | TECO | H/26-TEV-X0C10-BLOK-0-4 | 2 | DCA Appr. Req. 2 | WING_LEADING EDGE | BKK_H | SVC | A330.MPD.278000-03-1 | 2026-09-10 | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
463 | 70461604 | HS-TEV | 0016404173 |  | 2105138130 | AC01 |  | 2026-09-07 | 11LHM/A | 0010 | OPEN CARGO COMPT DOORS | TECO | H/26-TEV-X0C10-BLOK-I-N |  |  | FLOOR_ALL FLOOR | BKK_H | INS | A330.OPR.001ACA19 | 2026-09-06 | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
464 | 70461604 | HS-TEV | 0016404471 |  | 2105138418 | AC01 |  | 2026-09-10 | 11LHM/A | 0010 | TOP-UP SLAT SYS TORQUE LIMITER LH | TECO | H/26-TEV-X0C10-BLOK-0-4 | 2 | DCA Appr. Req. 2 | WING_LEADING EDGE | BKK_H | SVC | A330.MPD.278000-04-1,278000-04-3 | 2026-09-10 | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
465 | 70461604 | HS-TEV | 0016404472 |  | 2105138419 | AC01 |  | 2026-09-10 | 11LHM/A | 0010 | [TOP-UP SLAT SYS TORQUE LIMITER] RH | TECO | H/26-TEV-X0C10-BLOK-0-4 | 2 | DCA Appr. Req. 2 | WING_LEADING EDGE | BKK_H | SVC | A330.MPD.278000-04-1,278000-04-3 | 2026-09-10 | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
466 | 70461604 | HS-TEV | 0016404477 |  | 2105138424 | AC01 |  | 2026-09-12 | 11LQ/IE | 0010 | GVI BRAID CONDUIT END FITTING-FROM RIB | TECO | H/26-TEV-X0C10-BLOK-0-3 | 2 | DCA Appr. Req. 2 | IERA_WING | BKK_H | GVI | A330.MPD.200001-08-1 | 2026-09-15 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
467 | 70461604 | HS-TEV | 0016404495 |  | 2105138442 | AC01 |  | 2026-09-10 | 11LHM/A | 0010 | JOB SETUP INSP-WING ICE PROT. COMPONENTS | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | WING_LEADING EDGE | BKK_H | REM | A330.MPD.301100-01-1 | 2026-09-13 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
468 | 70461604 | HS-TEV | 0016404523 |  | 2105138470 | AC01 |  | 2026-08-25 | 11LHM/A | 0010 | INSTALLATION OF MLG WHEELS-LH MLG | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | FLOOR_LANDING GEAR | BKK_H | RES | A330.MPD.324100-05-1,324000-19-1 | 2026-08-24 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
469 | 70461604 | HS-TEV | 0016404525 |  | 2105138472 | AC01 |  | 2026-09-07 | 11LHM/A | 0010 | INSTALLATION OF MLG WHEEL BRAKE-LH MLG | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | FLOOR_LANDING GEAR | BKK_H | RES | A330.MPD.324100-05-1,324000-19-1 | 2026-08-24 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
470 | 70461604 | HS-TEV | 0016404529 |  | 2105138476 | AC01 |  | 2026-09-07 | 11LHM/A | 0010 | INSTALLATION OF MLG WHEELS-RH MLG | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | FLOOR_LANDING GEAR | BKK_H | RES | A330.MPD.324100-05-1,324000-19-1 | 2026-08-24 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
471 | 70461604 | HS-TEV | 0016404531 |  | 2105138478 | AC01 |  | 2026-09-07 | 11LHM/A | 0010 | INSTALLATION OF MLG WHEEL BRAKE-RH MLG | TECO | H/26-TEV-X0C10-BLOK-0-1 |  |  | FLOOR_LANDING GEAR | BKK_H | RES | A330.MPD.324100-05-1,324000-19-1 | 2026-08-24 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
472 | 70461604 | HS-TEV | 0016404559 |  | 2105138505 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | DRAIN FUEL TNK WTR CONTAMINATION-WING | TECO | H/26-TEV-X0C10-BLOK-F-I |  |  | WING_FUEL | BKK_H | INS | A330.OPR.901ACW15 | 2026-09-05 | 2026-09-06 | 08:15:00 | 2026-09-06 | 08:15:00
473 | 70461604 | HS-TEV | 0016403934 |  | 2105137928 | AC01 |  | 2026-08-27 | 11LQ/IA | 0010 | INSP FAN COWL DOOR HINGES ENG#2 | REL | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | WING_ENGINE | BKK_H | GVI | A330.MPD.711200-01-2 | 2026-09-23 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
474 | 70461604 | HS-TEV | 0016404056 |  | 2105138042 | AC01 |  | 2026-08-29 | 11NDT | 0010 | SDI (US) LARGE MEMBRANES AROUND 6 FASTEN | REL | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | FLOOR_FUSELAGE | BKK_H | SDI | A330.MPD.533187-01-3 | 2026-09-22 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
475 | 70461604 | HS-TEV | 0016404302 |  | 2105138251 | AC01 |  | 2026-08-27 | 11LQ/IA | 0010 | INSP OF DRAIN HOLE LWR FUSEL FR1,80 | REL | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | FLOOR_FUSELAGE | BKK_H | VIC | A330.MPD.531900-01-1 | 2026-09-09 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
476 | 70461604 | HS-TEV | 0016352224 | EV009C250526 | EV009C250526 | AC05 |  | 2026-08-24 | BKK_L | 0010 | 38 LAV 73 BUMPER AT OUTSIDE DOOR BROKEN | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2026-05-25 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
477 | 70461604 | HS-TEV | 0016352226 | EV009C250526 | EV009C250526 | AC05 |  | 2026-08-24 | 12LC/AP | 0020 | 38 LAV 73 BUMPER AT OUTSIDE DOOR BROKEN | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
478 | 70461604 | HS-TEV | 0016352225 | EV009C250526 | EV009C250526 | AC05 |  | 2026-08-24 | BKK_L | 0020 | 38 LAV 73 BUMPER AT OUTSIDE DOOR BROKEN | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
479 | 70461604 | HS-TEV | 0016352228 | EV010C250526 | EV010C250526 | AC05 |  | 2026-08-24 | BKK_L | 0010 | 25 30G ARMREST COVER BROKEN | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2026-05-25 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
480 | 70461604 | HS-TEV | 0016352230 | EV010C250526 | EV010C250526 | AC05 |  | 2026-08-24 | 12LC/AP | 0020 | 25 30G ARMREST COVER BROKEN | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
481 | 70461604 | HS-TEV | 0016352229 | EV010C250526 | EV010C250526 | AC05 |  | 2026-08-24 | BKK_L | 0020 | 25 30G ARMREST COVER BROKEN | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
482 | 70461604 | HS-TEV | 0015708144 | EV035C110525 | EV035C110525 | AC05 |  | 2026-08-24 | BKK_L | 0010 | 25 LAV 53 THERE IS SCRATCH ON THE CORNER | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
483 | 70461604 | HS-TEV | 0015708146 | EV035C110525 | EV035C110525 | AC05 |  | 2026-08-24 | 11CMPST | 0020 | 25 LAV 53 THERE IS SCRATCH ON THE CORNER | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2026-03-09 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
484 | 70461604 | HS-TEV | 0016000703 | EV072C281025 | EV072C281025 | AC05 |  | 2026-08-24 | BKK_L | 0010 | 11 20G PLACARD ''PASTEN SEAT BELT'' UNDE | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
485 | 70461604 | HS-TEV | 0016000704 | EV072C281025 | EV072C281025 | AC05 |  | 2026-08-24 | BKK_L | 0020 | 11 20G PLACARD ''PASTEN SEAT BELT'' UNDE | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2025-10-28 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
486 | 70461604 | HS-TEV | 0016504712 | EV085B260826 | EV085B260826 | AC05 |  | 2026-08-24 | 11CA | 0010 | CABIN;25 CARPET WALKWAY ALL ZONE NEED TO | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LHM/C | REP |  | 2026-09-04 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
487 | 70461604 | HS-TEV | 0016346262 | EV097C220526 | EV097C220526 | AC05 |  | 2026-08-24 | BKK_L | 0010 | 23 32A IFE SCREEN LOOSE FROM SOCKET . | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2026-05-22 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
488 | 70461604 | HS-TEV | 0016346264 | EV097C220526 | EV097C220526 | AC05 |  | 2026-08-24 | 12LC/AP | 0020 | 23 32A IFE SCREEN LOOSE FROM SOCKET . | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
489 | 70461604 | HS-TEV | 0016346263 | EV097C220526 | EV097C220526 | AC05 |  | 2026-08-24 | BKK_L | 0020 | 23 32A IFE SCREEN LOOSE FROM SOCKET . | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
490 | 70461604 | HS-TEV | 0016533928 | EV133A120926 | EV133A120926 | AC05 |  | 2026-09-12 | 11PAINT | 0010 | WINGS - GENERAL | REL | H/26-TEV-X0C10-NONR |  |  |  | 11PAINT | REP |  | 2026-10-02 | 2026-09-12 | 11:04:00 | 2026-09-19 | 16:00:00
491 | 70461604 | HS-TEV | 0016533956 | EV134B120926 | EV134B120926 | AC05 |  | 2026-08-24 | 11LHM/C | 0010 | 25:DADO PANEL | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
492 | 70461604 | HS-TEV | 0016533957 | EV134B120926 | EV134B120926 | AC05 |  | 2026-08-24 | 11CLEAN | 0020 | 25:DADO PANEL | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  | 2026-09-12 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
493 | 70461604 | HS-TEV | 0016533958 | EV134B120926 | EV134B120926 | AC05 |  | 2026-08-24 | 11CMPST | 0030 | 25:DADO PANEL | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
494 | 70461604 | HS-TEV | 0016533959 | EV134B120926 | EV134B120926 | AC05 |  | 2026-08-24 | 11PAINT | 0040 | 25:DADO PANEL | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
495 | 70461604 | HS-TEV | 0016533960 | EV134B120926 | EV134B120926 | AC05 |  | 2026-08-24 | 11LHM/C | 0050 | 25:DADO PANEL | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
496 | 70461604 | HS-TEV | 0016553519 | EV149B230926 | EV149B230926 | AC05 |  | 2026-08-24 | 11CMPST | 0010 | LOWER FUSELAGE ZONE 100 SERVICE DOORS L/ | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  | 2026-09-25 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
497 | 70461604 | HS-TEV | 0016553520 | EV149B230926 | EV149B230926 | AC05 |  | 2026-08-24 | 11PAINT | 0020 | LOWER FUSELAGE ZONE 100 SERVICE DOORS L/ | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  | 2026-09-29 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
498 | 70461604 | HS-TEV | 0016555357 | EV156B240926 | EV156B240926 | AC05 |  | 2026-09-24 | 11SH | 0010 | INSP FOUND FUSELAGE SKIN PANEL AT FR83+9 | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  |  | 2026-09-24 | 13:54:00 | 2026-09-24 | 19:00:00
499 | 70461604 | HS-TEV | 0016555358 | EV156B240926 | EV156B240926 | AC05 |  | 2026-09-24 | 11SH | 0020 | INSP FOUND FUSELAGE SKIN PANEL AT FR83+9 | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  |  | 2026-09-24 | 13:54:00 | 2026-09-24 | 19:00:00
500 | 70461604 | HS-TEV | 0016555359 | EV156B240926 | EV156B240926 | AC05 |  | 2026-09-24 | 11SH | 0030 | INSP FOUND FUSELAGE SKIN PANEL AT FR83+9 | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  |  | 2026-09-24 | 13:54:00 | 2026-09-24 | 19:00:00
501 | 70461604 | HS-TEV | 0016555360 | EV156B240926 | EV156B240926 | AC05 |  | 2026-09-24 | 11NDT | 0040 | INSP FOUND FUSELAGE SKIN PANEL AT FR83+9 | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  | 2026-09-24 | 2026-09-24 | 13:54:00 | 2026-09-24 | 19:00:00
502 | 70461604 | HS-TEV | 0016556084 | EV156B240926 | EV156B240926 | AC05 |  | 2026-09-24 | 11NDT | 0050 | INSP FOUND FUSELAGE SKIN PANEL AT FR83+9 | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  | 2026-09-24 | 2026-09-24 | 13:54:00 | 2026-09-24 | 19:00:00
503 | 70461604 | HS-TEV | 0016556085 | EV156B240926 | EV156B240926 | AC05 |  | 2026-09-24 | 11SH | 0060 | INSP FOUND FUSELAGE SKIN PANEL AT FR83+9 | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  |  | 2026-09-24 | 13:54:00 | 2026-09-24 | 19:00:00
504 | 70461604 | HS-TEV | 0016556086 | EV156B240926 | EV156B240926 | AC05 |  | 2026-09-24 | 11PAINT | 0070 | INSP FOUND FUSELAGE SKIN PANEL AT FR83+9 | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  |  | 2026-09-24 | 13:54:00 | 2026-09-24 | 19:00:00
505 | 70461604 | HS-TEV | 0016563680 | EV165B300926 | EV165B300926 | AC05 |  | 2026-08-24 | 11PAINT | 0010 | RH WING MOVABLE FLAP TRACK FAIRING NO.2 | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  | 2026-10-01 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
506 | 70461604 | HS-TEV | 0016566540 | EV167B021026 | EV167B021026 | AC05 |  | 2026-10-02 | 11CMPST | 0010 | FWD.CARGO COMPARTMENT UNDER FLOOR COOLIN | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  | 2026-10-02 | 2026-10-02 | 10:37:00 | 2026-10-03 | 19:00:00
507 | 70461604 | HS-TEV | 0016404021 |  | 2105138011 | AC01 |  | 2026-08-29 | 11NDT | 0010 | SDI-FRAMES CORNER FITTING AREA FR67-68 | REL | H/26-TEV-X0C10-BLOK-0-3 |  |  | FLOOR_FUSELAGE | BKK_H | SDI | A330.MPD.534014-01-1 | 2026-09-24 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
508 | 70461604 | HS-TEV | 0016403836 |  | 2105137837 | AC01 |  | 2026-08-29 | 11LHM/A | 0010 | FUC FAN COWL LATCH TENSION-RR ENG#1 | REL | H/26-TEV-X0C10-BLOK-0-3 | 2 | DCA Appr. Req. 2 | WING_ENGINE | BKK_H | FUC | A330.MPD.711300-R4-1 | 2026-09-22 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
509 | 70461604 | HS-TEV | 0016404087 |  | 2105138068 | AC01 |  | 2026-08-27 | 11LHM/A | 0010 | GVI SHROUD BOX (EWIS) LHW | REL | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | WING_FUEL | BKK_H | GVI | A330.MPD.ZL-572-01-5 | 2026-09-10 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
510 | 70461604 | HS-TEV | 0016404095 |  | 2105138076 | AC01 |  | 2026-08-27 | 11LHM/A | 0010 | GVI OF T/R 6 O'CLOCK BEAM PIVOT E#1 | REL | H/26-TEV-X0C10-BLOK-0-2 |  |  | WING_ENGINE | BKK_H | GVI | A330.MPD.783227-01-1 | 2026-09-06 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
511 | 70461604 | HS-TEV | 0016404205 |  | 2105138161 | AC01 |  | 2026-08-31 | 11LHM/A | 0010 | CLEAN-PICCOLO TUBE OF SMOKE DETECTION | REL | H/26-TEV-X0C10-BLOK-0-4 | 1 | DCA Appr. Req. 1 | FLOOR_FWD COMPT | BKK_H | RES | A330.MPD.261500-02-1 | 2026-09-24 | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
512 | 70461604 | HS-TEV | 0016506098 | EV087B270826 | EV087B270826 | AC05 |  | 2026-08-24 | 11PAINT | 0010 | 11:GREEN HYD.SERVICE PANEL PLACARD | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  | 2026-09-07 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
513 | 70461604 | HS-TEV | 0015916759 | 1103087039 | 2105002939 | AC03 |  | 2026-08-22 | 11NDT | 0010 | 531335:INSP FR40 SKIN PANEL JUNCTION | REL | H/26-TEV-X0C10-MOD -G-F | 0 | AD |  | BKK_H | INS | A330.TO.ITO-531335 | 2026-09-10 | 2026-08-22 | 00:00:00 | 2026-09-02 | 00:00:00
514 | 70461604 | HS-TEV | 0015916760 | 1103087039 | 2105002939 | AC03 |  | 2026-08-22 | 11NDT | 0020 | 531335:INSP FR40 SKIN PANEL JUNCTION | REL | H/26-TEV-X0C10-MOD -G-F | 0 | AD |  | BKK_H | INS | A330.TO.ITO-531335 | 2026-09-10 | 2026-08-22 | 00:00:00 | 2026-09-02 | 00:00:00
515 | 70461604 | HS-TEV | 0015916761 | 1103087039 | 2105002939 | AC03 |  | 2026-08-22 | 11SH | 0030 | 531335:INSP FR40 SKIN PANEL JUNCTION | REL | H/26-TEV-X0C10-MOD -G-F | 0 | AD |  | BKK_H | INS | A330.TO.ITO-531335 | 2026-09-11 | 2026-08-22 | 00:00:00 | 2026-09-02 | 00:00:00
516 | 70461604 | HS-TEV | 0015916762 | 1103087039 | 2105002939 | AC03 |  | 2026-08-22 | 11NDT | 0040 | 531335:INSP FR40 SKIN PANEL JUNCTION | REL | H/26-TEV-X0C10-MOD -G-F | 0 | AD |  | BKK_H | INS | A330.TO.ITO-531335 |  | 2026-08-22 | 00:00:00 | 2026-09-02 | 00:00:00
517 | 70461604 | HS-TEV | 0015916763 | 1103087039 | 2105002939 | AC03 |  | 2026-08-22 | 11SH | 0050 | 531335:INSP FR40 SKIN PANEL JUNCTION | REL | H/26-TEV-X0C10-MOD -G-F | 0 | AD |  | BKK_H | INS | A330.TO.ITO-531335 | 2026-09-12 | 2026-08-22 | 00:00:00 | 2026-09-02 | 00:00:00
518 | 70461604 | HS-TEV | 0015916764 | 1103087039 | 2105002939 | AC03 |  | 2026-08-22 | 11SH | 0060 | 531335:INSP FR40 SKIN PANEL JUNCTION | REL | H/26-TEV-X0C10-MOD -G-F | 0 | AD |  | BKK_H | INS | A330.TO.ITO-531335 |  | 2026-08-22 | 00:00:00 | 2026-09-02 | 00:00:00
519 | 70461604 | HS-TEV | 0015916765 | 1103087039 | 2105002939 | AC03 |  | 2026-08-22 | 11LHM/A | 0070 | 531335:INSP FR40 SKIN PANEL JUNCTION | REL | H/26-TEV-X0C10-MOD -G-F | 0 | AD |  | BKK_H | INS | A330.TO.ITO-531335 |  | 2026-08-22 | 00:00:00 | 2026-09-02 | 00:00:00
520 | 70461604 | HS-TEV | 0016501222 | EV073A240826 | EV073A240826 | AC05 |  | 2026-08-24 | 11LHM/A | 0010 | LOWER DECK CARGO LOADING SYSTEM | REL | H/26-TEV-X0C10-NONR |  |  |  | 11SH | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
521 | 70461604 | HS-TEV | 0016501223 | EV073A240826 | EV073A240826 | AC05 |  | 2026-08-24 | 11SH | 0020 | LOWER DECK CARGO LOADING SYSTEM | REL | H/26-TEV-X0C10-NONR |  |  |  | 11SH | REP |  | 2026-08-27 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
522 | 70461604 | HS-TEV | 0016501224 | EV073A240826 | EV073A240826 | AC05 |  | 2026-08-24 | 11LHM/A | 0030 | LOWER DECK CARGO LOADING SYSTEM | REL | H/26-TEV-X0C10-NONR |  |  |  | 11SH | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
523 | 70461604 | HS-TEV | 0016501225 | EV074A240826 | EV074A240826 | AC05 |  | 2026-08-24 | 11LHM/A | 0010 | LOWER DECK CARGO LOADING SYS | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LHM/A | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
524 | 70461604 | HS-TEV | 0016501226 | EV074A240826 | EV074A240826 | AC05 |  | 2026-08-24 | 11SH | 0020 | LOWER DECK CARGO LOADING SYS | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LHM/A | REP |  | 2026-08-27 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
525 | 70461604 | HS-TEV | 0016501227 | EV074A240826 | EV074A240826 | AC05 |  | 2026-08-24 | 11LHM/A | 0030 | LOWER DECK CARGO LOADING SYS | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LHM/A | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
526 | 70461604 | HS-TEV | 0016404048 |  | 2105138037 | AC01 |  | 2026-08-20 | 11LQ/IA | 0010 | DET OF OF NOSE LANDING GEAR, HINGES | REL | H/26-TEV-X0C10-BLOK-0-1 | 2 | DCA Appr. Req. 2 | FLOOR_LANDING GEAR | BKK_H | DET | A330.MPD.528203-01-3 | 2026-09-05 | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
527 | 70461604 | HS-TEV | 0016404049 |  | 2105138037 | AC01 |  | 2026-08-20 | 11LQ/IA | 0020 | DET OF OF NOSE LANDING GEAR, HINGES | REL | H/26-TEV-X0C10-BLOK-0-1 | 2 | DCA Appr. Req. 2 | FLOOR_LANDING GEAR | BKK_H | DET | A330.MPD.528203-01-3 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
528 | 70461604 | HS-TEV | 0016491389 | 1103188486 | 2105162146 | AC02 |  | 2026-08-24 | 11LHM/A | 0010 | GVI-LININGS,FLOOR PANELS,SEALING STRIPS, | REL | H/26-TEV-X0C10-NONR | 1 | DCA Appr. Req. 1 |  | BKK_H | VCK | A330.MPD.255200-01-1 | 2026-09-23 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
529 | 70461604 | HS-TEV | 0015807713 | EV029C100725 | EV029C100725 | AC05 |  | 2026-08-24 | BKK_L | 0010 | 25 24K IN ARM MONITOR LOOSE | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2025-07-11 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
530 | 70461604 | HS-TEV | 0015807714 | EV029C100725 | EV029C100725 | AC05 |  | 2026-08-24 | BKK_L | 0020 | 25 24K IN ARM MONITOR LOOSE | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
531 | 70461604 | HS-TEV | 0016503085 | EV081B250826 | EV081B250826 | AC05 |  | 2026-08-24 | 11CMPST | 0010 | CABIN LAVATORY | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
532 | 70461604 | HS-TEV | 0016506088 | EV081B250826 | EV081B250826 | AC05 |  | 2026-08-24 | 11PAINT | 0020 | CABIN LAVATORY | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  | 2026-08-27 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
533 | 70461604 | HS-TEV | 0016528755 | EV117B080926 | EV117B080926 | AC05 |  | 2026-08-24 | 11LHM/A | 0010 | FWD.CARGO COMPARTMENT ROLLER TRACK SECTI | REL | H/26-TEV-X0C10-NONR |  |  |  | 11E | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
534 | 70461604 | HS-TEV | 0016528756 | EV117B080926 | EV117B080926 | AC05 |  | 2026-08-24 | 11SH | 0020 | FWD.CARGO COMPARTMENT ROLLER TRACK SECTI | REL | H/26-TEV-X0C10-NONR |  |  |  | 11E | REP |  | 2026-09-19 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
535 | 70461604 | HS-TEV | 0016528757 | EV117B080926 | EV117B080926 | AC05 |  | 2026-08-24 | 11LHM/A | 0030 | FWD.CARGO COMPARTMENT ROLLER TRACK SECTI | REL | H/26-TEV-X0C10-NONR |  |  |  | 11E | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
536 | 70461604 | HS-TEV | 0016531933 | EV121B100926 | EV121B100926 | AC05 |  | 2026-08-24 | 11LHM/E | 0010 | LH/RH WING NAVIGATION LIGHT LENSES CLOUD | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  | 2026-09-15 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
537 | 70461604 | HS-TEV | 0016531934 | EV121B100926 | EV121B100926 | AC05 |  | 2026-08-24 | 21SDB1 | 0020 | LH/RH WING NAVIGATION LIGHT LENSES CLOUD | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  | 2026-09-15 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
538 | 70461604 | HS-TEV | 0016531935 | EV121B100926 | EV121B100926 | AC05 |  | 2026-08-24 | 11LHM/E | 0030 | LH/RH WING NAVIGATION LIGHT LENSES CLOUD | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
539 | 70461604 | HS-TEV | 0016532572 | EV128B110926 | EV128B110926 | AC05 |  | 2026-09-11 | 11LHM/A | 0010 | AFT. CARGO COMPARTMENT POWER DRIVE UNIT | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  | 2026-09-11 | 2026-09-11 | 10:06:00 | 2026-09-11 | 19:00:00
540 | 70461604 | HS-TEV | 0016533924 | EV132B120926 | EV132B120926 | AC05 |  | 2026-09-12 | 11LHM/C | 0010 | 25:B/C PASSENGER SEAT | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  | 2026-09-22 | 2026-09-12 | 10:28:00 | 2026-09-12 | 19:00:00
541 | 70461604 | HS-TEV | 0016533925 | EV132B120926 | EV132B120926 | AC05 |  | 2026-09-12 | 11CLEAN | 0020 | 25:B/C PASSENGER SEAT | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  | 2026-09-12 | 2026-09-12 | 10:28:00 | 2026-09-12 | 19:00:00
542 | 70461604 | HS-TEV | 0016533926 | EV132B120926 | EV132B120926 | AC05 |  | 2026-09-12 | 11CMPST | 0030 | 25:B/C PASSENGER SEAT | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  | 2026-09-16 | 2026-09-12 | 10:28:00 | 2026-09-12 | 19:00:00
543 | 70461604 | HS-TEV | 0016533927 | EV132B120926 | EV132B120926 | AC05 |  | 2026-09-12 | 11LHM/C | 0040 | 25:B/C PASSENGER SEAT | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  |  | 2026-09-12 | 10:28:00 | 2026-09-12 | 19:00:00
544 | 70461604 | HS-TEV | 0016557946 | EV160B250926 | EV160B250926 | AC05 |  | 2026-09-25 | 11LHM/A | 0010 | AFT.CARGO COMPARTMENT ROLLER TRACK AFTER | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  |  | 2026-09-25 | 16:28:00 | 2026-09-29 | 19:00:00
545 | 70461604 | HS-TEV | 0016557947 | EV160B250926 | EV160B250926 | AC05 |  | 2026-09-25 | 11SH | 0020 | AFT.CARGO COMPARTMENT ROLLER TRACK AFTER | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  | 2026-10-01 | 2026-09-25 | 16:28:00 | 2026-09-29 | 19:00:00
546 | 70461604 | HS-TEV | 0016557948 | EV160B250926 | EV160B250926 | AC05 |  | 2026-09-25 | 11LHM/A | 0030 | AFT.CARGO COMPARTMENT ROLLER TRACK AFTER | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  |  | 2026-09-25 | 16:28:00 | 2026-09-29 | 19:00:00
547 | 70461604 | HS-TEV | 0016331674 | EV073C140526 | EV073C140526 | AC05 |  | 2026-08-24 | BKK_L | 0010 | 25 ESPRESSO MAKER COMP 1A06 INOP | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_L | REP |  | 2026-05-15 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
548 | 70461604 | HS-TEV | 0016331675 | EV073C140526 | EV073C140526 | AC05 |  | 2026-08-24 | BKK_L | 0020 | 25 ESPRESSO MAKER COMP 1A06 INOP | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_L | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
549 | 70461604 | HS-TEV | 0016170950 | EV081C080226 | EV081C080226 | AC05 |  | 2026-08-24 | BKK_L | 0010 | 25 SEAT 41A HEADREST COVER MISSING. | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_L | REP |  | 2026-02-08 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
550 | 70461604 | HS-TEV | 0016177828 | EV081C080226 | EV081C080226 | AC05 |  | 2026-08-24 | BKK_L | 0020 | 25 SEAT 41A HEADREST COVER MISSING. | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_L | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
551 | 70461604 | HS-TEV | 0016403893 |  | 2105137891 | AC01 |  | 2026-08-25 | 11LHM/A | 0010 | JOB SET-UP FOR NDT WING REAR SPAR FW -LH | REL | H/26-TEV-X0C10-BLOK-0-1 |  |  | WING_FUEL | BKK_H | REM | A330.MPD.572052-03-4,-5,-7 | 2026-09-14 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
552 | 70461604 | HS-TEV | 0016403901 |  | 2105137897 | AC01 |  | 2026-08-25 | 11LHM/A | 0010 | JOB SET-UP FOR NDT WING REAR SPAR FW -RH | REL | H/26-TEV-X0C10-BLOK-0-1 |  |  | WING_FUEL | BKK_H | REM | A330.MPD.572052-03-4,-5,-7 | 2026-09-14 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
553 | 70461604 | HS-TEV | 0015993488 | EV019C201025 | EV019C201025 | AC05 |  | 2026-08-24 | BKK_L | 0010 | 23 50K MONITOR LOOSED | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_L | REP |  | 2025-10-22 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
554 | 70461604 | HS-TEV | 0015994297 | EV019C201025 | EV019C201025 | AC05 |  | 2026-08-24 | BKK_L | 0020 | 23 50K MONITOR LOOSED | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_L | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
555 | 70461604 | HS-TEV | 0015777113 | 1103063888 | 2104962726 | AC03 |  | 2026-08-22 | 11SH | 0010 | 570785: INSP FASTENER HOLES AT FR 40 | REL | H/26-TEV-X0C10-MOD -G-F | 0 | AD |  | BKK_H | NDT | A330.TO.570785-08 | 2026-09-07 | 2026-08-22 | 00:00:00 | 2026-09-02 | 00:00:00
556 | 70461604 | HS-TEV | 0015777114 | 1103063888 | 2104962726 | AC03 |  | 2026-08-22 | 11NDT | 0020 | 570785: INSP FASTENER HOLES AT FR 40 | REL | H/26-TEV-X0C10-MOD -G-F | 0 | AD |  | BKK_H | NDT | A330.TO.570785-08 | 2026-09-09 | 2026-08-22 | 00:00:00 | 2026-09-02 | 00:00:00
557 | 70461604 | HS-TEV | 0015777115 | 1103063888 | 2104962726 | AC03 |  | 2026-08-22 | 11LHM/A | 0030 | 570785: INSP FASTENER HOLES AT FR 40 | REL | H/26-TEV-X0C10-MOD -G-F | 0 | AD |  | BKK_H | NDT | A330.TO.570785-08 |  | 2026-08-22 | 00:00:00 | 2026-09-02 | 00:00:00
558 | 70461604 | HS-TEV | 0016403914 |  | 2105137908 | AC01 |  | 2026-08-29 | 11NDT | 0010 | NDT SPLICE PLATE CIRCUMFER FR72 LH/RH. | REL | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | CABIN_INTERIOR | BKK_H | SDI | A330.MPD.534107-02-5 | 2026-09-14 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
559 | 70461604 | HS-TEV | 0016511928 |  | 2105137908 | AC01 |  | 2026-08-29 | 11SH | 0020 | NDT SPLICE PLATE CIRCUMFER FR72 LH/RH. | REL | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | CABIN_INTERIOR | BKK_H | SDI | A330.MPD.534107-02-5 | 2026-09-14 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
560 | 70461604 | HS-TEV | 0016476768 | EV014C090826 | EV014C090826 | AC05 |  | 2026-08-24 | BKK_L | 0010 | 25 SEAT 17K RECLINE INOP . | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_L | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
561 | 70461604 | HS-TEV | 0016476770 | EV014C090826 | EV014C090826 | AC05 |  | 2026-08-24 | 12LC/AP | 0020 | 25 SEAT 17K RECLINE INOP . | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_L | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
562 | 70461604 | HS-TEV | 0016476769 | EV014C090826 | EV014C090826 | AC05 |  | 2026-08-24 | BKK_L | 0020 | 25 SEAT 17K RECLINE INOP . | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_L | REP |  | 2026-08-09 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
563 | 70461604 | HS-TEV | 0016564567 | EV166B011026 | EV166B011026 | AC05 |  | 2026-10-01 | 11LHM/A | 0010 | FWD.CARGO COMPARTMENT POWER DRIVE UNIT R | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  | 2026-10-01 | 2026-10-01 | 10:37:00 | 2026-10-02 | 19:00:00
564 | 70461604 | HS-TEV | 0015843868 | 1103075136 | 2104982322 | AC02 |  | 2026-08-24 | 11LHM/A | 0010 | CLN IP AND HP COMPRESSORS - ENG 1 | REL | H/26-TEV-X0C10-NONR | 4 | TG Appr. Req. 4 |  | BKK_H | REP | A330.MPD.7200200-TG01 |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
565 | 70461604 | HS-TEV | 0015843869 | 1103075136 | 2104982322 | AC02 |  | 2026-08-24 | 11LHM/E | 0020 | CLN IP AND HP COMPRESSORS - ENG 1 | REL | H/26-TEV-X0C10-NONR | 4 | TG Appr. Req. 4 |  | BKK_H | REP | A330.MPD.7200200-TG01 | 2026-08-04 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
566 | 70461604 | HS-TEV | 0016404297 |  | 2105138246 | AC01 |  | 2026-09-02 | 11SH | 0010 | INST-MID PAX/CREW DOOR SCUFF PLATE | REL | H/26-TEV-X0C10-BLOK-0-5 |  |  | CABIN_DOOR | BKK_H | DVI | A330.MPD.532124-01-1 | 2026-09-15 | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
567 | 70461604 | HS-TEV | 0016404299 |  | 2105138248 | AC01 |  | 2026-09-02 | 11SH | 0010 | INST-AFT PAX/CREW DOOR SCUFF PLATES | REL | H/26-TEV-X0C10-BLOK-0-5 |  |  | CABIN_DOOR | BKK_H | DVI | A330.MPD.534132-01-1;534132-02-1 | 2026-09-14 | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
568 | 70461604 | HS-TEV | 0016404301 |  | 2105138250 | AC01 |  | 2026-09-04 | 11SH | 0010 | INST-BULK CARGO DOOR SCUFF PLATE | REL | H/26-TEV-X0C10-BLOK-0-6 |  |  | FLOOR_AFT COMPT | BKK_H | DVI | A330.MPD.534144-01-1,534144-03-1 | 2026-09-22 | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
569 | 70461604 | HS-TEV | 0016404538 |  | 2105138484 | AC01 |  | 2026-08-20 | 11LHM/A | 0010 | Service NLG Shock Absorber | REL | H/26-TEV-X0C10-BLOK-0-5 | 2 | DCA Appr. Req. 2 | FLOOR_LANDING GEAR | BKK_H | SVC | A330.MPD.322100-03-1 | 2026-09-13 | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
570 | 70461604 | HS-TEV | 0016404537 |  | 2105138484 | AC01 |  | 2026-08-20 | 11LHM/A | 0020 | Service NLG Shock Absorber | REL | H/26-TEV-X0C10-BLOK-0-5 | 2 | DCA Appr. Req. 2 | FLOOR_LANDING GEAR | BKK_H | SVC | A330.MPD.322100-03-1 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
571 | 70461604 | HS-TEV | 0016111989 | EV001C291225 | EV001C291225 | AC05 |  | 2026-08-24 | BKK_L | 0010 | 25 27B HANDSET INOP. | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_L | REP |  | 2026-04-28 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
572 | 70461604 | HS-TEV | 0016112700 | EV001C291225 | EV001C291225 | AC05 |  | 2026-08-24 | BKK_L | 0020 | 25 27B HANDSET INOP. | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_L | REP |  | 2026-01-01 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
573 | 70461604 | HS-TEV | 0016304640 | EV001C291225 | EV001C291225 | AC05 |  | 2026-08-24 | BKK_L | 0030 | 25 27B HANDSET INOP. | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_L | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
574 | 70461604 | HS-TEV | 0016428208 | EV084C110726 | EV084C110726 | AC05 |  | 2026-08-24 | BKK_L | 0010 | 23 SEAT 31A, 31F, 41A, 41B, 51D IFE INOP | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2026-07-14 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
575 | 70461604 | HS-TEV | 0016428210 | EV084C110726 | EV084C110726 | AC05 |  | 2026-08-24 | 12LC/AP | 0020 | 23 SEAT 31A, 31F, 41A, 41B, 51D IFE INOP | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
576 | 70461604 | HS-TEV | 0016428209 | EV084C110726 | EV084C110726 | AC05 |  | 2026-08-24 | BKK_L | 0020 | 23 SEAT 31A, 31F, 41A, 41B, 51D IFE INOP | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
577 | 70461604 | HS-TEV | 0015824394 | EV093C200725 | EV093C200725 | AC05 |  | 2026-08-24 | BKK_L | 0010 | 23 31B MONITOR BROKEN. | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_L | REP |  | 2025-07-26 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
578 | 70461604 | HS-TEV | 0015824395 | EV093C200725 | EV093C200725 | AC05 |  | 2026-08-24 | BKK_L | 0020 | 23 31B MONITOR BROKEN. | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_L | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
579 | 70461604 | HS-TEV | 0016490187 | EV097F170826 | EV097F170826 | AC05 |  | 2026-08-24 | BKK_L | 0010 | 21 VENT PACK BAY VENT FAULT | REL | H/26-TEV-X0C10-NONR | C | Category C |  | BKK_L | REP |  | 2026-08-17 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
580 | 70461604 | HS-TEV | 0016490188 | EV097F170826 | EV097F170826 | AC05 |  | 2026-08-24 | BKK_L | 0020 | 21 VENT PACK BAY VENT FAULT | REL | H/26-TEV-X0C10-NONR | C | Category C |  | BKK_L | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
581 | 70461604 | HS-TEV | 0016499044 |  | 2105137977 | AC01 |  | 2026-08-29 | 11LHM/C | 0010 | REPLACE SEAT COVERS | REL | H/26-TEV-X0C10-BLOK-0-3 | 4 | TG Appr. Req. 4 | CABIN_INTERIOR | BKK_H | RAR | A330.MPD.2521000002-TG01 |  | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
582 | 70461604 | HS-TEV | 0016403985 |  | 2105137977 | AC01 |  | 2026-08-29 | 11LHM/C | 0030 | REPLACE SEAT COVERS | REL | H/26-TEV-X0C10-BLOK-0-3 | 4 | TG Appr. Req. 4 | CABIN_INTERIOR | BKK_H | RAR | A330.MPD.2521000002-TG01 |  | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
583 | 70461604 | HS-TEV | 0016404407 |  | 2105138354 | AC01 |  | 2026-08-29 | 11LQ/IC | 0010 | INSP - COMPRESSOR INLET FILTER | REL | H/26-TEV-X0C10-BLOK-0-3 | 2 | DCA Appr. Req. 2 | CABIN_LAVATORY | BKK_H | DVI | A330.MPD.384200-01-1 |  | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
584 | 70461604 | HS-TEV | 0016571630 | EV034F051026 | EV034F051026 | AC05 |  | 2026-10-05 | BKK_H | 0010 | 78 : ENG#2 T/R INBD. HING ACCESS COVER | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
585 | 70461604 | HS-TEV | 0015897481 | EV099C280825 | EV099C280825 | AC05 |  | 2026-08-24 | BKK_L | 0010 | 25 51G MONITOR HINGE BROKEN | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
586 | 70461604 | HS-TEV | 0015897482 | EV099C280825 | EV099C280825 | AC05 |  | 2026-08-24 | BKK_L | 0020 | 25 51G MONITOR HINGE BROKEN | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
587 | 70461604 | HS-TEV | 0016402770 |  | 2105137751 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | OPC CROSSFEED VALVE USING IND MOTOR | REL | H/26-TEV-X0C10-BLOK-0-7 |  |  | WING_FUEL | BKK_H | INS | A330.MPD.282300-02-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
588 | 70461604 | HS-TEV | 0016402773 |  | 2105137754 | AC01 |  | 2026-08-27 | 11LHM/A | 0010 | JOB SET-UP GVI INNER T/E FIXED STRUCTURE | REL | H/26-TEV-X0C10-BLOK-0-1 |  |  | WING_TRAILING EDGE | BKK_H | REM | A330.MPD.ZL-573-01-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
589 | 70461604 | HS-TEV | 0016402775 |  | 2105137756 | AC01 | EWIS | 2026-08-27 | 11LQ/IA | 0010 | GVI INNER T/E FIXED STRUCTURE -LH | REL | H/26-TEV-X0C10-BLOK-0-2 |  |  | WING_TRAILING EDGE | BKK_H | GVI | A330.MPD.ZL-573-01-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
590 | 70461604 | HS-TEV | 0016403776 |  | 2105137757 | AC01 | EWIS | 2026-08-27 | 11LQ/IA | 0010 | GVI INNER T/E FIXED STRUCTURE -RH | REL | H/26-TEV-X0C10-BLOK-0-2 |  |  | WING_TRAILING EDGE | BKK_H | GVI | A330.MPD.ZL-573-01-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
591 | 70461604 | HS-TEV | 0016403777 |  | 2105137758 | AC01 |  | 2026-09-02 | 11LHM/A | 0010 | CLOSE-UP GVI INNER T/E FIXED STRUCTURE | REL | H/26-TEV-X0C10-BLOK-0-5 |  |  | WING_TRAILING EDGE | BKK_H | RES | A330.MPD.ZL-573-01-1 |  | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
592 | 70461604 | HS-TEV | 0016403779 |  | 2105137780 | AC01 |  | 2026-08-25 | 11LHM/A | 0010 | JOB SET-UP FOR GVI LH CENTER T/E FIXED | REL | H/26-TEV-X0C10-BLOK-0-1 |  |  | WING_TRAILING EDGE | BKK_H | REM | A330.MPD.ZL-574-01-1 |  | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
593 | 70461604 | HS-TEV | 0016403781 |  | 2105137782 | AC01 | EWIS | 2026-08-29 | 11LQ/IA | 0010 | GVI LH CENTER T/E FIXED STRUCTURE | REL | H/26-TEV-X0C10-BLOK-0-3 |  |  | WING_TRAILING EDGE | BKK_H | GVI | A330.MPD.ZL-574-01-1 |  | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
594 | 70461604 | HS-TEV | 0016403782 |  | 2105137783 | AC01 | EWIS | 2026-08-29 | 11LQ/IA | 0010 | GVI RH CENTER T/E FIXED STRUCTURE | REL | H/26-TEV-X0C10-BLOK-0-3 |  |  | WING_TRAILING EDGE | BKK_H | GVI | A330.MPD.ZL-574-01-1 |  | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
595 | 70461604 | HS-TEV | 0016403785 |  | 2105137786 | AC01 |  | 2026-08-25 | 11LHM/A | 0010 | JOB SET-UP FOR GVI LH OUTER T/E FIXED | REL | H/26-TEV-X0C10-BLOK-0-1 |  |  | WING_TRAILING EDGE | BKK_H | REM | A330.MPD.ZL-575-01-1 |  | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
596 | 70461604 | HS-TEV | 0016403786 |  | 2105137787 | AC01 |  | 2026-08-25 | 11LHM/A | 0010 | JOB SET-UP FOR GVI RH OUTER T/E FIXED | REL | H/26-TEV-X0C10-BLOK-0-1 |  |  | WING_TRAILING EDGE | BKK_H | REM | A330.MPD.ZL-575-01-1 |  | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
597 | 70461604 | HS-TEV | 0016403805 |  | 2105137806 | AC01 |  | 2026-09-04 | 11LHM/E | 0010 | OPERATIONAL CHECK OF SLAT AND FLAP SENSO | REL | H/26-TEV-X0C10-BLOK-0-6 |  |  | IERA_WING | BKK_H | INS | A330.MPD.315000-01-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
598 | 70461604 | HS-TEV | 0016403814 |  | 2105137815 | AC01 |  | 2026-09-05 | 11LHM/E | 0010 | LOW RANGE LEAK CHECK OF PRINCIPAL | REL | H/26-TEV-X0C10-BLOK-0-7 | 2 | DCA Appr. Req. 2 | IERA_FLOOR | BKK_H | OPC | A330.MPD.341300-04-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
599 | 70461604 | HS-TEV | 0016403816 |  | 2105137817 | AC01 |  | 2026-09-05 | 11LHM/E | 0010 | LOW RANGE LEAK CHECK OF STANDBY PNEUMATI | REL | H/26-TEV-X0C10-BLOK-0-7 | 1 | DCA Appr. Req. 1 | IERA_FLOOR | BKK_H | OPC | A330.MPD.342200-02-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
600 | 70461604 | HS-TEV | 0016403825 |  | 2105137826 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | OPC FLY-BY-WIRE RUDDER TRIM STBY. CH. | REL | H/26-TEV-X0C10-BLOK-0-7 | 2 | DCA Appr. Req. 2 | FLOOR_TAIL | BKK_H | VIC | A330.MPD.272100-19-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
601 | 70461604 | HS-TEV | 0016403826 |  | 2105137827 | AC01 |  | 2026-09-04 | 11LHM/A | 0010 | OPC RUDDER DAMPING MEASUREMENT BY BITE. | REL | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | FLOOR_TAIL | BKK_H | OPC | A330.MPD.272400-08-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
602 | 70461604 | HS-TEV | 0016403828 |  | 2105137829 | AC01 |  | 2026-09-04 | 11LHM/A | 0010 | OPC OF THSA CHECKABLE SHEAR PIN. | REL | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | FLOOR_TAIL | BKK_H | OPC | A330.MPD.274000-18-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
603 | 70461604 | HS-TEV | 0016403830 |  | 2105137831 | AC01 | EWIS | 2026-08-27 | 11LQ/IA | 0010 | INSP FAN AND ACCESSORY GEARBOX -RR ENG#1 | REL | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | WING_ENGINE | BKK_H | GVI | A330.MPD.ZL-412-02-3 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
604 | 70461604 | HS-TEV | 0016403831 |  | 2105137832 | AC01 | EWIS | 2026-08-27 | 11LQ/IA | 0010 | INSP FAN AND ACCESSORY GEARBOX -RR ENG#2 | REL | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | WING_ENGINE | BKK_H | GVI | A330.MPD.ZL-412-02-3 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
605 | 70461604 | HS-TEV | 0016403832 |  | 2105137833 | AC01 | EWIS | 2026-08-27 | 11LQ/IA | 0010 | INSPECTION OF HOT SECTION -RR ENG#1 | REL | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | WING_ENGINE | BKK_H | GVI | A330.MPD.ZL-413-02-3 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
606 | 70461604 | HS-TEV | 0016403833 |  | 2105137834 | AC01 | EWIS | 2026-08-27 | 11LQ/IA | 0010 | INSPECTION OF HOT SECTION -RR ENG#2 | REL | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | WING_ENGINE | BKK_H | GVI | A330.MPD.ZL-413-02-3 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
607 | 70461604 | HS-TEV | 0016403834 |  | 2105137835 | AC01 | EWIS | 2026-08-27 | 11LHM/A | 0010 | INSPECTION OF THRUST REVERSER-RR ENG#1 | REL | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | WING_ENGINE | BKK_H | GVI | A330.MPD.ZL-417-02-3 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
608 | 70461604 | HS-TEV | 0016403835 |  | 2105137836 | AC01 | EWIS | 2026-08-27 | 11LHM/A | 0010 | INSPECTION OF THRUST REVERSER-RR ENG#2 | REL | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | WING_ENGINE | BKK_H | GVI | A330.MPD.ZL-417-02-3 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
609 | 70461604 | HS-TEV | 0016403837 |  | 2105137838 | AC01 |  | 2026-08-29 | 11LHM/A | 0010 | FUC FAN COWL LATCH TENSION-RR ENG#2 | REL | H/26-TEV-X0C10-BLOK-0-3 | 2 | DCA Appr. Req. 2 | WING_ENGINE | BKK_H | FUC | A330.MPD.711300-R4-1 |  | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
610 | 70461604 | HS-TEV | 0016403840 |  | 2105137841 | AC01 |  | 2026-08-27 | 11LQ/IA | 0010 | INSP THRUST RESERVER HINGE-RR ENG#1 | REL | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | WING_ENGINE | BKK_H | SDI | A330.MPD.783200-03-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
611 | 70461604 | HS-TEV | 0016403841 |  | 2105137842 | AC01 |  | 2026-08-27 | 11LQ/IA | 0010 | INSP THRUST RESERVER HINGE-RR ENG#2 | REL | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | WING_ENGINE | BKK_H | SDI | A330.MPD.783200-03-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
612 | 70461604 | HS-TEV | 0016403842 |  | 2105137843 | AC01 |  | 2026-08-27 | 11LQ/IA | 0010 | INSP T/R INNER FIXED STRUCTURE-RR ENG#1 | REL | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | WING_ENGINE | BKK_H | VIC | A330.MPD.783201-R1-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
613 | 70461604 | HS-TEV | 0016403843 |  | 2105137844 | AC01 |  | 2026-08-27 | 11LQ/IA | 0010 | INSP T/R INNER FIXED STRUCTURE-RR ENG#2 | REL | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | WING_ENGINE | BKK_H | VIC | A330.MPD.783201-R1-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
614 | 70461604 | HS-TEV | 0016403844 |  | 2105137845 | AC01 |  | 2026-08-27 | 11LQ/IA | 0010 | INSP T/R LATCHES, SURROUNDING-RR ENG#1 | REL | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | WING_ENGINE | BKK_H | SPC | A330.MPD.783245-01-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
615 | 70461604 | HS-TEV | 0016403845 |  | 2105137846 | AC01 |  | 2026-08-27 | 11LQ/IA | 0010 | INSP T/R LATCHES, SURROUNDING-RR ENG#2 | REL | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | WING_ENGINE | BKK_H | SPC | A330.MPD.783245-01-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
616 | 70461604 | HS-TEV | 0016403846 |  | 2105137847 | AC01 |  | 2026-08-25 | 11LHM/A | 0010 | JOB SETUP FOR DVI T/E SKIN RIB8-12 ,LH | REL | H/26-TEV-X0C10-BLOK-0-1 |  |  | WING_TRAILING EDGE | BKK_H | REM | A330.MPD.575025-01-5;575025-01-7 |  | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
617 | 70461604 | HS-TEV | 0016403849 |  | 2105137850 | AC01 |  | 2026-08-25 | 11LHM/A | 0010 | JOB SETUP FOR DVI T/E SKIN RIB8-12 ,RH | REL | H/26-TEV-X0C10-BLOK-0-1 |  |  | WING_TRAILING EDGE | BKK_H | REM | A330.MPD.575025-01-5;575025-01-7 |  | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
618 | 70461604 | HS-TEV | 0016403850 |  | 2105137851 | AC01 |  | 2026-08-29 | 11LQ/IA | 0010 | INSPECTION OF T/E SKIN RIB8-12 ,RH | REL | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | WING_TRAILING EDGE | BKK_H | DET | A330.MPD.575025-01-5;575025-01-7 |  | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
619 | 70461604 | HS-TEV | 0016403855 |  | 2105137856 | AC01 |  | 2026-09-06 | 11LHM/A | 0010 | DEPRESERVATION OF ENGINE -RR ENG#2 | REL | H/26-TEV-X0C10-BLOK-F-I |  |  | WING_ENGINE | BKK_H | SVC | A330.OPR.DEPRESERVE ENGINE |  | 2026-09-06 | 08:15:00 | 2026-09-06 | 08:15:00
620 | 70461604 | HS-TEV | 0016403864 |  | 2105137865 | AC01 |  | 2026-09-04 | 11LHM/A | 0010 | OPC TO CFM CLOSR OF VALVES 3 POS SW. | REL | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | WING_FUEL | BKK_H | OPC | A330.MPD.282700-02-4 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
621 | 70461604 | HS-TEV | 0016403868 |  | 2105137868 | AC01 |  | 2026-09-06 | 11LHM/E | 0010 | DISCONNECT-AIRCRAFT STATIC GROUNDING | REL | H/26-TEV-X0C10-BLOK-F-I |  |  | IERA_FLOOR | BKK_H | SVC | A330.OPR.CONNECT-AIRCRAF |  | 2026-09-06 | 08:15:00 | 2026-09-06 | 08:15:00
622 | 70461604 | HS-TEV | 0016403870 |  | 2105137870 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | OPC SECONDARY AND TERTIARY LOCK-RR ENG#1 | REL | H/26-TEV-X0C10-BLOK-0-7 | 1 | DCA Appr. Req. 1 | WING_ENGINE | BKK_H | OPC | A330.MPD.783700-R1-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
623 | 70461604 | HS-TEV | 0016403871 |  | 2105137871 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | OPC SECONDARY AND TERTIARY LOCK-RR ENG#2 | REL | H/26-TEV-X0C10-BLOK-0-7 | 1 | DCA Appr. Req. 1 | WING_ENGINE | BKK_H | OPC | A330.MPD.783700-R1-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
624 | 70461604 | HS-TEV | 0016403872 |  | 2105137872 | AC01 | EWIS | 2026-08-27 | 11LQ/IA | 0010 | INSPECTION OF EXHAUST NOZZLE-RR ENG#1 | REL | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | WING_ENGINE | BKK_H | GVI | A330.MPD.ZL-414-02-3 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
625 | 70461604 | HS-TEV | 0016403873 |  | 2105137873 | AC01 | EWIS | 2026-08-27 | 11LQ/IA | 0010 | INSPECTION OF EXHAUST NOZZLE-RR ENG#2 | REL | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | WING_ENGINE | BKK_H | GVI | A330.MPD.ZL-414-02-3 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
626 | 70461604 | HS-TEV | 0016403874 |  | 2105137874 | AC01 | EWIS | 2026-08-27 | 11LQ/IA | 0010 | INSPECTION CHECK OF FAN COWLS-RR ENG#1 | REL | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | WING_ENGINE | BKK_H | GVI | A330.MPD.ZL-415-02-3 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
627 | 70461604 | HS-TEV | 0016403875 |  | 2105137875 | AC01 | EWIS | 2026-08-27 | 11LQ/IA | 0010 | INSPECTION CHECK OF FAN COWLS-RR ENG#2 | REL | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | WING_ENGINE | BKK_H | GVI | A330.MPD.ZL-415-02-3 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
628 | 70461604 | HS-TEV | 0016403878 |  | 2105137878 | AC01 |  | 2026-09-04 | 11LHM/A | 0010 | INSTALL PYLON ACCESS PANELS PYLON1 | REL | H/26-TEV-X0C10-BLOK-0-6 |  |  | WING_ENGINE | BKK_H | RES | A330.MPD.ZL-453-01-1,ZL-454-05-2 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
629 | 70461604 | HS-TEV | 0016403879 |  | 2105137879 | AC01 |  | 2026-09-04 | 11LHM/A | 0010 | INSTALL PYLON ACCESS PANELS PYLON2 | REL | H/26-TEV-X0C10-BLOK-0-6 |  |  | WING_ENGINE | BKK_H | RES | A330.MPD.ZL-453-01-1,ZL-454-05-2 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
630 | 70461604 | HS-TEV | 0016403882 |  | 2105137882 | AC01 | EWIS | 2026-08-27 | 11LQ/IA | 0010 | INSP LOWER PYLON - RR PYLON#1 | REL | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | WING_ENGINE | BKK_H | GVI | A330.MPD.ZL-453-01-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
631 | 70461604 | HS-TEV | 0016403883 |  | 2105137883 | AC01 | EWIS | 2026-08-27 | 11LQ/IA | 0010 | INSP LOWER PYLON - RR PYLON#2 | REL | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | WING_ENGINE | BKK_H | GVI | A330.MPD.ZL-453-01-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
632 | 70461604 | HS-TEV | 0016403886 |  | 2105137886 | AC01 |  | 2026-09-04 | 11LHM/A | 0010 | OPC MANUAL BLEED SHUT OFF - RR ENG#1 | REL | H/26-TEV-X0C10-BLOK-0-6 | 1 | DCA Appr. Req. 1 | WING_ENGINE | BKK_H | OPC | A330.MPD.361100-06-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
633 | 70461604 | HS-TEV | 0016403887 |  | 2105137887 | AC01 |  | 2026-09-04 | 11LHM/A | 0010 | OPC MANUAL BLEED SHUT OFF - RR ENG#2 | REL | H/26-TEV-X0C10-BLOK-0-6 | 1 | DCA Appr. Req. 1 | WING_ENGINE | BKK_H | OPC | A330.MPD.361100-06-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
634 | 70461604 | HS-TEV | 0016403888 |  | 2105137888 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | OPC/VIC COMPART A, C, F DRAIN-RR PYLON1 | REL | H/26-TEV-X0C10-BLOK-0-7 | 1 | DCA Appr. Req. 1 | WING_ENGINE | BKK_H | OPC | A330.MPD.545100-04-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
635 | 70461604 | HS-TEV | 0016403889 |  | 2105137889 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | OPC/VIC COMPART A, C, F DRAIN-RR PYLON2 | REL | H/26-TEV-X0C10-BLOK-0-7 | 1 | DCA Appr. Req. 1 | WING_ENGINE | BKK_H | OPC | A330.MPD.545100-04-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
636 | 70461604 | HS-TEV | 0016403894 |  | 2105137892 | AC01 |  | 2026-08-25 | 11CLEAN | 0010 | RMV PAINT FOR NDT WING RIB 1-7 , LH | REL | H/26-TEV-X0C10-BLOK-0-1 |  |  | WING_FUEL | BKK_H | INS | A330.MPD.572052-03-4,-5,-7 |  | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
637 | 70461604 | HS-TEV | 0016403896 |  | 2105137894 | AC01 |  | 2026-08-29 | 11CLEAN | 0010 | APPLY PAINT FOR NDT WING RIB 1-7 , LH | REL | H/26-TEV-X0C10-BLOK-0-3 |  |  | WING_FUEL | BKK_H | INS | A330.MPD.572052-03-4,-5,-7 |  | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
638 | 70461604 | HS-TEV | 0016403902 |  | 2105137898 | AC01 |  | 2026-08-25 | 11CLEAN | 0010 | RMV PAINT FOR NDT WING RIB 1-7 , RH | REL | H/26-TEV-X0C10-BLOK-0-1 |  |  | WING_FUEL | BKK_H | INS | A330.MPD.572052-03-4,-5,-7 |  | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
639 | 70461604 | HS-TEV | 0016403904 |  | 2105137900 | AC01 |  | 2026-08-29 | 11CLEAN | 0010 | APPLY PAINT FOR NDT WING RIB 1-7 , RH | REL | H/26-TEV-X0C10-BLOK-0-3 |  |  | WING_FUEL | BKK_H | INS | A330.MPD.572052-03-4,-5,-7 |  | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
640 | 70461604 | HS-TEV | 0016403907 |  | 2105137903 | AC01 |  | 2026-09-05 | 11LHM/E | 0010 | OPC and CLEAN OF THE ULB | REL | H/26-TEV-X0C10-BLOK-0-7 |  |  | IERA_FLOOR | BKK_H | OPC | A330.MPD.313300-03-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
641 | 70461604 | HS-TEV | 0016403915 |  | 2105137909 | AC01 |  | 2026-09-02 | 11LHM/C | 0010 | CLOSE-UP FOR NDT SPLICE PLATE FR72. | REL | H/26-TEV-X0C10-BLOK-0-5 |  |  | CABIN_INTERIOR | BKK_H | INS | A330.MPD.534107-02-5 |  | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
642 | 70461604 | HS-TEV | 0016403920 |  | 2105137914 | AC01 |  | 2026-08-24 | 11LQ/IA | 0010 | RECORD-REMAINING FUEL ALL FUEL TANK. | REL | H/26-TEV-X0C10-BLOK-I-N |  |  | WING_FUEL | BKK_H | INS | PP.OPR.INIT_FINAL |  | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
643 | 70461604 | HS-TEV | 0016403921 |  | 2105137915 | AC01 |  | 2026-09-04 | 11LHM/A | 0010 | OPC TO CONFIRM LP VALVE RR ENG#1 | REL | H/26-TEV-X0C10-BLOK-0-6 | 1 | DCA Appr. Req. 1 | WING_ENGINE | BKK_H | OPC | A330.MPD.282400-03-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
644 | 70461604 | HS-TEV | 0016403922 |  | 2105137916 | AC01 |  | 2026-09-04 | 11LHM/A | 0010 | OPC TO CONFIRM LP VALVE RR ENG#2 | REL | H/26-TEV-X0C10-BLOK-0-6 | 1 | DCA Appr. Req. 1 | WING_ENGINE | BKK_H | OPC | A330.MPD.282400-03-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
645 | 70461604 | HS-TEV | 0016403923 |  | 2105137917 | AC01 |  | 2026-08-24 | 11LHM/A | 0010 | ARRANGEMENT OF DOCKS -WING GROUP | REL | H/26-TEV-X0C10-BLOK-I-N | 4 | TG Appr. Req. 4 | WING_ALL WING | BKK_H | SVC | PP.OPR.FOR ARRANGE DOCK |  | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
646 | 70461604 | HS-TEV | 0016403924 |  | 2105137918 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | DE-DOCK AND CHECKLIST-WING GROUP | REL | H/26-TEV-X0C10-BLOK-0-7 | 4 | TG Appr. Req. 4 | WING_ALL WING | BKK_H | SVC | PP.OPR.FOR DE-DOCK |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
647 | 70461604 | HS-TEV | 0016403925 |  | 2105137919 | AC01 |  | 2026-08-24 | 11LHM/A | 0010 | ARRANGEMENT OF DOCKS -FLOOR GROUP | REL | H/26-TEV-X0C10-BLOK-I-N | 4 | TG Appr. Req. 4 | FLOOR_ALL FLOOR | BKK_H | SVC | PP.OPR.FOR ARRANGE DOCK |  | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
648 | 70461604 | HS-TEV | 0016403926 |  | 2105137920 | AC01 |  | 2026-08-24 | 11LHM/C | 0010 | ARRANGEMENT OF DOCKS -CABIN GROUP | REL | H/26-TEV-X0C10-BLOK-I-N | 4 | TG Appr. Req. 4 | CABIN_ALL CABIN | BKK_H | SVC | PP.OPR.FOR ARRANGE DOCK |  | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
649 | 70461604 | HS-TEV | 0016403927 |  | 2105137921 | AC01 |  | 2026-08-24 | 11LHM/E | 0010 | ARRANGEMENT OF DOCKS -IERA GROUP | REL | H/26-TEV-X0C10-BLOK-I-N | 4 | TG Appr. Req. 4 | IERA_ALL IERA | BKK_H | SVC | PP.OPR.FOR ARRANGE DOCK |  | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
650 | 70461604 | HS-TEV | 0016403928 |  | 2105137922 | AC01 |  | 2026-08-24 | 11LHM/A | 0010 | ARRANGEMENT OF DOCKS-LA-C GROUP | REL | H/26-TEV-X0C10-BLOK-I-N | 4 | TG Appr. Req. 4 | ALL_ALL GRP | BKK_H | SVC | PP.OPR.FOR ARRANGE DOCK |  | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
651 | 70461604 | HS-TEV | 0016403929 |  | 2105137923 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | DE-DOCK AND CHECKLIST-FLOOR GROUP | REL | H/26-TEV-X0C10-BLOK-0-7 | 4 | TG Appr. Req. 4 | FLOOR_ALL FLOOR | BKK_H | SVC | PP.OPR.FOR DE-DOCK |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
652 | 70461604 | HS-TEV | 0016403930 |  | 2105137924 | AC01 |  | 2026-09-06 | 11LHM/C | 0010 | DE-DOCK AND CHECKLIST- CABIN GROUP | REL | H/26-TEV-X0C10-BLOK-F-I | 4 | TG Appr. Req. 4 | CABIN_ALL CABIN | BKK_H | SVC | PP.OPR.FOR DE-DOCK |  | 2026-09-06 | 08:15:00 | 2026-09-06 | 08:15:00
653 | 70461604 | HS-TEV | 0016403931 |  | 2105137925 | AC01 |  | 2026-09-06 | 11LHM/E | 0010 | DE-DOCK AND CHECKLIST- IERA GROUP | REL | H/26-TEV-X0C10-BLOK-F-I | 4 | TG Appr. Req. 4 | IERA_ALL IERA | BKK_H | SVC | PP.OPR.FOR DE-DOCK |  | 2026-09-06 | 08:15:00 | 2026-09-06 | 08:15:00
654 | 70461604 | HS-TEV | 0016403932 |  | 2105137926 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | DE-DOCK AND CHECKLIST LA-C GROUP | REL | H/26-TEV-X0C10-BLOK-0-7 | 4 | TG Appr. Req. 4 | ALL_ALL GRP | BKK_H | SVC | PP.OPR.FOR DE-DOCK |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
655 | 70461604 | HS-TEV | 0016403933 |  | 2105137927 | AC01 |  | 2026-08-27 | 11LQ/IA | 0010 | INSP FAN COWL DOOR HINGES ENG#1 | REL | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | WING_ENGINE | BKK_H | GVI | A330.MPD.711200-01-2 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
656 | 70461604 | HS-TEV | 0016403935 |  | 2105137929 | AC01 |  | 2026-08-27 | 11LQ/IA | 0010 | INSP FAN COWL DOOR LATCHES ENG#1 | REL | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | WING_ENGINE | BKK_H | GVI | A330.MPD.711246-01-2 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
657 | 70461604 | HS-TEV | 0016403936 |  | 2105137930 | AC01 |  | 2026-08-27 | 11LQ/IA | 0010 | INSP FAN COWL DOOR LATCHES ENG#2 | REL | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | WING_ENGINE | BKK_H | GVI | A330.MPD.711246-01-2 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
658 | 70461604 | HS-TEV | 0016403937 |  | 2105137931 | AC01 |  | 2026-08-27 | 11LQ/IC | 0010 | INSP-PORTABLE OXYGEN FLOW MASK. | REL | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | CABIN_INTERIOR | BKK_H | DI | A330.MPD.353200-06-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
659 | 70461604 | HS-TEV | 0016403941 |  | 2105137935 | AC01 |  | 2026-08-27 | 11LQ/IA | 0010 | GVI THE FAN COWL ENG#1 | REL | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | WING_ENGINE | BKK_H | GVI | A330.MPD.711300-R7-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
660 | 70461604 | HS-TEV | 0016403942 |  | 2105137936 | AC01 |  | 2026-08-27 | 11LQ/IA | 0010 | GVI THE FAN COWL ENG#2 | REL | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | WING_ENGINE | BKK_H | GVI | A330.MPD.711300-R7-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
661 | 70461604 | HS-TEV | 0016403943 |  | 2105137937 | AC01 |  | 2026-08-27 | 11LQ/IA | 0010 | GVI THE GAS GENERATOR FAIRINGS ENG#1 | REL | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | WING_ENGINE | BKK_H | GVI | A330.MPD.722200-R1-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
662 | 70461604 | HS-TEV | 0016403944 |  | 2105137938 | AC01 |  | 2026-08-27 | 11LQ/IA | 0010 | GVI THE GAS GENERATOR FAIRINGS ENG#2 | REL | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | WING_ENGINE | BKK_H | GVI | A330.MPD.722200-R1-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
663 | 70461604 | HS-TEV | 0016403945 |  | 2105137939 | AC01 |  | 2026-08-27 | 11LQ/IA | 0010 | GVI THE AIR INTAKE COWL ENG#1 | REL | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | WING_ENGINE | BKK_H | GVI | A330.MPD.716100-R4-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
664 | 70461604 | HS-TEV | 0016403946 |  | 2105137940 | AC01 |  | 2026-08-27 | 11LQ/IA | 0010 | GVI THE AIR INTAKE COWL ENG#2 | REL | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | WING_ENGINE | BKK_H | GVI | A330.MPD.716100-R4-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
665 | 70461604 | HS-TEV | 0016403947 |  | 2105137941 | AC01 |  | 2026-08-27 | 11LQ/IA | 0010 | GVI THE SPLITTER FAIRING ENG#1 | REL | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | WING_ENGINE | BKK_H | GVI | A330.MPD.722200-R2-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
666 | 70461604 | HS-TEV | 0016403948 |  | 2105137942 | AC01 |  | 2026-08-27 | 11LQ/IA | 0010 | GVI THE SPLITTER FAIRING ENG#2 | REL | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | WING_ENGINE | BKK_H | GVI | A330.MPD.722200-R2-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
667 | 70461604 | HS-TEV | 0016403949 |  | 2105137943 | AC01 |  | 2026-08-27 | 11LQ/IA | 0010 | GVI THRUST REVERSER STRUCTURE ENG#1 | REL | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | WING_ENGINE | BKK_H | GVI | A330.MPD.783201-R5-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
668 | 70461604 | HS-TEV | 0016403950 |  | 2105137944 | AC01 |  | 2026-08-27 | 11LQ/IA | 0010 | GVI THRUST REVERSER STRUCTURE ENG#2 | REL | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | WING_ENGINE | BKK_H | GVI | A330.MPD.783201-R5-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
669 | 70461604 | HS-TEV | 0016403954 |  | 2105137948 | AC01 |  | 2026-09-04 | 11LHM/E | 0010 | FUC AIR EXTRACTION POINT | REL | H/26-TEV-X0C10-BLOK-0-6 |  |  | FLOOR_FWD COMPT | BKK_H | OPC | A330.MPD.261800-13-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
670 | 70461604 | HS-TEV | 0016403973 |  | 2105137965 | AC01 |  | 2026-08-31 | 11LHM/A | 0010 | INSTALL LOWER FAIRING (RR)#RH | REL | H/26-TEV-X0C10-BLOK-0-4 |  |  | WING_ENGINE | BKK_H | RES | A330.OPR.545100-07-1,545100-10-1 |  | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
671 | 70461604 | HS-TEV | 0016403994 |  | 2105137984 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | TEST HIPRESSURE GROUND CONNECTOR | REL | H/26-TEV-X0C10-BLOK-0-7 | 2 | DCA Appr. Req. 2 | FLOOR_AIR COND | BKK_H | FNC | A330.MPD.215200-01-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
672 | 70461604 | HS-TEV | 0016404002 |  | 2105137992 | AC01 |  | 2026-08-27 | 11LQ/IA | 0010 | INSP FUSELAGE SKIN FR53.5 TO FR53.7 | REL | H/26-TEV-X0C10-BLOK-0-2 |  |  | FLOOR_FUSELAGE | BKK_H | DET | A330.MPD.533201-01-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
673 | 70461604 | HS-TEV | 0016404006 |  | 2105137996 | AC01 |  | 2026-09-04 | 11LHM/A | 0010 | INSTALL BELLY FAIRING 195 196 | REL | H/26-TEV-X0C10-BLOK-0-6 |  |  | FLOOR_FUSELAGE | BKK_H | RES | A330.MPD.ZL-195-03-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
674 | 70461604 | HS-TEV | 0016404012 |  | 2105138002 | AC01 |  | 2026-08-27 | 11LHM/A | 0010 | INSP IP BLEED CHECK VALVE ENG#1 | REL | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | WING_ENGINE | BKK_H | DET | A330.MPD.361141-02-2 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
675 | 70461604 | HS-TEV | 0016404013 |  | 2105138003 | AC01 |  | 2026-08-27 | 11LHM/A | 0010 | INSP IP BLEED CHECK VALVE ENG#2 | REL | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | WING_ENGINE | BKK_H | DET | A330.MPD.361141-02-2 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
676 | 70461604 | HS-TEV | 0016404014 |  | 2105138004 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | OPC ENG AIR INT ICE PROTECTION ENG#1 | REL | H/26-TEV-X0C10-BLOK-0-7 | 1 | DCA Appr. Req. 1 | WING_ENGINE | BKK_H | OPC | A330.MPD.302103-01-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
677 | 70461604 | HS-TEV | 0016404015 |  | 2105138005 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | OPC ENG AIR INT ICE PROTECTION ENG#2 | REL | H/26-TEV-X0C10-BLOK-0-7 | 1 | DCA Appr. Req. 1 | WING_ENGINE | BKK_H | OPC | A330.MPD.302103-01-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
678 | 70461604 | HS-TEV | 0016404016 |  | 2105138006 | AC01 |  | 2026-08-27 | 11LHM/C | 0010 | CHECK ECONOMY SEAT SCHEDULED. | REL | H/26-TEV-X0C10-BLOK-0-2 | 4 | TG Appr. Req. 4 | CABIN_INTERIOR | BKK_H | FUC | A330.MPD.2521010303-TG01 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
679 | 70461604 | HS-TEV | 0016404018 |  | 2105138008 | AC01 |  | 2026-09-04 | 11LHM/E | 0010 | OPC-LOW FREQUENCY UNDERWATER LOCATOR | REL | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | IERA_FLOOR | BKK_H | OPC | A330.MPD.256536-01-1-STC01 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
680 | 70461604 | HS-TEV | 0016404022 |  | 2105138012 | AC01 |  | 2026-08-25 | 11LHM/A | 0010 | REM - INSULATION BLANKETS FR67-68/FR70 | REL | H/26-TEV-X0C10-BLOK-0-1 |  |  | FLOOR_AFT COMPT | BKK_H | REM | A330.OPR.534014-01-1 |  | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
681 | 70461604 | HS-TEV | 0016404028 |  | 2105138018 | AC01 |  | 2026-09-04 | 11LHM/A | 0010 | OPC-EACH EMERGENCY ISOLATION VALVE | REL | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | IERA_WING | BKK_H | OPC | A330.MPD.281100-05-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
682 | 70461604 | HS-TEV | 0016404032 |  | 2105138022 | AC01 |  | 2026-09-04 | 11LHM/C | 0010 | OPC OF INERTIA LOCKING DEVICE MECHANISM. | REL | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | CABIN_ALL CABIN | BKK_H | OPC | A330.MPD.252100-11-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
683 | 70461604 | HS-TEV | 0016404035 |  | 2105138025 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | OPC of THS Actuator Override Mechanism | REL | H/26-TEV-X0C10-BLOK-0-7 | 1 | DCA Appr. Req. 1 | FLOOR_TAIL | BKK_H | OPC | A330.MPD.274000-20-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
684 | 70461604 | HS-TEV | 0016404046 |  | 2105138035 | AC01 |  | 2026-08-24 | 11LHM/E | 0010 | Operational Check of Manual and Automati | REL | H/26-TEV-X0C10-BLOK-I-N | 1 | DCA Appr. Req. 1 | IERA_ALL IERA | BKK_H | OPC | A330.MPD.464000-03-1 |  | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
685 | 70461604 | HS-TEV | 0016404054 |  | 2105138040 | AC01 |  | 2026-08-31 | 11LHM/A | 0010 | DVI Aft Engine Mount Lower Beam Engine1 | REL | H/26-TEV-X0C10-BLOK-0-4 |  |  | WING_ENGINE | BKK_H | DET | A330.MPD.712201-07-1 |  | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
686 | 70461604 | HS-TEV | 0016404055 |  | 2105138041 | AC01 |  | 2026-08-31 | 11LHM/A | 0010 | DVI Aft Engine Mount Lower Beam Engine2 | REL | H/26-TEV-X0C10-BLOK-0-4 |  |  | WING_ENGINE | BKK_H | DET | A330.MPD.712201-07-1 |  | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
687 | 70461604 | HS-TEV | 0016404063 |  | 2105138047 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | FUNCTIONAL CHECK OF APU BLEED VALVE | REL | H/26-TEV-X0C10-BLOK-0-7 | 0 | AD | FLOOR_TAIL | BKK_H | FNC | A330.MPD.361200-04-2 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
688 | 70461604 | HS-TEV | 0016404074 |  | 2105138057 | AC01 |  | 2026-08-20 | 11NDT | 0010 | SDI (US & X-RAY) OUT WING BOT SKIN STR15 | REL | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | WING_ALL WING | BKK_H | SDI | A330.MPD.572183-02-10 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
689 | 70461604 | HS-TEV | 0016404075 |  | 2105138057 | AC01 |  | 2026-08-20 | 11NDT | 0020 | SDI (US & X-RAY) OUT WING BOT SKIN STR15 | REL | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | WING_ALL WING | BKK_H | SDI | A330.MPD.572183-02-10 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
690 | 70461604 | HS-TEV | 0016404088 |  | 2105138069 | AC01 |  | 2026-08-27 | 11LHM/A | 0010 | GVI SHROUD BOX (EWIS) RHW | REL | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | WING_FUEL | BKK_H | GVI | A330.MPD.ZL-572-01-5 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
691 | 70461604 | HS-TEV | 0016404091 |  | 2105138072 | AC01 |  | 2026-08-27 | 11LHM/A | 0010 | DETAILED INSP ENG T/R E#1 | REL | H/26-TEV-X0C10-BLOK-0-2 |  |  | WING_ENGINE | BKK_H | DVI | A330.MPD.783224-01-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
692 | 70461604 | HS-TEV | 0016404092 |  | 2105138073 | AC01 |  | 2026-08-27 | 11LHM/A | 0010 | DETAILED INSP ENG T/R E#2 | REL | H/26-TEV-X0C10-BLOK-0-2 |  |  | WING_ENGINE | BKK_H | DVI | A330.MPD.783224-01-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
693 | 70461604 | HS-TEV | 0016404093 |  | 2105138074 | AC01 |  | 2026-08-27 | 11LHM/A | 0010 | DETAILED INSP ENG T/R PIVOT DOOR E#1 | REL | H/26-TEV-X0C10-BLOK-0-2 |  |  | WING_ENGINE | BKK_H | DVI | A330.MPD.783225-01-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
694 | 70461604 | HS-TEV | 0016404094 |  | 2105138075 | AC01 |  | 2026-08-27 | 11LHM/A | 0010 | DETAILED INSP ENG T/R PIVOT DOOR E#2 | REL | H/26-TEV-X0C10-BLOK-0-2 |  |  | WING_ENGINE | BKK_H | DVI | A330.MPD.783225-01-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
695 | 70461604 | HS-TEV | 0016404096 |  | 2105138077 | AC01 |  | 2026-08-27 | 11LHM/A | 0010 | GVI OF T/R 6 O'CLOCK BEAM PIVOT E#2 | REL | H/26-TEV-X0C10-BLOK-0-2 |  |  | WING_ENGINE | BKK_H | GVI | A330.MPD.783227-01-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
696 | 70461604 | HS-TEV | 0016404097 |  | 2105138078 | AC01 |  | 2026-08-20 | 11LQ/IA | 0010 | GVI 2Ku components for proper mounting | REL | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | FLOOR_FUSELAGE | BKK_H | GVI | A330.MPD.23-11335-01-STC |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
697 | 70461604 | HS-TEV | 0016404098 |  | 2105138078 | AC01 |  | 2026-08-20 | 11LHM/A | 0020 | GVI 2Ku components for proper mounting | REL | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | FLOOR_FUSELAGE | BKK_H | GVI | A330.MPD.23-11335-01-STC |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
698 | 70461604 | HS-TEV | 0016404099 |  | 2105138079 | AC01 |  | 2026-08-20 | 11NDT | 0010 | DET tap test 2Ku entire radome and skirt | REL | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | FLOOR_FUSELAGE | BKK_H | NDT | A330.MPD.53-11335-01-STC |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
699 | 70461604 | HS-TEV | 0016404100 |  | 2105138079 | AC01 |  | 2026-08-20 | 11LHM/A | 0020 | DET tap test 2Ku entire radome and skirt | REL | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | FLOOR_FUSELAGE | BKK_H | NDT | A330.MPD.53-11335-01-STC |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
700 | 70461604 | HS-TEV | 0016404101 |  | 2105138080 | AC01 |  | 2026-08-20 | 11NDT | 0010 | NDT DET 2Ku all fasteners at ex double | REL | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | FLOOR_FUSELAGE | BKK_H | NDT | A330.MPD.11339-20-STC |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
701 | 70461604 | HS-TEV | 0016404102 |  | 2105138080 | AC01 |  | 2026-08-20 | 11NDT | 0020 | NDT DET 2Ku all fasteners at ex double | REL | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | FLOOR_FUSELAGE | BKK_H | NDT | A330.MPD.11339-20-STC |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
702 | 70461604 | HS-TEV | 0016404103 |  | 2105138081 | AC01 |  | 2026-08-20 | 11NDT | 0010 | NDT 2Ku all lug attachment fastener hole | REL | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | FLOOR_FUSELAGE | BKK_H | NDT | A330.MPD.11339-21-STC |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
703 | 70461604 | HS-TEV | 0016404104 |  | 2105138081 | AC01 |  | 2026-08-20 | 11NDT | 0020 | NDT 2Ku all lug attachment fastener hole | REL | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | FLOOR_FUSELAGE | BKK_H | NDT | A330.MPD.11339-21-STC |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
704 | 70461604 | HS-TEV | 0016404105 |  | 2105138082 | AC01 |  | 2026-08-20 | 11NDT | 0010 | NDT DET 2Ku Lightning Grounding Clips | REL | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | FLOOR_FUSELAGE | BKK_H | NDT | A330.MPD.11339-22-STC |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
705 | 70461604 | HS-TEV | 0016404106 |  | 2105138082 | AC01 |  | 2026-08-20 | 11NDT | 0020 | NDT DET 2Ku Lightning Grounding Clips | REL | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | FLOOR_FUSELAGE | BKK_H | NDT | A330.MPD.11339-22-STC |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
706 | 70461604 | HS-TEV | 0016404107 |  | 2105138083 | AC01 |  | 2026-08-20 | 11NDT | 0010 | NDT DET 2Ku splice plate at FR53.3 FR54 | REL | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | FLOOR_FUSELAGE | BKK_H | NDT | A330.MPD.11339-25-STC |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
707 | 70461604 | HS-TEV | 0016404108 |  | 2105138083 | AC01 |  | 2026-08-20 | 11LHM/A | 0020 | NDT DET 2Ku splice plate at FR53.3 FR54 | REL | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | FLOOR_FUSELAGE | BKK_H | NDT | A330.MPD.11339-25-STC |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
708 | 70461604 | HS-TEV | 0016404112 |  | 2105138087 | AC01 |  | 2026-09-04 | 11LHM/E | 0010 | RESTORE (CLEAN) THE PANASONIC EXPHONE EW | REL | H/26-TEV-X0C10-BLOK-0-6 | 4 | TG Appr. Req. 4 | IERA_CABIN | BKK_H | CLN | A330.MPD.233600-92-1-TG01 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
709 | 70461604 | HS-TEV | 0016404113 |  | 2105138088 | AC01 |  | 2026-08-20 | 11LQ/IA | 0010 | GVI 2Ku components (LRU’s) for mounting | REL | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | FLOOR_FUSELAGE | BKK_H | GVI | A330.MPD.23-11339-01-STC |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
710 | 70461604 | HS-TEV | 0016404114 |  | 2105138088 | AC01 |  | 2026-08-20 | 11LHM/A | 0020 | GVI 2Ku components (LRU’s) for mounting | REL | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | FLOOR_FUSELAGE | BKK_H | GVI | A330.MPD.23-11339-01-STC |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
711 | 70461604 | HS-TEV | 0016404115 |  | 2105138089 | AC01 |  | 2026-09-04 | 11LHM/A | 0010 | FUN TEST BRAKE ACCUM WITH PARKI BRAKE ON | REL | H/26-TEV-X0C10-BLOK-0-6 |  |  | FLOOR_LANDING GEAR | BKK_H | INS | A330.MPD.324000-06-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
712 | 70461604 | HS-TEV | 0016404116 |  | 2105138090 | AC01 |  | 2026-09-04 | 11LHM/A | 0010 | FUN TEST OF THE BRAKE ACCUMULATORS | REL | H/26-TEV-X0C10-BLOK-0-6 | 1 | DCA Appr. Req. 1 | FLOOR_LANDING GEAR | BKK_H | INS | A330.MPD.324000-07-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
713 | 70461604 | HS-TEV | 0016404156 |  | 2105138114 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | CONNECT GREEN HYD. GRND PWR SUPPLY | REL | H/26-TEV-X0C10-BLOK-0-7 |  |  | WING_HYDRAULIC | BKK_H | INS | A330.OPR.001ACA03 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
714 | 70461604 | HS-TEV | 0016404157 |  | 2105138115 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | CONNECT BLUE HYD. GRND PWR SUPPLY | REL | H/26-TEV-X0C10-BLOK-0-7 |  |  | WING_HYDRAULIC | BKK_H | INS | A330.OPR.001ACA03 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
715 | 70461604 | HS-TEV | 0016404158 |  | 2105138116 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | CONNECT YELLOW HYD. GRND PWR SUPPLY | REL | H/26-TEV-X0C10-BLOK-0-7 |  |  | WING_HYDRAULIC | BKK_H | INS | A330.OPR.001ACA03 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
716 | 70461604 | HS-TEV | 0016404165 |  | 2105138122 | AC01 |  | 2026-08-24 | 11LHM/A | 0010 | RECORD TOWING TIME AIRCRAFT TO HMV-DOCK. | REL | H/26-TEV-X0C10-BLOK-I-N |  |  | ALL_ALL GRP | BKK_H | INS | A330.OPR.001ACA12 |  | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
717 | 70461604 | HS-TEV | 0016404170 |  | 2105138127 | AC01 |  | 2026-08-24 | 11LHM/A | 0010 | DEPRESSURIZARTION OF GREEN HYD. SYSTEM | REL | H/26-TEV-X0C10-BLOK-I-N |  |  | WING_HYDRAULIC | BKK_H | INS | A330.OPR.001ACA18 |  | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
718 | 70461604 | HS-TEV | 0016404171 |  | 2105138128 | AC01 |  | 2026-08-24 | 11LHM/A | 0010 | DEPRESSURIZARTION OF BLUE HYD. SYSTEM | REL | H/26-TEV-X0C10-BLOK-I-N |  |  | WING_HYDRAULIC | BKK_H | INS | A330.OPR.001ACA18 |  | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
719 | 70461604 | HS-TEV | 0016404172 |  | 2105138129 | AC01 |  | 2026-08-24 | 11LHM/A | 0010 | DEPRESSURIZARTION OF YELLOW HYD. SYSTEM | REL | H/26-TEV-X0C10-BLOK-I-N |  |  | WING_HYDRAULIC | BKK_H | INS | A330.OPR.001ACA18 |  | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
720 | 70461604 | HS-TEV | 0016404178 |  | 2105138135 | AC01 |  | 2026-08-24 | 11LHM/C | 0010 | CHK TECH MANUALS | REL | H/26-TEV-X0C10-BLOK-I-N |  |  | CABIN_COCKPIT | BKK_H | INS | A330.OPR.001ACA56 |  | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
721 | 70461604 | HS-TEV | 0016404192 |  | 2105138149 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | OPC OF DRAIN HOLES | REL | H/26-TEV-X0C10-BLOK-0-7 | 2 | DCA Appr. Req. 2 | FLOOR_FUSELAGE | BKK_H | OPC | A330.MPD.531900-02-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
722 | 70461604 | HS-TEV | 0016404201 |  | 2105138157 | AC01 |  | 2026-08-25 | 11LHM/A | 0010 | REMOVAL-FLOOR PANELS Z-131/132 | REL | H/26-TEV-X0C10-BLOK-0-1 |  |  | FLOOR_FWD COMPT | BKK_H | REM | A330.MPD.261500-02-1 |  | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
723 | 70461604 | HS-TEV | 0016404218 |  | 2105138169 | AC01 |  | 2026-09-02 | 11LHM/A | 0010 | CLOSE-UP-NDT FWD CARGO ATTACH FITTING | REL | H/26-TEV-X0C10-BLOK-0-5 |  |  | FLOOR_FWD COMPT | BKK_H | SDI | A330.MPD.523105-01-1,523105-01-2 |  | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
724 | 70461604 | HS-TEV | 0016404225 |  | 2105138176 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | OPC-PISTON DRAIN VALVE IN FWD CGO | REL | H/26-TEV-X0C10-BLOK-0-7 | 2 | DCA Appr. Req. 2 | FLOOR_FWD COMPT | BKK_H | OPC | A330.MPD.532900-01-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
725 | 70461604 | HS-TEV | 0016404226 |  | 2105138177 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | OPC- PISTON DRAIN VALVE IN AFT CGO | REL | H/26-TEV-X0C10-BLOK-0-7 | 2 | DCA Appr. Req. 2 | FLOOR_AFT COMPT | BKK_H | OPC | A330.MPD.532900-01-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
726 | 70461604 | HS-TEV | 0016404227 |  | 2105138178 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | OPC-PISTON DRAIN VALVE IN LWR FUSEL | REL | H/26-TEV-X0C10-BLOK-0-7 | 2 | DCA Appr. Req. 2 | FLOOR_FUSELAGE | BKK_H | OPC | A330.MPD.532900-01-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
727 | 70461604 | HS-TEV | 0016404231 |  | 2105138180 | AC01 |  | 2026-08-29 | 11LQ/IA | 0010 | INSP-FWD CARGO DOOR LOCK FITTING | REL | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | FLOOR_FWD COMPT | BKK_H | GVI | A330.MPD.532107-01-1 |  | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
728 | 70461604 | HS-TEV | 0016404232 |  | 2105138181 | AC01 |  | 2026-08-31 | 11CLEAN | 0010 | GVI-FWD CARGO DOOR LOCK FITTING | REL | H/26-TEV-X0C10-BLOK-0-4 |  |  | FLOOR_FWD COMPT | BKK_H | CLN | A330.MPD.532107-01-1 |  | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
729 | 70461604 | HS-TEV | 0016404247 |  | 2105138196 | AC01 |  | 2026-09-04 | 11LHM/A | 0010 | OPC -THE PACK CONTROL&INDICATING SYSTEM | REL | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | FLOOR_AIR COND | BKK_H | RES | A330.MPD.215200-01-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
730 | 70461604 | HS-TEV | 0016404248 |  | 2105138197 | AC01 |  | 2026-09-04 | 11LHM/A | 0010 | TEST-THE PACK CONTROL&INDICATING SYSTEM | REL | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | FLOOR_AIR COND | BKK_H | RES | A330.MPD.215200-01-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
731 | 70461604 | HS-TEV | 0016404261 |  | 2105138210 | AC01 | EWIS | 2026-08-27 | 11LQ/IA | 0010 | INSP OF AIR CONDITION COMPT AND FAIRINGS | REL | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | FLOOR_AIR COND | BKK_H | GVI | A330.MPD.ZL-191-01-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
732 | 70461604 | HS-TEV | 0016404264 |  | 2105138213 | AC01 |  | 2026-09-02 | 11LQ/IA | 0010 | INST-PARTITION PANEL FR39.1 | REL | H/26-TEV-X0C10-BLOK-0-5 |  |  | FLOOR_FWD COMPT | BKK_H | RES | A330.MPD.215000-05-1,215000-06-1 |  | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
733 | 70461604 | HS-TEV | 0016404265 |  | 2105138214 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | OPC-EMERG RAM AIR INLET SYSTEM | REL | H/26-TEV-X0C10-BLOK-0-7 | 2 | DCA Appr. Req. 2 | FLOOR_AIR COND | BKK_H | OPC | A330.MPD.215500-01-1;215500-04-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
734 | 70461604 | HS-TEV | 0016404266 |  | 2105138215 | AC01 |  | 2026-09-02 | 11LHM/A | 0010 | OPC OF PRESS SEAL DRAIN UPPER AFT END | REL | H/26-TEV-X0C10-BLOK-0-5 | 2 | DCA Appr. Req. 2 | WING_FUEL | BKK_H | OPC | A330.MPD.533900-01-1 |  | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
735 | 70461604 | HS-TEV | 0016404267 |  | 2105138216 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | OPC OF LOW EXTRACTION FLOW WARNING | REL | H/26-TEV-X0C10-BLOK-0-7 | 2 | DCA Appr. Req. 2 | FLOOR_AIR COND | BKK_H | OPC | A330.MPD.212600-01-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
736 | 70461604 | HS-TEV | 0016404268 |  | 2105138217 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | OPC OF OVERRIDE FUNCTION | REL | H/26-TEV-X0C10-BLOK-0-7 | 2 | DCA Appr. Req. 2 | FLOOR_AIR COND | BKK_H | OPC | A330.MPD.212600-02-2 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
737 | 70461604 | HS-TEV | 0016404269 |  | 2105138218 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | OPC OF AIR COND COMP VENTILATE SYS WARN | REL | H/26-TEV-X0C10-BLOK-0-7 | 2 | DCA Appr. Req. 2 | FLOOR_AIR COND | BKK_H | OPC | A330.MPD.212500-01-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
738 | 70461604 | HS-TEV | 0016404270 |  | 2105138219 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | OPC-OUTFLOW VALVE CLOSE IN DITCH CONFIG | REL | H/26-TEV-X0C10-BLOK-0-7 | 2 | DCA Appr. Req. 2 | FLOOR_AIR COND | BKK_H | OPC | A330.MPD.213100-02-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
739 | 70461604 | HS-TEV | 0016404271 |  | 2105138220 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | OPC-OUTFLOW VALVE OPENING(50%) | REL | H/26-TEV-X0C10-BLOK-0-7 | 2 | DCA Appr. Req. 2 | FLOOR_AIR COND | BKK_H | OPC | A330.MPD.213100-03-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
740 | 70461604 | HS-TEV | 0016404272 |  | 2105138221 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | OPC-LANDING FIELD ELEVATION SELECTOR | REL | H/26-TEV-X0C10-BLOK-0-7 | 2 | DCA Appr. Req. 2 | FLOOR_AIR COND | BKK_H | OPC | A330.MPD.213100-04-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
741 | 70461604 | HS-TEV | 0016404280 |  | 2105138229 | AC01 |  | 2026-09-02 | 11LHM/A | 0010 | INSTLL/CLOSE ACCESS PNL BULK CGO (FR73) | REL | H/26-TEV-X0C10-BLOK-0-5 |  |  | FLOOR_AFT COMPT | BKK_H | INS | A330.OPR.161ACP02 |  | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
742 | 70461604 | HS-TEV | 0016404284 |  | 2105138233 | AC01 |  | 2026-08-25 | 11CLEAN | 0010 | CLEAN-BULK CARGO DOOR STOP FITTINGS | REL | H/26-TEV-X0C10-BLOK-0-1 |  |  | FLOOR_AFT COMPT | BKK_H | DVI | A330.MPD.523303-01-1 |  | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
743 | 70461604 | HS-TEV | 0016404291 |  | 2105138240 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | OPC OF PRESS SEAL DRAIN OF BULK CGO DOOR | REL | H/26-TEV-X0C10-BLOK-0-7 | 2 | DCA Appr. Req. 2 | FLOOR_AFT COMPT | BKK_H | OPC | A330.MPD.534900-01-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
744 | 70461604 | HS-TEV | 0016404292 |  | 2105138241 | AC01 |  | 2026-09-04 | 11LHM/A | 0010 | OPC OF DOOR BALANCE MECH N DOOR LATCHING | REL | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | FLOOR_AFT COMPT | BKK_H | OPC | A330.MPD.523300-01-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
745 | 70461604 | HS-TEV | 0016404294 |  | 2105138243 | AC01 |  | 2026-09-02 | 11LHM/A | 0010 | CLOSE-UP NDT INSP AFT CARO ATTACH FITTIN | REL | H/26-TEV-X0C10-BLOK-0-5 |  |  | FLOOR_AFT COMPT | BKK_H | SDI | A330.MPD.523205-01-1,523205-01-2 |  | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
746 | 70461604 | HS-TEV | 0016404309 |  | 2105138258 | AC01 |  | 2026-09-02 | 11CLEAN | 0010 | CLEANING - GALLEY AREAS. | REL | H/26-TEV-X0C10-BLOK-0-5 | 4 | TG Appr. Req. 4 | CABIN_GALLEY | BKK_H | RES | A330.MPD.2500000101-TG01 |  | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
747 | 70461604 | HS-TEV | 0016404310 |  | 2105138259 | AC01 |  | 2026-08-27 | 11CLEAN | 0010 | CLEANING - INTERIOR AREAS. | REL | H/26-TEV-X0C10-BLOK-0-2 | 4 | TG Appr. Req. 4 | CABIN_INTERIOR | BKK_H | RES | A330.MPD.2500000101-TG01 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
748 | 70461604 | HS-TEV | 0016404311 |  | 2105138260 | AC01 |  | 2026-09-06 | 11CLEAN | 0010 | CLEANING - CABIN AREAS(FINAL) | REL | H/26-TEV-X0C10-BLOK-F-I | 4 | TG Appr. Req. 4 | CABIN_INTERIOR | BKK_H | RES | A330.MPD.2500000101-TG01 |  | 2026-09-06 | 08:15:00 | 2026-09-06 | 08:15:00
749 | 70461604 | HS-TEV | 0016404312 |  | 2105138261 | AC01 |  | 2026-08-27 | 11CLEAN | 0010 | CLEANING - COCKPIT AREAS. | REL | H/26-TEV-X0C10-BLOK-0-2 | 4 | TG Appr. Req. 4 | CABIN_COCKPIT | BKK_H | RES | A330.MPD.2500000101-TG01 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
750 | 70461604 | HS-TEV | 0016404313 |  | 2105138262 | AC01 |  | 2026-09-05 | 11CLEAN | 0010 | CLEANING - COCKPIT AREAS(FINAL) | REL | H/26-TEV-X0C10-BLOK-0-7 | 4 | TG Appr. Req. 4 | CABIN_COCKPIT | BKK_H | RES | A330.MPD.2500000101-TG01 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
751 | 70461604 | HS-TEV | 0016404317 |  | 2105138266 | AC01 |  | 2026-09-02 | 11LHM/C | 0010 | INST - EMERG EXIT DOOR FRAME LININGS | REL | H/26-TEV-X0C10-BLOK-0-5 |  |  | CABIN_DOOR | BKK_H | INS | A330.OPR.200ACD48 |  | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
752 | 70461604 | HS-TEV | 0016404319 |  | 2105138268 | AC01 |  | 2026-09-04 | 11LHM/C | 0010 | INST - PASSENGER SEAT CUSHIONS | REL | H/26-TEV-X0C10-BLOK-0-6 | 4 | TG Appr. Req. 4 | CABIN_INTERIOR | BKK_H | RES | A330.MPD.2521000004-TG01 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
753 | 70461604 | HS-TEV | 0016404321 |  | 2105138270 | AC01 |  | 2026-08-27 | 11LQ/IC | 0010 | INSP - PASSENGER SEATS | REL | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | CABIN_INTERIOR | BKK_H | DET | A330.MPD.252100-01-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
754 | 70461604 | HS-TEV | 0016404324 |  | 2105138273 | AC01 |  | 2026-08-27 | 11LQ/IC | 0010 | INSP-ALL HOLDER STRAPS AND FITTING | REL | H/26-TEV-X0C10-BLOK-0-2 | 4 | TG Appr. Req. 4 | CABIN_INTERIOR | BKK_H | DVI | A330.MPD.2500000401-TG01 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
755 | 70461604 | HS-TEV | 0016404332 |  | 2105138281 | AC01 |  | 2026-09-04 | 11LHM/C | 0010 | INST - DECORATIVE COVER TO CLOSE ACCESS | REL | H/26-TEV-X0C10-BLOK-0-6 |  |  | CABIN_DOOR | BKK_H | RST | A330.MPD.521000-07-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
756 | 70461604 | HS-TEV | 0016404342 |  | 2105138291 | AC01 |  | 2026-08-25 | 11LHM/C | 0010 | CLEAN-COCKPIT SIDE WINDOWS | REL | H/26-TEV-X0C10-BLOK-0-1 |  |  | CABIN_COCKPIT | BKK_H | DVI | A330.MPD.531102-01-1 |  | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
757 | 70461604 | HS-TEV | 0016404343 |  | 2105138292 | AC01 |  | 2026-08-27 | 11LQ/IC | 0010 | INSP-COCKPIT SIDE WINDOWS | REL | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | CABIN_COCKPIT | BKK_H | DVI | A330.MPD.531102-01-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
758 | 70461604 | HS-TEV | 0016404374 |  | 2105138321 | AC01 |  | 2026-09-05 | 11LHM/E | 0010 | FUC-ENGINE FIRE PUSHBUTTON SW FUNCTIONS | REL | H/26-TEV-X0C10-BLOK-0-7 | 1 | DCA Appr. Req. 1 | IERA_WING | BKK_H | OPC | A330.MPD.262100-14-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
759 | 70461604 | HS-TEV | 0016404377 |  | 2105138324 | AC01 |  | 2026-09-04 | 11LHM/E | 0010 | OPC-FCPC & FCSC AILERON SERVO LOOPS | REL | H/26-TEV-X0C10-BLOK-0-6 | 1 | DCA Appr. Req. 1 | IERA_WING | BKK_H | OPC | A330.MPD.279000-01-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
760 | 70461604 | HS-TEV | 0016404379 |  | 2105138326 | AC01 |  | 2026-09-04 | 11LHM/E | 0010 | OPC-LDG GEAR INDICATING CIRCUITS | REL | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | IERA_FLOOR | BKK_H | OPC | A330.MPD.326100-01-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
761 | 70461604 | HS-TEV | 0016404387 |  | 2105138334 | AC01 |  | 2026-09-04 | 11LHM/E | 0010 | OPC-APU FIREX LOW-PRESS INDICATING CCT | REL | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | IERA_FLOOR | BKK_H | OPC | A330.MPD.262200-03-2 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
762 | 70461604 | HS-TEV | 0016404390 |  | 2105138337 | AC01 |  | 2026-09-04 | 11LHM/E | 0010 | OPC-PITOT PROBE HEATING&ADR/AOA PWR SUPP | REL | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | IERA_FLOOR | BKK_H | OPC | A330.MPD.341300-01-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
763 | 70461604 | HS-TEV | 0016404392 |  | 2105138339 | AC01 |  | 2026-09-04 | 11LHM/E | 0010 | OPC-RADIO ALTIMETER FAN | REL | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | IERA_FLOOR | BKK_H | OPC | A330.MPD.344200-01-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
764 | 70461604 | HS-TEV | 0016404393 |  | 2105138340 | AC01 |  | 2026-09-04 | 11LHM/E | 0010 | OPC-AFT APU PUMP SHED I LAND RECOVERY CF | REL | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | IERA_FLOOR | BKK_H | OPC | A330.MPD.245000-05-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
765 | 70461604 | HS-TEV | 0016404394 |  | 2105138341 | AC01 |  | 2026-09-04 | 11LHM/E | 0010 | OPC-FCPC 3 POWER SUPPLY | REL | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | IERA_WING | BKK_H | OPC | A330.MPD.279000-11-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
766 | 70461604 | HS-TEV | 0016404395 |  | 2105138342 | AC01 |  | 2026-09-04 | 11LHM/E | 0010 | OPC-ENHANCED GPWC BY BITE | REL | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | IERA_FLOOR | BKK_H | OPC | A330.MPD.344800-01-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
767 | 70461604 | HS-TEV | 0016404424 |  | 2105138371 | AC01 |  | 2026-09-04 | 11LHM/A | 0010 | OPC OF APU EMERG SHUTDOWN | REL | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | FLOOR_TAIL | BKK_H | OPC | A330.MPD.496200-01-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
768 | 70461604 | HS-TEV | 0016404425 |  | 2105138372 | AC01 |  | 2026-09-04 | 11LHM/A | 0010 | OPC APU EMERG SHUT DWN CIRCUIT | REL | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | FLOOR_TAIL | BKK_H | OPC | A330.MPD.496200-02-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
769 | 70461604 | HS-TEV | 0016404426 |  | 2105138373 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | OPC OF CROSSBLEED VLV IN MNL MODE | REL | H/26-TEV-X0C10-BLOK-0-7 | 2 | DCA Appr. Req. 2 | FLOOR_AIR COND | BKK_H | OPC | A330.MPD.361200-01-2,361200-01-3 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
770 | 70461604 | HS-TEV | 0016404434 |  | 2105138381 | AC01 |  | 2026-09-04 | 11LHM/E | 0010 | OPC-ENG FIREX BOTTLE LOW PRESS IND CCT | REL | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | IERA_WING | BKK_H | OPC | A330.MPD.262100-11-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
771 | 70461604 | HS-TEV | 0016404435 |  | 2105138382 | AC01 |  | 2026-09-04 | 11LHM/E | 0010 | TEST-ENGINE FIRING CIRCUIT CONTINUITY | REL | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | IERA_WING | BKK_H | FUC | A330.MPD.262100-13-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
772 | 70461604 | HS-TEV | 0016404437 |  | 2105138384 | AC01 |  | 2026-09-04 | 11LHM/A | 0010 | OPC ENG DRIVEN PUMP DEPRESS(BLUE SYSTEM) | REL | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | WING_ENGINE | BKK_H | OPC | A330.MPD.291000-03-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
773 | 70461604 | HS-TEV | 0016404438 |  | 2105138385 | AC01 |  | 2026-09-04 | 11LHM/A | 0010 | OPC ENG DRIVEN PUMP DEPRESS(YELLOW SYS) | REL | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | WING_ENGINE | BKK_H | OPC | A330.MPD.291000-03-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
774 | 70461604 | HS-TEV | 0016404452 |  | 2105138399 | AC01 |  | 2026-09-04 | 11LHM/A | 0010 | OPC-NO#2 RH MAIN FUEL PUMP | REL | H/26-TEV-X0C10-BLOK-0-6 | 1 | DCA Appr. Req. 1 | WING_FUEL | BKK_H | OPC | A330.MPD.282100-10-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
775 | 70461604 | HS-TEV | 0016404453 |  | 2105138400 | AC01 |  | 2026-09-04 | 11LHM/A | 0010 | OPC STANDBY FUEL PUMP AUTOMATIC CONTROL | REL | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | WING_FUEL | BKK_H | OPC | A330.MPD.282100-06-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
776 | 70461604 | HS-TEV | 0016404454 |  | 2105138401 | AC01 |  | 2026-09-02 | 11LHM/A | 0010 | FUC-TRIM TANK TRF LINE SHROUD CONNECTORS | REL | H/26-TEV-X0C10-BLOK-0-5 | 1 | DCA Appr. Req. 1 | WING_FUEL | BKK_H | FUC | A330.MPD.282700-05-1 |  | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
777 | 70461604 | HS-TEV | 0016404455 |  | 2105138402 | AC01 |  | 2026-09-04 | 11LHM/A | 0010 | OPC OF INNER TANK LOW LEVEL SENSING | REL | H/26-TEV-X0C10-BLOK-0-6 | 1 | DCA Appr. Req. 1 | WING_FUEL | BKK_H | OPC | A330.MPD.284600-02-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
778 | 70461604 | HS-TEV | 0016404457 |  | 2105138404 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | OPC-MAIN FUEL PUMP SYSTEM | REL | H/26-TEV-X0C10-BLOK-0-7 | 1 | DCA Appr. Req. 1 | WING_FUEL | BKK_H | OPC | A330.MPD.282100-02-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
779 | 70461604 | HS-TEV | 0016404459 |  | 2105138406 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | OPC-HYD FIRE SOV GREEN SYSTEM | REL | H/26-TEV-X0C10-BLOK-0-7 | 1 | DCA Appr. Req. 1 | WING_HYDRAULIC | BKK_H | OPC | A330.MPD.291000-04-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
780 | 70461604 | HS-TEV | 0016404460 |  | 2105138407 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | OPC-HYD FIRE SOV BLUE SYSTEM | REL | H/26-TEV-X0C10-BLOK-0-7 | 1 | DCA Appr. Req. 1 | WING_HYDRAULIC | BKK_H | OPC | A330.MPD.291000-04-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
781 | 70461604 | HS-TEV | 0016404461 |  | 2105138408 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | [OPC-HYD FIRE SOV YELLOW SYSTEM] | REL | H/26-TEV-X0C10-BLOK-0-7 | 1 | DCA Appr. Req. 1 | WING_HYDRAULIC | BKK_H | OPC | A330.MPD.291000-04-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
782 | 70461604 | HS-TEV | 0016404462 |  | 2105138409 | AC01 |  | 2026-09-04 | 11LHM/E | 0010 | OPC-ELEC PUMP OF ENG PUMP SUCTION FSOV | REL | H/26-TEV-X0C10-BLOK-0-6 |  |  | IERA_WING | BKK_H | INS | A330.MPD.291000-04-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
783 | 70461604 | HS-TEV | 0016404463 |  | 2105138410 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | TEST GREEN SERVO TRAVEL SPEED,RAT EXTND | REL | H/26-TEV-X0C10-BLOK-0-7 | 1 | DCA Appr. Req. 1 | WING_HYDRAULIC | BKK_H | OPC | A330.MPD.279000-05-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
784 | 70461604 | HS-TEV | 0016404464 |  | 2105138411 | AC01 |  | 2026-09-04 | 11LHM/A | 0010 | OPC-AILERON DAMPING MEASUREMENT BY BITE | REL | H/26-TEV-X0C10-BLOK-0-6 | 1 | DCA Appr. Req. 1 | WING_TRAILING EDGE | BKK_H | OPC | A330.MPD.271400-01-1,271400-01-2 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
785 | 70461604 | HS-TEV | 0016404465 |  | 2105138412 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | OPC-HYD OVERHEAT DETECTION SYSTEM | REL | H/26-TEV-X0C10-BLOK-0-7 | 2 | DCA Appr. Req. 2 | WING_HYDRAULIC | BKK_H | OPC | A330.MPD.293000-03-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
786 | 70461604 | HS-TEV | 0016404480 |  | 2105138427 | AC01 |  | 2026-08-25 | 11LHM/A | 0010 | OPENING-TRACK FAIRING ACCESS | REL | H/26-TEV-X0C10-BLOK-0-1 |  |  | WING_TRAILING EDGE | BKK_H | GVI | A330.MPD.ZL-531-01-1 |  | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
787 | 70461604 | HS-TEV | 0016404481 |  | 2105138428 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | [CLOSING-TRACK FAIRING ACCESS] | REL | H/26-TEV-X0C10-BLOK-0-7 |  |  | WING_TRAILING EDGE | BKK_H | GVI | A330.MPD.ZL-531-01-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
788 | 70461604 | HS-TEV | 0016404492 |  | 2105138439 | AC01 | EWIS | 2026-08-27 | 11LQ/IA | 0010 | INSP EXTERNAL WING -LH WING | REL | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | WING_TRAILING EDGE | BKK_H | GVI | A330.MPD.ZL-500-02-1;ZL-531-01-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
789 | 70461604 | HS-TEV | 0016404499 |  | 2105138446 | AC01 |  | 2026-09-02 | 11LHM/A | 0010 | CLOSE-UP INSP-WING ICE PROT. COMPONENTS | REL | H/26-TEV-X0C10-BLOK-0-5 |  |  | WING_LEADING EDGE | BKK_H | RES | A330.MPD.301100-01-1 |  | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
790 | 70461604 | HS-TEV | 0016404519 |  | 2105138466 | AC01 |  | 2026-08-27 | 11LQ/IE | 0010 | DVI-CONNECTORS ON RAM AIR TURBINE | REL | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | IERA_WING | BKK_H | DVI | A330.MPD.200001-03-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
791 | 70461604 | HS-TEV | 0016404535 |  | 2105138482 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | OPC OF THE PARKING BRAKE SYSTEM | REL | H/26-TEV-X0C10-BLOK-0-7 | 3 | TG Appr. Req. 3 | FLOOR_LANDING GEAR | BKK_H | OPC | A330.MPD.324500-01-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
792 | 70461604 | HS-TEV | 0016404540 |  | 2105138486 | AC01 |  | 2026-09-04 | 11LHM/A | 0010 | CHECK NITROGEN PRESSURE ON NLG STEERING | REL | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | FLOOR_LANDING GEAR | BKK_H | DVI | A330.MPD.325100-02-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
793 | 70461604 | HS-TEV | 0016404552 |  | 2105138498 | AC01 |  | 2026-09-06 | 11LHM/E | 0010 | RMV CVR PITOT AND STATIC INTAKE | REL | H/26-TEV-X0C10-BLOK-F-I |  |  | IERA_FLOOR | BKK_H | INS | A330.OPR.901ACW01 |  | 2026-09-06 | 08:15:00 | 2026-09-06 | 08:15:00
794 | 70461604 | HS-TEV | 0016404554 |  | 2105138500 | AC01 |  | 2026-09-06 | 11LHM/C | 0010 | FILL THE POTABLE WATER SYSTEM | REL | H/26-TEV-X0C10-BLOK-F-I |  |  | CABIN_GALLEY | BKK_H | INS | A330.OPR.901ACW05 |  | 2026-09-06 | 08:15:00 | 2026-09-06 | 08:15:00
795 | 70461604 | HS-TEV | 0016404556 |  | 2105138502 | AC01 |  | 2026-09-06 | 11LHM/C | 0010 | REMOVE SEAT COVERS | REL | H/26-TEV-X0C10-BLOK-F-I |  |  | CABIN_INTERIOR | BKK_H | INS | A330.OPR.901ACW12 |  | 2026-09-06 | 08:15:00 | 2026-09-06 | 08:15:00
796 | 70461604 | HS-TEV | 0016404557 |  | 2105138503 | AC01 |  | 2026-09-06 | 11LHM/A | 0010 | RECORD TOWING TIMES AND TEST FLIGHT. | REL | H/26-TEV-X0C10-BLOK-F-I |  |  | ALL_ALL GRP | BKK_H | INS | A330.OPR.901ACW13 |  | 2026-09-06 | 08:15:00 | 2026-09-06 | 08:15:00
797 | 70461604 | HS-TEV | 0016404558 |  | 2105138504 | AC01 |  | 2026-09-06 | 11LHM/A | 0010 | DLV A/C AFTER MAINT FROM MD(MO) TO LC | REL | H/26-TEV-X0C10-BLOK-F-I |  |  | ALL_ALL GRP | BKK_H | INS | A330.OPR.901ACW14 |  | 2026-09-06 | 08:15:00 | 2026-09-06 | 08:15:00
798 | 70461604 | HS-TEV | 0016404562 |  | 2105138508 | AC01 |  | 2026-09-06 | 11LHM/A | 0010 | CLOSE MDG DOORS | REL | H/26-TEV-X0C10-BLOK-F-I |  |  | FLOOR_LANDING GEAR | BKK_H | INS | A330.OPR.901ACW17 |  | 2026-09-06 | 08:15:00 | 2026-09-06 | 08:15:00
799 | 70461604 | HS-TEV | 0016404563 |  | 2105138509 | AC01 |  | 2026-09-06 | 11LHM/A | 0010 | CLOSE NLG DOORS | REL | H/26-TEV-X0C10-BLOK-F-I |  |  | FLOOR_LANDING GEAR | BKK_H | INS | A330.OPR.902ACW17 |  | 2026-09-06 | 08:15:00 | 2026-09-06 | 08:15:00
800 | 70461604 | HS-TEV | 0016404564 |  | 2105138510 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | AIRCRAFT REFUELING | REL | H/26-TEV-X0C10-BLOK-0-7 |  |  | WING_FUEL | BKK_H | INS | A330.OPR.901ACW18 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
801 | 70461604 | HS-TEV | 0016404565 |  | 2105138511 | AC01 |  | 2026-09-06 | 11LHM/C | 0010 | INSTALLATION OF FLASHLIGHTS | REL | H/26-TEV-X0C10-BLOK-F-I |  |  | CABIN_INTERIOR | BKK_H | INS | A330.OPR.901ACW19 |  | 2026-09-06 | 08:15:00 | 2026-09-06 | 08:15:00
802 | 70461604 | HS-TEV | 0016404566 |  | 2105138512 | AC01 |  | 2026-09-06 | 11LHM/C | 0010 | RMV -PROTECTIVE COVERED OVER CARPET | REL | H/26-TEV-X0C10-BLOK-F-I |  |  | CABIN_INTERIOR | BKK_H | INS | A330.OPR.901ACW20 |  | 2026-09-06 | 08:15:00 | 2026-09-06 | 08:15:00
803 | 70461604 | HS-TEV | 0016404567 |  | 2105138513 | AC01 |  | 2026-09-06 | 11LHM/A | 0010 | REMOVE SAFETY COMPONENT | REL | H/26-TEV-X0C10-BLOK-F-I |  |  | ALL_ALL GRP | BKK_H | INS | A330.OPR.901ACW24 |  | 2026-09-06 | 08:15:00 | 2026-09-06 | 08:15:00
804 | 70461604 | HS-TEV | 0016404568 |  | 2105138514 | AC01 |  | 2026-09-06 | 11LHM/A | 0010 | MSC PRIOR TO FLIGHT | REL | H/26-TEV-X0C10-BLOK-F-I |  |  | ALL_ALL GRP | BKK_H | INS | A330.OPR.901ACW29 |  | 2026-09-06 | 08:15:00 | 2026-09-06 | 08:15:00
805 | 70461604 | HS-TEV | 0016404569 |  | 2105138515 | AC01 |  | 2026-09-06 | 11LHM/A | 0010 | RESET IDG DISCONNECT | REL | H/26-TEV-X0C10-BLOK-F-I |  |  | WING_ENGINE | BKK_H | INS | A330.OPR.901ACW37 |  | 2026-09-06 | 08:15:00 | 2026-09-06 | 08:15:00
806 | 70461604 | HS-TEV | 0016404570 |  | 2105138516 | AC01 |  | 2026-09-06 | 11LHM/A | 0010 | RESET IDG DISCONNECT | REL | H/26-TEV-X0C10-BLOK-F-I |  |  | WING_ENGINE | BKK_H | INS | A330.OPR.901ACW37 |  | 2026-09-06 | 08:15:00 | 2026-09-06 | 08:15:00
807 | 70461604 | HS-TEV | 0016404571 |  | 2105138517 | AC01 |  | 2026-09-06 | 11LHM/C | 0010 | CHECK TECH .MANUAL INSTALLED | REL | H/26-TEV-X0C10-BLOK-F-I |  |  | CABIN_COCKPIT | BKK_H | INS | A330.OPR.901ACW57 |  | 2026-09-06 | 08:15:00 | 2026-09-06 | 08:15:00
808 | 70461604 | HS-TEV | 0016404577 |  | 2105138521 | AC01 |  | 2026-09-06 | 11LHM/A | 0010 | LIST REMAINING ITEMS FLOOR GROUP | REL | H/26-TEV-X0C10-BLOK-F-I |  |  | FLOOR_ALL FLOOR | BKK_H | INS | A330.OPR.905ACW45 |  | 2026-09-06 | 08:15:00 | 2026-09-06 | 08:15:00
809 | 70461604 | HS-TEV | 0016404578 |  | 2105138522 | AC01 |  | 2026-09-06 | 11LHM/C | 0010 | LIST REMAINING ITEMS CABIN GROUP | REL | H/26-TEV-X0C10-BLOK-F-I |  |  | CABIN_ALL CABIN | BKK_H | INS | A330.OPR.905ACW46 |  | 2026-09-06 | 08:15:00 | 2026-09-06 | 08:15:00
810 | 70461604 | HS-TEV | 0016404579 |  | 2105138523 | AC01 |  | 2026-09-06 | 11LHM/E | 0010 | LIST REMAINING ITEMS IERA GROUP | REL | H/26-TEV-X0C10-BLOK-F-I |  |  | IERA_ALL IERA | BKK_H | INS | A330.OPR.905ACW47 |  | 2026-09-06 | 08:15:00 | 2026-09-06 | 08:15:00
811 | 70461604 | HS-TEV | 0016404580 |  | 2105138524 | AC01 |  | 2026-09-06 | 11LHM/A | 0010 | LIST REMAINING ITEMS LH/RH WINGS/ENGS. | REL | H/26-TEV-X0C10-BLOK-F-I |  |  | WING_ALL WING | BKK_H | INS | A330.OPR.905ACW48 |  | 2026-09-06 | 08:15:00 | 2026-09-06 | 08:15:00
812 | 70461604 | HS-TEV | 0016404581 |  | 2105138525 | AC01 |  | 2026-09-06 | 11LHM/A | 0010 | CLEAR REPORT BEFORE TRIMMIMG | REL | H/26-TEV-X0C10-BLOK-F-I |  |  | ALL_ALL GRP | BKK_H | INS | A330.OPR.905ACW50 |  | 2026-09-06 | 08:15:00 | 2026-09-06 | 08:15:00
813 | 70461604 | HS-TEV | 0016404582 |  | 2105138526 | AC01 |  | 2026-09-06 | 11LHM/A | 0010 | FINAL CHK PRIMARY FLT.CTRL-AILERON | REL | H/26-TEV-X0C10-BLOK-F-I |  |  | WING_TRAILING EDGE | BKK_H | INS | A330.OPR.906ACW20 |  | 2026-09-06 | 08:15:00 | 2026-09-06 | 08:15:00
814 | 70461604 | HS-TEV | 0016404583 |  | 2105138527 | AC01 |  | 2026-09-06 | 11LHM/A | 0010 | FINAL CHK PRIMARY FLT.CTRL-RUDDER | REL | H/26-TEV-X0C10-BLOK-F-I |  |  | FLOOR_TAIL | BKK_H | INS | A330.OPR.906ACW20 |  | 2026-09-06 | 08:15:00 | 2026-09-06 | 08:15:00
815 | 70461604 | HS-TEV | 0016404584 |  | 2105138528 | AC01 |  | 2026-09-06 | 11LHM/A | 0010 | FINAL CHK PRIMARY FLT.CTRL-ELEVATOR | REL | H/26-TEV-X0C10-BLOK-F-I |  |  | FLOOR_TAIL | BKK_H | INS | A330.OPR.906ACW20 |  | 2026-09-06 | 08:15:00 | 2026-09-06 | 08:15:00
816 | 70461604 | HS-TEV | 0016404585 |  | 2105138529 | AC01 |  | 2026-09-06 | 11LHM/A | 0010 | FINAL CHK PRIMARY FLT.CTRL-RUDDER | REL | H/26-TEV-X0C10-BLOK-F-I |  |  | FLOOR_TAIL | BKK_H | INS | A330.OPR.906ACW20 |  | 2026-09-06 | 08:15:00 | 2026-09-06 | 08:15:00
817 | 70461604 | HS-TEV | 0016404586 |  | 2105138530 | AC01 |  | 2026-09-06 | 11E | 0010 | CHK LIST FOR ENGINE START/SHUTDOWN. | REL | H/26-TEV-X0C10-BLOK-F-I |  |  | WING_ENGINE | BKK_H | INS | A330.OPR.906ACW21 |  | 2026-09-06 | 08:15:00 | 2026-09-06 | 08:15:00
818 | 70461604 | HS-TEV | 0016404587 |  | 2105138531 | AC01 |  | 2026-09-06 | 11E | 0010 | ENGINE RUN UP GROUND IDLE. | REL | H/26-TEV-X0C10-BLOK-F-I |  |  | WING_ENGINE | BKK_H | INS | A330.OPR.906ACW36 |  | 2026-09-06 | 08:15:00 | 2026-09-06 | 08:15:00
819 | 70461604 | HS-TEV | 0016404590 |  | 2105138534 | AC01 |  | 2026-08-29 | 11LQ/IA | 0010 | INSP-FASTENER AREA AT WINDOW FRAME | REL | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | FLOOR_FUSELAGE | BKK_H | DET | A330.MPD.533106-01-2;533106-01-3 |  | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
820 | 70461604 | HS-TEV | 0016404592 |  | 2105138536 | AC01 |  | 2026-08-29 | 11LQ/IA | 0010 | INSP-HEATSHIELD | REL | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | FLOOR_AIR COND | BKK_H | GVI | A330.MPD.216000-08-1 |  | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
821 | 70461604 | HS-TEV | 0016404597 |  | 2105138541 | AC01 |  | 2026-09-04 | 11LHM/A | 0010 | OPC-AFT CARGO BRAKING ROLLER | REL | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | FLOOR_AFT COMPT | BKK_H | OPC | A330.MPD.255101-04-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
822 | 70461604 | HS-TEV | 0016495230 | 1103188611 | 2105163310 | AC02 |  | 2026-08-24 | 11LHM/E | 0010 | CHK. EXPIRED BATT-LOW FREQUENCY ULB | REL | H/26-TEV-X0C10-NONR | 2 | DCA Appr. Req. 2 | IERA_FLOOR | BKK_H | RPL | A330.MPD.256536-02-1-STC01 |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
823 | 70461604 | HS-TEV | 0016473210 | EV004C070826 | EV004C070826 | AC05 |  | 2026-08-24 | BKK_L | 0010 | 25 SEAT 27J LEGREST DROP ALL THE TIME. | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_L | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
824 | 70461604 | HS-TEV | 0016473211 | EV004C070826 | EV004C070826 | AC05 |  | 2026-08-24 | BKK_L | 0020 | 25 SEAT 27J LEGREST DROP ALL THE TIME. | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_L | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
825 | 70461604 | HS-TEV | 0016543388 | EV023F100926 | EV023F100926 | AC05 |  | 2026-09-10 | BKK_H | 0010 | REQUIRE DE-PRESERVATION OF THE APU | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  |  | 2026-09-10 | 00:00:00 | 2026-09-10 | 00:00:00
826 | 70461604 | HS-TEV | 0016124603 | EV038C080126 | EV038C080126 | AC05 |  | 2026-08-24 | BKK_L | 0010 | 25 40G STOWAGE BOX MONITOR POOR CONDITIO | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
827 | 70461604 | HS-TEV | 0016124604 | EV038C080126 | EV038C080126 | AC05 |  | 2026-08-24 | BKK_L | 0020 | 25 40G STOWAGE BOX MONITOR POOR CONDITIO | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
828 | 70461604 | HS-TEV | 0016418344 | EV044C050726 | EV044C050726 | AC05 |  | 2026-08-24 | BKK_L | 0010 | 44 26A THE HANDSET BROKEN | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
829 | 70461604 | HS-TEV | 0016418345 | EV044C050726 | EV044C050726 | AC05 |  | 2026-08-24 | BKK_L | 0020 | 44 26A THE HANDSET BROKEN | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
830 | 70461604 | HS-TEV | 0015574171 | EV046C160225 | EV046C160225 | AC05 |  | 2026-08-24 | FUK | 0010 | 33 BAR LIGHT CANNOT TURN OFF | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
831 | 70461604 | HS-TEV | 0015574172 | EV046C160225 | EV046C160225 | AC05 |  | 2026-08-24 | BKK_L | 0020 | 33 BAR LIGHT CANNOT TURN OFF | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
832 | 70461604 | HS-TEV | 0016485369 | EV047C140826 | EV047C140826 | AC05 |  | 2026-08-24 | BKK_L | 0010 | 23 23A MONITOR LOOSE | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_L | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
833 | 70461604 | HS-TEV | 0016485371 | EV047C140826 | EV047C140826 | AC05 |  | 2026-08-24 | 12LC/AP | 0020 | 23 23A MONITOR LOOSE | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_L | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
834 | 70461604 | HS-TEV | 0016485370 | EV047C140826 | EV047C140826 | AC05 |  | 2026-08-24 | BKK_L | 0020 | 23 23A MONITOR LOOSE | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_L | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
835 | 70461604 | HS-TEV | 0016486325 | EV055C150826 | EV055C150826 | AC05 |  | 2026-08-24 | BKK_L | 0010 | 25 SEAT 25K,53J,53K IFE INOP. | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_L | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
836 | 70461604 | HS-TEV | 0016486326 | EV055C150826 | EV055C150826 | AC05 |  | 2026-08-24 | BKK_L | 0020 | 25 SEAT 25K,53J,53K IFE INOP. | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_L | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
837 | 70461604 | HS-TEV | 0016487639 | EV059C160826 | EV059C160826 | AC05 |  | 2026-08-24 | BKK_L | 0010 | 23 SEAT 34A 45D 37F 33K 35G IFE INOP. | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_L | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
838 | 70461604 | HS-TEV | 0016487640 | EV059C160826 | EV059C160826 | AC05 |  | 2026-08-24 | BKK_L | 0020 | 23 SEAT 34A 45D 37F 33K 35G IFE INOP. | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_L | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
839 | 70461604 | HS-TEV | 0016487641 | EV060C160826 | EV060C160826 | AC05 |  | 2026-08-24 | BKK_L | 0010 | 25 LAV. L53 FAUCET INOP. | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_L | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
840 | 70461604 | HS-TEV | 0016487642 | EV060C160826 | EV060C160826 | AC05 |  | 2026-08-24 | BKK_L | 0020 | 25 LAV. L53 FAUCET INOP. | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_L | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
841 | 70461604 | HS-TEV | 0016376706 | EV064C110626 | EV064C110626 | AC05 |  | 2026-08-24 | BKK_L | 0010 | 25 FRIDFE AT GALLEY 4 INOP | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_L | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
842 | 70461604 | HS-TEV | 0016376707 | EV064C110626 | EV064C110626 | AC05 |  | 2026-08-24 | BKK_L | 0020 | 25 FRIDFE AT GALLEY 4 INOP | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_L | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
843 | 70461604 | HS-TEV | 0016425511 | EV068C090726 | EV068C090726 | AC05 |  | 2026-08-24 | BKK_L | 0010 | 25 AFT GALLEY FRIDGE INOP | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
844 | 70461604 | HS-TEV | 0016425513 | EV068C090726 | EV068C090726 | AC05 |  | 2026-08-24 | 12LC/AP | 0020 | 25 AFT GALLEY FRIDGE INOP | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
845 | 70461604 | HS-TEV | 0016425512 | EV068C090726 | EV068C090726 | AC05 |  | 2026-08-24 | BKK_L | 0020 | 25 AFT GALLEY FRIDGE INOP | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
846 | 70461604 | HS-TEV | 0016492593 | EV069C170826 | EV069C170826 | AC05 |  | 2026-08-24 | BKK_L | 0010 | 25 SEAT 35G, 35J, 34B IFE INOP 43A, 46A, | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_L | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
847 | 70461604 | HS-TEV | 0016492594 | EV069C170826 | EV069C170826 | AC05 |  | 2026-08-24 | BKK_L | 0020 | 25 SEAT 35G, 35J, 34B IFE INOP 43A, 46A, | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_L | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
848 | 70461604 | HS-TEV | 0015769433 | EV074C160625 | EV074C160625 | AC05 |  | 2026-08-24 | BKK_L | 0010 | 25 OHSC OPPOSITE 14A RUBBER SEAL NO COMP | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
849 | 70461604 | HS-TEV | 0015769434 | EV074C160625 | EV074C160625 | AC05 |  | 2026-08-24 | BKK_L | 0020 | 25 OHSC OPPOSITE 14A RUBBER SEAL NO COMP | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
850 | 70461604 | HS-TEV | 0015769436 | EV075C160625 | EV075C160625 | AC05 |  | 2026-08-24 | BKK_L | 0010 | 25 OHSC OPPOSITE 16A,18A,19A,20A RUBBER | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
851 | 70461604 | HS-TEV | 0015769437 | EV075C160625 | EV075C160625 | AC05 |  | 2026-08-24 | BKK_L | 0020 | 25 OHSC OPPOSITE 16A,18A,19A,20A RUBBER | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
852 | 70461604 | HS-TEV | 0016131883 | EV080C160126 | EV080C160126 | AC05 |  | 2026-08-24 | BKK_L | 0010 | 23 50D, 50J IFE INOP (NO SOUND) | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_L | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
853 | 70461604 | HS-TEV | 0016131884 | EV080C160126 | EV080C160126 | AC05 |  | 2026-08-24 | BKK_L | 0020 | 23 50D, 50J IFE INOP (NO SOUND) | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_L | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
854 | 70461604 | HS-TEV | 0016506099 | EV088B270826 | EV088B270826 | AC05 |  | 2026-08-24 | 11PAINT | 0010 | 11:PLACARD YELLOW SERVICE PANEL | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
855 | 70461604 | HS-TEV | 0015819485 | EV092C200725 | EV092C200725 | AC05 |  | 2026-08-24 | BKK_L | 0010 | 25 29B,30B ARMREST BROKEN TEMPORARY FIXE | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
856 | 70461604 | HS-TEV | 0015822138 | EV092C200725 | EV092C200725 | AC05 |  | 2026-08-24 | 12LC/AP | 0020 | 25 29B,30B ARMREST BROKEN TEMPORARY FIXE | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
857 | 70461604 | HS-TEV | 0015822137 | EV092C200725 | EV092C200725 | AC05 |  | 2026-08-24 | BKK_L | 0020 | 25 29B,30B ARMREST BROKEN TEMPORARY FIXE | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
858 | 70461604 | HS-TEV | 0016342848 | EV093C210526 | EV093C210526 | AC05 |  | 2026-08-24 | BKK_L | 0010 | 23 EM MOVIE NOT CORRECT A/C CONFIGURATIO | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_L | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
859 | 70461604 | HS-TEV | 0016342850 | EV093C210526 | EV093C210526 | AC05 |  | 2026-08-24 | 12LC/AP | 0020 | 23 EM MOVIE NOT CORRECT A/C CONFIGURATIO | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_L | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
860 | 70461604 | HS-TEV | 0016342849 | EV093C210526 | EV093C210526 | AC05 |  | 2026-08-24 | BKK_L | 0020 | 23 EM MOVIE NOT CORRECT A/C CONFIGURATIO | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_L | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
861 | 70461604 | HS-TEV | 0016506149 | EV096B270826 | EV096B270826 | AC05 |  | 2026-08-24 | 11LHM/A | 0010 | A/C NEED TO PARK OUTSIDE HANGAR DUE TO H | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
862 | 70461604 | HS-TEV | 0016543701 | EV097C240826 | EV097C240826 | AC05 |  | 2026-08-24 | BKK_H | 0010 | MONITOR SEATS 31,32,33,34,35,36,37 | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-08-24 | 00:00:00
863 | 70461604 | HS-TEV | 0016543696 | EV098C240826 | EV098C240826 | AC05 |  | 2026-08-24 | BKK_H | 0010 | SEAT 41B 41K IN-ARM MONITOR ASSY REMOVED | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-08-24 | 00:00:00
864 | 70461604 | HS-TEV | 0016471915 | EV100C050826 | EV100C050826 | AC05 |  | 2026-08-24 | BKK_L | 0010 | 23 17K INDIVIDUAL SWITCH INOP | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_L | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
865 | 70461604 | HS-TEV | 0016471916 | EV100C050826 | EV100C050826 | AC05 |  | 2026-08-24 | BKK_L | 0020 | 23 17K INDIVIDUAL SWITCH INOP | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_L | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
866 | 70461604 | HS-TEV | 0016532524 | EV125B100926 | EV125B100926 | AC05 |  | 2026-08-24 | 11SH | 0010 | CABIN GALLEY | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
867 | 70461604 | HS-TEV | 0016532529 | EV126B100926 | EV126B100926 | AC05 |  | 2026-08-24 | 11SH | 0010 | CABIN GALLEY | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
868 | 70461604 | HS-TEV | 0016533884 | EV129B110926 | EV129B110926 | AC05 |  | 2026-09-11 | 11CLEAN | 0010 | AFT.CARGO COMPARTMENT AREA LOWER AROUND | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  |  | 2026-09-11 | 10:16:00 | 2026-09-11 | 19:00:00
869 | 70461604 | HS-TEV | 0016553187 | EV147B230926 | EV147B230926 | AC05 |  | 2026-09-23 | 11PAINT | 0010 | FWD L/E VHF ANTENNA PAINT PEEL OFF. | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  |  | 2026-09-23 | 11:32:00 | 2026-09-24 | 19:00:00
870 | 70461604 | HS-TEV | 0016553188 | EV148B230926 | EV148B230926 | AC05 |  | 2026-09-23 | 11PAINT | 0010 | RH SIDE EXTERNAL FUSELAGE NEAR PAX DOOR | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  |  | 2026-09-23 | 11:54:00 | 2026-09-24 | 19:00:00
871 | 70461604 | HS-TEV | 0016555302 | EV155B240926 | EV155B240926 | AC05 |  | 2026-08-24 | 11PAINT | 0010 | RH LWR WING OUTER SKIN PAINT PEEL OFF. | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
872 | 70461604 | HS-TEV | 0015916766 | 1103087036 | 2105002940 | AC03 |  | 2026-08-22 | 11LHM/A | 0010 | 531627: IMPROVE DRAIN AT FR53.2 STR51 | REL | H/26-TEV-X0C10-MOD -G-F | 1 | DCA Appr. Req. 1 |  | BKK_H | MOD | A330.TO.MTO-531627 |  | 2026-08-22 | 00:00:00 | 2026-09-02 | 00:00:00
873 | 70461604 | HS-TEV | 0015916767 | 1103087036 | 2105002940 | AC03 |  | 2026-08-22 | 11LHM/A | 0020 | 531627: IMPROVE DRAIN AT FR53.2 STR51 | REL | H/26-TEV-X0C10-MOD -G-F | 1 | DCA Appr. Req. 1 |  | BKK_H | MOD | A330.TO.MTO-531627 |  | 2026-08-22 | 00:00:00 | 2026-09-02 | 00:00:00
874 | 70461604 | HS-TEV | 0016403912 |  | 2105137906 | AC01 |  | 2026-09-02 | 11LHM/C | 0010 | CLOSE-UP FOR NDT SPLICING AREA FR48-53. | REL | H/26-TEV-X0C10-BLOK-0-5 |  |  | CABIN_INTERIOR | BKK_H | INS | A330.MPD.533161-01-9 |  | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
875 | 70461604 | HS-TEV | 0016404089 |  | 2105138070 | AC01 |  | 2026-08-27 | 11LHM/A | 0010 | ENG T/R DETAILED INSPECTION E#1 | REL | H/26-TEV-X0C10-BLOK-0-2 |  |  | WING_ENGINE | BKK_H | DVI | A330.MPD.783200-06-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
876 | 70461604 | HS-TEV | 0016404090 |  | 2105138071 | AC01 |  | 2026-08-27 | 11LHM/A | 0010 | ENG T/R DETAILED INSPECTION E#2 | REL | H/26-TEV-X0C10-BLOK-0-2 |  |  | WING_ENGINE | BKK_H | DVI | A330.MPD.783200-06-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
877 | 70461604 | HS-TEV | 0016556399 | EV001C240926 | EV001C240926 | AC05 |  | 2026-09-24 | BKK_H | 0010 | 25 : CABIN ATTENDANT SEATS 3L BOTTOM SEA | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  |  | 2026-09-24 | 00:00:00 | 2026-09-24 | 00:00:00
878 | 70461604 | HS-TEV | 0016550782 | EV099C210926 | EV099C210926 | AC05 |  | 2026-09-21 | BKK_H | 0010 | ARMCAP. B/C SEAT | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  |  | 2026-09-21 | 00:00:00 | 2026-09-21 | 00:00:00
879 | 70461604 | HS-TEV | 0016403838 |  | 2105137839 | AC01 |  | 2026-08-27 | 11LHM/A | 0010 | INSP AFT ENG MOUNT FAIL-SAFE -RR ENG#1 | REL | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | WING_ENGINE | BKK_H | SDI | A330.MPD.712204-03-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
880 | 70461604 | HS-TEV | 0016403839 |  | 2105137840 | AC01 |  | 2026-08-27 | 11LHM/A | 0010 | INSP AFT ENG MOUNT FAIL-SAFE -RR ENG#2 | REL | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | WING_ENGINE | BKK_H | SDI | A330.MPD.712204-03-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
881 | 70461604 | HS-TEV | 0016403857 |  | 2105137858 | AC01 |  | 2026-08-31 | 11LHM/A | 0010 | LUBBRICATE OF FLAP TRACK/CARRIAGE -LH | REL | H/26-TEV-X0C10-BLOK-0-4 | 2 | DCA Appr. Req. 2 | WING_TRAILING EDGE | BKK_H | LUB | A330.MPD.275400-04-2 |  | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
882 | 70461604 | HS-TEV | 0016403858 |  | 2105137859 | AC01 |  | 2026-08-31 | 11LHM/A | 0010 | LUBBRICATE OF FLAP TRACK/CARRIAGE -RH | REL | H/26-TEV-X0C10-BLOK-0-4 | 2 | DCA Appr. Req. 2 | WING_TRAILING EDGE | BKK_H | LUB | A330.MPD.275400-04-2 |  | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
883 | 70461604 | HS-TEV | 0016403916 |  | 2105137910 | AC01 |  | 2026-09-05 | 11CLEAN | 0010 | DISINSECTION OF THE AIRCRAFT EQUIPMENT. | REL | H/26-TEV-X0C10-BLOK-0-7 |  |  | CABIN_ALL CABIN | BKK_H | SV | A330.MPD.1221000204-TG01 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
884 | 70461604 | HS-TEV | 0016404177 |  | 2105138134 | AC01 |  | 2026-08-24 | 11LHM/C | 0010 | INSTALL SEAT PROTECTIVE CVR | REL | H/26-TEV-X0C10-BLOK-I-N |  |  | CABIN_INTERIOR | BKK_H | INS | A330.OPR.001ACA46 |  | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
885 | 70461604 | HS-TEV | 0016404188 |  | 2105138145 | AC01 |  | 2026-08-27 | 11PAINT | 0010 | ACT OF NLG WHEEL WELL | REL | H/26-TEV-X0C10-BLOK-0-2 |  |  | FLOOR_LANDING GEAR | BKK_H | ACT | A330.MPD.ZL-123-01-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
886 | 70461604 | HS-TEV | 0016404199 |  | 2105138155 | AC01 |  | 2026-08-31 | 11LHM/A | 0010 | INST ACCESS PANEL ABOUT 131 132 | REL | H/26-TEV-X0C10-BLOK-0-4 |  |  | FLOOR_FWD COMPT | BKK_H | RES | A330.MPD.262300-01-1 |  | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
887 | 70461604 | HS-TEV | 0016404223 |  | 2105138174 | AC01 |  | 2026-08-27 | 11PAINT | 0010 | ACT -FWD CARGO DOOR HINGE ARMS | REL | H/26-TEV-X0C10-BLOK-0-2 |  |  | FLOOR_FWD COMPT | BKK_H | ACT | A330.MPD.523104-01-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
888 | 70461604 | HS-TEV | 0016404233 |  | 2105138182 | AC01 |  | 2026-08-27 | 11PAINT | 0010 | ACT-FWD CARGO DOOR LOCK FITTING | REL | H/26-TEV-X0C10-BLOK-0-2 |  |  | FLOOR_FWD COMPT | BKK_H | ACT | A330.MPD.532107-01-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
889 | 70461604 | HS-TEV | 0016404277 |  | 2105138226 | AC01 |  | 2026-08-27 | 11PAINT | 0010 | ACT -AFT CARGO DOOR HINGE ARM | REL | H/26-TEV-X0C10-BLOK-0-2 |  |  | FLOOR_AFT COMPT | BKK_H | ACT | A330.MPD.523204-01-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
890 | 70461604 | HS-TEV | 0016404285 |  | 2105138234 | AC01 |  | 2026-08-27 | 11PAINT | 0010 | ACT -BULK CARGO DOOR STOP FITTINGS | REL | H/26-TEV-X0C10-BLOK-0-2 |  |  | FLOOR_AFT COMPT | BKK_H | ACT | A330.MPD.523303-01-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
891 | 70461604 | HS-TEV | 0016404290 |  | 2105138239 | AC01 |  | 2026-09-02 | 11PAINT | 0010 | ACT -BULK CARGO DOOR CUTOUT | REL | H/26-TEV-X0C10-BLOK-0-5 |  |  | FLOOR_AFT COMPT | BKK_H | ACT | A330.MPD.534149-01-1 |  | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
892 | 70461604 | HS-TEV | 0016404330 |  | 2105138279 | AC01 |  | 2026-08-31 | 11LHM/C | 0010 | FUC&LUB OF DOOR GIRT BAR SLIDER MECH | REL | H/26-TEV-X0C10-BLOK-0-4 | 0 | AD | CABIN_DOOR | BKK_H | FUC | A330.MPD.521000-07-1 |  | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
893 | 70461604 | HS-TEV | 0016404333 |  | 2105138282 | AC01 |  | 2026-08-31 | 11LHM/C | 0010 | FUC & LUB OF EMERG EXIT DOOR GIRT BAR. | REL | H/26-TEV-X0C10-BLOK-0-4 | 0 | AD | CABIN_DOOR | BKK_H | FUC | A330.MPD.522200-09-1 |  | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
894 | 70461604 | HS-TEV | 0016404386 |  | 2105138333 | AC01 |  | 2026-09-04 | 11LHM/E | 0010 | OPC-APU FIRING CIRCUIT CONTINUITY | REL | H/26-TEV-X0C10-BLOK-0-6 | 1 | DCA Appr. Req. 1 | IERA_FLOOR | BKK_H | OPC | A330.MPD.262200-02-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
895 | 70461604 | HS-TEV | 0016404399 |  | 2105138346 | AC01 |  | 2026-09-02 | 11LHM/C | 0010 | LUB-ALL EMERGENCY EXIT DOORS | REL | H/26-TEV-X0C10-BLOK-0-5 | 1 | DCA Appr. Req. 1 | CABIN_DOOR | BKK_H | LUB | A330.MPD.522200-03-1 |  | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
896 | 70461604 | HS-TEV | 0016404410 |  | 2105138357 | AC01 |  | 2026-08-31 | 11LHM/A | 0010 | LUBRICATION OF THS. ATTACH FITTING | REL | H/26-TEV-X0C10-BLOK-0-4 | 2 | DCA Appr. Req. 2 | FLOOR_TAIL | BKK_H | LUB | A330.MPD.551600-01-1 |  | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
897 | 70461604 | HS-TEV | 0016404411 |  | 2105138358 | AC01 |  | 2026-08-31 | 11LHM/A | 0010 | LUBRICATION OF THS. ATTACH FITTING | REL | H/26-TEV-X0C10-BLOK-0-4 | 2 | DCA Appr. Req. 2 | FLOOR_TAIL | BKK_H | LUB | A330.MPD.551600-02-1 |  | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
898 | 70461604 | HS-TEV | 0016404436 |  | 2105138383 | AC01 |  | 2026-09-04 | 11LHM/A | 0010 | OPC ENG DRIVEN PUMP DEPRESS(GREEN SYS) | REL | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | WING_ENGINE | BKK_H | OPC | A330.MPD.291000-03-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
899 | 70461604 | HS-TEV | 0016404446 |  | 2105138393 | AC01 |  | 2026-09-02 | 11LHM/A | 0010 | INST UPPER FWD PYLON PANEL-RR PYL#1 | REL | H/26-TEV-X0C10-BLOK-0-5 |  |  | WING_ENGINE | BKK_H | RES | A330.MPD.ZL-452-01-1 |  | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
900 | 70461604 | HS-TEV | 0016404456 |  | 2105138403 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | CHECK-FOR CORRET AIR PRESSURE BY GAUGE | REL | H/26-TEV-X0C10-BLOK-0-7 | 2 | DCA Appr. Req. 2 | WING_HYDRAULIC | BKK_H | VIC | A330.MPD.291000-05-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
901 | 70461604 | HS-TEV | 0016404561 |  | 2105138507 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | DOWNJACK A/C AFTER MAINTENANCE | REL | H/26-TEV-X0C10-BLOK-0-7 |  |  | ALL_ALL GRP | BKK_H | INS | A330.OPR.901ACW16 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
902 | 70461604 | HS-TEV | 0016428419 | 1103176776 | 2105145473 | AC02 |  | 2026-08-24 | 11LHM/C | 0010 | CLN FILTER-WASHBASIN DRAIN VALVE | REL | H/26-TEV-X0C10-NONR | 2 | DCA Appr. Req. 2 | CABIN GROUP. | BKK_H | REP | A330.MPD.383242-01-1 |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
903 | 70461604 | HS-TEV | 0016486413 | 1103187684 | 2105160660 | AC02 |  | 2026-08-24 | 11LHM/A | 0010 | CHECK AND SERVING IDG OIL- ENG#1 | REL | H/26-TEV-X0C10-NONR | 4 | TG Appr. Req. 4 |  | BKK_H | SVC | A330.MPD.242100-18-1TG |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
904 | 70461604 | HS-TEV | 0016486414 | 1103187685 | 2105160661 | AC02 |  | 2026-08-24 | 11LHM/A | 0010 | CHECK AND SERVING IDG OIL- ENG#2 | REL | H/26-TEV-X0C10-NONR | 4 | TG Appr. Req. 4 |  | BKK_H | SVC | A330.MPD.242100-18-2TG |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
905 | 70461604 | HS-TEV | 0016219065 | EV056B090326 | EV056B090326 | AC05 |  | 2026-08-24 | 12LC/AP | 0010 | 21:AIR CONDITION | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
906 | 70461604 | HS-TEV | 0016559412 | EV161B270926 | EV161B270926 | AC05 |  | 2026-09-27 | 11LHM/C | 0010 | CABIN LAVATORY | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  |  | 2026-09-27 | 11:34:00 | 2026-09-27 | 19:00:00
907 | 70461604 | HS-TEV | 0016559418 | EV163B270926 | EV163B270926 | AC05 |  | 2026-09-27 | 11LHM/C | 0010 | CABIN GALLEY | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  |  | 2026-09-27 | 12:04:00 | 2026-09-27 | 19:00:00
908 | 70461604 | HS-TEV | 0016403778 |  | 2105137759 | AC01 |  | 2026-09-02 | 11LHM/A | 0010 | CLOSE-UP GVI INNER T/E FIXED STRUCTURE | REL | H/26-TEV-X0C10-BLOK-0-5 |  |  | WING_TRAILING EDGE | BKK_H | RES | A330.MPD.ZL-573-01-1 |  | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
909 | 70461604 | HS-TEV | 0016403827 |  | 2105137828 | AC01 |  | 2026-09-04 | 11LHM/A | 0010 | OPC ELEVATOR DAMPING MEASUREMENT BY BITE | REL | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | FLOOR_TAIL | BKK_H | OPC | A330.MPD.273400-01-1,273400-01-2 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
910 | 70461604 | HS-TEV | 0016403908 |  | 2105137904 | AC01 |  | 2026-08-25 | 11LHM/C | 0010 | PREPARE FOR NDT SPLICING AREA FR48-53. | REL | H/26-TEV-X0C10-BLOK-0-1 |  |  | CABIN_INTERIOR | BKK_H | INS | A330.MPD.533161-01-9 |  | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
911 | 70461604 | HS-TEV | 0016404068 |  | 2105138052 | AC01 |  | 2026-08-29 | 11LHM/A | 0010 | DET OUT WING BOT SKIN LOW SURFACE - LH | REL | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | WING_ALL WING | BKK_H | DET | A330.MPD.572111-01-12,572111-01-13 |  | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
912 | 70461604 | HS-TEV | 0016404307 |  | 2105138256 | AC01 | EWIS | 2026-08-27 | 11LQ/IA | 0010 | INSP-AIRCONDITIONING COMPARTMENT | REL | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | FLOOR_AIR COND | BKK_H | GVI | A330.MPD.ZL-193-01-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
913 | 70461604 | HS-TEV | 0016404323 |  | 2105138272 | AC01 |  | 2026-08-27 | 11LQ/IC | 0010 | INSP - GALLEY FLOOR COVERING. | REL | H/26-TEV-X0C10-BLOK-0-2 | 4 | TG Appr. Req. 4 | CABIN_INTERIOR | BKK_H | DVI | A330.MPD.2528000101-TG01 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
914 | 70461604 | HS-TEV | 0016404502 |  | 2105138449 | AC01 |  | 2026-08-29 | 11LQ/IA | 0010 | LHW INSP FIXED L/E PLATE AND STRAPS | REL | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | WING_LEADING EDGE | BKK_H | DVI | A330.MPD.574109-02-2;574109-02-3 |  | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
915 | 70461604 | HS-TEV | 0016404596 |  | 2105138540 | AC01 |  | 2026-09-04 | 11LHM/A | 0010 | OPC-FWD CARGO BRAKING ROLLER | REL | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | FLOOR_FWD COMPT | BKK_H | OPC | A330.MPD.255101-04-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
916 | 70461604 | HS-TEV | 0016361807 | EV031C020626 | EV031C020626 | AC05 |  | 2026-08-24 | CGK | 0010 | 25 SEAT 31B IFE INOP | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
917 | 70461604 | HS-TEV | 0016361808 | EV031C020626 | EV031C020626 | AC05 |  | 2026-08-24 | BKK_L | 0020 | 25 SEAT 31B IFE INOP | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
918 | 70461604 | HS-TEV | 0016220308 | EV082C070326 | EV082C070326 | AC05 |  | 2026-08-24 | BKK_L | 0010 | 23 31A MONITOR INOP | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
919 | 70461604 | HS-TEV | 0016220309 | EV082C070326 | EV082C070326 | AC05 |  | 2026-08-24 | BKK_L | 0020 | 23 31A MONITOR INOP | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
920 | 70461604 | HS-TEV | 0016537835 | EV138B140926 | EV138B140926 | AC05 |  | 2026-08-24 | 11SH | 0010 | INSP FOUND RH WING FLAP TRACK FIXED FAIR | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
921 | 70461604 | HS-TEV | 0016403780 |  | 2105137781 | AC01 |  | 2026-08-25 | 11LHM/A | 0010 | JOB SET-UP FOR GVI RH CENTER T/E FIXED | REL | H/26-TEV-X0C10-BLOK-0-1 |  |  | WING_TRAILING EDGE | BKK_H | REM | A330.MPD.ZL-574-01-1 |  | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
922 | 70461604 | HS-TEV | 0016403880 |  | 2105137880 | AC01 | EWIS | 2026-08-27 | 11LQ/IA | 0010 | INSP PYLON LEADING EDGE -RR PYLON#1 | REL | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | WING_ENGINE | BKK_H | GVI | A330.MPD.ZL-451-02-3 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
923 | 70461604 | HS-TEV | 0016404051 |  | 2105138039 | AC01 |  | 2026-08-20 | 11NDT | 0010 | SDI of OUTER WING REAR SPAR AFT FACE BE | REL | H/26-TEV-X0C10-BLOK-0-4 | 1 | DCA Appr. Req. 1 | WING_ALL WING | BKK_H | SDI | A330.MPD.572054-01-8 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
924 | 70461604 | HS-TEV | 0016404052 |  | 2105138039 | AC01 |  | 2026-08-20 | 11SH | 0020 | SDI of OUTER WING REAR SPAR AFT FACE BE | REL | H/26-TEV-X0C10-BLOK-0-4 | 1 | DCA Appr. Req. 1 | WING_ALL WING | BKK_H | SDI | A330.MPD.572054-01-8 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
925 | 70461604 | HS-TEV | 0016404053 |  | 2105138039 | AC01 |  | 2026-08-20 | 11LHM/A | 0030 | SDI of OUTER WING REAR SPAR AFT FACE BE | REL | H/26-TEV-X0C10-BLOK-0-4 | 1 | DCA Appr. Req. 1 | WING_ALL WING | BKK_H | SDI | A330.MPD.572054-01-8 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
926 | 70461604 | HS-TEV | 0016404246 |  | 2105138195 | AC01 |  | 2026-08-31 | 11LHM/A | 0010 | INST-THE PACK TEMPERATURE SENSOR | REL | H/26-TEV-X0C10-BLOK-0-4 | 2 | DCA Appr. Req. 2 | FLOOR_AIR COND | BKK_H | RES | A330.MPD.215200-01-1 |  | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
927 | 70461604 | HS-TEV | 0016404262 |  | 2105138211 | AC01 |  | 2026-08-27 | 11LQ/IA | 0010 | INSP-AIRCONDITIONING PACKS | REL | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | FLOOR_AIR COND | BKK_H | GVI | A330.MPD.215000-05-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
928 | 70461604 | HS-TEV | 0016452456 |  | 2105151066 | AC01 |  | 2026-09-04 | 11LHM/A | 0010 | FNC LEAK CHECK OF ALL BLEED AIR DUCTING | REL | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | WING_ALL WING | BKK_H | FNC | A330.MPD.360000-19-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
929 | 70461604 | HS-TEV | 0016526022 | EV103A070926 | EV103A070926 | AC05 |  | 2026-09-07 | 11LHM/A | 0010 | WASTE TANK | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LHM/A | REP |  |  | 2026-09-07 | 10:09:00 | 2026-09-14 | 17:00:00
930 | 70461604 | HS-TEV | 0016526023 | EV103A070926 | EV103A070926 | AC05 |  | 2026-09-07 | 11LHM/A | 0020 | WASTE TANK | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LHM/A | REP |  |  | 2026-09-07 | 10:09:00 | 2026-09-14 | 17:00:00
931 | 70461604 | HS-TEV | 0016535583 | EV136A130926 | EV136A130926 | AC05 |  | 2026-09-13 | 11SH | 0010 | AFT CARGO COMPT DOOR | REL | H/26-TEV-X0C10-NONR |  |  |  | 11SH | REP |  |  | 2026-09-13 | 13:35:00 | 2026-09-14 | 17:00:00
932 | 70461604 | HS-TEV | 0016557308 | EV159B250926 | EV159B250926 | AC05 |  | 2026-08-24 | 11LHM/A | 0010 | LH WING FAIRING ASSY-MOVABLE NUMBER 3 I/ | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
933 | 70461604 | HS-TEV | 0016566543 | EV168B021026 | EV168B021026 | AC05 |  | 2026-10-02 | 11LHM/A | 0010 | LH WING SLAT NUMBER 7 O/B SEAL TORN OFF. | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  |  | 2026-10-02 | 11:07:00 | 2026-10-04 | 19:00:00
934 | 70461604 | HS-TEV | 0016340971 | 1103160978 | 2105119059 | AC02 |  | 2026-08-22 | 11LHM/E | 0010 | G/26-079:INSP WIRING BTW SACL AND ACPU | REL | H/26-TEV-X0C10-MOD -G-I | 4 | TG Appr. Req. 4 | IERA_IERA | BKK_H | REP | A330.ED.BKKJA-G/26-079 |  | 2026-08-22 | 00:00:00 | 2026-09-02 | 00:00:00
935 | 70461604 | HS-TEV | 0016402769 |  | 2105137750 | AC01 |  | 2026-09-06 | 11CLEAN | 0010 | A/C EXTERIOR CLEANING AFTER MAINTENANCE | REL | H/26-TEV-X0C10-BLOK-F-I | 4 | TG Appr. Req. 4 | ALL_ALL GRP | BKK_H | RES | A330.MPD.5100000203-TG01 |  | 2026-09-06 | 08:15:00 | 2026-09-06 | 08:15:00
936 | 70461604 | HS-TEV | 0016402774 |  | 2105137755 | AC01 |  | 2026-08-27 | 11LHM/A | 0010 | JOB SET-UP GVI INNER T/E FIXED STRUCTURE | REL | H/26-TEV-X0C10-BLOK-0-1 |  |  | WING_TRAILING EDGE | BKK_H | REM | A330.MPD.ZL-573-01-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
937 | 70461604 | HS-TEV | 0016403822 |  | 2105137823 | AC01 |  | 2026-08-27 | 11LHM/C | 0010 | CLEANING OF THE TOILET WASTE LINES | REL | H/26-TEV-X0C10-BLOK-0-2 | 3 | TG Appr. Req. 3 | CABIN_LAVATORY | BKK_H | CLN | A330.MPD.383100-05-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
938 | 70461604 | HS-TEV | 0016403854 |  | 2105137855 | AC01 |  | 2026-09-06 | 11LHM/A | 0010 | DEPRESERVATION OF ENGINE -RR ENG#1 | REL | H/26-TEV-X0C10-BLOK-F-I |  |  | WING_ENGINE | BKK_H | SVC | A330.OPR.DEPRESERVE ENGINE |  | 2026-09-06 | 08:15:00 | 2026-09-06 | 08:15:00
939 | 70461604 | HS-TEV | 0016403881 |  | 2105137881 | AC01 | EWIS | 2026-08-27 | 11LQ/IA | 0010 | INSP PYLON LEADING EDGE -RR PYLON#2 | REL | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | WING_ENGINE | BKK_H | GVI | A330.MPD.ZL-451-02-3 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
940 | 70461604 | HS-TEV | 0016403913 |  | 2105137907 | AC01 |  | 2026-08-25 | 11LHM/C | 0010 | PREPARE FOR NDT SPLICE PLATE FR72. | REL | H/26-TEV-X0C10-BLOK-0-1 |  |  | CABIN_INTERIOR | BKK_H | INS | A330.MPD.534107-02-5 |  | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
941 | 70461604 | HS-TEV | 0016403919 |  | 2105137913 | AC01 |  | 2026-09-02 | 11LHM/C | 0010 | CLOSE-UP FOR INSP TORSION BOX DOOR3. | REL | H/26-TEV-X0C10-BLOK-0-5 |  |  | CABIN_INTERIOR | BKK_H | RES | A330.MPD.533198-01-1 |  | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
942 | 70461604 | HS-TEV | 0016403971 |  | 2105137963 | AC01 |  | 2026-08-31 | 11LHM/A | 0010 | INSTALL LOWER FAIRING (RR)#LH | REL | H/26-TEV-X0C10-BLOK-0-4 |  |  | WING_ENGINE | BKK_H | RES | A330.OPR.545100-07-1,545100-10-1 |  | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
943 | 70461604 | HS-TEV | 0016403995 |  | 2105137985 | AC01 |  | 2026-08-31 | 11LHM/A | 0010 | LUB RUDDER PEDALS ADJUSTMNT MECH | REL | H/26-TEV-X0C10-BLOK-0-4 | 2 | DCA Appr. Req. 2 | FLOOR_TAIL | BKK_H | LUB | A330.MPD.272100-05-1 |  | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
944 | 70461604 | HS-TEV | 0016404023 |  | 2105138013 | AC01 |  | 2026-09-04 | 11LHM/A | 0010 | INST - INSULATION BLANKETS FR67-68/FR70 | REL | H/26-TEV-X0C10-BLOK-0-6 |  |  | FLOOR_AFT COMPT | BKK_H | REM | A330.OPR.534014-01-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
945 | 70461604 | HS-TEV | 0016537865 |  | 2105138085 | AC01 |  | 2026-09-14 | 11LHM/C | 0010 | DISCARD CHEMICAL OXYGEN GENERATORS - PAS | REL | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | CABIN_ALL CABIN | BKK_H | FUC | A330.MPD.352142-01-1 |  | 2026-09-14 | 08:15:00 | 2026-09-15 | 08:15:00
946 | 70461604 | HS-TEV | 0016404110 |  | 2105138085 | AC01 |  | 2026-09-14 | 11LHM/C | 0030 | DISCARD CHEMICAL OXYGEN GENERATORS - PAS | REL | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | CABIN_ALL CABIN | BKK_H | FUC | A330.MPD.352142-01-1 |  | 2026-09-14 | 08:15:00 | 2026-09-15 | 08:15:00
947 | 70461604 | HS-TEV | 0016528818 |  | 2105138085 | AC01 |  | 2026-09-14 | 11LHM/C | 0060 | DISCARD CHEMICAL OXYGEN GENERATORS - PAS | REL | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | CABIN_ALL CABIN | BKK_H | FUC | A330.MPD.352142-01-1 |  | 2026-09-14 | 08:15:00 | 2026-09-15 | 08:15:00
948 | 70461604 | HS-TEV | 0016404234 |  | 2105138183 | AC01 |  | 2026-09-02 | 11LHM/A | 0010 | CHK LWR LDCC FIREX PIPING | REL | H/26-TEV-X0C10-BLOK-0-5 | 1 | DCA Appr. Req. 1 | FLOOR_FWD COMPT | BKK_H | FUC | A330.MPD.262300-06-1 |  | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
949 | 70461604 | HS-TEV | 0016404353 |  | 2105138302 | AC01 |  | 2026-08-20 | 11LQ/IC | 0010 | OPC-FULL-FACE/QUICK-DONNING OXYGEN MASKS | REL | H/26-TEV-X0C10-BLOK-0-6 | 1 | DCA Appr. Req. 1 | CABIN_COCKPIT | BKK_H | OPC | A330.MPD.351200-03-1 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
950 | 70461604 | HS-TEV | 0016404398 |  | 2105138345 | AC01 |  | 2026-09-02 | 11LHM/C | 0010 | LUB-ALL PAX/CREW DOORS | REL | H/26-TEV-X0C10-BLOK-0-5 |  |  | CABIN_DOOR | BKK_H | LUB | A330.MPD.521121-01-1 |  | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
951 | 70461604 | HS-TEV | 0016404405 |  | 2105138352 | AC01 |  | 2026-08-25 | 11LHM/C | 0010 | RMV -PANEL 251/252XW&INSULATION. | REL | H/26-TEV-X0C10-BLOK-0-1 |  |  | CABIN_INTERIOR | BKK_H | DVI | A330.MPD.533115-01-4,533114-01-10 |  | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
952 | 70461604 | HS-TEV | 0016404406 |  | 2105138353 | AC01 |  | 2026-08-31 | 11LHM/C | 0010 | INST-PANEL 251/252XW&INSULATION. | REL | H/26-TEV-X0C10-BLOK-0-4 |  |  | CABIN_INTERIOR | BKK_H | DVI | A330.MPD.533115-01-4,533114-01-10 |  | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
953 | 70461604 | HS-TEV | 0016404448 |  | 2105138395 | AC01 |  | 2026-09-02 | 11LHM/A | 0010 | INST UPPER FWD PYLON PANEL-RR PYL#2 | REL | H/26-TEV-X0C10-BLOK-0-5 |  |  | WING_ENGINE | BKK_H | RES | A330.MPD.ZL-452-01-1 |  | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
954 | 70461604 | HS-TEV | 0016404553 |  | 2105138499 | AC01 |  | 2026-09-06 | 11LHM/C | 0010 | SERVICING OF THE TOILET SYSTEM | REL | H/26-TEV-X0C10-BLOK-F-I |  |  | CABIN_LAVATORY | BKK_H | INS | A330.OPR.901ACW04 |  | 2026-09-06 | 08:15:00 | 2026-09-06 | 08:15:00
955 | 70461604 | HS-TEV | 0016404555 |  | 2105138501 | AC01 |  | 2026-09-06 | 11LHM/A | 0010 | REMOVE ENGINE COVERS | REL | H/26-TEV-X0C10-BLOK-F-I |  |  | WING_ENGINE | BKK_H | INS | A330.OPR.901ACW11 |  | 2026-09-06 | 08:15:00 | 2026-09-06 | 08:15:00
956 | 70461604 | HS-TEV | 0016513117 | EV013F280826 | EV013F280826 | AC05 |  | 2026-08-28 | BKK_L | 0010 | REMOVE PYLON#2 LOWER FAIRING | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_L | REP |  |  | 2026-08-28 | 00:00:00 | 2026-08-28 | 00:00:00
957 | 70461604 | HS-TEV | 0016513118 | EV014F280826 | EV014F280826 | AC05 |  | 2026-08-28 | BKK_L | 0010 | REMOVE BULK CARGO DOOR INNER HANDLE | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_L | REP |  |  | 2026-08-28 | 00:00:00 | 2026-08-28 | 00:00:00
958 | 70461604 | HS-TEV | 0016485507 | EV061C160826 | EV061C160826 | AC05 |  | 2026-08-24 | CGK | 0010 | 25 51F TRAY TABLE LOCK BROKEN | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_L | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
959 | 70461604 | HS-TEV | 0016491130 | EV061C160826 | EV061C160826 | AC05 |  | 2026-08-24 | BKK_L | 0020 | 25 51F TRAY TABLE LOCK BROKEN | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_L | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
960 | 70461604 | HS-TEV | 0016503081 | EV079B250826 | EV079B250826 | AC05 |  | 2026-08-24 | 11LHM/C | 0010 | CABIN LAVATORY | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-08-27 | 19:00:00
961 | 70461604 | HS-TEV | 0016526692 | EV106B070926 | EV106B070926 | AC05 |  | 2026-09-07 | 11LHM/A | 0010 | FWD./AFT.CARGO COMPARTMENT LATCH-XZ,SING | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  |  | 2026-09-07 | 14:44:00 | 2026-09-08 | 19:00:00
962 | 70461604 | HS-TEV | 0016526695 | EV108B070926 | EV108B070926 | AC05 |  | 2026-09-07 | 11LHM/A | 0010 | BULK CARGO COMPARTMENT PLATE-SCUFF BOLT | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  |  | 2026-09-07 | 14:54:00 | 2026-09-08 | 19:00:00
963 | 70461604 | HS-TEV | 0016528680 | EV114B080926 | EV114B080926 | AC05 |  | 2026-08-24 | 11CMPST | 0010 | LOWER FUSELAGE SERVICE DOORS FWD LIP SKI | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
964 | 70461604 | HS-TEV | 0016528681 | EV114B080926 | EV114B080926 | AC05 |  | 2026-08-24 | 11PAINT | 0020 | LOWER FUSELAGE SERVICE DOORS FWD LIP SKI | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
965 | 70461604 | HS-TEV | 0016531973 | EV123B100926 | EV123B100926 | AC05 |  | 2026-08-24 | 11LHM/A | 0010 | RH WING LEADING EDGE SLAT NO.1 O/B LIP S | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
966 | 70461604 | HS-TEV | 0016532519 | EV124B100926 | EV124B100926 | AC05 |  | 2026-08-24 | 11SH | 0010 | LH/RH PYLON ACCESS PANEL NUT LOOSEN 16 E | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
967 | 70461604 | HS-TEV | 0016535580 | EV135A130926 | EV135A130926 | AC05 |  | 2026-09-13 | 11LHM/A | 0010 | 25: FWD CARGO ROLLER TRACK | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  |  | 2026-09-13 | 11:39:00 | 2026-09-13 | 19:00:00
968 | 70461604 | HS-TEV | 0016535581 | EV135A130926 | EV135A130926 | AC05 |  | 2026-09-13 | 11SH | 0020 | 25: FWD CARGO ROLLER TRACK | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  |  | 2026-09-13 | 11:39:00 | 2026-09-13 | 19:00:00
969 | 70461604 | HS-TEV | 0016535582 | EV135A130926 | EV135A130926 | AC05 |  | 2026-09-13 | 11LHM/A | 0030 | 25: FWD CARGO ROLLER TRACK | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  |  | 2026-09-13 | 11:39:00 | 2026-09-13 | 19:00:00
970 | 70461604 | HS-TEV | 0016553186 | EV146B230926 | EV146B230926 | AC05 |  | 2026-09-23 | 11PAINT | 0010 | PAX DOOR NUMBER 3 FRAME LH UPPER CORNER | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  |  | 2026-09-23 | 11:15:00 | 2026-09-24 | 19:00:00
971 | 70461604 | HS-TEV | 0016556763 | EV157B250926 | EV157B250926 | AC05 |  | 2026-08-24 | 11LHM/A | 0010 | LH/RH FLAP TRACK FAIRING TAIL CONE ASSY | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
972 | 70461604 | HS-TEV | 0016567584 | EV169B031026 | EV169B031026 | AC05 |  | 2026-10-03 | 11LHM/A | 0010 | FOUND ALL CAPET DEVELOPE MOLD | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LHM/A | REP |  |  | 2026-10-03 | 10:09:00 | 2026-10-12 | 19:00:00
973 | 70461604 | HS-TEV | 0016567585 | EV169B031026 | EV169B031026 | AC05 |  | 2026-10-03 | 11LHM/A | 0020 | FOUND ALL CAPET DEVELOPE MOLD | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LHM/A | REP |  |  | 2026-10-03 | 10:09:00 | 2026-10-12 | 19:00:00
974 | 70461604 | HS-TEV | 0016567586 | EV169B031026 | EV169B031026 | AC05 |  | 2026-10-03 | 11LHM/A | 0030 | FOUND ALL CAPET DEVELOPE MOLD | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LHM/A | REP |  |  | 2026-10-03 | 10:09:00 | 2026-10-12 | 19:00:00
975 | 70461604 | HS-TEV | 0016567587 | EV169B031026 | EV169B031026 | AC05 |  | 2026-10-03 | 11LHM/A | 0040 | FOUND ALL CAPET DEVELOPE MOLD | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LHM/A | REP |  |  | 2026-10-03 | 10:09:00 | 2026-10-12 | 19:00:00
976 | 70461604 | HS-TEV | 0016567648 | EV170B051026 | EV170B051026 | AC05 |  | 2026-08-24 | 11LHM/A | 0010 | REQUIRED TO REPLACE ALL WATER DRAIN VALV | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LHM/A | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
977 | 70461604 | HS-TEV | 0016513105 | EV011F280826 | EV011F280826 | AC05 |  | 2026-08-28 | BKK_L | 0010 | Engine#1 REMOVE TO HS-TEN | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_L | REP |  |  | 2026-08-28 | 00:00:00 | 2026-08-28 | 00:00:00
978 | 70461604 | HS-TEV | 0016513116 | EV012F280826 | EV012F280826 | AC05 |  | 2026-08-28 | BKK_L | 0010 | Engine#2 REMOVE TO HS-TEN | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_L | REP |  |  | 2026-08-28 | 00:00:00 | 2026-08-28 | 00:00:00
979 | 70461604 | HS-TEV | 0016551063 | EV029F210926 | EV029F210926 | AC05 |  | 2026-09-21 | BKK_H | 0010 | PLENUM CHAMBER REPLACE ONE OF SCREW ASSY | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  |  | 2026-09-21 | 00:00:00 | 2026-09-21 | 00:00:00
980 | 70461604 | HS-TEV | 0016565634 | EV032F011026 | EV032F011026 | AC05 |  | 2026-08-24 | 11LHM/A | 0010 | 28 : WING TANK PROBE REMOVED TO HS-TEO | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LHM/A | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
981 | 70461604 | HS-TEV | 0016571584 | EV033F051026 | EV033F051026 | AC05 |  | 2026-10-05 | BKK_H | 0010 | 53 : NOSE RADOME REMOVED TO HS-TEO | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  |  | 2026-10-05 | 00:00:00 | 2026-10-05 | 00:00:00
982 | 70461604 | HS-TEV | 0015414488 | 1103002857 | 2104874107 | AC02 |  | 2026-08-22 | 11SH-LQ | 0010 | E/24-190: INSP OF FUSELAGE SKIN PNLs | REL | H/26-TEV-X0C10-MOD -G-F | 4 | TG Appr. Req. 4 |  | BKK_H | DET | A330.ED.BKKJA-E/24-190 |  | 2026-08-22 | 00:00:00 | 2026-09-02 | 00:00:00
983 | 70461604 | HS-TEV | 0015414489 | 1103002857 | 2104874107 | AC02 |  | 2026-08-22 | 11SH | 0020 | E/24-190: INSP OF FUSELAGE SKIN PNLs | REL | H/26-TEV-X0C10-MOD -G-F | 4 | TG Appr. Req. 4 |  | BKK_H | DET | A330.ED.BKKJA-E/24-190 |  | 2026-08-22 | 00:00:00 | 2026-09-02 | 00:00:00
984 | 70461604 | HS-TEV | 0015414490 | 1103002857 | 2104874107 | AC02 |  | 2026-08-22 | 11PAINT | 0030 | E/24-190: INSP OF FUSELAGE SKIN PNLs | REL | H/26-TEV-X0C10-MOD -G-F | 4 | TG Appr. Req. 4 |  | BKK_H | DET | A330.ED.BKKJA-E/24-190 |  | 2026-08-22 | 00:00:00 | 2026-09-02 | 00:00:00
985 | 70461604 | HS-TEV | 0015444361 | 1103007972 | 2104881106 | AC03 |  | 2026-08-22 | 11LHM/C | 0010 | 210789: INSTL WARNING LABEL ON LP/HP GND | REL | H/26-TEV-X0C10-MOD -G-W | 4 | TG Appr. Req. 4 |  | BKK_H | RAR | A330.TO.MTO-210789 |  | 2026-08-22 | 00:00:00 | 2026-09-02 | 00:00:00
986 | 70461604 | HS-TEV | 0015780738 | 1103064539 | 2104962937 | AC03 |  | 2026-08-22 | 11LHM/A | 0010 | 570985: MOD FASTENER HOLES AT FR 40 | REL | H/26-TEV-X0C10-MOD -G-F | 1 | DCA Appr. Req. 1 |  | BKK_H | MOD | A330.TO.570985 |  | 2026-08-22 | 00:00:00 | 2026-09-02 | 00:00:00
987 | 70461604 | HS-TEV | 0015780739 | 1103064539 | 2104962937 | AC03 |  | 2026-08-22 | 11SH | 0020 | 570985: MOD FASTENER HOLES AT FR 40 | REL | H/26-TEV-X0C10-MOD -G-F | 1 | DCA Appr. Req. 1 |  | BKK_H | MOD | A330.TO.570985 |  | 2026-08-22 | 00:00:00 | 2026-09-02 | 00:00:00
988 | 70461604 | HS-TEV | 0015780740 | 1103064539 | 2104962937 | AC03 |  | 2026-08-22 | 11NDT | 0030 | 570985: MOD FASTENER HOLES AT FR 40 | REL | H/26-TEV-X0C10-MOD -G-F | 1 | DCA Appr. Req. 1 |  | BKK_H | MOD | A330.TO.570985 |  | 2026-08-22 | 00:00:00 | 2026-09-02 | 00:00:00
989 | 70461604 | HS-TEV | 0015780741 | 1103064539 | 2104962937 | AC03 |  | 2026-08-22 | 11LHM/A | 0040 | 570985: MOD FASTENER HOLES AT FR 40 | REL | H/26-TEV-X0C10-MOD -G-F | 1 | DCA Appr. Req. 1 |  | BKK_H | MOD | A330.TO.570985 |  | 2026-08-22 | 00:00:00 | 2026-09-02 | 00:00:00
990 | 70461604 | HS-TEV | 0016403852 |  | 2105137853 | AC01 |  | 2026-08-24 | 11LHM/A | 0010 | PRESERVATION OF ENGINE -RR ENG#1 | REL | H/26-TEV-X0C10-BLOK-I-N |  |  | WING_ENGINE | BKK_H | SVC | A330.OPR.PRESERVE ENGINE |  | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
991 | 70461604 | HS-TEV | 0016403853 |  | 2105137854 | AC01 |  | 2026-08-24 | 11LHM/A | 0010 | PRESERVATION OF ENGINE -RR ENG#2 | REL | H/26-TEV-X0C10-BLOK-I-N | 2 | DCA Appr. Req. 2 | WING_ENGINE | BKK_H | SVC | A330.OPR.PRESERVE ENGINE |  | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
992 | 70461604 | HS-TEV | 0016404009 |  | 2105137999 | AC01 |  | 2026-08-27 | 11NDT | 0010 | INSP PYLON PYRAMID PYL#2 | REL | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | WING_ENGINE | BKK_H | NDT | A330.MPD.545105-01-3 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
993 | 70461604 | HS-TEV | 0016404574 |  | 2105138519 | AC01 |  | 2026-08-20 | 11LHM/A | 0010 | APU PRE/DE-PRESERVATION. | REL | H/26-TEV-X0C10-BLOK-0-7 |  |  | FLOOR_TAIL | BKK_H | INS | A330.OPR.4900000101-TG01 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
994 | 70461604 | HS-TEV | 0016404575 |  | 2105138519 | AC01 |  | 2026-08-20 | 11LHM/A | 0020 | APU PRE/DE-PRESERVATION. | REL | H/26-TEV-X0C10-BLOK-0-7 |  |  | FLOOR_TAIL | BKK_H | INS | A330.OPR.4900000101-TG01 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
995 | 70461604 | HS-TEV | 0016556400 | EV002C240926 | EV002C240926 | AC05 |  | 2026-09-24 | BKK_H | 0010 | 25 : STATION 3R HEADREST COVER TORN | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  |  | 2026-09-24 | 00:00:00 | 2026-09-24 | 00:00:00
996 | 70461604 | HS-TEV | 0016556401 | EV003C240926 | EV003C240926 | AC05 |  | 2026-09-24 | BKK_H | 0010 | 25: LIFE VEST STORAGE POUNCH AT 31K TORN | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  |  | 2026-09-24 | 00:00:00 | 2026-09-24 | 00:00:00
997 | 70461604 | HS-TEV | 0016513126 | EV016F280826 | EV016F280826 | AC05 |  | 2026-08-28 | BKK_L | 0010 | REMOVE ENG#1 AIR INTAKE COWL | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_L | REP |  |  | 2026-08-28 | 00:00:00 | 2026-08-28 | 00:00:00
998 | 70461604 | HS-TEV | 0016543386 | EV025F160926 | EV025F160926 | AC05 |  | 2026-09-16 | BKK_H | 0010 | REMOVED ENG#2 LH T/R TO HS-TEP | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  |  | 2026-09-16 | 00:00:00 | 2026-09-16 | 00:00:00
999 | 70461604 | HS-TEV | 0016543383 | EV026F170926 | EV026F170926 | AC05 |  | 2026-09-17 | BKK_H | 0010 | WING TAKE PROB AND DUAL TEMP SENSOR | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  |  | 2026-09-17 | 00:00:00 | 2026-09-17 | 00:00:00
1000 | 70461604 | HS-TEV | 0016563441 | EV031F240926 | EV031F240926 | AC05 |  | 2026-09-24 | BKK_H | 0010 | PORTABLE FIRE EXTINGUISHER REM.TO HS-TEX | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  |  | 2026-09-24 | 00:00:00 | 2026-09-24 | 00:00:00
1001 | 70461604 | HS-TEV | 0016480377 | EV035C120826 | EV035C120826 | AC05 |  | 2026-08-24 | BKK_L | 0010 | 25 27 A,J FOOT REST BROKEN. | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_L | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1002 | 70461604 | HS-TEV | 0016484280 | EV035C120826 | EV035C120826 | AC05 |  | 2026-08-24 | BKK_L | 0020 | 25 27 A,J FOOT REST BROKEN. | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_L | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1003 | 70461604 | HS-TEV | 0016501184 | EV071A240826 | EV071A240826 | AC05 |  | 2026-08-24 | 11LHM/A | 0010 | LOWER DECK CARGO LOADING SYS | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LHM/A | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1004 | 70461604 | HS-TEV | 0016501203 | EV072A240826 | EV072A240826 | AC05 |  | 2026-08-24 | 11LHM/A | 0010 | LOWER DECK CARGO LOADING SYS | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LHM/A | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1005 | 70461604 | HS-TEV | 0015934871 | 1102995329 | 2104861538 | AC03 |  | 2026-08-22 | 11LHM/A | 0010 | 271087:O/B FLAP-VI Drive Station Element | REL | H/26-TEV-X0C10-MOD -G-W | 0 | AD | WING_TRAILING EDGE | BKK_H | MOD | A330.TO.271087 |  | 2026-08-22 | 00:00:00 | 2026-09-02 | 00:00:00
1006 | 70461604 | HS-TEV | 0016147977 | 1103126840 | 2105063610 | AC02 |  | 2026-08-24 | 11LHM/E | 0010 | DOWNLOAD DFDR DATA | REL | H/26-TEV-X0C10-NONR | 0 | AD |  | BKK_H | REP | A330.MPD.313300-04-1 |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1007 | 70461604 | HS-TEV | 0016203905 | 1103136332 | 2105079340 | AC02 |  | 2026-08-22 | 11LHM/A | 0010 | FULL BODY WASHING THE AIRPLANE. | REL | H/26-TEV-X0C10-NONR | 4 | TG Appr. Req. 4 |  | BKK_H | REP | A330.OPR.5100000201-TG01 |  | 2026-08-22 | 00:00:00 | 2026-09-02 | 00:00:00
1008 | 70461604 | HS-TEV | 0016203906 | 1103136332 | 2105079340 | AC02 |  | 2026-08-22 | 11CLEAN | 0020 | FULL BODY WASHING THE AIRPLANE. | REL | H/26-TEV-X0C10-NONR | 4 | TG Appr. Req. 4 |  | BKK_H | REP | A330.OPR.5100000201-TG01 |  | 2026-08-22 | 00:00:00 | 2026-09-02 | 00:00:00
1009 | 70461604 | HS-TEV | 0016203907 | 1103136332 | 2105079340 | AC02 |  | 2026-08-22 | 11LHM/E | 0030 | FULL BODY WASHING THE AIRPLANE. | REL | H/26-TEV-X0C10-NONR | 4 | TG Appr. Req. 4 |  | BKK_H | REP | A330.OPR.5100000201-TG01 |  | 2026-08-22 | 00:00:00 | 2026-09-02 | 00:00:00
1010 | 70461604 | HS-TEV | 0016331567 | 1103159707 | 2105115894 | AC02 |  | 2026-08-22 | 11LHM/A | 0010 | DVI LP COMPRESSOR BLADES ENG#2 | REL | H/26-TEV-X0C10-MOD -G-W | 2 | DCA Appr. Req. 2 | INSP-W_ENGINE | BKK_H | DET | A330.MPD.723100-R1-1-TG02 |  | 2026-08-22 | 00:00:00 | 2026-09-02 | 00:00:00
1011 | 70461604 | HS-TEV | 0016348905 | 1103162575 | 2105121806 | AC02 |  | 2026-08-24 | 11LHM/A | 0010 | CLEAN OF LP COMPRESSOR ROTOR BLADES-ENG2 | REL | H/26-TEV-X0C10-NONR | 4 | TG Appr. Req. 4 |  | BKK_H | REP | A330.MPD.7200100-TG02 |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1012 | 70461604 | HS-TEV | 0016377847 | 1103168108 | 2105130035 | AC02 |  | 2026-08-24 | 11LHM/A | 0010 | CLN IP AND HP COMPRESSORS - ENG 2 | REL | H/26-TEV-X0C10-NONR | 4 | TG Appr. Req. 4 |  | BKK_H | REP | A330.MPD.7200200-TG02 |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1013 | 70461604 | HS-TEV | 0016377848 | 1103168108 | 2105130035 | AC02 |  | 2026-08-24 | 11LHM/E | 0020 | CLN IP AND HP COMPRESSORS - ENG 2 | REL | H/26-TEV-X0C10-NONR | 4 | TG Appr. Req. 4 |  | BKK_H | REP | A330.MPD.7200200-TG02 |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1014 | 70461604 | HS-TEV | 0016403884 |  | 2105137884 | AC01 |  | 2026-09-06 | 11LHM/A | 0010 | FUC OF OVERPRESSURE VALVE- RR ENG#1 | REL | H/26-TEV-X0C10-BLOK-F-I | 2 | DCA Appr. Req. 2 | WING_ENGINE | BKK_H | FUC | A330.MPD.361100-04-1,361100-04-2 |  | 2026-09-06 | 08:15:00 | 2026-09-06 | 08:15:00
1015 | 70461604 | HS-TEV | 0016403885 |  | 2105137885 | AC01 |  | 2026-09-06 | 11LHM/A | 0010 | FUC OF OVERPRESSURE VALVE- RR ENG#2 | REL | H/26-TEV-X0C10-BLOK-F-I | 2 | DCA Appr. Req. 2 | WING_ENGINE | BKK_H | FUC | A330.MPD.361100-04-1,361100-04-2 |  | 2026-09-06 | 08:15:00 | 2026-09-06 | 08:15:00
1016 | 70461604 | HS-TEV | 0016403938 |  | 2105137932 | AC01 |  | 2026-08-25 | 11LHM/C | 0010 | CLEAN - VACUUM WASTE LINE TOILET TUBE. | REL | H/26-TEV-X0C10-BLOK-0-1 | 2 | DCA Appr. Req. 2 | CABIN_LAVATORY | BKK_H | RST | A330.MPD.383100-02-1-02,383100-02-1 |  | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
1017 | 70461604 | HS-TEV | 0016403976 |  | 2105137968 | AC01 |  | 2026-08-31 | 11LHM/A | 0010 | LH-WING LUB OF IPGB AND DDS FLAP TRACKS | REL | H/26-TEV-X0C10-BLOK-0-4 | 3 | TG Appr. Req. 3 | WING_TRAILING EDGE | BKK_H | LUB | A330.MPD.275400-12-1,275400-12-2 |  | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
1018 | 70461604 | HS-TEV | 0016403977 |  | 2105137969 | AC01 |  | 2026-08-31 | 11LHM/A | 0010 | RH-WING LUB OF IPGB AND DDS FLAP TRACKS | REL | H/26-TEV-X0C10-BLOK-0-4 | 3 | TG Appr. Req. 3 | WING_TRAILING EDGE | BKK_H | LUB | A330.MPD.275400-12-1,275400-12-2 |  | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
1019 | 70461604 | HS-TEV | 0016403980 |  | 2105137972 | AC01 |  | 2026-09-04 | 11LHM/A | 0010 | LHW-OPC OF HYD.LOCKING FUNCTION | REL | H/26-TEV-X0C10-BLOK-0-6 | 3 | TG Appr. Req. 3 | WING_TRAILING EDGE | BKK_H | OPC | A330.MPD.276400-03-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
1020 | 70461604 | HS-TEV | 0016403981 |  | 2105137973 | AC01 |  | 2026-09-04 | 11LHM/A | 0010 | RHW-OPC OF HYD.LOCKING FUNCTION | REL | H/26-TEV-X0C10-BLOK-0-6 | 3 | TG Appr. Req. 3 | WING_TRAILING EDGE | BKK_H | OPC | A330.MPD.276400-03-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
1021 | 70461604 | HS-TEV | 0016403997 |  | 2105137987 | AC01 |  | 2026-08-31 | 11LHM/A | 0010 | LUB OF FLAP STEADY BEARINGS - LHW | REL | H/26-TEV-X0C10-BLOK-0-4 | 2 | DCA Appr. Req. 2 | WING_TRAILING EDGE | BKK_H | LUB | A330.MPD.275400-08-1 |  | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
1022 | 70461604 | HS-TEV | 0016403998 |  | 2105137988 | AC01 |  | 2026-08-31 | 11LHM/A | 0010 | LUB OF FLAP STEADY BEARINGS - RHW | REL | H/26-TEV-X0C10-BLOK-0-4 | 2 | DCA Appr. Req. 2 | WING_TRAILING EDGE | BKK_H | LUB | A330.MPD.275400-08-1 |  | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
1023 | 70461604 | HS-TEV | 0016404008 |  | 2105137998 | AC01 |  | 2026-08-27 | 11NDT | 0010 | INSP PYLON PYRAMID PYL#1 | REL | H/26-TEV-X0C10-BLOK-0-2 | 1 | DCA Appr. Req. 1 | WING_ENGINE | BKK_H | NDT | A330.MPD.545105-01-3 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
1024 | 70461604 | HS-TEV | 0016404019 |  | 2105138009 | AC01 |  | 2026-09-04 | 11LHM/A | 0010 | CHK BLEED AIR DUCTING PYLON AREA PYL#1 | REL | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | WING_ENGINE | BKK_H | CHK | A330.MPD.361141-05-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
1025 | 70461604 | HS-TEV | 0016404020 |  | 2105138010 | AC01 |  | 2026-09-04 | 11LHM/A | 0010 | CHK BLEED AIR DUCTING PYLON AREA PYL#2 | REL | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | WING_ENGINE | BKK_H | CHK | A330.MPD.361141-05-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
1026 | 70461604 | HS-TEV | 0016404041 |  | 2105138031 | AC01 |  | 2026-08-20 | 11NDT | 0010 | SDI (HFEC) OF HORIZONTAL STAB CENTER BOX | REL | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | FLOOR_TAIL | BKK_H | SDI | A330.MPD.551016-01-10 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
1027 | 70461604 | HS-TEV | 0016404042 |  | 2105138031 | AC01 |  | 2026-08-20 | 11LHM/A | 0020 | SDI (HFEC) OF HORIZONTAL STAB CENTER BOX | REL | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | FLOOR_TAIL | BKK_H | SDI | A330.MPD.551016-01-10 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
1028 | 70461604 | HS-TEV | 0016404082 |  | 2105138064 | AC01 |  | 2026-08-20 | 11LHM/A | 0010 | GVI AREA BELOW THE BROADBAND ANTENNA RAD | REL | H/26-TEV-X0C10-BLOK-0-3 | 2 | DCA Appr. Req. 2 | FLOOR_FUSELAGE | BKK_H | GVI | A330.MPD.ZL-200-03-1 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
1029 | 70461604 | HS-TEV | 0016404083 |  | 2105138064 | AC01 |  | 2026-08-20 | 11LHM/A | 0020 | GVI AREA BELOW THE BROADBAND ANTENNA RAD | REL | H/26-TEV-X0C10-BLOK-0-3 | 2 | DCA Appr. Req. 2 | FLOOR_FUSELAGE | BKK_H | GVI | A330.MPD.ZL-200-03-1 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
1030 | 70461604 | HS-TEV | 0016404174 |  | 2105138131 | AC01 |  | 2026-08-24 | 11LHM/A | 0010 | INSTALL ENGINE COVER | REL | H/26-TEV-X0C10-BLOK-I-N |  |  | WING_ENGINE | BKK_H | INS | A330.OPR.001ACA21 |  | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
1031 | 70461604 | HS-TEV | 0016404176 |  | 2105138133 | AC01 |  | 2026-08-24 | 11LHM/A | 0010 | TOWING AIRCRAFT | REL | H/26-TEV-X0C10-BLOK-I-N |  |  | ALL_ALL GRP | BKK_H | INS | A330.OPR.001ACA43 |  | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
1032 | 70461604 | HS-TEV | 0016404194 |  | 2105138151 | AC01 |  | 2026-08-20 | 11LHM/A | 0010 | FUC-POSITIVE&NEGATIVE DELTA P-SAFETY VLV | REL | H/26-TEV-X0C10-BLOK-0-7 | 2 | DCA Appr. Req. 2 | FLOOR_AIR COND | BKK_H | FUC | A330.MPD.213100-05-1;213100-05-2 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
1033 | 70461604 | HS-TEV | 0016404195 |  | 2105138151 | AC01 |  | 2026-08-20 | 11LHM/A | 0020 | FUC-POSITIVE&NEGATIVE DELTA P-SAFETY VLV | REL | H/26-TEV-X0C10-BLOK-0-7 | 2 | DCA Appr. Req. 2 | FLOOR_AIR COND | BKK_H | FUC | A330.MPD.213100-05-1;213100-05-2 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
1034 | 70461604 | HS-TEV | 0016404200 |  | 2105138156 | AC01 |  | 2026-09-04 | 11LHM/E | 0010 | OPC-LDCC FIREX FIRING CIRCUIT CONTINUIT | REL | H/26-TEV-X0C10-BLOK-0-6 | 1 | DCA Appr. Req. 1 | IERA_FLOOR | BKK_H | OPC | A330.MPD.262300-01-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
1035 | 70461604 | HS-TEV | 0016404202 |  | 2105138158 | AC01 |  | 2026-09-02 | 11LHM/A | 0010 | INSTALL-FLOOR PANELS Z-131/132 | REL | H/26-TEV-X0C10-BLOK-0-5 |  |  | FLOOR_FWD COMPT | BKK_H | RES | A330.MPD.261500-02-1 |  | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
1036 | 70461604 | HS-TEV | 0016404315 |  | 2105138264 | AC01 |  | 2026-09-04 | 11LHM/C | 0010 | INST-COFFEE CONTAINERS | REL | H/26-TEV-X0C10-BLOK-0-6 | 4 | TG Appr. Req. 4 | CABIN_GALLEY | BKK_H | RES | A330.MPD.2536010201-TG01 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
1037 | 70461604 | HS-TEV | 0016404350 |  | 2105138299 | AC01 |  | 2026-08-31 | 11LQ/IC | 0010 | FUC-HOR & VERT MECH CONT CABLE ADJ | REL | H/26-TEV-X0C10-BLOK-0-4 | 2 | DCA Appr. Req. 2 | INSP-C_COCKPIT | BKK_H | FUC | A330.MPD.251100-02-1 |  | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
1038 | 70461604 | HS-TEV | 0016404388 |  | 2105138335 | AC01 |  | 2026-09-04 | 11LHM/E | 0010 | OPC-APU FIRE PUSHBUTTON SWITCH FUNCTION | REL | H/26-TEV-X0C10-BLOK-0-6 | 1 | DCA Appr. Req. 1 | IERA_FLOOR | BKK_H | OPC | A330.MPD.262200-06-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
1039 | 70461604 | HS-TEV | 0016404412 |  | 2105138359 | AC01 |  | 2026-08-31 | 11LHM/A | 0010 | LUBRICATE THS. MECH CTRL. CHAINS | REL | H/26-TEV-X0C10-BLOK-0-4 | 2 | DCA Appr. Req. 2 | FLOOR_TAIL | BKK_H | LUB | A330.MPD.274100-01-1 |  | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
1040 | 70461604 | HS-TEV | 0016404417 |  | 2105138364 | AC01 |  | 2026-08-27 | 11LQ/IA | 0010 | INSP OF REAR FUSELAGE SECTION | REL | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | FLOOR_TAIL | BKK_H | GVI | A330.MPD.ZL-300-01-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
1041 | 70461604 | HS-TEV | 0016404429 |  | 2105138376 | AC01 | SCT | 2026-08-27 | 11LHM/A | 0010 | INSP OF TRIMMING MECH CTRL | REL | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | FLOOR_TAIL | BKK_H | FUC | A330.MPD.274100-04-1 |  | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
1042 | 70461604 | HS-TEV | 0016404431 |  | 2105138378 | AC01 |  | 2026-08-29 | 11LHM/A | 0010 | INSP OF THS HYD ACTUATION (INTEGRITY) | REL | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | FLOOR_TAIL | BKK_H | FUC | A330.MPD.274400-08-1 |  | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
1043 | 70461604 | HS-TEV | 0016404439 |  | 2105138386 | AC01 |  | 2026-09-02 | 11LHM/A | 0010 | CHK DISTRIB PIPE FOR LEAK&OBST-RR PYLON1 | REL | H/26-TEV-X0C10-BLOK-0-5 | 1 | DCA Appr. Req. 1 | WING_ENGINE | BKK_H | FUC | A330.MPD.262100-12-1 |  | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
1044 | 70461604 | HS-TEV | 0016404451 |  | 2105138398 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | FUC-GREEN BLUE&YELLOW LOW LEVEL WARNING | REL | H/26-TEV-X0C10-BLOK-0-7 | 1 | DCA Appr. Req. 1 | WING_HYDRAULIC | BKK_H | FUC | A330.MPD.292000-05-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
1045 | 70461604 | HS-TEV | 0016404458 |  | 2105138405 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | OPC-AUTO CLOSURE OF FIRE SOV /LOW LEVEL | REL | H/26-TEV-X0C10-BLOK-0-7 | 1 | DCA Appr. Req. 1 | WING_HYDRAULIC | BKK_H | OPC | A330.MPD.291100-03-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
1046 | 70461604 | HS-TEV | 0016404466 |  | 2105138413 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | OPC-RESERVOIR LOW AIR PRESSURE WARNING | REL | H/26-TEV-X0C10-BLOK-0-7 | 2 | DCA Appr. Req. 2 | WING_HYDRAULIC | BKK_H | OPC | A330.MPD.293000-02-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
1047 | 70461604 | HS-TEV | 0016404467 |  | 2105138414 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | FUC-MONITOR INT LEAK RATE,GREEN HYD(VWX) | REL | H/26-TEV-X0C10-BLOK-0-7 | 1 | DCA Appr. Req. 1 | WING_HYDRAULIC | BKK_H | FUC | A330.MPD.292000-04-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
1048 | 70461604 | HS-TEV | 0016404468 |  | 2105138415 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | OPC R A T AUTOMATIC DEPLOYMENT | REL | H/26-TEV-X0C10-BLOK-0-7 | 1 | DCA Appr. Req. 1 | WING_HYDRAULIC | BKK_H | OPC | A330.MPD.292400-01-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
1049 | 70461604 | HS-TEV | 0016404473 |  | 2105138420 | AC01 |  | 2026-09-02 | 11LHM/A | 0010 | OPC-LP FUEL VALVE USING INDIVIDUAL MOTOR | REL | H/26-TEV-X0C10-BLOK-0-5 | 2 | DCA Appr. Req. 2 | WING_FUEL | BKK_H | OPC | A330.MPD.282400-04-1 |  | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
1050 | 70461604 | HS-TEV | 0016404494 |  | 2105138441 | AC01 |  | 2026-08-25 | 11LHM/A | 0010 | JOB SETUP INSP-WING ICE PROT. COMPONENTS | REL | H/26-TEV-X0C10-BLOK-0-1 |  |  | WING_LEADING EDGE | BKK_H | REM | A330.MPD.301100-01-1 |  | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
1051 | 70461604 | HS-TEV | 0016404510 |  | 2105138457 | AC01 |  | 2026-08-29 | 11LHM/A | 0010 | [LHW-INSPECTION OF FLAP TRANSMISSION ASS | REL | H/26-TEV-X0C10-BLOK-0-3 | 2 | DCA Appr. Req. 2 | WING_TRAILING EDGE | BKK_H | DVI | A330.MPD.275400-02-1 |  | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
1052 | 70461604 | HS-TEV | 0016404513 |  | 2105138460 | AC01 |  | 2026-08-29 | 11LHM/A | 0010 | [RHW-INSPECTION OF FLAP TRANSMISSION ASS | REL | H/26-TEV-X0C10-BLOK-0-3 | 2 | DCA Appr. Req. 2 | WING_TRAILING EDGE | BKK_H | DVI | A330.MPD.275400-02-1 |  | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
1053 | 70461604 | HS-TEV | 0016404516 |  | 2105138463 | AC01 |  | 2026-08-29 | 11LHM/A | 0010 | LHW-INSP CRUISE ROLLER,FLAP TRACK,ETC | REL | H/26-TEV-X0C10-BLOK-0-3 | 2 | DCA Appr. Req. 2 | WING_TRAILING EDGE | BKK_H | DVI | A330.MPD.275400-03-1 |  | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
1054 | 70461604 | HS-TEV | 0016404518 |  | 2105138465 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | OPC-R A T MAN DPLOYMNT,FUC-R A T | REL | H/26-TEV-X0C10-BLOK-0-7 | 1 | DCA Appr. Req. 1 | WING_HYDRAULIC | BKK_H | OPC | A330.MPD.292400-03-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
1055 | 70461604 | HS-TEV | 0016404521 |  | 2105138468 | AC01 |  | 2026-08-31 | 11LHM/A | 0010 | RHW-LUB OF FLAP TRACK/CARRIAGE ROLLER | REL | H/26-TEV-X0C10-BLOK-0-4 |  |  | WING_TRAILING EDGE | BKK_H | INS | A330.MPD.275400-03-1 |  | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
1056 | 70461604 | HS-TEV | 0016404534 |  | 2105138481 | AC01 |  | 2026-09-04 | 11LHM/A | 0010 | CHK FLUID LEVEL OF BRAKE LOW PREES RESE | REL | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | FLOOR_LANDING GEAR | BKK_H | SVC | A330.MPD.324300-01-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
1057 | 70461604 | HS-TEV | 0016404536 |  | 2105138483 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | FUC CHARGE PRESS OF NLG SHOCK ABSORBER | REL | H/26-TEV-X0C10-BLOK-0-7 | 2 | DCA Appr. Req. 2 | FLOOR_LANDING GEAR | BKK_H | FUC | A330.MPD.322100-04-1 |  | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
1058 | 70461604 | HS-TEV | 0016404539 |  | 2105138485 | AC01 |  | 2026-09-02 | 11LHM/A | 0010 | FUNCTIONAL CHECK NLG TORQUE LINK ASSY | REL | H/26-TEV-X0C10-BLOK-0-5 | 2 | DCA Appr. Req. 2 | FLOOR_LANDING GEAR | BKK_H | FUC | A330.MPD.322100-05-1 |  | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
1059 | 70461604 | HS-TEV | 0016404542 |  | 2105138488 | AC01 |  | 2026-08-24 | 11LHM/A | 0010 | REPLENISH LH MLG SHOCK ABSORB-ON WHEELS | REL | H/26-TEV-X0C10-BLOK-I-N | 2 | DCA Appr. Req. 2 | FLOOR_LANDING GEAR | BKK_H | SVC | A330.MPD.321100-04-1 |  | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
1060 | 70461604 | HS-TEV | 0016404543 |  | 2105138489 | AC01 |  | 2026-08-24 | 11LHM/A | 0010 | REPLENISH LH MLG SHOCK ABSORBER-ON JACKS | REL | H/26-TEV-X0C10-BLOK-I-N | 2 | DCA Appr. Req. 2 | FLOOR_LANDING GEAR | BKK_H | SVC | A330.MPD.321100-04-1 |  | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
1061 | 70461604 | HS-TEV | 0016404544 |  | 2105138490 | AC01 |  | 2026-08-24 | 11LHM/A | 0010 | REPLENISH RH MLG SHOCK ABSORB-ON WHEELS | REL | H/26-TEV-X0C10-BLOK-I-N | 2 | DCA Appr. Req. 2 | FLOOR_LANDING GEAR | BKK_H | SVC | A330.MPD.321100-04-1 |  | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
1062 | 70461604 | HS-TEV | 0016404545 |  | 2105138491 | AC01 |  | 2026-08-24 | 11LHM/A | 0010 | REPLENISH RH MLG SHOCK ABSORBER-ON JACKS | REL | H/26-TEV-X0C10-BLOK-I-N | 2 | DCA Appr. Req. 2 | FLOOR_LANDING GEAR | BKK_H | SVC | A330.MPD.321100-04-1 |  | 2026-08-24 | 08:15:00 | 2026-08-24 | 08:15:00
1063 | 70461604 | HS-TEV | 0016404546 |  | 2105138492 | AC01 |  | 2026-09-04 | 11LHM/A | 0010 | CHECK-CHRG PRESS OF LH-MLG SHOCK ABSORB | REL | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | FLOOR_LANDING GEAR | BKK_H | FUC | A330.MPD.321100-03-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
1064 | 70461604 | HS-TEV | 0016404547 |  | 2105138493 | AC01 |  | 2026-09-04 | 11LHM/A | 0010 | CHECK-CHRG PRESS OF RH-MLG SHOCK ABSORB | REL | H/26-TEV-X0C10-BLOK-0-6 | 2 | DCA Appr. Req. 2 | FLOOR_LANDING GEAR | BKK_H | FUC | A330.MPD.321100-03-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
1065 | 70461604 | HS-TEV | 0016412647 | 1103173852 | 2105140380 | AC02 |  | 2026-08-24 | 11LHM/A | 0010 | OPC OP WATER DRN VALVES TO DRN ACC WATER | REL | H/26-TEV-X0C10-NONR | 2 | DCA Appr. Req. 2 | "FUSELAGE, CARGO AND TAIL." | BKK_H | REP | A330.MPD.281100-02-1 |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1066 | 70461604 | HS-TEV | 0016491395 | 1103188492 | 2105162150 | AC02 |  | 2026-08-24 | 11LHM/A | 0010 | OPERATE WATER DRAIN VALVES TO DRAIN ACCU | REL | H/26-TEV-X0C10-NONR | 2 | DCA Appr. Req. 2 | "WING, PYLONS AND APU." | BKK_H | REP | A330.MPD.281100-08-1 |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1067 | 70461604 | HS-TEV | 0016531090 | EV022F090926 | EV022F090926 | AC05 |  | 2026-09-09 | BKK_H | 0010 | RP OXYGEN BOX REMOVED TO HS-TEO | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  |  | 2026-09-09 | 00:00:00 | 2026-09-09 | 00:00:00
1068 | 70461604 | HS-TEV | 0016552599 | EV030F220926 | EV030F220926 | AC05 |  | 2026-09-22 | BKK_H | 0010 | 34 : RA FAN (3SA2) REMOVE TO HS-TEX | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  |  | 2026-09-22 | 00:00:00 | 2026-09-22 | 00:00:00
1069 | 70461604 | HS-TEV | 0016503078 | EV077A250826 | EV077A250826 | AC05 |  | 2026-08-24 | 11LHM/A | 0010 | WHEELS AND BRAKES | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LHM/A | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1070 | 70461604 | HS-TEV | 0016503079 | EV077A250826 | EV077A250826 | AC05 |  | 2026-08-24 | 11LHM/A | 0020 | WHEELS AND BRAKES | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LHM/A | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1071 | 70461604 | HS-TEV | 0016503080 | EV078A250826 | EV078A250826 | AC05 |  | 2026-08-24 | 11LHM/A | 0010 | NORMAL BRAKING | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LHM/A | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1072 | 70461604 | HS-TEV | 0016551062 | EV028F200926 | EV028F200926 | AC05 |  | 2026-09-20 | BKK_H | 0010 | AFT COMPSMOKE DETECTOR REMOVED TO HS-TEW | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  |  | 2026-09-20 | 00:00:00 | 2026-09-20 | 00:00:00
1073 | 70461604 | HS-TEV-27-44-5104-1CS | 0015743975 | 1103057911 | 2104955452 | AC03 |  | 2026-08-22 | 11LHM/A | 0010 | 271204:A330 THSA MOD AND INTRO 47172-540 | REL | H/26-TEV-X0C10-MOD -G-W | 0 | AD | FLOOR_ALL FLOOR | BKK_H | MOD | A330.TO.271204 |  | 2026-08-22 | 00:00:00 | 2026-09-02 | 00:00:00
1074 | 70461604 | HS-TEV-27-44-5104-1CS | 0015743976 | 1103057911 | 2104955452 | AC03 |  | 2026-08-22 | 11LHM/A | 0020 | 271204:A330 THSA MOD AND INTRO 47172-540 | REL | H/26-TEV-X0C10-MOD -G-W | 0 | AD | FLOOR_ALL FLOOR | BKK_H | MOD | A330.TO.271204 |  | 2026-08-22 | 00:00:00 | 2026-09-02 | 00:00:00
1075 | 70461604 | HS-TEV | 0016404244 |  | 2105138193 | AC01 |  | 2026-08-31 | 11LHM/A | 0010 | INST-CONDENSER | REL | H/26-TEV-X0C10-BLOK-0-4 | 2 | DCA Appr. Req. 2 | FLOOR_AIR COND | BKK_H | RES | A330.MPD.215000-12-1,215200-01-1 |  | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
1076 | 70461604 | HS-TEV | 0016513122 | EV015F280826 | EV015F280826 | AC05 |  | 2026-08-28 | BKK_L | 0010 | REMOVE APU AFT FUEL PUMP | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_L | REP |  |  | 2026-08-28 | 00:00:00 | 2026-08-28 | 00:00:00
1077 | 70461604 | HS-TEV | 0016534264 | EV024F120926 | EV024F120926 | AC05 |  | 2026-09-12 | BKK_L | 0010 | L/G,DOOR SELECTOR VLV MANIFOLD ASSY RMVD | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_L | REP |  |  | 2026-09-12 | 00:00:00 | 2026-09-12 | 00:00:00
1078 | 70461604 | HS-TEV | 0015924160 | EV045C110925 | EV045C110925 | AC05 |  | 2026-08-24 | HKG | 0010 | 25 42A TRAY TABLE BROKEN AND HAS SHARP E | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1079 | 70461604 | HS-TEV | 0015924161 | EV045C110925 | EV045C110925 | AC05 |  | 2026-08-24 | BKK_L | 0020 | 25 42A TRAY TABLE BROKEN AND HAS SHARP E | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1080 | 70461604 | HS-TEV | 0016503088 | EV083A250826 | EV083A250826 | AC05 |  | 2026-08-24 | 11LHM/A | 0010 | MAIN GEAR AXLE SEEEVE | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LHM/A | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1081 | 70461604 | HS-TEV | 0016503089 | EV083A250826 | EV083A250826 | AC05 |  | 2026-08-24 | 11LHM/A | 0020 | MAIN GEAR AXLE SEEEVE | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LHM/A | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1082 | 70461604 | HS-TEV | 0016503090 | EV083A250826 | EV083A250826 | AC05 |  | 2026-08-24 | 11LHM/A | 0030 | MAIN GEAR AXLE SEEEVE | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LHM/A | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1083 | 70461604 | HS-TEV | 0016503091 | EV083A250826 | EV083A250826 | AC05 |  | 2026-08-24 | 11LHM/A | 0040 | MAIN GEAR AXLE SEEEVE | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LHM/A | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1084 | 70461604 | HS-TEV | 0016042972 | EV088C021125 | EV088C021125 | AC05 |  | 2026-08-24 | BKK_L | 0010 | 23 29F , 27A HANDSET INOP . | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1085 | 70461604 | HS-TEV | 0016042974 | EV088C021125 | EV088C021125 | AC05 |  | 2026-08-24 | 12LC/AP | 0020 | 23 29F , 27A HANDSET INOP . | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1086 | 70461604 | HS-TEV | 0016042973 | EV088C021125 | EV088C021125 | AC05 |  | 2026-08-24 | BKK_L | 0020 | 23 29F , 27A HANDSET INOP . | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1087 | 70461604 | HS-TEV | 0016531091 | EV120B090926 | EV120B090926 | AC05 |  | 2026-08-24 | 11SH | 0010 | RUDDER TAILING EDGE LIP SKILL CRACKING A | REL | H/26-TEV-X0C10-NONR |  |  |  | 11PAINT | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1088 | 70461604 | HS-TEV | 0016531880 | EV120B090926 | EV120B090926 | AC05 |  | 2026-08-24 | 11PAINT | 0020 | RUDDER TAILING EDGE LIP SKILL CRACKING A | REL | H/26-TEV-X0C10-NONR |  |  |  | 11PAINT | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1089 | 70461604 | HS-TEV | 0016383655 | 1103168663 | 2105132537 | AC02 |  | 2026-08-24 | 11LHM/C | 0010 | DISINFECT OF POTABLE WATER SYSTEM | REL | H/26-TEV-X0C10-NONR | 2 | DCA Appr. Req. 2 |  | BKK_H | REP | A330.MPD.381000-01-1,381000-03-1 |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1090 | 70461604 | HS-TEV | 0016383656 | 1103168663 | 2105132537 | AC02 |  | 2026-08-24 | 11LHM/C | 0020 | DISINFECT OF POTABLE WATER SYSTEM | REL | H/26-TEV-X0C10-NONR | 2 | DCA Appr. Req. 2 |  | BKK_H | REP | A330.MPD.381000-01-1,381000-03-1 |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1091 | 70461604 | HS-TEV | 0016403824 |  | 2105137825 | AC01 |  | 2026-08-31 | 11LHM/C | 0010 | LEAK CHECK VACUUM TOILET AFTER CLEAN | REL | H/26-TEV-X0C10-BLOK-0-4 |  |  | CABIN_LAVATORY | BKK_H | OPC | A330.MPD.383100-05-1 |  | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
1092 | 70461604 | HS-TEV | 0016403861 |  | 2105137862 | AC01 |  | 2026-09-04 | 11LHM/E | 0010 | OPC THE AUTOMATIC START OF THE BLUE ELEC | REL | H/26-TEV-X0C10-BLOK-0-6 |  |  | IERA_FLOOR | BKK_H | OP | A330.MPD.292000-06-1 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
1093 | 70461604 | HS-TEV | 0016404030 |  | 2105138020 | AC01 |  | 2026-09-04 | 11LHM/E | 0010 | FUNCTIONAL TEST OF THE ADM ACCURACY. | REL | H/26-TEV-X0C10-BLOK-0-6 | 1 | DCA Appr. Req. 1 | IERA_ALL IERA | BKK_H | FUC | A330.MPD.341300-07-2 |  | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
1094 | 70461604 | HS-TEV | 0016404213 |  | 2105138165 | AC01 |  | 2026-08-20 | 11LHM/E | 0010 | CHECK-LWR DECK CARGO FIRE EXTING PIPING | REL | H/26-TEV-X0C10-BLOK-0-7 | 1 | DCA Appr. Req. 1 | FLOOR_FWD COMPT | BKK_H | DVI | A330.MPD.262300-04-2;262300-05-1 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
1095 | 70461604 | HS-TEV | 0016404214 |  | 2105138165 | AC01 |  | 2026-08-20 | 11LHM/E | 0020 | CHECK-LWR DECK CARGO FIRE EXTING PIPING | REL | H/26-TEV-X0C10-BLOK-0-7 | 1 | DCA Appr. Req. 1 | FLOOR_FWD COMPT | BKK_H | DVI | A330.MPD.262300-04-2;262300-05-1 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
1096 | 70461604 | HS-TEV | 0016404440 |  | 2105138387 | AC01 |  | 2026-09-02 | 11LHM/A | 0010 | CHK DISTRIB PIPE FOR LEAK&OBST-RR PYLON2 | REL | H/26-TEV-X0C10-BLOK-0-5 | 1 | DCA Appr. Req. 1 | WING_ENGINE | BKK_H | FUC | A330.MPD.262100-12-1 |  | 2026-09-02 | 08:15:00 | 2026-09-02 | 08:15:00
1097 | 70461604 | HS-TEV | 0016404500 |  | 2105138447 | AC01 |  | 2026-08-25 | 11LHM/A | 0010 | JOB SETUP:INSP FIXED L/E PLATE AND STRAP | REL | H/26-TEV-X0C10-BLOK-0-1 |  |  | WING_LEADING EDGE | BKK_H | REM | A330.MPD.574109-02-3 |  | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
1098 | 70461604 | HS-TEV | 0016404515 |  | 2105138462 | AC01 |  | 2026-08-31 | 11LHM/A | 0010 | LHW-LUB OF FLAP TRACK/CARRIAGE ROLLER | REL | H/26-TEV-X0C10-BLOK-0-4 |  |  | WING_TRAILING EDGE | BKK_H | INS | A330.MPD.275400-03-1 |  | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
1099 | 70461604 | HS-TEV | 0016488364 |  | 2105161341 | AC01 |  | 2026-08-20 | 11LHM/A | 0010 | GVI FUSE SKIN BELOW BROADBAND ANTENNA | REL | H/26-TEV-X0C10-BLOK-0-3 | 2 | DCA Appr. Req. 2 | FLOOR_FUSELAGE | BKK_H | GVI | A330.MPD.534020-03-1 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
1100 | 70461604 | HS-TEV | 0016488365 |  | 2105161341 | AC01 |  | 2026-08-20 | 11LHM/A | 0020 | GVI FUSE SKIN BELOW BROADBAND ANTENNA | REL | H/26-TEV-X0C10-BLOK-0-3 | 2 | DCA Appr. Req. 2 | FLOOR_FUSELAGE | BKK_H | GVI | A330.MPD.534020-03-1 |  | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
1101 | 70461604 | HS-TEV | 0016530084 | 1103195266 | 2105171742 | AC03 |  | 2026-08-24 | 11LHM/E | 0010 | 220336: MOD FMGEC HONEYWELL STD P6H7 | REL | H/26-TEV-X0C10-MOD -G-I | 3 | TG Appr. Req. 3 | IERA_CABIN | BKK_H | MOD | A330.TO.220336-01 |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1102 | 70461604 | HS-TEV | 0016513145 | EV017F280826 | EV017F280826 | AC05 |  | 2026-08-28 | BKK_L | 0010 | REMOVE ENG#2 AIR INTAKE COWL | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_L | REP |  |  | 2026-08-28 | 00:00:00 | 2026-08-28 | 00:00:00
1103 | 70461604 | HS-TEV | 0016519781 | EV020F030926 | EV020F030926 | AC05 |  | 2026-09-03 | BKK_L | 0010 | MAGNETIC / TRUE NORTH PUSH BUTTON SW. NO | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_L | REP |  |  | 2026-09-03 | 00:00:00 | 2026-09-03 | 00:00:00
1104 | 70461604 | HS-TEV | 0016529102 | EV021F080926 | EV021F080926 | AC05 |  | 2026-09-08 | BKK_H | 0010 | SFCC2 WAS REMOVED TO HS-TEW | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_L | REP |  |  | 2026-09-08 | 00:00:00 | 2026-09-08 | 00:00:00
1105 | 70461604 | HS-TEV | 0016224438 | EV093C110326 | EV093C110326 | AC05 |  | 2026-08-24 | BKK_L | 0010 | 23 31F,54A MONITOR BLACK OUT | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1106 | 70461604 | HS-TEV | 0016224439 | EV093C110326 | EV093C110326 | AC05 |  | 2026-08-24 | BKK_L | 0020 | 23 31F,54A MONITOR BLACK OUT | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1107 | 70461604 | HS-TEV | 0016557295 | EV158B250926 | EV158B250926 | AC05 |  | 2026-08-24 | 11LHM/A | 0010 | FWD/AFT CARGO ROLLER TRACK SCREW & WASHE | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1108 | 70461604 | HS-TEV | 0016404193 |  | 2105138150 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | OPC OF MANUAL MODE PRESS CTRL N MONITOR | REL | H/26-TEV-X0C10-BLOK-0-7 | 1 | DCA Appr. Req. 1 | FLOOR_AIR COND | BKK_H | OPC | A330.MPD.213100-01-1 | 2026-09-12 | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
1109 | 70461604 | HS-TEV | 0016404197 |  | 2105138153 | AC01 |  | 2026-09-05 | 11LHM/A | 0010 | INSTLL/CLOSE ACCESS PNL FWD CGO DOOR | REL | H/26-TEV-X0C10-BLOK-0-7 |  |  | FLOOR_FWD COMPT | BKK_H | GVI | A330.MPD.523100-01-1,ZL-821-03-1 | 2026-09-12 | 2026-09-05 | 08:15:00 | 2026-09-05 | 08:15:00
1110 | 70461604 | HS-TEV | 0016404220 |  | 2105138171 | AC01 |  | 2026-08-27 | 11LHM/A | 0010 | REM&INST ATTACHMENT SCREW FOR NDT | REL | H/26-TEV-X0C10-BLOK-0-2 |  |  | FLOOR_FWD COMPT | BKK_H | SDI | A330.MPD.532153-01-2 | 2026-09-08 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
1111 | 70461604 | HS-TEV | 0016404274 |  | 2105138223 | AC01 |  | 2026-09-04 | 11LHM/A | 0010 | INSTLL/CLOSE ACCESS PNL AFT CGO DOOR | REL | H/26-TEV-X0C10-BLOK-0-6 |  |  | FLOOR_AFT COMPT | BKK_H | RES | A330.MPD.523200-01-1;ZL-822-02-1 | 2026-09-12 | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
1112 | 70461604 | HS-TEV | 0016404486 |  | 2105138433 | AC01 | EWIS | 2026-08-27 | 11LQ/IA | 0010 | LH,INSP-EXTERNAL WING AREA | REL | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | WING_LEADING EDGE | BKK_H | GVI | A330.MPD.ZL-521-01-1 | 2026-09-24 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
1113 | 70461604 | HS-TEV | 0016404490 |  | 2105138437 | AC01 | EWIS | 2026-08-27 | 11LQ/IA | 0010 | LH,INSP-EXTERNAL WING AREA | REL | H/26-TEV-X0C10-BLOK-0-2 | 2 | DCA Appr. Req. 2 | WING_LEADING EDGE | BKK_H | GVI | A330.MPD.ZL-523-01-1 | 2026-09-24 | 2026-08-27 | 08:15:00 | 2026-08-27 | 08:15:00
1114 | 70461604 | HS-TEV | 0016404496 |  | 2105138443 | AC01 |  | 2026-08-29 | 11LQ/IA | 0010 | INSP-WING ICE PROTECTION COMPONENTS,LH | REL | H/26-TEV-X0C10-BLOK-0-3 | 2 | DCA Appr. Req. 2 | WING_LEADING EDGE | BKK_H | DET | A330.MPD.301100-01-1 | 2026-09-24 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
1115 | 70461604 | HS-TEV | 0016404576 |  | 2105138520 | AC01 |  | 2026-09-04 | 11LHM/E | 0010 | ACTIVATION ELEC SOCKET | REL | H/26-TEV-X0C10-BLOK-0-6 |  |  | IERA_CABIN | BKK_H | INS | A330.OPR.901ACW71 | 2026-08-26 | 2026-09-04 | 08:15:00 | 2026-09-04 | 08:15:00
1116 | 70461604 | HS-TEV | 0015764482 | EV064C150625 | EV064C150625 | AC05 |  | 2026-08-24 | 11LHM/C | 0010 | 25 28B (28B) OUTER SHELL LINING TRIM LOO | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2025-06-15 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1117 | 70461604 | HS-TEV | 0015769448 | EV064C150625 | EV064C150625 | AC05 |  | 2026-08-24 | 11LHM/C | 0020 | 25 28B (28B) OUTER SHELL LINING TRIM LOO | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1118 | 70461604 | HS-TEV | 0015769447 | EV064C150625 | EV064C150625 | AC05 |  | 2026-08-24 | BKK_L | 0020 | 25 28B (28B) OUTER SHELL LINING TRIM LOO | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2026-08-04 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1119 | 70461604 | HS-TEV | 0016506103 | EV089B270826 | EV089B270826 | AC05 |  | 2026-08-24 | 11PAINT | 0010 | 11:PLACARD REFUEL PANEL | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  | 2026-09-14 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1120 | 70461604 | HS-TEV | 0016506104 | EV090B270826 | EV090B270826 | AC05 |  | 2026-08-24 | 11PAINT | 0010 | 11:FLAP TRACK FAIRING NUMERING | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  | 2026-09-07 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1121 | 70461604 | HS-TEV | 0016506109 | EV092B270826 | EV092B270826 | AC05 |  | 2026-08-24 | 11PAINT | 0010 | 11:WING FLAP TRACK FAIRING NUMBERING | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  | 2026-09-10 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1122 | 70461604 | HS-TEV | 0016553521 | EV150B230926 | EV150B230926 | AC05 |  | 2026-08-24 | 11PAINT | 0010 | LOWER FUSELAGE ALL SERVICE DOORS /RAMAI | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  | 2026-09-24 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1123 | 70461604 | HS-TEV | 0016555300 | EV154B240926 | EV154B240926 | AC05 |  | 2026-08-24 | 11CMPST | 0010 | LH/RH FWD FLAP TRACK FIXED FAIRING L/E S | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  | 2026-09-25 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1124 | 70461604 | HS-TEV | 0016555301 | EV154B240926 | EV154B240926 | AC05 |  | 2026-08-24 | 11PAINT | 0020 | LH/RH FWD FLAP TRACK FIXED FAIRING L/E S | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  | 2026-09-30 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1125 | 70461604 | HS-TEV | 0016559413 | EV162B270926 | EV162B270926 | AC05 |  | 2026-09-27 | 11CMPST | 0010 | CABIN GALLEY | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  | 2026-09-30 | 2026-09-27 | 11:40:00 | 2026-09-27 | 19:00:00
1126 | 70461604 | HS-TEV | 0016404236 |  | 2105138185 | AC01 |  | 2026-08-31 | 11LHM/A | 0010 | INSTALLATION OF WATER EXTRACTOR | REL | H/26-TEV-X0C10-BLOK-0-4 | 2 | DCA Appr. Req. 2 | FLOOR_AIR COND | BKK_H | INS | A330.MPD.215000-12-1;215200-01-1 | 2026-09-23 | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
1127 | 70461604 | HS-TEV | 0016404243 |  | 2105138192 | AC01 |  | 2026-08-31 | 11LHM/A | 0010 | INST-CONDENSER PIPE ASSIES | REL | H/26-TEV-X0C10-BLOK-0-4 | 2 | DCA Appr. Req. 2 | FLOOR_AIR COND | BKK_H | RES | A330.MPD.215200-01-1-TG02,215200-01-1 | 2026-09-23 | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
1128 | 70461604 | HS-TEV | 0016404065 |  | 2105138049 | AC01 |  | 2026-08-29 | 11NDT | 0010 | SDI (US) RUDDER SIDE PANEL IN AREA OF FR | REL | H/26-TEV-X0C10-BLOK-0-3 | 1 | DCA Appr. Req. 1 | FLOOR_TAIL | BKK_H | SDI | A330.MPD.554010-02-1 | 2026-09-22 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
1129 | 70461604 | HS-TEV | 0016404616 |  | 2105138548 | AC01 |  | 2026-08-29 | 11LQ/IA | 0010 | INSP THE FWD CARGO COMP (ZONE 821) | REL | H/26-TEV-X0C10-BLOK-0-3 | 2 | DCA Appr. Req. 2 | FLOOR_FWD COMPT | BKK_H | INS | A330.MPD.ZL-821-01-1 | 2026-08-24 | 2026-08-29 | 08:15:00 | 2026-08-29 | 08:15:00
1130 | 70461604 | HS-TEV | 0016559431 | EV164B270926 | EV164B270926 | AC05 |  | 2026-09-27 | 11CMPST | 0010 | CABIN LAVATORY | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  | 2026-09-30 | 2026-09-27 | 14:21:00 | 2026-09-27 | 19:00:00
1131 | 70461604 | HS-TEV | 0016528678 | EV113B080926 | EV113B080926 | AC05 |  | 2026-09-08 | 11CMPST | 0010 | LOWER FUSELAGE RAM AIR INLET DOOR INLET | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  | 2026-09-12 | 2026-09-08 | 11:32:00 | 2026-09-08 | 19:00:00
1132 | 70461604 | HS-TEV | 0016528679 | EV113B080926 | EV113B080926 | AC05 |  | 2026-09-08 | 11PAINT | 0020 | LOWER FUSELAGE RAM AIR INLET DOOR INLET | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  | 2026-09-11 | 2026-09-08 | 11:32:00 | 2026-09-08 | 19:00:00
1133 | 70461604 | HS-TEV | 0015955192 | 1103092854 | 2105013320 | AC02 |  | 2026-08-22 | 11LHM/E | 0010 | G/25-041:T/S LOOSE LOCK ON SOCKET B-CONN | REL | H/26-TEV-X0C10-MOD -G-I | 4 | TG Appr. Req. 4 |  | BKK_H | REP | A330.ED.BKKJA-G/25-041 | 2025-10-16 | 2026-08-22 | 00:00:00 | 2026-09-02 | 00:00:00
1134 | 70461604 | HS-TEV | 0016404238 |  | 2105138187 | AC01 |  | 2026-08-31 | 11LHM/A | 0010 | INST-THE REHEATER PIPE ASSY | REL | H/26-TEV-X0C10-BLOK-0-4 | 2 | DCA Appr. Req. 2 | FLOOR_AIR COND | BKK_H | DIS | A330.MPD.215000-12-1;215200-01-1 | 2026-09-23 | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
1135 | 70461604 | HS-TEV | 0016404514 |  | 2105138461 | AC01 |  | 2026-08-25 | 11CLEAN | 0010 | LHW-CLEAN OF FLAP HYD ACTUATION&POWER TR | REL | H/26-TEV-X0C10-BLOK-0-1 |  |  | WING_TRAILING EDGE | BKK_H | INS | A330.MPD.275400-03-1 | 2026-09-24 | 2026-08-25 | 08:15:00 | 2026-08-25 | 08:15:00
1136 | 70461604 | HS-TEV | 0016523591 | EV019F300826 | EV019F300826 | AC05 |  | 2026-08-30 | BKK_H | 0010 | PACK 2 CLAMP AT REHEATER RMV TO HS-TEP | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  | 2026-09-01 | 2026-08-30 | 00:00:00 | 2026-08-30 | 00:00:00
1137 | 70461604 | HS-TEV | 0016003088 | EV055C261025 | EV055C261025 | AC05 |  | 2026-08-24 | BKK_L | 0010 | 25 L11 PAPER SEAT STOWAGE BOX HINGE LOSO | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2026-03-09 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1138 | 70461604 | HS-TEV | 0016003090 | EV055C261025 | EV055C261025 | AC05 |  | 2026-08-24 | 12LC/AP | 0020 | 25 L11 PAPER SEAT STOWAGE BOX HINGE LOSO | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  |  | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1139 | 70461604 | HS-TEV | 0016003089 | EV055C261025 | EV055C261025 | AC05 |  | 2026-08-24 | BKK_L | 0020 | 25 L11 PAPER SEAT STOWAGE BOX HINGE LOSO | REL | H/26-TEV-X0C10-NONR | P | Responsible Planner |  | BKK_H | REP |  | 2026-03-10 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1140 | 70461604 | HS-TEV | 0016506113 | EV093B270826 | EV093B270826 | AC05 |  | 2026-08-24 | 11PAINT | 0010 | 11:INLET RAM AIRDOOR | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  | 2026-09-09 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1141 | 70461604 | HS-TEV | 0016506131 | EV094B270826 | EV094B270826 | AC05 |  | 2026-08-24 | 11CMPST | 0010 | ENG#1 LH FAN COWL INSP FOUND INTERNAL SU | REL | H/26-TEV-X0C10-NONR |  |  |  | BKK_H | REP |  | 2026-09-30 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1142 | 70461604 | HS-TEV | 0016533890 | EV131B110926 | EV131B110926 | AC05 |  | 2026-09-11 | 11CMPST | 0010 | LH/RH WING FWD.FLAP TRACK FIXED FAIRING | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  | 2026-09-10 | 2026-09-11 | 14:07:00 | 2026-09-11 | 19:00:00
1143 | 70461604 | HS-TEV | 0016533891 | EV131B110926 | EV131B110926 | AC05 |  | 2026-09-11 | 11PAINT | 0020 | LH/RH WING FWD.FLAP TRACK FIXED FAIRING | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LQ/IA | REP |  | 2026-09-22 | 2026-09-11 | 14:07:00 | 2026-09-11 | 19:00:00
1144 | 70461604 | HS-TEV | 0016532550 | EV127A100926 | EV127A100926 | AC05 |  | 2026-08-24 | 11LHM/A | 0010 | DRAIN MAST | REL | H/26-TEV-X0C10-NONR |  |  |  | 11LHM/A | REP |  | 2026-09-14 | 2026-08-24 | 00:00:00 | 2026-09-09 | 24:00:00
1145 | 70461604 | HS-TEV | 0016404240 |  | 2105138189 | AC01 |  | 2026-08-31 | 11LHM/A | 0010 | INST-THE REHEATER | REL | H/26-TEV-X0C10-BLOK-0-4 | 2 | DCA Appr. Req. 2 | FLOOR_AIR COND | BKK_H | DIS | A330.MPD.215000-12-1;215200-01-1 | 2026-09-23 | 2026-08-31 | 08:15:00 | 2026-08-31 | 08:15:00
1146 | 70461604 | HS-TEV | 0015663780 | 1103044132 | 2104934912 | AC02 |  | 2026-08-22 | 11LHM/E | 0010 | G/25-042: T/S NO COMMUNICATION TO SACL | REL | H/26-TEV-X0C10-MOD -G-I | 4 | TG Appr. Req. 4 |  | BKK_H | REP | A330.ED.BKKJA-G/25-042 | 2025-06-06 | 2026-08-22 | 00:00:00 | 2026-09-02 | 00:00:00
1147 | 70461604 | HS-TEV | 0016313840 | 1103155446 | 2105108896 | AC02 |  | 2026-08-22 | 11LHM/E | 0010 | G/26-062:REPL STAND-ALONE CONTENT LOADER | REL | H/26-TEV-X0C10-MOD -G-I | 4 | TG Appr. Req. 4 |  | BKK_H | REP | A330.ED.BKKJA-G/26-062 | 2026-05-08 | 2026-08-22 | 00:00:00 | 2026-09-02 | 00:00:00
1148 | 70461604 | HS-TEV | 0016313841 | 1103155446 | 2105108896 | AC02 |  | 2026-08-22 | 11LHM/E | 0020 | G/26-062:REPL STAND-ALONE CONTENT LOADER | REL | H/26-TEV-X0C10-MOD -G-I | 4 | TG Appr. Req. 4 |  | BKK_H | REP | A330.ED.BKKJA-G/26-062 | 2026-05-08 | 2026-08-22 | 00:00:00 | 2026-09-02 | 00:00:00
1149 | 70461604 | HS-TEV | 0016403865 |  | 2105137866 | AC01 |  | 2026-08-20 | 11LHM/A | 0010 | DVI PDU ROLLER FOR WEAR AND DAMAGE | REL | H/26-TEV-X0C10-BLOK-0-3 | 2 | DCA Appr. Req. 2 | FLOOR_AFT COMPT | BKK_H | DET | A330.MPD.255101-08-1 | 2026-08-24 | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00
1150 | 70461604 | HS-TEV | 0016403866 |  | 2105137866 | AC01 |  | 2026-08-20 | 11LHM/A | 0020 | DVI PDU ROLLER FOR WEAR AND DAMAGE | REL | H/26-TEV-X0C10-BLOK-0-3 | 2 | DCA Appr. Req. 2 | FLOOR_AFT COMPT | BKK_H | DET | A330.MPD.255101-08-1 | 2026-08-24 | 2026-08-20 | 00:00:00 | 2026-08-20 | 24:00:00

## TEXT TEV
EST. TAT XX DAYS // PERIOD 24AUG26-XXOCT26
TOW IN : 24AUG26 H3 TIME 1800 PM ,LAST FLIGHT 23 AUG. 2026 TG322 DAC-BKK
AIRCRAFT SERIAL NUMBER HS-TEV /0990 AIRCRAFT EFFECTIVITY CODE 151 TEN
########## WORK HIGHLIGHT 29 OCT. 2026 ##########
IN HANGAR 01-02 NOV FOR E/26-219:PARKING NOT MORE THAN 3M-INITIA
######### HS-TEV PLAN TIME LINE ACTIVITY AS BELOW ##########
XXNOV26 : WAIT ENG#1-2
XXNOV26 : ENGINE#1-2 INSTALLATION → SYSTEM CONNECTION → INSPECTION → GROUND RUN → PRE-FLIGHT CLEARANCE → TEST FLIGHT → POST-FLIGHT / SNAG CLEARANCE → FINAL RELEASE → RTS
REMARK : COPY LINK FULL DASHBOARD ON DESKTOP TG ONLY : http://acm-hpv-app07.dt.thaiairways.co.th/RevisionPlan/BKKStatus.html

## TQM
HS-TQM_PDM+CABIN REFURBISH+PAINT DATE 15 OCT. 2026
Item | Revision | Functional loc. | Confirmation | Notification | Order | Order Type | Ident.Insp.Task | Reference Date | Oper.WorkCenter | Activity | Description | Syste | User status | WBS ord. header | Priority | Priority | Working Group | Main WorkCtr | MaintActivType | External Ident. | Actual start | Bas. start date | Start time | Basic fin. date | Basic fin. time
1 | 70466532 | HS-TQM | 0016557376 |  | 2105178548 | AC02 |  | 2026-10-05 | 11LHM/A | 0010 | DEPRES: A&B,1-10 Put A/C Back to Service | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | ALL_ALL GRP | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-06 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
2 | 70466532 | HS-TQM | 0016557377 |  | 2105178548 | AC02 |  | 2026-10-05 | 11LHM/A | 0020 | DEPRES: A&B,1-10 Put A/C Back to Service | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | ALL_ALL GRP | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
3 | 70466532 | HS-TQM | 0016557378 |  | 2105178548 | AC02 |  | 2026-10-05 | 11LHM/A | 0030 | DEPRES: A&B,1-10 Put A/C Back to Service | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | ALL_ALL GRP | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
4 | 70466532 | HS-TQM | 0016557379 |  | 2105178548 | AC02 |  | 2026-10-05 | 11LHM/A | 0040 | DEPRES: A&B,1-10 Put A/C Back to Service | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | ALL_ALL GRP | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
5 | 70466532 | HS-TQM | 0016557380 |  | 2105178549 | AC02 |  | 2026-10-05 | 11LHM/C | 0010 | DEPRES: 64.Fire Protection Systems | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | ALL_ALL GRP | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-05 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
6 | 70466532 | HS-TQM | 0016557381 |  | 2105178549 | AC02 |  | 2026-10-05 | 11LHM/C | 0020 | DEPRES: 64.Fire Protection Systems | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | ALL_ALL GRP | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-05 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
7 | 70466532 | HS-TQM | 0016557382 |  | 2105178549 | AC02 |  | 2026-10-05 | 11LHM/C | 0030 | DEPRES: 64.Fire Protection Systems | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | ALL_ALL GRP | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-05 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
8 | 70466532 | HS-TQM | 0016557383 |  | 2105178549 | AC02 |  | 2026-10-05 | 11LHM/C | 0040 | DEPRES: 64.Fire Protection Systems | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | ALL_ALL GRP | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-05 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
9 | 70466532 | HS-TQM | 0016557384 |  | 2105178549 | AC02 |  | 2026-10-05 | 11LHM/C | 0050 | DEPRES: 64.Fire Protection Systems | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | ALL_ALL GRP | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-05 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
10 | 70466532 | HS-TQM | 0016557385 |  | 2105178549 | AC02 |  | 2026-10-05 | 11LHM/C | 0060 | DEPRES: 64.Fire Protection Systems | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | ALL_ALL GRP | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-05 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
11 | 70466532 | HS-TQM | 0016557386 |  | 2105178549 | AC02 |  | 2026-10-05 | 11LHM/C | 0070 | DEPRES: 64.Fire Protection Systems | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | ALL_ALL GRP | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-05 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
12 | 70466532 | HS-TQM | 0016557387 |  | 2105178549 | AC02 |  | 2026-10-05 | 11LHM/C | 0080 | DEPRES: 64.Fire Protection Systems | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | ALL_ALL GRP | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-05 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
13 | 70466532 | HS-TQM | 0016557388 |  | 2105178549 | AC02 |  | 2026-10-05 | 11LHM/C | 0090 | DEPRES: 64.Fire Protection Systems | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | ALL_ALL GRP | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-05 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
14 | 70466532 | HS-TQM | 0016557389 |  | 2105178549 | AC02 |  | 2026-10-05 | 11LHM/C | 0100 | DEPRES: 64.Fire Protection Systems | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | ALL_ALL GRP | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-05 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
15 | 70466532 | HS-TQM | 0016557390 |  | 2105178549 | AC02 |  | 2026-10-05 | 11LHM/C | 0110 | DEPRES: 64.Fire Protection Systems | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | ALL_ALL GRP | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
16 | 70466532 | HS-TQM | 0016557391 |  | 2105178549 | AC02 |  | 2026-10-05 | 11LHM/C | 0120 | DEPRES: 64.Fire Protection Systems | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | ALL_ALL GRP | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
17 | 70466532 | HS-TQM | 0016557392 |  | 2105178549 | AC02 |  | 2026-10-05 | 11LHM/C | 0130 | DEPRES: 64.Fire Protection Systems | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | ALL_ALL GRP | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
18 | 70466532 | HS-TQM | 0016557433 |  | 2105178868 | AC02 |  | 2026-10-05 | 11LHM/C | 0010 | DEPRES: 31-32.batteries | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 |  | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-05 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
19 | 70466532 | HS-TQM | 0016557434 |  | 2105178868 | AC02 |  | 2026-10-05 | 11LHM/C | 0020 | DEPRES: 31-32.batteries | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 |  | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-05 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
20 | 70466532 | HS-TQM | 0016557435 |  | 2105178868 | AC02 |  | 2026-10-05 | 11LHM/C | 0030 | DEPRES: 31-32.batteries | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 |  | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
21 | 70466532 | HS-TQM | 0016557436 |  | 2105178868 | AC02 |  | 2026-10-05 | 11LHM/C | 0040 | DEPRES: 31-32.batteries | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 |  | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
22 | 70466532 | HS-TQM | 0016557437 |  | 2105178868 | AC02 |  | 2026-10-05 | 11LHM/C | 0050 | DEPRES: 31-32.batteries | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 |  | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
23 | 70466532 | HS-TQM | 0016557457 |  | 2105178876 | AC02 |  | 2026-10-05 | 11LHM/A | 0010 | DEPRES: 55-58 Filght Con. Lub form 60 D | TECO |  | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-03 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
24 | 70466532 | HS-TQM | 0016557458 |  | 2105178876 | AC02 |  | 2026-10-05 | 11LHM/A | 0020 | DEPRES: 55-58 Filght Con. Lub form 60 D | TECO |  | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
25 | 70466532 | HS-TQM | 0016557459 |  | 2105178876 | AC02 |  | 2026-10-05 | 11LHM/A | 0030 | DEPRES: 55-58 Filght Con. Lub form 60 D | TECO |  | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
26 | 70466532 | HS-TQM | 0016557460 |  | 2105178876 | AC02 |  | 2026-10-05 | 11LHM/A | 0040 | DEPRES: 55-58 Filght Con. Lub form 60 D | TECO |  | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
27 | 70466532 | HS-TQM | 0016557461 |  | 2105178876 | AC02 |  | 2026-10-05 | 11LHM/A | 0050 | DEPRES: 55-58 Filght Con. Lub form 60 D | TECO |  | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
28 | 70466532 | HS-TQM | 0016557462 |  | 2105178876 | AC02 |  | 2026-10-05 | 11LHM/A | 0060 | DEPRES: 55-58 Filght Con. Lub form 60 D | TECO |  | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
29 | 70466532 | HS-TQM | 0016557463 |  | 2105178876 | AC02 |  | 2026-10-05 | 11LHM/A | 0070 | DEPRES: 55-58 Filght Con. Lub form 60 D | TECO |  | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
30 | 70466532 | HS-TQM | 0016557464 |  | 2105178876 | AC02 |  | 2026-10-05 | 11LHM/A | 0080 | DEPRES: 55-58 Filght Con. Lub form 60 D | TECO |  | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
31 | 70466532 | HS-TQM | 0016557465 |  | 2105178876 | AC02 |  | 2026-10-05 | 11LHM/A | 0090 | DEPRES: 55-58 Filght Con. Lub form 60 D | TECO |  | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
32 | 70466532 | HS-TQM | 0016557466 |  | 2105178876 | AC02 |  | 2026-10-05 | 11LHM/A | 0100 | DEPRES: 55-58 Filght Con. Lub form 60 D | TECO |  | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
33 | 70466532 | HS-TQM | 0016557467 |  | 2105178876 | AC02 |  | 2026-10-05 | 11LHM/A | 0110 | DEPRES: 55-58 Filght Con. Lub form 60 D | TECO |  | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
34 | 70466759 | HS-TQM | 0016468973 | 1103184498 | 2105156375 | AC03 |  | 2026-09-30 | 11LHM/E | 0010 | 440208:LOAD S/W AND CONTENT TO THA VER. | TECO |  | L/26-TQM-LI-MSC-M | 4 | TG Appr. Req. 4 | IERA_CABIN | BKK_H | MOD | 787.TO.440208 | 2026-09-30 | 2026-09-30 | 06:00:00 | 2026-09-30 | 19:00:00
35 | 70466759 | HS-TQM | 0016537583 | 1103196918 | 2105173741 | AC03 |  | 2026-09-30 | 11LHM/C | 0010 | 253889:CODING COCKPIT DR,CREW REST DR | TECO |  | L/26-TQM-LI-MSC-M | 2 | DCA Appr. Req. 2 |  | BKK_H | MOD | 787.TO.253889-01 | 2026-09-30 | 2026-09-30 | 06:00:00 | 2026-09-30 | 19:00:00
36 | 70466459 | HS-TQM | 0016360600 | QM014D040626 | QM014D040626 | AC05 |  | 2026-10-05 | 11LHM/C | 0010 | 25-CABIN: EY PAX SEAT COVER | TECO | ODAT | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP |  | 2026-06-04 | 2026-09-25 | 06:00:00 | 2026-09-25 | 19:00:00
37 | 70466459 | HS-TQM | 0016360601 | QM014D040626 | QM014D040626 | AC05 |  | 2026-10-05 | 11LHM/C | 0020 | 25-CABIN: EY PAX SEAT COVER | TECO | ODAT | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP |  | 2026-10-03 | 2026-09-25 | 06:00:00 | 2026-09-25 | 19:00:00
38 | 70464374 | HS-TQM | 0016494296 | 1103189025 | 2105162883 | AC03 |  | 2026-10-05 | 11LHM/C | 0010 | 253884: B/C SEAT COVERS CHANGE | TECO |  | L/26-TQM-LI-MSC-M | 4 | TG Appr. Req. 4 | CABIN_ALL CABIN | BKK_H | RAR | 787.TO.253884 | 2026-10-04 | 2026-09-03 | 06:00:00 | 2026-09-03 | 19:00:00
39 | 70466151 | HS-TQM | 0016530897 | 1103195344 | 2105172127 | AC03 |  | 2026-10-07 | 11LHM/C | 0010 | 253886: Y/C SEAT COVERS CHANGE | TECO |  | L/26-TQM-LI-MSC-M | 4 | TG Appr. Req. 4 | CABIN_ALL CABIN | BKK_H | RAR | 787.TO.253886 | 2026-10-04 | 2026-09-25 | 06:00:00 | 2026-09-25 | 19:00:00
40 | 70466152 | HS-TQM | 0016436333 | 1103178227 | 2105147416 | AC02 |  | 2026-10-05 | 11LHM/C | 0010 | G/26-114:EMERG EQUIPMENT RFID REGISTRATI | TECO | DPRC REMN ODRC ODAT | L/26-TQM-LI-MSC-N | 4 | TG Appr. Req. 4 | CABIN_INTERIOR | BKK_H | RAR | 787.ED.BKKJA-G/26-114 | 2026-10-06 | 2026-09-25 | 06:00:00 | 2026-09-25 | 19:00:00
41 | 70466759 | HS-TQM | 0016539775 | 1103197450 | 2105174570 | AC03 |  | 2026-10-06 | 11LHM/C | 0010 | 253895:INSTALL HANDICAP LAVATORY KEY | TECO |  | L/26-TQM-LI-MSC-M | 2 | DCA Appr. Req. 2 |  | BKK_H | MOD | 787.TO.253895 | 2026-10-02 | 2026-09-30 | 06:00:00 | 2026-09-30 | 19:00:00
42 | 70464374 | HS-TQM | 0016365184 | 1103165105 | 2105126599 | AC02 |  | 2026-09-07 | 11LHM/C | 0010 | G/26-047:CABIN INSPECTION FOR REFURBISH | TECO | DPRC REMN ODRC ODAT | L/26-TQM-LI-MSC-N | 4 | TG Appr. Req. 4 | CABIN_ALL CABIN | BKK_H | SVC | 787.ED.BKKJA-G/26-047-01 |  | 2026-09-03 | 06:00:00 | 2026-09-03 | 19:00:00
43 | 70464374 | HS-TQM | 0016365185 | 1103165106 | 2105126640 | AC02 |  | 2026-09-07 | 11LHM/C | 0010 | G/26-048:COCKPIT DR,OFCR &OFAR RECODING | TECO | DPRC REMN ODRC ODAT | L/26-TQM-LI-MSC-N | 4 | TG Appr. Req. 4 | CABIN_COCKPIT | BKK_H | RST | 787.ED.BKKJA-G/26-048 |  | 2026-09-03 | 06:00:00 | 2026-09-03 | 19:00:00
44 | 70464374 | HS-TQM | 0016365186 | 1103165106 | 2105126640 | AC02 |  | 2026-09-07 | 11LHM/C | 0020 | G/26-048:COCKPIT DR,OFCR &OFAR RECODING | TECO | DPRC REMN ODRC ODAT | L/26-TQM-LI-MSC-N | 4 | TG Appr. Req. 4 | CABIN_COCKPIT | BKK_H | RST | 787.ED.BKKJA-G/26-048 |  | 2026-09-03 | 06:00:00 | 2026-09-03 | 19:00:00
45 | 70464374 | HS-TQM | 0016365187 | 1103165106 | 2105126640 | AC02 |  | 2026-09-07 | 11LHM/C | 0030 | G/26-048:COCKPIT DR,OFCR &OFAR RECODING | TECO | DPRC REMN ODRC ODAT | L/26-TQM-LI-MSC-N | 4 | TG Appr. Req. 4 | CABIN_COCKPIT | BKK_H | RST | 787.ED.BKKJA-G/26-048 |  | 2026-09-03 | 06:00:00 | 2026-09-03 | 19:00:00
46 | 70466459 | HS-TQM | 0016360604 | QM016D040626 | QM016D040626 | AC05 |  | 2026-10-05 | 11LHM/C | 0010 | 25-CABIN: CLEAN SEAT & PAX AREA (A/C) | TECO | ODAT | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP |  |  | 2026-09-25 | 06:00:00 | 2026-09-25 | 19:00:00
47 | 70466459 | HS-TQM | 0016447929 | QM049D240726 | QM049D240726 | AC05 |  | 2026-10-05 | 11LHM/C | 0010 | 25-CABIN:CURTAIN RAIL. | TECO | ODAT | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP |  |  | 2026-09-25 | 06:00:00 | 2026-09-25 | 19:00:00
48 | 70466459 | HS-TQM | 0016447953 | QM054D240726 | QM054D240726 | AC05 |  | 2026-10-05 | 11LHM/C | 0010 | 25-CABIN:PASSENGER SEAT. | TECO | ODAT | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP |  |  | 2026-09-25 | 06:00:00 | 2026-09-25 | 19:00:00
49 | 70466459 | HS-TQM | 0016447965 | QM065D240726 | QM065D240726 | AC05 |  | 2026-10-05 | 11LHM/C | 0010 | 25-CABIN:PASSENGER SEATS | TECO | ODAT | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP |  |  | 2026-09-25 | 06:00:00 | 2026-09-25 | 19:00:00
50 | 70466459 | HS-TQM | 0016447972 | QM071D240726 | QM071D240726 | AC05 |  | 2026-10-05 | 11LHM/C | 0010 | 25-CABIN:PASSENGER SEATS. | TECO | ODAT | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP |  |  | 2026-09-25 | 06:00:00 | 2026-09-25 | 19:00:00
51 | 70466532 | HS-TQM | 0016557393 |  | 2105178550 | AC02 |  | 2026-10-07 | 11LHM/A | 0010 | DEPRES: 78.Dust | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | ALL_ALL GRP | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
52 | 70466532 | HS-TQM | 0016557405 |  | 2105178555 | AC02 |  | 2026-10-07 | 11LHM/C | 0010 | DEPRES: 74-76.Doors | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | CABIN_DOOR | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
53 | 70466532 | HS-TQM | 0016557409 |  | 2105178559 | AC02 |  | 2026-10-07 | 11LHM/C | 0010 | Depress: 59,60 Depreservation of the air | TECO |  | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP | 787.MAM.787-59,60 |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
54 | 70466532 | HS-TQM | 0016557410 |  | 2105178559 | AC02 |  | 2026-10-07 | 11LHM/C | 0020 | Depress: 59,60 Depreservation of the air | TECO |  | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP | 787.MAM.787-59,60 |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
55 | 70466532 | HS-TQM | 0016557411 |  | 2105178559 | AC02 |  | 2026-10-07 | 11LHM/C | 0030 | Depress: 59,60 Depreservation of the air | TECO |  | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP | 787.MAM.787-59,60 |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
56 | 70466532 | HS-TQM | 0016557412 |  | 2105178559 | AC02 |  | 2026-10-07 | 11LHM/C | 0040 | Depress: 59,60 Depreservation of the air | TECO |  | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP | 787.MAM.787-59,60 |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
57 | 70466532 | HS-TQM | 0016557413 |  | 2105178559 | AC02 |  | 2026-10-07 | 11LHM/C | 0050 | Depress: 59,60 Depreservation of the air | TECO |  | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP | 787.MAM.787-59,60 |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
58 | 70466532 | HS-TQM | 0016557414 |  | 2105178559 | AC02 |  | 2026-10-07 | 11LHM/C | 0060 | Depress: 59,60 Depreservation of the air | TECO |  | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP | 787.MAM.787-59,60 |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
59 | 70466532 | HS-TQM | 0016557415 |  | 2105178559 | AC02 |  | 2026-10-07 | 11LHM/C | 0070 | Depress: 59,60 Depreservation of the air | TECO |  | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP | 787.MAM.787-59,60 |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
60 | 70466532 | HS-TQM | 0016557416 |  | 2105178559 | AC02 |  | 2026-10-07 | 11LHM/C | 0080 | Depress: 59,60 Depreservation of the air | TECO |  | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP | 787.MAM.787-59,60 |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
61 | 70466532 | HS-TQM | 0016557417 |  | 2105178559 | AC02 |  | 2026-10-07 | 11LHM/C | 0090 | Depress: 59,60 Depreservation of the air | TECO |  | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP | 787.MAM.787-59,60 |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
62 | 70466532 | HS-TQM | 0016557418 |  | 2105178559 | AC02 |  | 2026-10-07 | 11LHM/C | 0100 | Depress: 59,60 Depreservation of the air | TECO |  | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP | 787.MAM.787-59,60 |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
63 | 70466532 | HS-TQM | 0016557419 |  | 2105178559 | AC02 |  | 2026-10-07 | 11LHM/C | 0110 | Depress: 59,60 Depreservation of the air | TECO |  | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP | 787.MAM.787-59,60 |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
64 | 70466532 | HS-TQM | 0016557420 |  | 2105178559 | AC02 |  | 2026-10-07 | 11LHM/C | 0120 | Depress: 59,60 Depreservation of the air | TECO |  | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP | 787.MAM.787-59,60 |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
65 | 70466532 | HS-TQM | 0016557421 |  | 2105178559 | AC02 |  | 2026-10-07 | 11LHM/C | 0130 | Depress: 59,60 Depreservation of the air | TECO |  | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP | 787.MAM.787-59,60 |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
66 | 70466532 | HS-TQM | 0016557422 |  | 2105178860 | AC02 |  | 2026-10-05 | 11LHM/E | 0010 | DEPRES: 38 Examine VFSG | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | ALL_ALL GRP | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
67 | 70466532 | HS-TQM | 0016557429 |  | 2105178866 | AC02 |  | 2026-10-07 | 11LHM/C | 0010 | DEPRES: 15-16. Drains | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | CABIN_ALL CABIN | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
68 | 70466532 | HS-TQM | 0016557430 |  | 2105178866 | AC02 |  | 2026-10-07 | 11LHM/C | 0020 | DEPRES: 15-16. Drains | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | CABIN_ALL CABIN | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
69 | 70466532 | HS-TQM | 0016557431 |  | 2105178866 | AC02 |  | 2026-10-07 | 11LHM/C | 0030 | DEPRES: 15-16. Drains | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | CABIN_ALL CABIN | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
70 | 70466532 | HS-TQM | 0016557432 |  | 2105178867 | AC02 |  | 2026-10-07 | 11LHM/A | 0010 | DEPRES: 30.NGS | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | FLOOR_ALL FLOOR | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
71 | 70466532 | HS-TQM | 0016557438 |  | 2105178869 | AC02 |  | 2026-10-05 | 11LHM/A | 0010 | DEPRES: 29.Fuel system | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | WING_ALL WING | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
72 | 70466532 | HS-TQM | 0016557439 |  | 2105178869 | AC02 |  | 2026-10-05 | 11LHM/A | 0020 | DEPRES: 29.Fuel system | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | WING_ALL WING | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
73 | 70466532 | HS-TQM | 0016557440 |  | 2105178869 | AC02 |  | 2026-10-05 | 11LHM/A | 0030 | DEPRES: 29.Fuel system | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | WING_ALL WING | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
74 | 70466532 | HS-TQM | 0016557441 |  | 2105178870 | AC02 |  | 2026-10-07 | 11LHM/C | 0010 | DEPRES: 61.Inflation cylinders | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | ALL_ALL GRP | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
75 | 70466532 | HS-TQM | 0016557451 |  | 2105178873 | AC02 |  | 2026-10-07 | 11LHM/A | 0010 | DEPRES: 50-51 Eleve PCU Compensator test | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 |  | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
76 | 70466532 | HS-TQM | 0016557452 |  | 2105178873 | AC02 |  | 2026-10-07 | 11LHM/A | 0020 | DEPRES: 50-51 Eleve PCU Compensator test | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 |  | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
77 | 70466532 | HS-TQM | 0016557453 |  | 2105178874 | AC02 |  | 2026-10-07 | 11LHM/A | 0010 | DEPRES: 53-54 control systems | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | WING_ALL WING | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
78 | 70466532 | HS-TQM | 0016557454 |  | 2105178874 | AC02 |  | 2026-10-07 | 11LHM/A | 0020 | DEPRES: 53-54 control systems | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | WING_ALL WING | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
79 | 70466532 | HS-TQM | 0016557455 |  | 2105178875 | AC02 |  | 2026-10-07 | 11LHM/A | 0010 | DEPRES: 47-48.Flight Con. more 30 D | TECO |  | L/26-TQM-LI-MSC-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
80 | 70466532 | HS-TQM | 0016557456 |  | 2105178875 | AC02 |  | 2026-10-07 | 11LHM/A | 0020 | DEPRES: 47-48.Flight Con. more 30 D | TECO |  | L/26-TQM-LI-MSC-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
81 | 70466532 | HS-TQM | 0016557468 |  | 2105178877 | AC02 |  | 2026-10-05 | 11LHM/A | 0010 | DEPRES: 68.Fuel temperature | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | WING_ALL WING | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
82 | 70466532 | HS-TQM | 0016557469 |  | 2105178878 | AC02 |  | 2026-10-05 | 11LHM/A | 0010 | DEPRES: 39 VFSG TASK PARK MORE THAN 60 D | TECO |  | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
83 | 70466532 | HS-TQM | 0016557470 |  | 2105178878 | AC02 |  | 2026-10-05 | 11LHM/A | 0020 | DEPRES: 39 VFSG TASK PARK MORE THAN 60 D | TECO |  | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
84 | 70466532 | HS-TQM | 0016557471 |  | 2105178878 | AC02 |  | 2026-10-05 | 11LHM/A | 0030 | DEPRES: 39 VFSG TASK PARK MORE THAN 60 D | TECO |  | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
85 | 70466532 | HS-TQM | 0016557472 |  | 2105178878 | AC02 |  | 2026-10-05 | 11LHM/A | 0040 | DEPRES: 39 VFSG TASK PARK MORE THAN 60 D | TECO |  | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
86 | 70466532 | HS-TQM | 0016557476 |  | 2105178880 | AC02 |  | 2026-10-05 | 11LHM/A | 0010 | DEPRES: 70.Depreserve Engine (GEnx) | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | WING_ALL WING | BKK_H | REP | 787.MAM.B787-A-G71-00-03-11A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
87 | 70466532 | HS-TQM | 0016557477 |  | 2105178880 | AC02 |  | 2026-10-05 | 11LHM/A | 0020 | DEPRES: 70.Depreserve Engine (GEnx) | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | WING_ALL WING | BKK_H | REP | 787.MAM.B787-A-G71-00-03-11A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
88 | 70466532 | HS-TQM | 0016557488 |  | 2105178882 | AC02 |  | 2026-10-07 | 11LHM/C | 0010 | DEPRES: 42 AIRCON SYSTEM | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | IERA_ALL IERA | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
89 | 70466532 | HS-TQM | 0016557489 |  | 2105178882 | AC02 |  | 2026-10-07 | 11LHM/C | 0020 | DEPRES: 42 AIRCON SYSTEM | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | IERA_ALL IERA | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
90 | 70466532 | HS-TQM | 0016557490 |  | 2105178882 | AC02 |  | 2026-10-07 | 11LHM/C | 0030 | DEPRES: 42 AIRCON SYSTEM | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | IERA_ALL IERA | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
91 | 70466532 | HS-TQM | 0016557491 |  | 2105178882 | AC02 |  | 2026-10-07 | 11LHM/C | 0040 | DEPRES: 42 AIRCON SYSTEM | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | IERA_ALL IERA | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
92 | 70466532 | HS-TQM | 0016557492 |  | 2105178882 | AC02 |  | 2026-10-07 | 11LHM/C | 0050 | DEPRES: 42 AIRCON SYSTEM | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | IERA_ALL IERA | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
93 | 70466532 | HS-TQM | 0016557493 |  | 2105178882 | AC02 |  | 2026-10-07 | 11LHM/C | 0060 | DEPRES: 42 AIRCON SYSTEM | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | IERA_ALL IERA | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
94 | 70466532 | HS-TQM | 0016557494 |  | 2105178882 | AC02 |  | 2026-10-07 | 11LHM/C | 0070 | DEPRES: 42 AIRCON SYSTEM | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | IERA_ALL IERA | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
95 | 70466532 | HS-TQM | 0016557502 |  | 2105178887 | AC02 |  | 2026-10-07 | 11LHM/A | 0010 | DEPRES: 79.APU DEPRESERVE (GEnx) | TECO |  | L/26-TQM-LI-MSC-N | 4 | TG Appr. Req. 4 | WING_ENGINE | BKK_H | SPC | 787.MAM.49-11-00-04A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
96 | 70466532 | HS-TQM | 0016557503 |  | 2105178887 | AC02 |  | 2026-10-07 | 11U | 0020 | DEPRES: 79.APU DEPRESERVE (GEnx) | TECO |  | L/26-TQM-LI-MSC-N | 4 | TG Appr. Req. 4 | WING_ENGINE | BKK_H | SPC | 787.MAM.49-11-00-04A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
97 | 70466917 | HS-TQM | 0016457201 | 1103182227 | 2105152701 | AC02 |  | 2026-10-02 | 11E | 0010 | E/26-131: REPL A/C BRIEFING CARD | TECO | ODAT | L/26-TQM-LI-MSC-N | 4 | TG Appr. Req. 4 | CABIN_COCKPIT | BKK_H | REP | 787.ED.JA-E/26-131 |  | 2026-10-02 | 06:00:00 | 2026-10-02 | 19:00:00
98 | 70466759 | HS-TQM | 0016537626 | 1103196989 | 2105173773 | AC03 |  | 2026-10-08 | 11LHM/C | 0010 | 253891:INSTALL BABY BASSINET | TECO |  | L/26-TQM-LI-MSC-M | 2 | DCA Appr. Req. 2 |  | BKK_H | MOD | 787.TO.253891 |  | 2026-09-30 | 06:00:00 | 2026-09-30 | 19:00:00
99 | 70466759 | HS-TQM | 0016542540 | 1103197829 | 2105175083 | AC03 |  | 2026-10-01 | 11LHM/C | 0010 | 253900:PREPARE PART-PROTECT STEAM OVEN | TECO | MNOA | L/26-TQM-LI-MSC-M | 2 | DCA Appr. Req. 2 |  | BKK_H | MOD | 787.TO.253900 |  | 2026-09-30 | 06:00:00 | 2026-09-30 | 19:00:00
100 | 70467088 | HS-TQM | 0016569769 | 1103203711 | 2105181227 | AC02 |  | 2026-10-05 | 11LHM/C | 0010 | G/26-197:INSP EXPIRE DATE PLACARD OXYGEN | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 |  | BKK_H | REP | 787.EO.BKKJA-G/26-197 |  | 2026-10-05 | 06:00:00 | 2026-10-05 | 19:00:00
101 | 70466459 | HS-TQM | 0016447927 | QM048D240726 | QM048D240726 | AC05 |  | 2026-10-05 | 11LHM/C | 0010 | 25-CABIN:OVERHEAD STOEAGE MODULE. | TECO | NOGO ODAT | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP |  |  | 2026-09-25 | 06:00:00 | 2026-09-25 | 19:00:00
102 | 70466532 | HS-TQM | 0016557427 |  | 2105178865 | AC02 |  | 2026-10-07 | 11LHM/C | 0010 | DEPRES: 17.Clean and Wash the airplane | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | ALL_ALL GRP | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
103 | 70466532 | HS-TQM | 0016557428 |  | 2105178865 | AC02 |  | 2026-10-07 | 11LHM/C | 0020 | DEPRES: 17.Clean and Wash the airplane | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | ALL_ALL GRP | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
104 | 70466759 | HS-TQM | 0016540504 | 1103197509 | 2105174603 | AC03 |  | 2026-09-30 | 11LHM/C | 0010 | 253899:INSTALL SOAP BOTTLE ADAPTER | TECO |  | L/26-TQM-LI-MSC-M | 2 | DCA Appr. Req. 2 |  | BKK_H | MOD | 787.TO.253899 |  | 2026-09-30 | 06:00:00 | 2026-09-30 | 19:00:00
105 | 70466917 | HS-TQM | 0016546321 | 1103198768 | 2105175909 | AC02 |  | 2026-10-02 | 11LHM/A | 0010 | DRAIN WATER FROM ALL FUEL TANK | TECO | ODAT | L/26-TQM-LI-MSC-N | 4 | TG Appr. Req. 4 | WING_FUEL | BKK_H | REP | 787.MPD.2800000101-TG01 |  | 2026-10-02 | 06:00:00 | 2026-10-02 | 19:00:00
106 | 70466919 | HS-TQM-72-00-0001-ENG1 | 0016501572 | 1103190679 | 2105164451 | AC02 |  | 2026-10-02 | 11LHM/A | 0010 | Rep. GEnx ENGINE IGNITER | TECO |  | L/26-TQM-LI-MSC-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 787.MPD.RPL IGNITERS-GENX-TG00 |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
107 | 70466919 | HS-TQM-72-00-0001-ENG2 | 0016504228 | 1103190969 | 2105165411 | AC02 |  | 2026-10-05 | 11LHM/A | 0010 | Rep. GEnx ENGINE IGNITER | TECO |  | L/26-TQM-LI-MSC-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 787.MPD.RPL IGNITERS-GENX-TG01 |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
108 | 70466459 | HS-TQM | 0016447952 | QM053D240726 | QM053D240726 | AC05 |  | 2026-10-05 | 11LHM/C | 0010 | 25-CABIN:PASSENGER SEAT. | TECO | ODAT | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP |  |  | 2026-09-25 | 06:00:00 | 2026-09-25 | 19:00:00
109 | 70466532 | HS-TQM | 0016557397 |  | 2105178554 | AC02 |  | 2026-10-05 | 11LHM/A | 0010 | DEPRES: 18-28.Landing Gear | TECO |  | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
110 | 70466532 | HS-TQM | 0016557398 |  | 2105178554 | AC02 |  | 2026-10-05 | 11LHM/A | 0020 | DEPRES: 18-28.Landing Gear | TECO |  | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
111 | 70466532 | HS-TQM | 0016557399 |  | 2105178554 | AC02 |  | 2026-10-05 | 11LHM/A | 0030 | DEPRES: 18-28.Landing Gear | TECO |  | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
112 | 70466532 | HS-TQM | 0016557400 |  | 2105178554 | AC02 |  | 2026-10-05 | 11LHM/A | 0040 | DEPRES: 18-28.Landing Gear | TECO |  | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
113 | 70466532 | HS-TQM | 0016557401 |  | 2105178554 | AC02 |  | 2026-10-05 | 11LHM/A | 0050 | DEPRES: 18-28.Landing Gear | TECO |  | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
114 | 70466532 | HS-TQM | 0016557402 |  | 2105178554 | AC02 |  | 2026-10-05 | 11LHM/A | 0060 | DEPRES: 18-28.Landing Gear | TECO |  | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
115 | 70466532 | HS-TQM | 0016557403 |  | 2105178554 | AC02 |  | 2026-10-05 | 11LHM/A | 0070 | DEPRES: 18-28.Landing Gear | TECO |  | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
116 | 70466532 | HS-TQM | 0016557404 |  | 2105178554 | AC02 |  | 2026-10-05 | 11LHM/A | 0080 | DEPRES: 18-28.Landing Gear | TECO |  | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
117 | 70466532 | HS-TQM | 0016557495 |  | 2105178883 | AC02 |  | 2026-10-07 | 11LHM/C | 0010 | DEPRES: 62.Oxygen | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | CABIN_ALL CABIN | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
118 | 70466532 | HS-TQM | 0016557496 |  | 2105178883 | AC02 |  | 2026-10-07 | 11LHM/C | 0020 | DEPRES: 62.Oxygen | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | CABIN_ALL CABIN | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
119 | 70466532 | HS-TQM | 0016557497 |  | 2105178883 | AC02 |  | 2026-10-07 | 11LHM/C | 0030 | DEPRES: 62.Oxygen | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | CABIN_ALL CABIN | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
120 | 70466532 | HS-TQM | 0016557501 |  | 2105178886 | AC02 |  | 2026-10-07 | 11LHM/C | 0010 | DEPRES: 63.Water and Waste System | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | CABIN_ALL CABIN | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
121 | 70466759 | HS-TQM | 0016554431 | 1103200147 | 2105178092 | AC02 |  | 2026-10-05 | 11LHM/C | 0010 | G/26-186:REPLACE LIFE VESTS & DEMO LIFE | TECO |  | L/26-TQM-LI-MSC-N | 4 | TG Appr. Req. 4 |  | BKK_H | DET | 787.ED.BKKJA-G/26-186 |  | 2026-09-30 | 06:00:00 | 2026-09-30 | 19:00:00
122 | 70466919 | HS-TQM-72-00-0001-ENG1 | 0016501571 | 1103190678 | 2105164450 | AC02 |  | 2026-10-02 | 11LHM/A | 0010 | A_DVI MAIN FUEL PUMP LUBE FLOW SCREEN | TECO |  | L/26-TQM-LI-MSC-N | 4 | TG Appr. Req. 4 | INSP-W_ENGINE | BKK_H | DI | 787.MPD.DVI MAIN FUEL PUMP-TG00 |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
123 | 70466919 | HS-TQM-72-00-0001-ENG1 | 0016501573 | 1103190680 | 2105164452 | AC02 |  | 2026-10-02 | 11LHM/A | 0010 | DETAIL INSP.DEBRIS MONITORING SYSTEM SEN | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 |  | BKK_H | REP | 787.MPD.DI DMS SENSOR-TG01 |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
124 | 70466919 | HS-TQM-72-00-0001-ENG1 | 0016501574 | 1103190680 | 2105164452 | AC02 |  | 2026-10-02 | 11LHM/A | 0020 | DETAIL INSP.DEBRIS MONITORING SYSTEM SEN | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 |  | BKK_H | REP | 787.MPD.DI DMS SENSOR-TG01 |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
125 | 70466919 | HS-TQM-72-00-0001-ENG2 | 0016504227 | 1103190968 | 2105165410 | AC02 |  | 2026-10-05 | 11LHM/A | 0010 | A_DVI MAIN FUEL PUMP LUBE FLOW SCREEN | TECO |  | L/26-TQM-LI-MSC-N | 4 | TG Appr. Req. 4 | INSP-W_ENGINE | BKK_H | DI | 787.MPD.DVI MAIN FUEL PUMP-TG01 |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
126 | 70464374 | HS-TQM | 0016322284 | 1103157747 | 2105111926 | AC02 |  | 2026-09-07 | 11LHM/A | 0010 | E/26-062:Check Spoiler PCU Dispatch Tool | TECO | DPRC REMN ODRC ODAT | L/26-TQM-LI-MSC-N | 4 | TG Appr. Req. 4 | WING_TRAILING EDGE | BKK_H | GVI | 787.ED.BKKJA-E/26-062 |  | 2026-09-03 | 06:00:00 | 2026-09-03 | 19:00:00
127 | 70467088 | HS-TQM | 0016546155 | 1103199344 | 2105177007 | AC02 |  | 2026-10-05 | 11LHM/E | 0010 | D/26-093:UPGRADE EFB BLOCKPOINT 4.7 | TECO |  | L/26-TQM-LI-MSC-N | 4 | TG Appr. Req. 4 | TG_E | BKK_H | REP | 787.ED.JA-D/26-093 |  | 2026-10-05 | 06:00:00 | 2026-10-05 | 19:00:00
128 | 70466459 | HS-TQM | 0016360602 | QM015D040626 | QM015D040626 | AC05 |  | 2026-10-05 | 11LHM/C | 0010 | 25-CABIN: CUSHION EY PAX SEAT | TECO | NOGO ODAT | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP |  |  | 2026-09-25 | 06:00:00 | 2026-09-25 | 19:00:00
129 | 70466459 | HS-TQM | 0016360603 | QM015D040626 | QM015D040626 | AC05 |  | 2026-10-05 | 11LHM/C | 0020 | 25-CABIN: CUSHION EY PAX SEAT | TECO | NOGO ODAT | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP |  |  | 2026-09-25 | 06:00:00 | 2026-09-25 | 19:00:00
130 | 70466759 | HS-TQM | 0016527468 | 1103194669 | 2105171510 | AC02 |  | 2026-10-01 | 11LHM/C | 0010 | G/26-164:INSTALL ECONOMY CLASS SEAT BELT | TECO |  | L/26-TQM-LI-MSC-N | 4 | TG Appr. Req. 4 | CABIN_INTERIOR | BKK_H | MOD | 787.ED.BKKJA-G/26-164 |  | 2026-09-30 | 06:00:00 | 2026-09-30 | 19:00:00
131 | 70464374 | HS-TQM | 0016527006 | QM072B070926 | QM072B070926 | AC05 |  | 2026-09-22 | 11LHM/E | 0010 | CORE NETWORK FILE SERVER MOD FAIL | TECO | NOGO | L/26-TQM-LI-MSC-N |  |  |  | 11LHM/E | REP |  |  | 2026-01-01 | 18:20:00 | 2026-12-31 | 23:59:00
132 | 70466917 | HS-TQM | 0016539014 | 1103197329 | 2105174372 | AC02 |  | 2026-10-02 | 11LHM/C | 0010 | D/26-098:STORE UMD ON A/C-1ST | TECO | ODAT | L/26-TQM-LI-MSC-N | 4 | TG Appr. Req. 4 | CABIN_COCKPIT | BKK_H | REP | 787.ED.JA-D/26-098 |  | 2026-10-02 | 06:00:00 | 2026-10-02 | 19:00:00
133 | 70466519 | HS-TOG | 0016514464 | 1103192785 | 2105167340 | AC02 |  | 2026-09-30 | 12LI/IE | 0010 | RECORD APU OPERATION HOUR & START CYCLE | TECO | ODAT | L/26-TOG-LI-MSC-N | 4 | TG Appr. Req. 4 |  | BKK_L | REP | A320.MPD.4970000101-TG01 | 2026-09-30 | 2026-09-30 | 06:00:00 | 2026-09-30 | 19:00:00
134 | 70466519 | HS-TOG | 0016544454 | 1103198348 | 2105175540 | AC02 |  | 2026-09-30 | 12LC/CM | 0010 | FNC EMERGENCY CYLINDER/ACCUMULATOR PRESS | TECO | ODAT | L/26-TOG-LI-MSC-N |  |  | CABIN_DOOR | BKK_L | FNC | A320.MPD.521000-01-1 | 2026-09-30 | 2026-09-30 | 06:00:00 | 2026-09-30 | 19:00:00
135 | 70466519 | HS-TOG | 0016556695 | 1103200519 | 2105178776 | AC02 |  | 2026-09-30 | 12LC/E | 0010 | D/26-108:CHANGE ACARS/PRINT REPORT 15 | TECO | ODAT | L/26-TOG-LI-MSC-N | 4 | TG Appr. Req. 4 | IERA_ALL IERA | BKK_L | REP | A320.ED.BKKJA-D/26-108 | 2026-09-30 | 2026-09-30 | 06:00:00 | 2026-09-30 | 19:00:00
136 | 70466519 | HS-TOG | 0016558606 | 1103201155 | 2105179427 | AC02 |  | 2026-09-30 | 12LC/E | 0010 | D/26-114:TERRAIN DATABASE UPDATE TO V190 | TECO | ODAT | L/26-TOG-LI-MSC-N | 4 | TG Appr. Req. 4 |  | BKK_L | REP | A320.ED.JA-D/26-114 | 2026-09-30 | 2026-09-30 | 06:00:00 | 2026-09-30 | 19:00:00
137 | 70466532 | HS-TQM | 0016557172 |  | 2105178547 | AC02 |  | 2026-10-04 | 11LHM/E | 0010 | DEPRES:66,67 EFB, OBEDS RTS | TECO |  | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP | 787.MAM.-10-11-07-03A-820A-A | 2026-10-04 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
138 | 70466532 | HS-TQM | 0016557173 |  | 2105178547 | AC02 |  | 2026-10-04 | 11LHM/E | 0020 | DEPRES:66,67 EFB, OBEDS RTS | TECO |  | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP | 787.MAM.-10-11-07-03A-820A-A | 2026-10-04 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
139 | 70466532 | HS-TQM | 0016557394 |  | 2105178551 | AC02 |  | 2026-10-04 | 11LHM/C | 0010 | DEPRES: 77.Flight Deck Windows | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | ALL_ALL GRP | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-04 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
140 | 70466532 | HS-TQM | 0016557395 |  | 2105178552 | AC02 |  | 2026-10-03 | 11LHM/C | 0010 | DEPRES: 13.Pitot/Angle of Attack Probe H | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | CABIN_ALL CABIN | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-03 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
141 | 70466532 | HS-TQM | 0016557407 |  | 2105178557 | AC02 |  | 2026-10-03 | 11LHM/E | 0010 | DEPRES: 11,12 Air Data System Test | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | ALL_ALL GRP | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-03 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
142 | 70466532 | HS-TQM | 0016557408 |  | 2105178558 | AC02 |  | 2026-10-03 | 11LHM/E | 0010 | DEPRES: 35,36 Supply Elec Power | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | ALL_ALL GRP | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-03 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
143 | 70466532 | HS-TQM | 0016557423 |  | 2105178861 | AC02 |  | 2026-10-05 | 11LHM/E | 0010 | DEPRES:46.OPC AFDS Crl Wheel Backdrive | TECO |  | L/26-TQM-LI-MSC-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-05 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
144 | 70466532 | HS-TQM | 0016557424 |  | 2105178862 | AC02 |  | 2026-10-05 | 11LHM/E | 0010 | DEPRES:49.OPC AFDS Rudderl Backdrive | TECO |  | L/26-TQM-LI-MSC-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-05 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
145 | 70466532 | HS-TQM | 0016557425 |  | 2105178863 | AC02 |  | 2026-10-05 | 11LHM/E | 0010 | DEPRES:52.OPC AFDS Ctrl Column Backdrive | TECO |  | L/26-TQM-LI-MSC-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-05 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
146 | 70466532 | HS-TQM | 0016557442 |  | 2105178871 | AC02 |  | 2026-10-03 | 11LHM/C | 0010 | DEPRES: 40-41.Circuit breaker | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | IERA_ALL IERA | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-03 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
147 | 70466532 | HS-TQM | 0016557443 |  | 2105178871 | AC02 |  | 2026-10-03 | 11LHM/C | 0020 | DEPRES: 40-41.Circuit breaker | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | IERA_ALL IERA | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-03 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
148 | 70466532 | HS-TQM | 0016557444 |  | 2105178872 | AC02 |  | 2026-10-05 | 11LHM/A | 0010 | DEPRES: 43-45.Flight Con More 30 D | TECO |  | L/26-TQM-LI-MSC-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-05 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
149 | 70466532 | HS-TQM | 0016557445 |  | 2105178872 | AC02 |  | 2026-10-05 | 11LHM/A | 0020 | DEPRES: 43-45.Flight Con More 30 D | TECO |  | L/26-TQM-LI-MSC-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-05 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
150 | 70466532 | HS-TQM | 0016557446 |  | 2105178872 | AC02 |  | 2026-10-05 | 11LHM/A | 0030 | DEPRES: 43-45.Flight Con More 30 D | TECO |  | L/26-TQM-LI-MSC-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-05 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
151 | 70466532 | HS-TQM | 0016557447 |  | 2105178872 | AC02 |  | 2026-10-05 | 11LHM/A | 0040 | DEPRES: 43-45.Flight Con More 30 D | TECO |  | L/26-TQM-LI-MSC-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-05 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
152 | 70466532 | HS-TQM | 0016557448 |  | 2105178872 | AC02 |  | 2026-10-05 | 11LHM/A | 0050 | DEPRES: 43-45.Flight Con More 30 D | TECO |  | L/26-TQM-LI-MSC-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-05 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
153 | 70466532 | HS-TQM | 0016557449 |  | 2105178872 | AC02 |  | 2026-10-05 | 11LHM/A | 0060 | DEPRES: 43-45.Flight Con More 30 D | TECO |  | L/26-TQM-LI-MSC-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-05 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
154 | 70466532 | HS-TQM | 0016557450 |  | 2105178872 | AC02 |  | 2026-10-05 | 11LHM/A | 0070 | DEPRES: 43-45.Flight Con More 30 D | TECO |  | L/26-TQM-LI-MSC-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-05 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
155 | 70466532 | HS-TQM | 0016557473 |  | 2105178879 | AC02 |  | 2026-10-05 | 11LHM/A | 0010 | DEPRES: 69.Remove CPC inlet Lipskin (GEn | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | WING_ALL WING | BKK_H | REP | 787.MAM.B787-A-G71-11-01-02A-259B-A | 2026-10-05 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
156 | 70466532 | HS-TQM | 0016557474 |  | 2105178879 | AC02 |  | 2026-10-05 | 11LHM/A | 0020 | DEPRES: 69.Remove CPC inlet Lipskin (GEn | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | WING_ALL WING | BKK_H | REP | 787.MAM.B787-A-G71-11-01-02A-259B-A | 2026-10-05 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
157 | 70466532 | HS-TQM | 0016557498 |  | 2105178884 | AC02 |  | 2026-10-03 | 11LHM/C | 0010 | DEPRES: 33.WELS | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | CABIN_ALL CABIN | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-03 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
158 | 70466532 | HS-TQM | 0016557499 |  | 2105178885 | AC02 |  | 2026-10-03 | 11LHM/C | 0010 | DEPRES: 34.Emergency Lighting Power | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | CABIN_ALL CABIN | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-03 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
159 | 70466532 | HS-TQM | 0016557500 |  | 2105178885 | AC02 |  | 2026-10-03 | 11LHM/C | 0020 | DEPRES: 34.Emergency Lighting Power | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | CABIN_ALL CABIN | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-03 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
160 | 70466759 | HS-TQM | 0016537589 | 1103196963 | 2105173747 | AC03 |  | 2026-10-06 | 11LHM/C | 0010 | 253890:INSTALL BROOM & DUST PAN | TECO |  | L/26-TQM-LI-MSC-M | 2 | DCA Appr. Req. 2 |  | BKK_H | MOD | 787.TO.253890 | 2026-10-06 | 2026-09-30 | 06:00:00 | 2026-09-30 | 19:00:00
161 | 70466917 | HS-TQM | 0016542167 | 1103197793 | 2105174996 | AC02 |  | 2026-10-02 | 11LHM/E | 0010 | D/25-068:FMF AMI SOFTWARE CHANGE | TECO | ODAT | L/26-TQM-LI-MSC-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 787.ED.JA-D/25-068 | 2026-10-02 | 2026-10-02 | 06:00:00 | 2026-10-02 | 19:00:00
162 | 70466917 | HS-TQM | 0016546320 | 1103198769 | 2105175908 | AC02 |  | 2026-10-02 | 11LHM/C | 0010 | ALL GALLEYS GWIV SYSTEM RINSE | TECO | ODAT | L/26-TQM-LI-MSC-N | 4 | TG Appr. Req. 4 | CABIN_GALLEY | BKK_H | CLN | 787.MPD.3831210002-TG01 | 2026-10-02 | 2026-10-02 | 06:00:00 | 2026-10-02 | 19:00:00
163 | 70466917 | HS-TQM | 0016558624 | 1103201140 | 2105179445 | AC02 |  | 2026-10-02 | 11LHM/E | 0010 | D/26-111:TERRAIN DATABASE UPDATE TO V654 | TECO | ODAT | L/26-TQM-LI-MSC-N | 4 | TG Appr. Req. 4 |  | BKK_H | REP | 787.ED.JA-D/26-111 | 2026-10-02 | 2026-10-02 | 06:00:00 | 2026-10-02 | 19:00:00
164 | 70466919 | HS-TQM-72-00-0001-ENG2 | 0016504230 | 1103190970 | 2105165412 | AC02 |  | 2026-10-03 | 11LHM/A | 0010 | DETAIL INSP.DEBRIS MONITORING SYSTEM SEN | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 |  | BKK_H | REP | 787.MPD.DI DMS SENSOR-TG01 | 2026-10-03 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
165 | 70466919 | HS-TQM-72-00-0001-ENG2 | 0016504231 | 1103190970 | 2105165412 | AC02 |  | 2026-10-03 | 11LHM/A | 0020 | DETAIL INSP.DEBRIS MONITORING SYSTEM SEN | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 |  | BKK_H | REP | 787.MPD.DI DMS SENSOR-TG01 | 2026-10-03 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
166 | 70466532 | HS-TQM | 0016557396 |  | 2105178553 | AC02 |  | 2026-10-03 | 11LHM/C | 0010 | DEPRES: 14.Total Air Temperature Probe H | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | CABIN_ALL CABIN | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-03 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
167 | 70466532 | HS-TQM | 0016557426 |  | 2105178864 | AC02 |  | 2026-10-04 | 11LHM/C | 0010 | DEPRES: 65.Flight Compartment Window | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | CABIN_COCKPIT | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-04 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
168 | 70466532 | HS-TQM | 0016557478 |  | 2105178881 | AC02 |  | 2026-10-05 | 11LHM/A | 0010 | DEPRES: 73.Checking T/R (GEnx) | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | WING_ALL WING | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-05 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
169 | 70466532 | HS-TQM | 0016557479 |  | 2105178881 | AC02 |  | 2026-10-05 | 11LHM/A | 0020 | DEPRES: 73.Checking T/R (GEnx) | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | WING_ALL WING | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-05 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
170 | 70466532 | HS-TQM | 0016557480 |  | 2105178881 | AC02 |  | 2026-10-05 | 11LHM/A | 0030 | DEPRES: 73.Checking T/R (GEnx) | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | WING_ALL WING | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-05 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
171 | 70466532 | HS-TQM | 0016557481 |  | 2105178881 | AC02 |  | 2026-10-05 | 11LHM/A | 0040 | DEPRES: 73.Checking T/R (GEnx) | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | WING_ALL WING | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-05 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
172 | 70466532 | HS-TQM | 0016557482 |  | 2105178881 | AC02 |  | 2026-10-05 | 11LHM/A | 0050 | DEPRES: 73.Checking T/R (GEnx) | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | WING_ALL WING | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-05 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
173 | 70466532 | HS-TQM | 0016557483 |  | 2105178881 | AC02 |  | 2026-10-05 | 11LHM/A | 0060 | DEPRES: 73.Checking T/R (GEnx) | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | WING_ALL WING | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-05 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
174 | 70466532 | HS-TQM | 0016557484 |  | 2105178881 | AC02 |  | 2026-10-05 | 11LHM/A | 0070 | DEPRES: 73.Checking T/R (GEnx) | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | WING_ALL WING | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-05 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
175 | 70466532 | HS-TQM | 0016557485 |  | 2105178881 | AC02 |  | 2026-10-05 | 11LHM/A | 0080 | DEPRES: 73.Checking T/R (GEnx) | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | WING_ALL WING | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-05 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
176 | 70466532 | HS-TQM | 0016557486 |  | 2105178881 | AC02 |  | 2026-10-05 | 11LHM/A | 0090 | DEPRES: 73.Checking T/R (GEnx) | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | WING_ALL WING | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-05 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
177 | 70466532 | HS-TQM | 0016557487 |  | 2105178881 | AC02 |  | 2026-10-05 | 11LHM/A | 0100 | DEPRES: 73.Checking T/R (GEnx) | TECO |  | L/26-TQM-LI-MSC-N | 3 | TG Appr. Req. 3 | WING_ALL WING | BKK_H | REP | 787.MAM.B787-A-10-11-07-03A-820A-A | 2026-10-05 | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
178 | 70466759 | HS-TQM | 0016365176 | 1103165090 | 2105126594 | AC02 |  | 2026-07-25 | 11LHM/E | 0010 | D/26-020:SATCOM AMI SOFTWARE CHANGE | TECO | DPRC REMN ODRC ODAT | L/26-TQM-LI-MSC-N | 4 | TG Appr. Req. 4 | IERA_ALL_IERA | BKK_H | REP | 787.ED.JA-D/26-020 | 2026-07-17 | 2026-09-30 | 06:00:00 | 2026-09-30 | 19:00:00
179 | 70466759 | HS-TQM | 0016341036 | 1103161053 | 2105119097 | AC02 |  | 2026-07-25 | 11LHM/C | 0010 | E/26-078:INST FIRE EXTINGUISHER PLACARDS | TECO | DPRC REMN ODRC ODAT | L/26-TQM-LI-MSC-N | 4 | TG Appr. Req. 4 | CABIN_ALL CABIN | BKK_H | REP | 787.ED.BKKJA-E/26-078 | 2026-09-03 | 2026-09-30 | 06:00:00 | 2026-09-30 | 19:00:00
180 | 70466759 | HS-TQM | 0016542685 | 1103197424 | 2105174551 | AC03 |  | 2026-10-01 | 11LHM/C | 0010 | 253894:INSTALL EARMUFF | TECO |  | L/26-TQM-LI-MSC-M | 2 | DCA Appr. Req. 2 |  | BKK_H | MOD | 787.TO.253894 | 2026-10-01 | 2026-09-30 | 06:00:00 | 2026-09-30 | 19:00:00
181 | 70466917 | HS-TQM | 0016533424 | 1103195762 | 2105172763 | AC02 |  | 2026-10-02 | 11LHM/E | 0010 | D/26-104:HYBRID AIRLINE CERT OAS AMI | TECO | ODAT | L/26-TQM-LI-MSC-N | 4 | TG Appr. Req. 4 | TG_E | BKK_H | REP | 787.ED.JA-D/26-104 | 2026-10-02 | 2026-10-02 | 06:00:00 | 2026-10-02 | 19:00:00
182 | 70466917 | HS-TQM | 0016546154 | 1103199366 | 2105177006 | AC02 |  | 2026-10-02 | 11LHM/E | 0010 | D/26-102:ECL AMI Rev Sep2026 SOFTWARE | TECO | ODAT | L/26-TQM-LI-MSC-N | 4 | TG Appr. Req. 4 | TG_E | BKK_H | REP | 787.ED.JA-D/26-102 | 2026-10-02 | 2026-10-02 | 06:00:00 | 2026-10-02 | 19:00:00
183 | 70464374 | HS-TQM | 0016467922 | 1103184197 | 2105156079 | AC02 |  | 2026-09-07 | 11LQ/IC | 0010 | SCHK:INSP-PAX/CREW OXY BOTTLE INITIATOR | TECO |  | L/26-TQM-LI-MSC-N | 1 | DCA Appr. Req. 1 | INSP-I_CABIN | BKK_H | DET | 787.MPD.35-055-00 | 2026-09-07 | 2026-09-03 | 06:00:00 | 2026-09-03 | 19:00:00
184 | 70464374 | HS-TQM | 0016513149 | 1103191924 | 2105166576 | AC03 |  | 2026-10-01 | 11LHM/C | 0010 | 253882: CABIN HAMONY CHANGE(EEL CHG) | TECO |  | L/26-TQM-LI-MSC-M | 4 | TG Appr. Req. 4 |  | BKK_H | MOD | 787.TO.253882-01 | 2026-09-07 | 2026-09-03 | 06:00:00 | 2026-09-03 | 19:00:00
185 | 70464374 | HS-TQM | 0016513150 | 1103191924 | 2105166576 | AC03 |  | 2026-10-01 | 11SH | 0020 | 253882: CABIN HAMONY CHANGE(EEL CHG) | TECO |  | L/26-TQM-LI-MSC-M | 4 | TG Appr. Req. 4 |  | BKK_H | MOD | 787.TO.253882-01 | 2026-09-07 | 2026-09-03 | 06:00:00 | 2026-09-03 | 19:00:00
186 | 70466759 | HS-TQM | 0016514021 | 1103192617 | 2105167154 | AC03 |  | 2026-10-05 | 11LHM/C | 0010 | 253887:REPL Y/C SEAT LIFE VEST POUCH | TECO |  | L/26-TQM-LI-MSC-M | 4 | TG Appr. Req. 4 | CABIN_ALL CABIN | BKK_H | RAR | 787.TO.253887 | 2026-10-02 | 2026-09-30 | 06:00:00 | 2026-09-30 | 19:00:00
187 | 70466917 | HS-TQM | 0016540318 | 1103197499 | 2105174638 | AC03 |  | 2026-10-02 | 11LHM/C | 0010 | 253898:INSTL SERVER FOR BEVERAGE MAKER | TECO | ODAT | L/26-TQM-LI-MSC-M | 2 | DCA Appr. Req. 2 |  | BKK_H | MOD | 787.TO.253898 | 2026-10-02 | 2026-10-02 | 06:00:00 | 2026-10-02 | 19:00:00
188 | 70465254 | HS-TQM | 0016436332 | 1103178204 | 2105147415 | AC02 |  | 2026-09-07 | 11LHM/C | 0010 | G/26-114:LIFE VEST RFID REGISTRATION | TECO | DPRC REMN ODRC ODAT | L/26-TQM-LI-MSC-N | 4 | TG Appr. Req. 4 | CABIN_INTERIOR | BKK_H | RAR | 787.ED.BKKJA-G/26-114 | 2026-10-04 | 2026-09-07 | 08:20:00 | 2026-09-07 | 19:00:00
189 | 70464374 | HS-TQM | 0016565255 | QM077B011026 | QM077B011026 | AC05 |  | 2026-01-01 | 11LHM/A | 0010 | 21: AIR CONDITIONING / FAN | TECO | NOGO MAVA | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP |  |  | 2026-01-01 | 15:04:00 | 2026-10-02 | 19:00:00
190 | 70466459 | HS-TQM | 0016368463 | QM023D080626 | QM023D080626 | AC05 |  | 2026-09-25 | 11LHM/E | 0010 | 44-IERA:SMART MONITOR HAS SCRATCHED | TECO | NOGO ODAT MAVA | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP |  |  | 2026-09-25 | 06:00:00 | 2026-09-25 | 19:00:00
191 | 70466919 | HS-TQM-72-00-0001-ENG1 | 0016504383 | 1103190991 | 2105165418 | AC03 |  | 2026-10-04 | 11LHM/A | 0010 | 730590:GEnx EEC MOISTURE REMOVAL | TECO | MAVA | L/26-TQM-LI-MSC-M | 0 | AD |  | BKK_H | MOD | 787.TO.ITO-730590 |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
192 | 70466919 | HS-TQM | 0016538937 | 1103196846 | 2105174304 | AC02 |  | 2026-10-04 | 11LHM/E | 0010 | DOWNLOAD EAFR FLIGHT DATA FROM A/C TO ML | TECO | MAVA | L/26-TQM-LI-MSC-N | 0 | AD | IERA_IERA | BKK_H | REP | 787.MPD.31-037-01-TG01 |  | 2026-10-04 | 06:00:00 | 2026-10-05 | 07:00:00
193 | 70464374 | HS-TQM | 0016509581 | 1103191685 | 2105166320 | AC03 |  | 2026-09-03 | 11LHM/C | 0010 | 253883: CABIN HAMONY CHANGE | TECO | MNOA | L/26-TQM-LI-MSC-M | 4 | TG Appr. Req. 4 |  | BKK_H | RAR | 787.TO.253883 |  | 2026-09-03 | 06:00:00 | 2026-09-03 | 19:00:00
194 | 70464374 | HS-TQM | 0016509582 | 1103191685 | 2105166320 | AC03 |  | 2026-09-03 | 11LHM/C | 0020 | 253883: CABIN HAMONY CHANGE | TECO | MNOA | L/26-TQM-LI-MSC-M | 4 | TG Appr. Req. 4 |  | BKK_H | RAR | 787.TO.253883 |  | 2026-09-03 | 06:00:00 | 2026-09-03 | 19:00:00
195 | 70464374 | HS-TQM | 0016509583 | 1103191685 | 2105166320 | AC03 |  | 2026-09-03 | 11LHM/C | 0030 | 253883: CABIN HAMONY CHANGE | TECO | MNOA | L/26-TQM-LI-MSC-M | 4 | TG Appr. Req. 4 |  | BKK_H | RAR | 787.TO.253883 |  | 2026-09-03 | 06:00:00 | 2026-09-03 | 19:00:00
196 | 70464374 | HS-TQM | 0016509584 | 1103191685 | 2105166320 | AC03 |  | 2026-09-03 | 11LHM/C | 0040 | 253883: CABIN HAMONY CHANGE | TECO | MNOA | L/26-TQM-LI-MSC-M | 4 | TG Appr. Req. 4 |  | BKK_H | RAR | 787.TO.253883 |  | 2026-09-03 | 06:00:00 | 2026-09-03 | 19:00:00
197 | 70464374 | HS-TQM | 0016509585 | 1103191685 | 2105166320 | AC03 |  | 2026-09-03 | 11LHM/C | 0050 | 253883: CABIN HAMONY CHANGE | TECO | MNOA | L/26-TQM-LI-MSC-M | 4 | TG Appr. Req. 4 |  | BKK_H | RAR | 787.TO.253883 |  | 2026-09-03 | 06:00:00 | 2026-09-03 | 19:00:00
198 | 70464374 | HS-TQM | 0016565254 | QM076B011026 | QM076B011026 | AC05 |  | 2026-01-01 | 11LHM/E | 0010 | 31: INDICATING/RECORDING SYSTEM | TECO | NOGO MNOA | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP |  |  | 2026-01-01 | 14:55:00 | 2026-10-02 | 19:00:00
199 | 70466459 | HS-TQM | 0016368464 | QM024D080626 | QM024D080626 | AC05 |  | 2026-09-25 | 11LHM/E | 0010 | 44-IERA:SMART MONITOR HAS SCRATCHED | TECO | NOGO ODAT MAVA | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP |  |  | 2026-09-25 | 06:00:00 | 2026-09-25 | 19:00:00
200 | 70466459 | HS-TQM | 0016565236 | QM075B011026 | QM075B011026 | AC05 |  | 2026-01-01 | 11PAINT | 0010 | 11: PLACARDS AND MARKINGS | TECO |  | L/26-TQM-LI-MSC-N |  |  |  | BKK_H | REP |  | 2026-10-03 | 2026-01-01 | 14:39:00 | 2026-10-02 | 19:00:00

## TEXT TQM
EST. TAT XX DAYS // PERIOD 01OCT26-10OCT26
TOW IN : 01OCT26 H1 TIME 1800 PM ,LAST FLIGHT TG8417 25 JUL 2026 DMK to BKK
AIRCRAFT SERIAL NUMBER HS-TQM /34929 AIRCRAFT EFFECTIVITY CODE 027 TQM
########## WORK HIGHLIGHT 11 OCT. 2026 ##########
COMPLETE RTS
FIRST FLIGHT TG.8092 BKK to NGO TIME 0900 AM
######### HS-TQM PLAN TIME LINE ACTIVITY AS BELOW ##########
01OCT26 : TOW IN AT HG1
02–05 OCT : CABIN / MOD / ENGINE WORK
05–07 OCT : SYSTEM & ENGINE DEPRESERVATION
06–08 OCT : LANDING GEAR / DOORS / FLIGHT CONTROL DEPRESERVATION
07–08 OCT : SYSTEM OPC / FUNCTIONAL TEST
08 OCT : GROUND TEST AND FLIGHT TEST (SEND FAX ALREADY)
08–09 OCT : SNAG CLEARANCE / RECTIFICATION
09 OCT : FINAL CLEANING / A/C WASH / CLOSE-UP
09 OCT : PUT A/C BACK TO SERVICE / CRS PREPARATION
11 OCT 2026 : RTS , FIRST FLT TG8092 TIME 0900 AM BKK TO NGO
REMARK : COPY LINK FULL DASHBOARD ON DESKTOP TG ONLY : http://acm-hpv-app07.dt.thaiairways.co.th/RevisionPlan/BKKStatus.html